## Removed from List
Milestone ID Number | Level | WBS | Site | WP Number | WP Title | FCTWPM | CAM | Milestone Title | Deliverable Title | Deliverable Description | Estimated Finish | Revised Finish | Actual Finish | Narrative | FY | Status | Main Document Title | Document Author/Creator | Document Owner | CUI Type | Uploaded Document Name | DMS Tracking Number | Keywords
ActivityFT-12IN0802027 Activity - Not a document. | M3 | 1.02.08.02.02 | INL | FT-12IN080202 | ST Field Testing - INL | Birk, Sandy | Sorenson, Ken | Report on Feasibility of Siting a Storage Demonstration Platform at an Exisitng ISFSI site or alternative site with HBU Fuel | Feasibility Study for HBU Demo | Support meetings, reviews, attendance at industry meetings inclusive of IAEA, EPRI, NEI, NRC other industry specific meetings. Develop feasibility report on siting a demonstration. This can include a demonstration at INL. | 2012-09-28 08:00 | 2012-07-13 02:00 | 2012-07-13 02:00 |  | 2012 | Complete |  | Wahnschaffe, Steve | Wahnschaffe, Steve | None | INL_Dry_Storage_Demo_Options_WhitePaper[1].docx Tev-1187.pdf | FCRD-UFD-2012-000484
M21UF041701 Requested, but no response. ULR - Draft. | M2 | 1.02.08.04 | SNL | FTSN11UF0417 | Concept Evaluations | [8 empty] | The milestone is on schedule | [6 empty] | Final Concepts Report.pdf
M2FT-12IN0802081 superseded by M2FT-13IN0802067 | M2 | 1.02.08.02.08 | INL | FT-12IN080208 | Long Term Used Nuclear Fuel Storage Viability - INL | Marschman, Steve | Sorenson, Ken | Long Term Used Nuclear Fuel Storage Viability Report | Long Term Used Nuclear Fuel Storage Viability Report | Long Term Used Nuclear Fuel Storage Viability | 2012-11-15 02:00 |  |  | on schedule | 2012 | 90 Day |  |  |  | None
M2FT-12OR0822014 same as M2FT-13OR08220311​ | M2 | 1.02.08.22.01 | ORNL | FT-12OR082201 | Characterization of Existing UNF | Wagner, John | Wagner, John | Final Report and Results for UNF Categorization | Final Report and Results for UNF Categorization | Final report on UNF categorization | 2012-10-31 |  |  | on schedule | 2012 | 90 Day |  |  |  | None
M2FT-12OR0822021 superseded by M2FT-13OR0914061 | M2 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Complete Initial Commercial UNF Database and Documentation | Complete Initial Commercial UNF Database and Documentation | Finalize and distribute initial commercial UNF database and associated documentation. | 2013-03-22 |  |  |  | 2012 | On Schedule |  |  |  | None
M2FT-12OR08220217 superseded by M2FT-13OR0914066 | M2 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Complete Initial Version of UNF M&S Toolset | Beta Version of UNF M&S Toolset | Complete and document functional version of the integrated M&S toolset, scope limited to neutronics and thermal analysis capabilities | 2012-12-21 |  |  | Deliverable is on schedule | 2012 | 90 Day |  |  |  | None
M2FT-12OR08220230 superseded by M2FT-13OR09140615 | M2 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Demonstrate Integrated Data & M&S Toolset | Demonstrate Integrated Data & M&S Toolset | Demonstrate the integrated data & M&S toolset on applications of interest to the UFDC | 2013-03-01 |  |  |  | 2012 | On Schedule |  |  |  | None
M2FT-12OR0822031 superseded by M2FT-13OR0822011 | M2 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | M&S and Experimental Integration RD&D plan | M&S and Experimental Integration RD&D plan | This milestone will be the blueprint for how to move forward for the next several years to resolve the numerous technical challenges related to ES of UNF that will require M&S, measured data, and UQ | 2012-10-26 | 2013-01-18 |  | on schedule for revised finish date | 2012 | Expected Late |  |  |  | None
M2FT-12OR08220310 Per Matt Brainard: M2FT-12OR08220310 - Originally planned for FY13 completion on 3/29/2013. It may have been superseded by M2FT-13OR0822015: Demonstration of Approach and Results on Used Fuel Performance Characterization which was completed on 9/30/2013. Report was uploaded to PICS:NE but is too big to send via e-mail (27 MB). I have access to Google Drive if you’d like me to upload it there and invite you to download it. Let me know. Another option would be to get it from Peter Swift as he has access to download it directly from PICS:NE. | M2 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Demonstration of Approach on Selected Technical Issue | Demonstration of Approach on Selected Technical Issue | Execution of RD&D Plan and Demonstration of Approach on Selected Technical Issue | 2013-03-29 |  |  | on schedule | 2012 | On Schedule |  |  |  | None
M2FT-12SN0804031 same as M2FT-13SN0804031 | M2 | 1.02.08.04.03 | SNL | FT-12SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Refine Repository Design Concepts and Thermal Analysis | Generic Repository Concepts and Thermal Analysis | This report will describe reference disposal concepts, including a generic "open" emplacement mode, and description of surface facilities for all concepts. It will contain rough cost estimates for each concept (following the approach used for the Generic Salt Repository). Also included will be numerical simulations to verify the approach developed for thermal analysis, uncertainty analysis for calculated temperatures, and thermal results for one or more additional fuel cycles identified on consultation with the Systems campaign. | 2012-11-15 10:00 |  |  | Peer review is underway and comments so far can be accommodated. | 2012 | 90 Day |  |  |  | None
M2FT-12SN0804031 same as M2FT-13SN0804031 | M2 | 1.02.08.04.03 | SNL | FT-12SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Refine Repository Design Concepts and Thermal Analysis | Generic Repository Concepts and Thermal Analysis | This report will describe reference disposal concepts, including a generic "open" emplacement mode, and description of surface facilities for all concepts. It will contain rough cost estimates for each concept (following the approach used for the Generic Salt Repository). Also included will be numerical simulations to verify the approach developed for thermal analysis, uncertainty analysis for calculated temperatures, and thermal results for one or more additional fuel cycles identified on consultation with the Systems campaign. | 2012-11-15 10:00 |  |  | Peer review is underway and comments so far can be accommodated. | 2012 | 90 Day |  |  |  | None
M2FT-13LA0807012 superceded by M2FT-14LA0814012 | M2 | 1.02.08.07.01 | LANL | FT-13LA080701 | Regional Geology - LANL |  | McMahon, Kevin | Report on a GIS Database for Alternative Host Rocks and Sensitivity to Potential Siting Guidelines | GIS Database for Alternative Host Rocks and Sensitivity to Potential Siting Guidelines | Activity will support continued development of a GIS database for regional geology and siting guidelines tool development, as well as support completion of a Level 2 Milestone due December 2013. | 2013-12-06 22:00 |  |  | On Schedule, but potential government shutdown may put rest of schedule at risk | 2013 | 90 Day |  |  |  | None
M2FT-13OR09140615 Per Matt Brainard: M2FT-12OR08220230 - Originally planned for FY13 completion on 3/1/2013. It was superseded by M2FT-13OR09140615: Demonstrate Integrated Data & M&S Toolset and completed on 4/4/2013. Deliverable not uploaded into PICS:NE. The deliverable form was submitted and approved blank. Narrative: “A demonstration of the integrated data and M&S toolset known as the Used Nuclear Fuel—Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS) was provided to the National Technical Director on April 4, 2013.” DMS No. FCRD-NFST-2013-000594. No other notes provided. | M2 | [20 empty] | FCRD-NFST-2013-000594
M2FT-13SN0806063 superceded by M2FT-14SN0806054 | M2 | 1.02.08.06.06 | SNL | FT-13SN080606 | DR Generic Engineered Barrier System Evaluations - SNL |  | McMahon, Kevin | International Collaborations on Engineered Barrier Systems: Experimental and Modeling Investigations Report | International Collaborations on Engineered Barrier Systems: Experimental and Modeling Investigations | International Collaborations on Engineered Barrier Systems. This report will be based on the collaborations with international partners (e.g., DECOVALEX, Mt. Terri site) on (1) experimental and modeling investigations on EBS materials and concepts, and (2) field-scale research on cement - opalinus clay (CI) interaction experiment at the Mt. Terri site. | 2013-12-11 14:00 |  |  | So far, the milestone deliverable is on schedule. However, progress in this activity may be impacted given the current budgetary uncertainty related to the federal government shutdown. | 2013 | 90 Day |  |  |  | None
M2FT-13SN08180341 Replaces M3FT-12SN08180227; Replaced by M2FT-12SN0806081 | M2 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Coupled Thermal-Hydrological-Mechanical Processes in Salt | Coupled Thermal-Hydrological-Mechanical Processes in Salt | Replaces M3FT-12SN08180227: Document for (UFD Milestone M2 M2FT-12SN0806081) Coupled Thermal-Hydrological-Mechanical Processes in Salt |  | 2013 | Complete |  | Hansen, Francis | Hansen, Francis | None | Milestone II coupled thm processes in salt FINAL 111512.pdf | FCRD-UFD-2012-000422
M2FT-13SN08180341 Replaces M3FT-12SN08180227; Replaced by M2FT-12SN0806081 | M2 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | Mackinnon, Robert | Coupled Thermal-Hydrological-Mechanical Processes in Salt | Coupled Thermal-Hydrological-Mechanical Processes in Salt | Replaces M3FT-12SN08180227: Document for (UFD Milestone M2 M2FT-12SN0806081) Coupled Thermal-Hydrological-Mechanical Processes in Salt | 2012-11-15 06:00 |  | 2012-11-15 02:00 |  | 2013 | Complete |  | Frank Hansen | Frank Hansen | None | Milestone II coupled thm processes in salt FINAL 111512.pdf | FCRD-UFD-2012-000422
M2FT-14AN09020513 Per Matt Brainard: Not available in PICS:NE. DMS Number FCRD-NFST-2014-000080 | M2 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | Update of UFD System Architecture Evaluation | Update of UFD System Architecture Evaluation | Integrate supporting analyses into final L-2 report. | 2013-10-31 06:00 |  | 2013-10-29 02:00 |  | 2014 | Complete | ?Update of UFD System Architecture Evaluation | Nutt, Mark | Nutt, Mark | None |  | FCRD-NFST-2014-000080
M2FT-14ID0820013. Document not available in PICS:NE. Note: “No Document” entered as Main Document Title on Deliverable Form. No document per Document Title. | M2 | 1.02.08.20.01 | DOE-ID | FT-14ID082001 | High Burnup Cask Demo Project - DOE-HQ | Larson, Ned | Couch, Brad | Design Modified Cask Lid | Complete Design of the Modified Cask Lid | Design Modified Cask Lid | 2014-09-18 06:00 |  | 2014-09-15 02:00 | Design Review completed as in a review meeting held the end of August. | 2014 | Complete | No Document |  |  | None |  | FCRD-UFD-2014-000073
M2FT-14ID0820014 Per Matt Brainard: Document not available in PICS:NE. The last performance status on 11/3/2014 indicates this to be a “FY15 Milestone”. Checking the FY15 High Burnup Cask Demo Project work package and this milestone no longer exists. It could have been dropped entirely. | M2 | 1.02.08.20.01 | DOE-ID | FT-14ID082001 | High Burnup Cask Demo Project - DOE-HQ | Larson, Ned | Couch, Brad | Design Basis Licensing Document (DBLD) | Complete the storage Design Basis Licensing Document (DBLD) | Design Basis Licensing Document (DBLD) | 2014-12-10 04:00 |  |  | FY15 Milestone. | 2014 | 90 Day |  |  |  | None |  | FCRD-UFD-2014-000074
M2FT-14ID0913032 Per Matt Brainard: Milestone was planned for FY15 completion on 3/31/2015, however it did not carry over into an associated FY15 work package. Therefore, there is no deliverable to send. Milestone deleted. | M2 | 1.02.09.13.03 | DOE-ID | FT-14ID091303 | Spent Nuclear Fuel Transportation Cask Design Study - Energy Solutions | Bates, Melissa | Feldman, Matt | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (EnergySolutions) | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (EnergySolutions) | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (EnergySolutions) | 2015-03-31 02:00 |  |  |  | 2014 | On Schedule |  |  |  | None
M2FT-14ID0913042 Per Matt Brainard: Milestone was planned for FY15 completion on 3/31/2015, however it did not carry over into an associated FY15 work package. Therefore, there is no deliverable to send. Milestone deleted. | M2 | 1.02.09.13.04 | DOE-ID | FT-14ID091304 | Spent Nuclear Fuel Transportation Cask Design Study - AREVA | Bates, Melissa | Feldman, Matt | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (AREVA) | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (EnergySolutions) | Final Cask Design Study Report for High-Burn Fuel Reusable Rail Casks (EnergySolutions) | 2015-03-31 02:00 |  |  |  | 2014 | On Schedule |  |  |  | None
M2FT-14SN0805054 Per Charles Bryan: This is an activity - not a report. | M2 | 1.02.08.05.05 | SNL | FT-14SN080505 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Procurement of full-scale mockup for stress corrosion cracking mockup testing | Procurement of a large-scale SNF storage canister mockup | The activity entails developing specifications for a full-scale welded mockup of the cylindrical section of a SNF interim storage canister, and procuring that mockup for experimental work assessing stress corrosion cracking and NDE detection of stress corrosion cracks in relevant materials and for relevant weld specifications. | 2014-09-26 04:00 |  | 2014-09-26 02:00 | The completion criteria for this L2 milestone are "Delivery of the mockup to Sandia National Laboratories or a designated alternative location by the specified date of completion." Manufacturing of the full-scale cylindrical mockup has been completed. However, at our request, the Ranor has agreed to store the mockup until we have identified a vendor for performing weld characterization studies on the mockup. At that point, the mockup will be shipped directly to the engineering firm doing the characterization work. This will result in significant cost savings relative to transporting the mockup to Sandia and then shipping it to the company doing the weld characterizations (especially if the final choice is a highly experienced UK company, which is a likely option). Because the mockup has been completed and is still at Ranor only because we have requested that they store it for us, this milestone has been met. | 2014 | Complete | N/A |  |  | None |  |  | mockup, SNF interim storage, storage canister, storage system. stress corrosion cracking, weld residual stresses
M2FT-14SN0806053 Note file name - I found M2FT-13SN0806062, FCRD-UFD-2013-000404, Final | M2 | 1.02.08.06.05 | SNL | FT-14SN080605 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Used Fuel Degradation: Experimental and Modeling Report | Used Fuel Degradation: Experimental and Modeling Study | Used Fuel Degradation: Experimental and Modeling Report. This report will be based on contributions from SNL, PNNL, and ANL national laboratory teams. Integration of these efforts with those in other related UFD work packages (e.g., within EBS, GDSE) will be investigated along with those in the areas of criticality, inventory, and storage. |  | 2014 | Complete | Used Fuel Degradation: Experimental and Modeling Report | Sassani, David | Jove Colon, Carlos | None | M2FT-13SN0806062_Used_Fuel_Degradation_Experimental_Modeling_Report_FINAL.pdf | FCRD-UFD-2014-000057
M2FT-14SN0806053 Note file name - I found M2FT-13SN0806062, FCRD-UFD-2013-000404, Final | M2 | 1.02.08.06.05 | SNL | FT-14SN080605 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Used Fuel Degradation: Experimental and Modeling Report | Used Fuel Degradation: Experimental and Modeling Study | Used Fuel Degradation: Experimental and Modeling Report. This report will be based on contributions from SNL, PNNL, and ANL national laboratory teams. Integration of these efforts with those in other related UFD work packages (e.g., within EBS, GDSE) will be investigated along with those in the areas of criticality, inventory, and storage. | 2013-10-17 08:00 |  | 2013-10-17 12:00 |  | 2014 | Complete | Used Fuel Degradation: Experimental and Modeling Report | David C. Sassani | Carlos F. Jove Colon | None | M2FT-13SN0806062_Used_Fuel_Degradation_Experimental_Modeling_Report_FINAL.pdf | FCRD-UFD-2014-000057
M2FT-14SN0807082 File name shows M2FT-13SN0807086 | M2 | 1.02.08.07.08 | SNL | FT-14SN080708 | Crystalline Disposal R&D International - SNL | Wang, Yifeng | McMahon, Kevin | Natural System Evaluations: International Collaborations Progress Report | Natural System Evaluations: International Collaborations Progress | The international collaborations at SNl will include (1) development of in-situ geophysical and geochemical characterization techniques at ROK KURT and (2)using Czech Bedrichov Tunnel testing data. The work will also include obtaining fracture mapping data at KURT for discrete fracture model development and demonstration. Natural System Evaluations: International Collaborations Progress Report |  | 2014 | Complete | Natural System Evaluation and Tool Development - International Collaborations: FY13 Progress Report | Wang, Yifeng | Wang, Yifeng | None | Wang, Yifeng | FCRD-UFD-2013-000628 |  | M2FT-13SN0807086final.pdf
M2FT-14SN0807082 File name shows M2FT-13SN0807086 | M2 | 1.02.08.07.08 | SNL | FT-14SN080708 | Crystalline Disposal R&D International - SNL | Wang, Yifeng | McMahon, Kevin | Natural System Evaluations: International Collaborations Progress Report | Natural System Evaluations: International Collaborations Progress | The international collaborations at SNl will include (1) development of in-situ geophysical and geochemical characterization techniques at ROK KURT and (2)using Czech Bedrichov Tunnel testing data. The work will also include obtaining fracture mapping data at KURT for discrete fracture model development and demonstration. Natural System Evaluations: International Collaborations Progress Report | 2013-12-09 06:00 |  | 2013-12-05 06:00 |  | 2014 | Complete | Natural System Evaluation and Tool Development - International Collaborations: FY13 Progress Report | Yifeng Wang | Yifeng Wang | None | M2FT-13SN0807086final.pdf | FCRD-UFD-2013-000628
M2FT-14SN0817022 Superceded by M2FT-13SN0817051, Final Report | M2 | 1.02.08.17.02 | SNL | FT-14SN081702 | DR Deep Borehole Disposal - SNL | Arnold, Bill | Mackinnon, Robert | Deep Borehole Disposal Research: RD&D Needs and Criteria and Alternatives for Demonstration Site Selection | Deep Borehole Disposal Research: RD&D Needs and Criteria and Alternatives for Demonstration Site Selection | The report will describe set of technical siting criteria to screen sites that are clearly unsuitable or inappropriate for a deep borehole disposal (DBD) demonstration. Technical criteria will focus on factors that are potentially important to waste isolation in the DBD concept and to the successful implementation of the DBD demonstration, including relevant regional-scale characteristics. The report will also include a literature survey to identify relevant existing information on time-dependent properties of candidate seal materials under a range of environmental conditions. The report will also develop a safety framework for DBD by organizing the existing information and analyses for DBD and implement a systematic systems engineering approach to prioritizing the identified science and engineering needs for the DBD demonstration. | 2013-10-25 08:00 |  | 2013-10-25 02:00 |  | 2014 | Complete | Deep Borehole Disposal Research: Demonstration Site Selection Guidelines, Borehole Seals Design, and RD&D Needs | SNL | Arnold, Bill | None | DBD_FY13_milestone_report_final.pdf | FCRD-UFD-2014-000070
M2FT-15HQ0817071 Document not available. Removed from list per Peter Swift. Per Geoff Freeze: This was never a “document”. It was a milestone for DOE-HQ that would have been achieved had we ever selected a site for the Deep Borehole Field Test. | M2 | 1.02.08.17.07 | DOE-HQ | FT-15HQ081707 | DR Deep Borehole Disposal - DOE-HQ | Couch, Brad | Mackinnon, Robert | Site Selection Recommendation | Site Selection Recommendation | Site for Field Test is recommended by DOE. | 2015-12-31 02:00 |  |  |  | 2015 | On Schedule |  |  |  | None |  | FCRD-UFD-2015-000016
M2FT-15OR0905011 Per Kaushik Banerjee: This is a software package - not a report. | M2 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Deployment of UNF Database and Analysis System, version 2.0 | Deployment of UNF Database and Analysis System, version 2.0 | Prepare Version 2 of the Unified UNF Database and analysis system (UNF-ST&DARDS) for release to NFST participants | 2015-09-30 06:00 |  | 2015-09-30 | Version 2 (Beta) of the UNF-ST&DARDS software was distributed on September 30, 2015 | 2015 | Complete | N/A | Banerjee, Kaushik | Scaglione, John | OUO |  | FCRD-NFST-2015-000107
M2FT-15PN0810041 Per Matt Brainard: Originally planned for FY16 completion on 1/29/2016 and then marked late, revised due date 9/30/2016. It may have been superseded by M2FT-16PN080203031: High Heat Load Thermal Analysis which was completed on 9/29/2016. | M2 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Thermal Analyses of Two Licensed Storage Systems | Thermal Analyses of Two Licensed Storage Systems | Conduct thermal analyses of two operating, licensed storage systems. | 2016-01-29 05:00 | 2016-09-30 15:00 |  | This will be the major focus of FY16. | 2015 | Expected Late |  |  |  | None |  | FCRD-UFD-2015-000118
M2FT-15SN0817061 Sassani, David: Hi Laura, this report is OUO and designated as "PREDECISIONAL DRAFT MATERIAL – DO NOT DISTRBUTE" There was an NDA associated with this that only a limited number of people were part of for the work. I have the file, but will need to check to see whether or not it can be put out for others to see at this point or not, before I send it. | M2 | 1.02.08.17.06 | SNL | FT-15SN081706 | Site Selection - SNL | Sassani, Dave | Mackinnon, Robert | Site Evaluation for Deep Borehole Field Test | Site Evaluation for Deep Borehole Field Test | Field report describing site evaluation and selection process. | 2015-06-04 06:00 |  | 2015-06-04 02:00 |  | 2015 | Complete | Site Selection Evaluation for Deep Borehole Field Test | Sassani, David | Sassani, David | None | Final M2FT_15SN0817061 Siting Evaluation UFD.pdf | FCRD-UFD-2015-000130 | deep borehole field test site evaluation
M2FT-16AN090302011 Per Matt Brainard: Note: “File too large for PICS. It will be provided directly to DMS.” DMS No. FCRD-NFST-2016-000091. Main Document Title: “Environmental Considerations for the Consolidated Storage of Commercial Spent Nuclear Fuel and Associated Operations”. Narrative: “The initial ECR was provided to DOE on schedule, totaling nearly 1,000 pages.” | M2 | 1.02.09.03.02.01 | ANL | FT-16AN09030201 | ST: NEPA - ANL | MacDonell, Margaret | Carter, Joe | Environmental Considerations for an Interim Storage Facility and Associated Operations (Initial) | Environmental Considerations for an Interim Storage Facility and Associated Operations (Initial) | Initial Environmental Considerations Report. While this is an L-2 milestone, it will still be considered draft and will be revised in subsequent fiscal years. | 2016-06-30 04:00 |  | 2016-06-30 05:00 |  | 2016 | Complete | Environmental Considerations for the Consolidated Storage of Commercial Spent Nuclear Fuel and Associated Operations |  | MacDonell, Margaret | None |  | FCRD-NFST-2016-000091
M2FT-16ID090402051 Per Matt Brainard: Develop START Version 2.0, The milestone was marked complete and “delivered on time”, however the Deliverable Form in PICS:NE was submitted and subsequently approved without an uploaded document. Deliverable is missing. DMS No. FCRD-NFST-2016-000093 referenced. Matt Feldman is CAM. Mark Nutt is NTD. It’s possible one of them has a copy. | M2 | 1.02.09.04.02.05 | DOE-ID | FT-16ID09040205 | TR: Operational - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | Develop START Version 2.0 | Release of START VERSION 2.0 | Release of a fully functional Version 2.0 of START to the START user community. | 2016-05-31 03:00 |  | 2016-05-31 02:00 |  | 2016 | Complete | Develop START Version 2.0 |  |  | None |  | FCRD-NFST-2016-000093
M2FT-16OR090105011 Per Kaushik Banerjee: This is a software package - not a report. | M2 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Deployment of UNF Database and Analysis System, Version 3.0 | Deployment of UNF Database and Analysis System, Version 3.0 | Deployment of UNF Database and Analysis System, Version 3.0 by 9/30/2016 –Prepare Version 3 of the Unified UNF Database and analysis system (UNF-ST&DARDS) for release to NFST participants | 2016-09-30 04:00 |  | 2016-09-30 | This is a software package that includes the unified database and integrated analysis system | 2016 | Complete | UNF-ST&DARDS Version 3 | Banerjee, Kaushik | Scaglione, John | OUO |  | FCRD-NFST-2016-000087
M2FT-16SN080308091 Requested copy, but no response - lac. | M2 | 1.02.08.03.08.09 | SNL | FT-16SN08030809 | Project Integration and Concept Evaluation - SNL | Freeze, Geoff | Mackinnon, Robert | Deep Borehole Field Test Project Plan, Revision 1 | Deep Borehole Field Test Project Plan, Revision 1 | This report will be a revision to the existing project plan and will describe updated management structure, project baseline, and project management activities, including WBS, costs, and schedule. | 2016-06-30 10:00 |  | 2016-06-30 02:00 |  | 2016 | Complete | Project Plan: Deep Borehole Field Test, Rev. 1 | Freeze, Geoff | Freeze, Geoff | None |  | FCRD-UFD-2016-000071 | deep borehole field test
M2SF-17ID020201076 Superseded by M2SF-18ID020201042 | M2 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | Final Generic Design Package/TSAR | All deliverables in Section 4.2 | Final Generic Design Package/TSAR | 2018-01-22 |  |  |  | 2017 | On Schedule |  |  |  | None |  | SFWD-IWM-2017-000223
M2SF-17ID020303051 Note from Matt Brainard: Deliverable not uploaded into PICS:NE. Milestone completed on 9/1/2017 however: “Based on a phone call with Melissa, I can say that the M2 milestone was satisfied on time. The railcar design approval authority, the Association of American Railroads Engineering Equipment Committee, is taking longer than they did for previous reviews. They requested some more analysis and some changes in the report format. But within the PICS environment, the contractor did submit the deliverable to DOE on time. Pat Schwab. Main Document Title: Completion of spent fuel transportation cask and buffer rail car designs for future prototype fabrication and testing. | M2 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Completed Cask and Buffer Railcar Design | Completed Cask and Buffer Railcar Design | Completion of spent fuel transportation cask and buffer rail car designs for future prototype fabrication and testing | 2017-09-30 |  | 2017-09-01 02:00 | Based on a phone call with Melissa, I can say that the M2 milestone was satisfied on time. The railcar design approval authority, the Association of American Railroads Engineering Equipment Committee, is taking longer than they did for previous reviews. They requested some more analysis and some changes in the report format. But within the PICS environment, the contractor did submit the deliverable to DOE on time. Pat Schwab | 2017 | Complete | Completion of spent fuel transportation cask and buffer rail car designs for future prototype fabrication and testing |  |  | None |  | SFWD-IWM-2017-000025
M2SF-17OR020101021 Document already uploaded to Deliverable Form M2SF-17AN020101011. | M2 | 1.08.02.01.01.02 | ORNL | SF-17OR02010102 | Siting Process Design - ORNL (CLOSED) | Howard, Rob | Howard, Rob | Combined Siting Considerations Document (ORNL) | Siting Considerations for Federal Interim Storage Facilities and Repositories | Combined Siting Considerations document for Interim Storage Facilities and Repositories | 2016-12-15 |  | 2016-12-15 |  | 2017 | Complete | Document already uploaded to Deliverable Form M2SF-17AN020101011. | Reim, Mike | Saraeva, Natalia | None |  | SFWD-IWM-2017-000020 | consent based siting, nuclear waste management, trust, fairness, opennes
M2SF-17SN010306012 Per Geoff Freeze: This report was delivered to DOE in September 2017 as an incomplete draft titled “Crystalline Basement Disposal Safety Case (SFWD-SFWST-2017-000009)”. It is marked as NOT APPROVED FOR UUR. I have a copy. Also note that there are two other “companion” documents with the same status - Crystalline Basement Disposal: Sampling and Analysis Plan DRAFT (SFWD-SFWST-2017–000011) and Preclosure Risk Assessment for Waste Disposal in Crystalline Basement Rock (DRAFT) (SFWD-SFWST-2017-000010). Removed from list per Peter Swift. | M2 | 1.08.01.03.06.01 | SNL | SF-17SN01030601 | Project Integration and Concept Evaluation - SNL | Freeze, Geoff | MacKinnon, Robert | Crystalline Basement Disposal Safety Case | Crystalline Basement Disposal Safety Case | This report describes the Safety Case approach and the results of a safety assessment. | 2017-09-29 08:00 |  | 2017-08-31 02:00 |  | 2017 | Complete | Crystalline Basement Disposal Safety Case | Freeze, Geoff | Freeze, Geoff | OUO |  | SFWD-SFWST-2017-000009
M2SF-17SN010306031 This M2 was submitted, then unsubmitted at the request of DOE-NE. Three Deep Borehole SAND reports were issued in 2019, included this report's final form (KK). | M2 | 1.08.01.03.06.03 | SNL | SF-17SN01030603 | Site Characterization - SNL | Kuhlman, Kris | Mackinnon, Robert | Crystalline Basement Disposal: Sampling and Analysis Plan | Crystalline Basement Disposal: Sampling and Analysis Plan | This report will describe the sampling and analysis plans for the Crystalline Basement Disposal. | 2017-08-31 06:00 |  | 2017-08-29 02:00 |  | 2017 | Complete | Deep Borehole Field Test Laboratory and Borehole Testing Strategy: Generic Drilling and Testing Plan | Kuhlman, Kris | Kuhlman, Kris | None |  | SFWD-SFWST-2017-000011
M2SF-17SN010306041 OUO Author: Hi Laura, this report is OUO and designated as "PREDECISIONAL DRAFT MATERIAL – DO NOT DISTRBUTE" There was an NDA associated with this that only a limited number of people were part of for the work. I have the file, but will need to check to see whether or not it can be put out for others to see at this point or not, before I send it. | M2 | 1.08.01.03.06.04 | SNL | SF-17SN01030604 | Site Geoscience Data Evaluation - SNL | Sassani, Dave | MacKinnon, Robert | Integrated Geoscience Data and Evaluation of Geologic Conditions for Crystalline Basement Disposal | Integrated Geoscience Data and Evaluation of Geologic Conditions for Crystalline Basement Disposal | This report will describe the synthesis of existing geoscience data, including any additional collected site characterization data and laboratory data, and the development of a site geologic framework model that will be used as the basis for describing and evaluating thermal-hydro-mechanical-chemical (THMC) conditions at the site and at depth. | 2017-09-15 06:00 |  | 2017-08-31 02:00 |  | 2017 | Complete | Integrated Geoscience Data and Evaluation of Geologic Conditions for Crystalline Basement Disposal | Sassani, David | Sassani, David | OUO |  | SFWD-SFWST-2017-000012 | Draft materials OUO
M2SF-18AN010201015 superceded by M2SF-19AN010201011 | M2 | 1.08.01.02.01.01 | ANL | SF-18AN01020101 | Sister Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | Initial Phase 1 Radial Hydride and Ring Compression Test Results | Final Report on Initial Phase 1 Radial Hydride and Ring Compression Test Results | Initial Phase 1 Radial Hydride and Ring Compression Test Results | 2019-03-31 |  |  | Work will commence after ANL receives defueled cladding samples from PNNL and/or ORNL. | 2018 | On Schedule |  |  |  | None
M2SF-18AN020402014 Per Matt Brainard: Integrated Waste Management Facility Configuration Evaluation, originally planned for FY19 completion on 2/28/2019. Superseded by FY19 milestone M2SF-19AN020402013 - Integrated Waste Management Facility Configuration Evaluation, attached. Note that the ORNL M2 Deliverable (M2SF-19OR020402061) appears to be satisfying the ANL M2 Milestone (M2SF-19AN020402013). | M2 | 1.08.02.04.02.01 | ANL | SF-18AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | Integrated Waste Management Facility Configuration Evaluation | Integrated Waste Management Facility Configuration Evaluation Report | Integrated Waste Management Facility Configuration Evaluation Report | 2019-02-28 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M2SF-18ID020201042 Supersedes M2SF-17ID020201076. Milestone completed on 3/22/2018 however: “The TSAR final deliverable is complete and delivered. This deliverable is too large to post on PICS and will be placed in CURIE.” Deliverable Description: “Generic Design and Topical Safety Analysis Report”. | M2 | 1.08.02.02.01.04 | DOE-ID | SF-18ID02020104 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Reeves, Steve | Carter, Joe | Final Generic Design Package/TSAR | All deliverables in Section 4.2 | Final Generic Design Package/TSAR | 2018-03-22 |  | 2018-03-22 |  | 2018 | Complete | Generic Design and Topical Safety Analysis Report |  |  | None
M2SF-18OR010201026 Per Matt Brainard: Document not available in PICS:NE. File marked Other, which prohibits upload into PICS:NE. Note added: Predecisional draft. Status as of 4/11/2018: “Document is currently awaiting review by the vendors Westinghouse and Framatome, and Dominion per the existing NDA. The document is currently listed as predecisional draft, and once cleared by DOE the updated file will be uploaded”. The file was never uploaded into PICS:NE. Predecisional Draft | M2 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Final Report on Sister Pin Non-destructive Tests | Final Report on Sister Pin Non-destructive Tests | Document results of all non-destructive testing performed on the 25 sister pins. | 2018-03-30 |  | 2018-03-30 |  | 2018 | Complete | Sister Rod Nondestructive Examination Final Report | Montgomery, Rose | Scaglione, John | Predecisional draft
M2SF-18OR010201027 Per Matt Brainard: Originally planned for FY19 completion on 3/29/2019. It was superseded by M2SF-19OR010201028: ORNL FY18 Results of FY18 Sister Pin Destructive Tests which was completed on 3/29/2019. | M2 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Results of FY18 Sister Pin Destructive Tests | Results of Sister Pin Destructive Tests | Document results of destructive tests performed on the sister pins through July 2018. | 2019-03-29 |  |  | work continues on schedule | 2018 | On Schedule |  |  |  | None
M2SF-18OR020302042 Per Matt Brainard: Transportation Cost Estimate Database Report, originally planned for FY19 completion on 1/25/2019. Superseded by FY19 milestone M2SF-19OR020302032 - Transportation Cost Estimate Database Report and was marked complete on 1/25/2019. However, the Deliverable was marked OUO, which prohibits upload into PICS:NE. Deliverable is missing. Other pertinent information is as follows: Narrative: “The main thrust of this project has been the research, development, and compilation of modern transportation and logistics data and its incorporation into the Unified Database and updates to the Next Generation Systems Analysis Model and in particular the transportation operations component of that model. The modernization of the transportation data is key to improving the fidelity of the systems analyses work supporting the development of an integrated waste management system.” Document Author and Owner: Matt Feldman. Notes: “This deliverable contains proprietary information and therefore its distribution is limited. Please contact Matt Feldman at feldmanmr@ornl.gov or (865) 241-8801 for further information.” | M2 | 1.08.02.03.02.04 | ORNL | SF-18OR02030204 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Cost Estimate Database Report | Transportation Cost Estimate Database Report | Leave 3 milestone report detailing up to date logistics and capital costs associated with SNF transport. | 2019-01-25 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M2SF-18OR020405014 Release of UNF-ST&DARDS Version 4.0, originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M2SF-19OR020405013 - Release of UNF-ST&DARDS Version 4.0 and marked complete on 1/31/2019. Deliverable was not uploaded into PICS:NE because it doesn’t exist. Notes: “This is a software package. Please contact Kaushik Banerjee (banerjeek@ornl.gov) for details.” Main Document Title: “UNF-ST&DARDS Version 4.0.” Deliverable Description: “Used Nuclear Fuel-Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS), version 4.0 has been released through RSICC (Radiation Safety Information Computational Center). UNF-ST&DARDS Version 4.0 capabilities include: • An SNF database (relational database tables) for storing and preserving SNF data and supplying data to various SNF analyses, • Various graphical user interface (GUI)-based data importers for importing user-specific data to the UNF-ST&DARDS database, • Automated assembly-specific depletion and decay analyses using SCALE nuclear code, • Canister-specific criticality and shielding analyses using SCALE nuclear code, • Canister-specific thermal analysis using COBRA-SFS thermal hydraulic code, • Design-basis decay, criticality, and shielding analyses using user-defined, design-basis assembly and loading configurations, • Various sensitivity analyses for defining bounding/design-basis configurations for dry storage systems, • GUI-based data interrogation capability, • GUI-based analysis template development capability, • Sample reactor (ORIGEN) libraries for selected PWR and BWR fuel types, and • Sample criticality (KENO), shielding (MAVRIC), and thermal (COBRA-SFS) templates.” | M2 | 1.08.02.04.05.01 | ORNL | SF-18OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Release of UNF-ST&DARDS Version 4.0 | UNF-ST&DARDS Version 4.0 | This deliverable includes UNF-ST&DARDS Version 4.0 software code with up-to-date user documentation. Version 4.0 is planned to be a general-purpose (rather than test & evaluation only) version with capabilities for use in performing thermal analysis in addition to those capabilities previously included in Version 3.1.1. Version 4.0 is currently planned to be a limited release through the Radiation Safety Information Computational Center (RSICC) and, similar to previous versions released through RSICC, will not include data in the unified database (UDB). | 2019-01-31 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18PN010203025 Superceded by M2SF-19PN010203021: BWR Dry Cask Simulator Thermal Analysis Results and completed on 1/25/2019. | M2 | 1.08.01.02.03.02 | PNNL | SF-18PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | BWR Dry Cask Simulator Thermal Analysis Results | BWR Dry Cask Simulator Thermal Analysis Results | Document analyses done for the EPRI/ESCP Thermal Analysis Subcommittee round robin. | 2019-01-25 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010301052 superceded by M2SF-19SN010301052 | M2 | 1.08.01.03.01.05 | SNL | SF-18SN01030105 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Expanded - Argillite Disposal R&D interim report - 2019 | Evaluation of Spent Nuclear Fuel Dispositon in Clay-Bearing Rocks - 2019 Interim Report | Interim progress report on Argillite Disposal R&D | 2019-06-30 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010302052 carried over to FY19 | M2 | 1.08.01.03.02.05 | SNL | SF-18SN01030205 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | FY19 Mid-report on spent fuel disposal in crystalline media | FY19 mid-year report on spent disposal in | The report will document all the work to be performed under the additional funding from the March 23rd Omnibus Bill for the crystalline work packages. | 2019-06-30 |  |  | On schedule | 2018 | On Schedule |  |  |  | None
M2SF-18SN010302052 carried over to FY19 | M2 | 1.08.01.03.02.05 | SNL | SF-18SN01030205 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | FY19 Mid-report on spent fuel disposal in crystalline media | FY19 mid-year report on spent disposal in | The report will document all the work to be performed under the additional funding from the March 23rd Omnibus Bill for the crystalline work packages. | 43646 |  |  | On schedule | 2018 | On Schedule |  |  |  | None
M2SF-18SN010304065 superceded by M2SF-19SN010304042 | M2 | 1.08.01.03.04.06 | SNL | SF-18SN01030406 | GDSA - Framework Development - SNL | Mariner, Paul | Mackinnon, Robert | GDSA Framework Development and Process Model Integration | Geologic Disposal Safety Assessment Status Report | Development of GDSA Framework and integration of process models in PA and the safety case. Includes integration workshops with Crystalline, Argillite, and Salt work packages. | 2019-04-30 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010304065 superseded by M2SF-19SN010304042 | M2 | 1.08.01.03.04.06 | SNL | SF-18SN01030406 | GDSA - Framework Development - SNL | Mariner, Paul | Mackinnon, Robert | GDSA Framework Development and Process Model Integration | Geologic Disposal Safety Assessment Status Report | Development of GDSA Framework and integration of process models in PA and the safety case. Includes integration workshops with Crystalline, Argillite, and Salt work packages. | 2019-04-30 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010304076 superceded by M2SF-19SN010304051 | M2 | 1.08.01.03.04.07 | SNL | SF-18SN01030407 | GDSA - Repository Systems Analysis - SNL | Sevougian, David | MacKinnon, Robert | GDSA Repository Systems Analysis Progress Report | GDSA Repository Systems Analysis Progress Report | This deliverable will report progress on developing and simulating generic reference case repositories with GDSA Framework, especially in a UZ host rock, and including DPC inventory and waste packages. | 2019-04-30 |  |  | We plan to finish M2 on schedule. | 2018 | On Schedule |  |  |  | None
M2SF-18SN010305052 not completed per Hardin | M2 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | MacKinnon, Robert | Analysis of Solutions for DPC Disposal | Analysis of Solutions for Disposal of Spent Fuel in DPCs - Draft | Report describing goals, technical options, uncertainties, and management cases for DPC disposal. | 2019-06-19 |  |  | Planning is complete, technical services subcontract let, and work has begun. | 2018 | On Schedule |  |  |  | None
M2SF-18SN010305052 not completed per Hardin | M2 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Mackinnon, Robert | Analysis of Solutions for DPC Disposal | Analysis of Solutions for Disposal of Spent Fuel in DPCs - Draft | Report describing goals, technical options, uncertainties, and management cases for DPC disposal. | 2019-06-19 |  |  | Planning is complete, technical services subcontract let, and work has begun. | 2018 | On Schedule |  |  |  | None
M2SF-18SN010305062 same as M2SF-19SN01030562 | M2 | 1.08.01.03.05.06 | SNL | SF-18SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | MacKinnon, Robert | Preliminary Probabilistic/Regulatory Analysis of Postclosure DPC Criticality Consequences | Preliminary Probabilistic Criticality Consequence Assessment for Geologic Disposal of Spent Fuel in DPCs | Probabilistic PA-style analysis of criticality consequences focusing on risk, including consequences from individual events (e.g., thermal and fission product inventory), and factors controlling event incidence (e.g., frequency and recurrence). | 2019-09-17 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010305062 same as M2SF-19SN01030562 | M2 | 1.08.01.03.05.06 | SNL | SF-18SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Mackinnon, Robert | Preliminary Probabilistic/Regulatory Analysis of Postclosure DPC Criticality Consequences | Preliminary Probabilistic Criticality Consequence Assessment for Geologic Disposal of Spent Fuel in DPCs | Probabilistic PA-style analysis of criticality consequences focusing on risk, including consequences from individual events (e.g., thermal and fission product inventory), and factors controlling event incidence (e.g., frequency and recurrence). | 43725 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010308044 superceded by M2SF-19SN010308042 | M2 | 1.08.01.03.08.04 | SNL | SF-18SN01030804 | Engineered Barrier System R&D - SNL | Matteo, Edward | McMahon, Kevin | Evaluation of Engineered Barrier Systems Mid-year Status Report | Evaluation of Engineered Barrier Systems Mid-year Status Report | Report on status of activities associated with FY18 funding. | 2019-06-30 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-18SN010401013 superceded by M2SF-19010401013 | M2 | 1.08.01.04.01.01 | SNL | SF-18SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Develop project/implementation plan(s) for stand-up of the recommended cloud environment | Project Implementation Plan | Develop project/implementation plan(s) for stand-up of the recommended a cloud environment | 2018-07-06 | 2018-07-18 04:00 | 2018-07-18 04:00 |  | 2018 | Completed Late | PICs Cloud Implementation plan update |  |  | None | PICs Cloud Implemtation plan update.docx
M2SF-18SR020201023 Per Matt Brainard: Canister Inspection and Remediation Facility – Report, Originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M2SF-19SR020201022 - Canister Inspection and Remediation Facility – Report, which isn’t due until FY20 on 11/30/2019. No Deliverable to provide as of yet. | M2 | 1.08.02.02.01.02 | SRNL | SF-18SR02020102 | Storage Design - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | M3 Milestone report for the design concept for canister inspection and remediation facility at an ISF | 2019-01-31 |  |  |  | 2018 | On Schedule |  |  |  | None
M2SF-19OR020302032 Per Matt Brainard: Deliverable not uploaded into PICS:NE. It was marked OUO, which prohibits upload into the system. Notes: “This deliverable contains proprietary information and therefore its distribution is limited. Please contact Matt Feldman at feldmanmr@ornl.gov or (865) 241-8801 for further information.” Main Document title: “Transportation Cost Estimate Database Report”. | M2 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Cost Estimate Database Report | Transportation Cost Estimate Database Report | Level 2 milestone report detailing up-to-date logistics and capital costs associated with SNF transport. | 2019-01-25 |  | 2019-01-25 |  | 2019 | Complete | Transportation Cost Estimate Database Report | Feldman, Matt | Feldman, Matt | OUO |  |  | Transportation, JTOM, Cost Data, UDB, NGSAM
M2SF-19OR020302032 Per Matt Brainard: Transportation Cost Estimate Database Report, Milestone marked complete on 1/25/2019, however the Deliverable was marked as OUO, which prohibits upload into PICS:NE. Notes: “This deliverable contains proprietary information and therefore its distribution is limited. Please contact Matt Feldman at feldmanmr@ornl.gov or (865) 241-8801 for further information.” Narrative: “The main thrust of this project has been the research, development, and compilation of modern transportation and logistics data and its incorporation into the Unified Database and updates to the Next Generation Systems Analysis Model and in particular the transportation operations component of that model. The modernization of the transportation data is key to improving the fidelity of the systems analyses work supporting the development of an integrated waste management system.” Supersedes M2SF-18OR020302042 | M2 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Cost Estimate Database Report | Transportation Cost Estimate Database Report | Level 2 milestone report detailing up-to-date logistics and capital costs associated with SNF transport. | 2019-01-25 |  | 2019-01-25 |  | 2019 | Complete | Transportation Cost Estimate Database Report | Feldman, Matt | Feldman, Matt | OUO |  |  | Transportation, JTOM, Cost Data, UDB, NGSAM
M2SF-19OR020405013 Per Kaushik Banerjee: This is a software package and not a report. You can get the software from RSICC. Supersedes M2SF-18OR020405014. | M2 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Release of UNF-ST&DARDS Version 4.0 | UNF-ST&DARDS Version 4.0 | This deliverable includes UNF-ST&DARDS Version 4.0 software code with up-to-date user documentation. Version 4.0 is planned to be a general-purpose (rather than test & evaluation only) version with capabilities for use in performing thermal analysis in addition to those capabilities previously included in Version 3.1.1. Version 4.0 is currently planned to be a limited release through the Radiation Safety Information Computational Center (RSICC) and, similar to previous versions released through RSICC, will not include data in the unified database (UDB). | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | UNF-ST&DARDS Version 4.0 | Kaushik Banerjee | Kaushik Banerjee | None
M2SF-19OR020405013 Per Kaushik Banerjee: This is a software package. No document/ | M2 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Release of UNF-ST&DARDS Version 4.0 | UNF-ST&DARDS Version 4.0 | This deliverable includes UNF-ST&DARDS Version 4.0 software code with up-to-date user documentation. Version 4.0 is planned to be a general-purpose (rather than test & evaluation only) version with capabilities for use in performing thermal analysis in addition to those capabilities previously included in Version 3.1.1. Version 4.0 is currently planned to be a limited release through the Radiation Safety Information Computational Center (RSICC) and, similar to previous versions released through RSICC, will not include data in the unified database (UDB). | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | UNF-ST&DARDS Version 4.0 | Banerjee, Kaushik | Banerjee, Kaushik | None
M2SF-19SN010201048 supercedes M3SF-18SN0102010414 Per Charles Bryaqn: M2SF-19SN010201048 is an milestone activity, not a report. There is no report. | M2 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Initiation of crack growth experiments at SNL using RH controlled load frames | Initiation of crack growth experiments at SNL using RH controlled load frames | Sandia will purchase one or more load frames for performing SCC crack growth testing in controlled RH environments, and will, by 3/15/19, have initiated SC crack growth experiments under atmospheric conditions. | 2019-03-15 |  |  | This work is on schedule. Experiments were initiated in January, and an email documenting the work and meeting the milestone will be submitted prior to March 15. | 2019 | 90 Day |  |  |  | None
M31UF020102 Per Mark Nutt: M31UF020102, FY11 UFD External and International Interaction Summary – I don’t have a record for this one. I think FY11 may have been when Jens Birkholzer became the UFD international lead. We may not have completed this milestone out of ANL. | M3 | 1.02.08.02 | ANL | FTAN11UF0201 | External and International Interactions - ANL |  |  | FY11 UFD External and International Interaction Summary
M31UF020502 Requested, but no response. | M3 | 1.02.08.02 | LBNL | FTLB11UF0205 | External and International Interactions - LBNL |  |  | International Activities Report (LBNL)
M31UF031102 Requested, but no response. | M3 | 1.02.08.03 | LANL | FTLA11UF0311 | Technical Bases / Lessons Learned |  |  | LANL Input to SNL L2 MS: Report on the Basis for Selection of Disposal Options
M31UF032005 Requested, but no response. | M3 | 1.02.08.03 | LANL | FTLA11UF0320 | Repository Science/Regional geology&tectonic hazard |  |  | End of FY 2011 Status Report for Repository Science/Regional Geology and Tectonic Hazard
M31UF033703 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0337 | Technical Bases / Lessons Learned |  |  | System-Wide Integration and Site Selection Concepts for Future Disposition Options for HLW
M31UF033802 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0338 | FEPS |  |  | Used Fuel Disposition Features, Events, and Processes (FEPs): FY11 Progress Report
M31UF034001 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0340 | Generic Natural System Evaluation |  |  | Long-term R&D plan for natural system evaluation & tool development
M31UF034302 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0343 | Perspectives on Nuclear Waste Management |  |  | Perspectives on Nuclear Waste Management
M31UF034602 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0346 | Repository Science/THCM near field |  |  | FY11 Development of Fully Coupled Repository THMC Simulation Tools report
M31UF034802 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0348 | Repository Science/waste form degradation & RN mobilization |  |  | Used Fuel Waste Form Degradation FY11 Summary Report
M31UF034902 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0349 | Repository Science/Engineered material performance |  |  | Engineered material performance - EOFY Status Report
M31UF035002 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0350 | Repository Science/flow and transport saturated media |  |  | Synthesis report on progress made FY11 in flow and transport saturated media
M31UF035303 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0353 | Repository Science/salt disposal investigations |  |  | Develop and deliver a test plan for hot salt reconsolidation work
M31UF035304 Requested, but no response. | M3 | 1.02.08.03 | SNL | FTSN11UF0353 | Repository Science/salt disposal investigations |  |  | EOFY FY11 Status report including a summary of progress on preliminary hot salt reconsolidation processes that will feed the development of a long term test plan.
M31UF035401 Requested, but no response. | M3 | 1.02.08.03 | SRNL | FTSR11UF0354 | Technical Bases / Lessons Learned |  |  | SRNL Input to SNL L2 MS: Report on the Basis for Selection of Disposal Options
M31UF035502 Requested, but no response. | M3 | 1.02.08.03 | SRNL | FTSR11UF0355 | Inventory |  |  | Fuel Cycle Waste Inventory Update
M31UF035701 Per Robert Jones: This appears to indicate an FY 2011 update to FCRD-USED-2010-000105, Rev 0; M4508032604 (FY 2010). I cannot find a Revision 1 to this document. | M3 | 1.02.08.03 | SRNL | FTSR11UF0357 | LLW Disposition |  |  | LLW Disposal Issues and Alternatives
M31UF040302 Requested, but no response. | M3 | 1.02.08.04 | INL | FTIN11UF0403 | Concept Evaluations | [8 empty] | Milestone completed | [6 empty] | Status Report for INL Concepts Evaluation.pdf
M31UF040402 Requested, but no response. | M3 | 1.02.08.04 | INL | FTIN11UF0404 | R&D Opportunities | [8 empty] | Milestone completed | [6 empty] | Status Report for INL R&D Opportunities.pdf
M31UF040702 Requested, but no response. | M3 | 1.02.08.04 | LLNL | FTLL11UF0407 | R&D Opportunities | [8 empty] | The "Summary letter report of LLNL support to Storage R&D" was delivered on schedule 8/31/11 via email to Cost Account Manager at SNL.
M31UF041203 Requested, but no response. | M3 | 1.02.08.04 | ORNL | FTOR11UF0412 | Transportation | [8 empty] | This milestone is under development. The necessary computations have been completed and results are currently being analyzed and written up. | [6 empty] | FTOR11UF0412_Year-end_Report_ORNL.pdf
M31UF041504 Requested, but no response. | M3 | 1.02.08.04 | PNNL | FTPN11UF0415 | Security | [8 empty] | Efforts to write different sections of the final end-of-year report were underway in August, as the Used Fuel Storage & Security working group moves to identify representative scenarios, and create baseline risk measurements to support future analysis. The draft report was submitted on 8/31/11.
M31UF041603 Requested, but no response. | M3 | 1.02.08.04 | PNNL | FTPN11UF0416 | Transportation | [8 empty] | Milestone completed on 8/31/11. | [6 empty] | PNNL-20691.pdf
M31UF041902 Requested, but no response. | M3 | 1.02.08.04 | SNL | FTSN11UF0419 | Security | [8 empty] | No variance. Milestone is on schedule.
M31UF042003 Requested, but no response. | M3 | 1.02.08.04 | SNL | FTSN11UF0420 | Transportation | [8 empty] | Report completed September 28, 2011; uploaded to FCPICS September 30, 2011. | [6 empty] | SNL_Transportation_yearendFY11_.docx
M31UF042108 Requested, but no response. ULR | M3 | 1.02.08.04 | SRNL | FTSR11UF0421 | Concept Evaluations | [8 empty] | On schedule. Milestone is on schedule to meet the 8/31/11 finish date. | [6 empty] | TEF Concept Evaluation Report Rev-0 Aug1211.pdf
M31UF042503 Requested, but no response. | M3 | 1.02.08.04 | INL | FTIN11UF0425 | Evaluation of Dry Cask Storage
M3508030502 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080305 | Rapid Response |  |  | End of Year Report Containing Summary of Inquiries Addressed FY10
M3508030502 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080305 | Rapid Response | [8 empty] | On schedule
M3508030601 Requested, but no response. | M3 | 1.5.08.03 | LLNL | LL1015080306 | Technical Bases - Lessons Learned |  |  | Provide expertise and input on L2 report on international approaches to site characterization and various geologic media
M3508030701 Requested, but no response. | M3 | 1.5.08.03 | LANL | LA1015080307 | Technical Bases - Lessons Learned |  |  | Provide expertise and input to L2 report on various geologic media
M3508030801 Requested, but no response. | M3 | 1.5.08.03 | SRNL | SR1015080308 | Technical Bases - Lessons Learned |  |  | Expertise and input to L2 report on lessons learned from LLW evaluations and various geologic media
M3508031201 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080312 | Legal and Regulatory Framework Analysis |  |  | Legal and Regulatory Framework Analysis End of FY10 Status Report
M3508031403 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080314 | Storage - R&D Opportunities | [8 empty] | Finished on schedule.
M3508031604 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080316 | Storage - Concept Evaluation | [8 empty] | Work is on schedule. | [6 empty] | Finalreportr-10-2010.pdf
M3508032102 Requested, but no response. | M3 | 1.5.08.03 | INL | IN1015080321 | LLW Disposition - Quantities and Inventory |  |  | LLW Inventory Once Through
M3508032903 Requested, but no response. | M3 | 1.5.08.03 | SNL | SN1015080329 | Storage - Security | [8 empty] | Milestone (final report) is on target -- currently in review. there is no milestone variance.
M3508033002 Requested, but no response. | M3 | 1.5.08.03 | INL | IN1015080330 | Storage - R&D Opportunities | [8 empty] | Work started in May to support FEPS review but time was limited and real work will not begin until mid June. Costs for work done in May were charged inappropriately and will be moved to the charge number next month. June: Work did not begin until mid June. Costs will be posted by next month for this months activities. Expected completion is now July 30.
M3508033003 Requested, but no response. | M3 | 1.5.08.03 | INL | IN1015080330 | Storage - R&D Opportunities | [8 empty] | Milestone delayed due to difficulty obtaining resources to perform work and project management at SNL revised date to delivery prior to quarterly meeting on July 27-28,2010
M3508033102 Requested, but no response. | M3 | 1.5.08.03 | INL | IN1015080331 | Storage - Concept Evaluation | [8 empty] | INL staff is not preparing this report but rather contributing to text and conducting reviews. Input provided in mid July. Costs will appear when subcontracts posts invoices.
M3508040101 Per Mark Nutt: M3508040101, FEPs Categorization and Cross-Map – I cannot find anything on this. Jim Cunnane, a long ago Argonne retiree was working with Geoff Freeze. Perhaps Jim sent an e-mail to Geoff Freeze with Argonne’s input since this was input to a higher-level milestone. | M3 | 1.5.08.04 | ANL | AN1015080401 | FEPs Categorization and Cross-Map |  |  | L3 Milestone to provide input and support for the SNL L2 milestone
M3508040201 Requested, but no response. | M3 | 1.5.08.04 | LBNL | LB1015080402 | FEPs Categorization and Cross-Map |  |  | L3 Milestone to provide inupt and support for the SNL L2 milestone
M3508040301 Requested, but no response. | M3 | 1.5.08.04 | LLNL | LL1015080403 | FEPs Categorization and Cross-Map |  |  | L3 Milestone to provide input and support for the SNL L2 milestone
M3508040401 Requested, but no response. | M3 | 1.5.08.04 | LANL | LA1015080404 | FEPs Categorization and Cross-Map |  |  | L3 Milestone to provide inupt and support for the SNL L2 milestone
M3508041301 Requested, but no response. | M3 | 1.5.08.04 | INL | IN1015080413 | Disposal Systems Evaluations - Direct Disposal of Electrorefiner Salt |  |  | Write report on processing issues relevant to direct disposal of ER salt
M3508041701 Requested, but no response. | M3 | 1.5.08.04 | SNL | SN1015080417 | Disposal Systems Evaluations and Tool Development - Natural System Evaluation |  |  | Submission of a detailed work plan
M3508041703 Requested, but no response. | M3 | 1.5.08.04 | SNL | SN1015080417 | Disposal Systems Evaluations and Tool Development - Natural System Evaluation |  |  | End of year progress report
M3508042602 Requested, but no response. | M3 | 1.5.08.04 | SNL | SN1015080426 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | End of FY10 Progress report
M3FT-12IN08130711 Per Matt Brainard: re-named, and re-dated in the FY13 Field Demonstration WP | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Perform inspections and prepare final data | Conduct Inspections and Prepare final data | This will require actual inspection, data gathering and final preparation of data for submittal to NRC as well as EPRI and DOE for analysis | 2012-09-28 02:00 | 2013-03-31 02:00 |  | Milestone to be renamed and redated in FY 13 Field Demonstration WP | 2012 | Expected Late |  |  |  | None
M3FT-12IN0813077 Per Matt Brainard: re-named, and re-dated in the FY13 Field Demonstration WP | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Utility/canister selection amd inspection method identified | Utility/canister selection amd inspection method identified | Select utility/canister vendor and develop inspection and data collection methods | 2012-04-30 02:00 | 2012-10-31 12:00 |  | Milestone renamed and dated for FY 13 in Field Demonstration WP | 2012 | Late |  |  |  | None
M3FT-12IN0813078 Per Matt Brainard: re-named, and re-dated in the FY13 Field Demonstration WP | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Fabricate inspection tooling | Fabricate inspection tooling | Inspection tooling is fabricated for initial facility | 2012-05-31 02:00 | 2012-12-31 12:00 |  | Milestone to be renamed and dated in FY13 Field Demonstration Testing Work Package | 2012 | Late |  |  |  | None
M3FT-12IN0813079 Per Matt Brainard: re-named, and re-dated in the FY13 Field Demonstration WP | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Qualify procedures and inspection techniques | Qualify procedures and inspection techniques | Qualify procedures and test inspection techniques | 2012-06-25 02:00 | 2012-12-31 12:00 |  | Milestone to be renamed and redated in FY 13 Field Demonstration WP | 2012 | Late |  |  |  | None
M3FT-12LA0805031 Per Matt Brainard: Was delayed into FY13, with a Revised Finish Date entered 12/14/2012. I am having a hard time tracking this milestone in FY13 in PICS:NE as Neil Brown was no longer a WPM in FY13 and his work package titled “ST Engineered Materials Experimental – LANL” also did not exist in FY13. If the Work Package didn’t carry over into FY13, it’s possible the milestone didn’t either. Suggest marking this milestone cancelled at the end of FY12. | M3 | 1.02.08.05.03 | LANL | FT-12LA080503 | ST Engineered Materials Experimental - LANL | Brown, Neil | Sorenson, Ken | Summary Report - Neutron Abosorber Sensitization and Corrosion Behavior | Summary Report - Neutron Absorber Behavior | Provide summary report describing work to date and planned future activities. | 2012-08-31 10:00 | 2012-12-14 06:00 |  | corrosion testing is beginning to be completed by revised date. | 2012 | Late |  |  |  | None
M3FT-12LA08180116 M3FT-12LA08180116 was superseded by FY13 milestone M3FT-13LA0818017 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Summary Report on Salt Instrumentation Development | Summary Report on Salt Instrumentation Development | Develop a summary report on the development of the generic salt measurement and data collection techniques and to make usefully benefit of the unique skill sets and resources currently available from past WIPP studies, the Yucca Mountain Project, and from salt testing performed internationally. This milestone as listed in the referenced study plan is scheduled for 9/16/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-03-29 12:00 |  |  |  | 2012 | On Schedule |  |  |  | None
M3FT-12LA0818013 carried over to FY13: M3FT-13LA0818012 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Test Plan for Forensic Analysis in the North Experimental Area of WIPP | Test Plan for Forensic Analysis in the North Experimental Area of WIPP | The Salt Disposal Investigations (SDI) test coordination office will develop a test plan that will determine the type, location and number of tests to examine during the re-entry of the North Experimental Area of WIPP. This milestone as listed in the referenced study plan is scheduled for 9/27/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-03-29 14:00 |  |  |  | 2012 | On Schedule |  |  |  | None
M3FT-12LA0818014 superceded by M4FT-13LA08018013 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Re-entry Plan for Mining into the North Experimental Area of WIPP | Re-entry Plan for Mining into the North Experimental Area of WIPP | WIPP M&O personnel and LANL will identify the process for planning a reentry into the north experimental area; this plan will be coordinated with the test planning. This milestone as listed in the referenced study plan is scheduled for 9/27/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-03-29 10:00 |  |  |  | 2012 | On Schedule |  |  |  | None
M3FT-12PN0805051 Per Matt Brainard: M3FT-12PN0805051 – Delayed past FY12. Revised finish date entered as 12/14/2012 – “The final repayment of $50K that HQ had directed to come from this account early in FY12 was finally received in September, but not early enough to allow the programmatic Test Plan for Cladding to be completed. This milestone (M3FT-12PN0805051) will now be completed by 12/14/12.” Note: The ST Engineered Materials Experimental – PNNL work package seems to have been cancelled for FY13, however FT-13PN080505 - ST Storage and Transportation Experiments – PNNL appears to have an M3 milestone due 12/14/2012 that was actually completed on 1/14/2013. There is no clear cross-walk in titles, but M3FT-13PN0805058: NDE for Weld Examination report may have superseded M3FT-12PN0805051: Clad Workshop and Test Plan, which is attached. Otherwise, this can be chalked up to missing deliverable. | M3 | 1.02.08.05.05 | PNNL | FT-12PN080505 | ST Engineered Materials Experimental - PNNL | Hanson, Brady | Sorenson, Ken | Clad Workshop and Test Plan | Clad Worshop and Test Plan | Clad workshop and test plan. | 2012-01-27 06:00 | 2012-12-14 03:00 |  | Milestone delayed. See Issues. | 2012 | Late |  |  |  | None
M3FT-12SN0806101 Per Matt Brainard: possibly superseded by FY13 milestone M2FT-13SN08180341 (Coupled Thermal-Hydrological-Mechanical Processes in Salt) – Best Guess. Milestone mapping inconsistent. | M3 | 1.02.08.06.10 | SNL | FT-12SN080610 | Salt Disposal Investigations (SDI) Coupled Processes - SNL | Hansen, Francis | McMahon, Kevin | Benchmark Thermomechanical Computational Evaluation | Benchmark evaluation of thermomechanical modeling | This workpackage will evaluate the state-of-the-art thermomechanical coupled modeling capabilities to establish the best tools for design, analysis, performance assessment and operations for a salt repository and any field testing that might be deployed to evaluate the proof of principle. | 2012-09-30 08:00 | 2012-10-01 02:00 |  | Late | 2012 | Expected Late |  |  |  | None
M3FT-12SN0814102 same as M3FT-13SN0905023 | M3 | 1.02.08.14.10 | SNL | FT-12SN081410 | Siting Experience Database - SNL | Price, Laura | Nutt, Mark | Status Memo | Interim Status of Siting Experience Archive | A memo to DOE that provides the status of the archive and database. | 41181 | 41239.4167 |  | The start of this project was delayed two months because of a delay in receiving funding. All milestones have thus been delayed two months. | 2012 | Expected Late |  |  |  | None
M3FT-12SN0814105 same as M3FT-13SN0905025 | M3 | 1.02.08.14.10 | SNL | FT-12SN081410 | Siting Experience Database - SNL | Price, Laura | Nutt, Mark | Provide a report describing the archive, its content, and its use | US Nuclear Facility Siting Experience Archive | Produce a report describing the archive, its content, and how it is used. The report will include a short synopsis of each facility for which documentation has been obtained and a summary of the siting information identified in the data base. | 41305.1667 | 41362.5 |  | The start of this project was delayed two months because of a delay in receiving funding. All milestones have thus been delayed two months. | 2012 | Expected Late |  |  |  | None |  | FCRD-UFD-2012-000088
M3FT-12SN0815053 Per Sam Durbin: No document is available. | M3 | 1.02.08.15.05 | SNL | FT-12SN081505 | ST Security - SNL | Duran, Felicia | Sorenson, Ken | OUO Report on Self Protection, Material Attractiveness and Security Assessment for Used Fuel Storage | OUO Report on Self Protection, Material Attractiveness and Security Assessment for Used Fuel Storage | OUO Report on Self Protection, Material Attractiveness and Security Assessment for Used Fuel Storage | 2012-08-15 04:00 | 2012-10-31 02:00 |  | Availability of staff during Aug/Sep has not allowed completion of milestone | 2012 | Late |  |  |  | None
M3FT-12SN0817033 Per Geoff Freeze: I do not have any record of the Deep Borehole Report you list below. I have attached one, also from 2012, with a similar title and a different FCRD # (FCRD-USED-2012-000269). | M3 | 1.02.08.17.03 | SNL | FT-12SN081703 | Deep Bore Hole - SNL | Mackinnon, Robert | Mackinnon, Robert | Plan for RD&D Roadmap | Plan for RD&D Roadmap | develop plan for the RD&D Roadmap within 30 days of receipt of money | 2012-05-15 02:00 | 2012-05-22 04:00 | 2012-05-22 02:00 | Milestone was completed one week late. | 2012 | Completed Late |  | Arnold, Bill | MacKinnon, Robert | None |  | FCRD-UFD-2012-000449
M3FT-12SN08180227 replaced by M2FT-12SN0806081 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | MacKinnon, Robert | MacKinnon, Robert | Document for (UFD Milestone M2 M2FT-12SN0806081) Coupled Thermal-Hydrological-Mechanical Processes in Salt | Coupled Thermal-Hydrological-Mechanical Processes in Salt | UFD Milestone M2 M2FT-12SN0806081 Coupled Thermal-Hydrological-Mechanical Processes in Salt, QRL3, is actually to be completed 11/15/2012. | 2012-11-15 06:00 |  |  | The draft is written and the deliverable is on schedule | 2012 | 90 Day |  |  |  | None
M3FT-12SN08180227 replaced by M2FT-12SN0806081 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Mackinnon, Robert | Mackinnon, Robert | Document for (UFD Milestone M2 M2FT-12SN0806081) Coupled Thermal-Hydrological-Mechanical Processes in Salt | Coupled Thermal-Hydrological-Mechanical Processes in Salt | UFD Milestone M2 M2FT-12SN0806081 Coupled Thermal-Hydrological-Mechanical Processes in Salt, QRL3, is actually to be completed 11/15/2012. | 2012-11-15 06:00 |  |  | The draft is written and the deliverable is on schedule | 2012 | 90 Day |  |  |  | None
M3FT-13AN09020134 Per Matt Brainard: TSM Version 7 was originally planned for FY14 completion on 1/31/2014 and was superseded by M3FT-14AN09020522 - Total System Model Version 7 Development, which was completed on 1/31/2014. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Completion of TSM Version 7. TSM Version 7 is the initial operating version of the Total System Model. The milestone includes: 1) TSM Version 7, 2) TSM Version 7 User Manual, 3) TSM Version 7 Preprocessor User Manual.” Document Author/Owner: “Terranear PMC”. Main Document Title: “Total System Model Version 7 Development”. DMS Number: “FCRD-NFST-2014-000349”. | M3 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL |  | Nutt, Mark | TSM Version 7 | TSM Version 7 | TSM Version 7 is identified as the initial operating version of the model. The milestone will include: 1) TSM Version 7, and 2) TSM Version 7 User Manual. | 2014-01-31 02:00 |  |  | On schedule | 2013 | On Schedule |  |  |  | None
M3FT-13AN0902057 Per Matt Brainard: Decision Roadmap was originally planned for FY14 completion on 11/29/2013 and was superseded by M3FT-14AN0902014 - Decision Roadmap, which was completed on 11/27/2013. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “The decision roadmap is a high level representation of the major decisions that will be required in the implementation of the Administration’s Strategy as it is currently interpreted.” Document Author/Owner: “Michael Samsa”. DMS Number: “FCRD-NFST-2014-000345”. | M3 | 1.02.09.02.05 | ANL | FT-13AN090205 | NFST Decision Framework - ANL |  | Nutt, Mark | Decision Roadmap | Initial NFST Decision Roadmap | The “decision roadmap” will outline major decision or “choice” milestones that require or are candidates for decision-analytic support. The decision roadmap will be a living document, updated as necessary to track future decision support requirements. | 2013-11-29 02:00 |  |  | On schedule. | 2013 | 90 Day |  |  |  | None
M3FT-13AN0902058 Per Matt Brainard: Preliminary Taxonomy was originally planned for FY14 completion on 12/31/2013, however the milestone did not get mapped into the follow-on FY14 work package accordingly. It appears to have been cancelled between fiscal years. Deliverable is missing. | M3 | 1.02.09.02.05 | ANL | FT-13AN090205 | NFST Decision Framework - ANL |  | Nutt, Mark | Preliminary Taxonomy | Preliminary Taxonomy of Metrics, Measures, and Tradeoff Preferences | Initial catalogue of decision metrics, measures, decision analytic techniques and tradeoff preferences. | 2013-12-31 04:00 |  |  |  | 2013 | On Schedule |  |  |  | None
M3FT-13AN0902067 Per Matt Brainard: Initial Execution Strategy Analysis Final Report was originally planned for FY14 completion on 3/31/2014 and was superseded by M3FT-14AN0902114 - Initial Execution Strategy Analysis Final Report, which was completed on 3/30/2014. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Report describing demonstration phase development of the NFST Execution Strategy Analysis tool.” Document Author/Owner: “Predicus LLC”. Deliverable Description: “Report describing demonstration phase development of the NFST Execution Strategy Analysis tool.” Main Document Title: “Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Demonstration Tool Development”. DMS Number: “FCRD-NFST-2014-000352”. Lab ID No - Other: “curie.ornl.gov”. Notes: “Transmitted to DMS via e-mail (wnutt@anl.gov to fctdms@inl.gov) on March 30, 2014”. | M3 | 1.02.09.02.06 | ANL | FT-13AN090206 | Execution Strategy Analysis - ANL |  | Nutt, Mark | Initial Execution Strategy Analysis Final Report | Initial Execution Strategy Analysis Final Report | Initial Execution Strategy Analysis Final Report | 2014-03-31 01:00 |  |  |  | 2013 | On Schedule |  |  |  | None
M3FT-13AN0902071 Per Matt Brainard: Next Generation UNF Simulation Tool Development Plan was originally planned for FY14 completion on 10/31/2013 and was superseded by M3FT-14AN09020311 Next Generation UNF Simulation Tool Development Plan, which was completed on 12/13/2013. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Review draft of Next Generation Waste Management Logistics Simulation Tool Development Plan completed and delivered on schedule.” Document Author/Owner: “James St. Aubin, ANL”. Main Document Title: “Next Generation UNF Simulation Tool Development Plan”. DMS Number: “FCRD-NFST-2014-000346”. | M3 | 1.02.09.02.07 | ANL | FT-13AN090207 | Next Generation UNF Logistics Modeling - ANL |  | Nutt, Mark | Next Generation UNF Simulation Tool Development Plan | Next Generation UNF Simulation Tool Development Plan | Next Generation UNF Simulation Tool Development Plan | 2013-10-31 05:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None
M3FT-13AN0902072 Per Matt Brainard: Draft Logistics Model Requirements Document was originally planned for FY14 completion on 10/11/2013 however the milestone did not get mapped into the follow-on FY14 work package or was embedded as part of another milestone accordingly. There is no clear mapping of the milestone from FY13 to FY14. Deliverable is missing. | M3 | 1.02.09.02.07 | ANL | FT-13AN090207 | Next Generation UNF Logistics Modeling - ANL |  | Nutt, Mark | Draft Logistics Model Requirements Document | Draft Logistics Model Requirements Document | Provide a draft of the logistics model requirements document for NFST management and DOE review | 2013-10-11 04:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None
M3FT-13AN0909011 Per Matt Brainard: Not available in PICS:NE. Draft maintained as NFST internal draft report only. No DMS number available. | M3 | 1.02.09.09.01 | ANL | FT-13AN090901 | Pre-Conceptual Planning and Obtain Mission Need (CD-0) Approval - ANL | Nutt, Mark | Nutt, Mark | Completion of DRAFT CD-0 Input Package for Initiation of Conceptual Design for Storage and Transportation System | Completion of DRAFT CD-0 Input Package for Initiation of Conceptual Design for Storage and Transportation System | Completion of DRAFT CD-0 input package for initiation of conceptual design of consolidated storage facility and associated transportation system | 2013-02-28 03:00 | 2013-03-03 01:00 | 2013-03-03 01:00 |  | 2013 | Completed Late |  | Nutt, Mark | Nutt, Mark | None
M3FT-13IN0802062 Per Charles Bryan: I don’t have this INL report. It is not clear from the notes if it was ever completed. | M3 | 1.02.08.02.06 | INL | FT-13IN080206 | ST Field Demonstration - INL |  | Sorenson, Ken | Data report on in-situ environmental corrosion data for SS canisters | Data report on in-situ environmental corrosion data for SS canisters | Data report on in-situ environmental corrosion data for SS canisters | 2013-09-30 06:00 | 2013-10-10 02:00 |  | All funds expended, the delivery device was not successfully completed and therefore no data could be taken. Development was stopped after an overrun of about $25K | 2013 | Expected Late |  |  |  | None
M3FT-13IN0907013 Per Matt Brainard: Draft Public Relations Needs Assessment, Planning, and Strategy Documentation and Draft Communication Plan was completed on 7/9/2013, however the Deliverable Form in PICS:NE was submitted and subsequently approved blank and without an uploaded document. Deliverable is missing. Narrative: “Documentation has been complete and delivered to DOE for review.” | M3 | 1.02.09.07.01 | INL | FT-13IN090701 | CX Communication Products - INL | Lientz, Amy | Nutt, Mark | Draft Public Relations Needs Assessment, Planning, and Strategy Documentation and Draft Communication Plan | Draft Public Relations Needs Assessment, Planning, and Strategy Documentation on July 12, 2013 for DOE review | Submit Draft Public Relations Needs Assessment, Planning, Strategy Documentation and Draft Communication Plan on July 12, 2013 for DOE review. | 2013-07-12 06:00 | 2013-07-09 02:00 | 2013-07-09 02:00 |  | 2013 | Complete |  |  |  | None
M3FT-13IN0907014 Per Matt Brainard: Final Needs Assessment and Draft Communication Plan was marked Late with a Revised Finish Date stated of 10/31/2013. There are no Milestones/Deliverables associated with the FY14 Follow-on work package, therefore this milestone appears to have been cancelled between fiscal years. Deliverable is missing. | M3 | 1.02.09.07.01 | INL | FT-13IN090701 | CX Communication Products - INL |  | Nutt, Mark | Final Needs Assessment and Draft Communication Plan | Provide Final Needs Assessment to US DOE | Provide Final Needs Assessment and Draft Communication Plan to US DOE | 2013-07-30 02:00 | 2013-10-31 02:00 |  | Extending the finish date one more more - still no update on when funding will be released and project will be able to resume. | 2013 | Late |  |  |  | None
M3FT-13LA0807046 input for other reports - copy not available per Painter | M3 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on integrated tool development for natural system evaluation | Integrated tool development for natural system evaluation | Report on integrated tool development | 2013-09-30 12:00 |  | 2013-09-30 02:00 | Report was delivered to UFD Campaign management on 9/30/2013. | 2013 | Complete |  | Painter, Scott | Painter, Scott | None | M3FT-13LA0807046.pdf | FCRD-UFD-2013-000375
M3FT-13LB0811022 Superseded by M2FT-14LB0811011 Listed in DR and ST Per Matt Brainard: Document unavailable in PICS NE. Delayed into FY14 and not easily mapped into another work package. Could not locate Deliverable. Note from Jens Birkholzer: I took a look and can't find it in my archives. I found the respective FY12 and FY14 versions of the report, but not this one. Then I looked at references in the FY14 version, and only found a reference to the FY12 version. So I believe now that the FY13 version was canceled. | M3 | 1.02.08.11.02 | LBNL | FT-13LB081102 | CX International - LBNL |  | Nutt, Mark | LBNL Report on the Status of UFD Campaign International Activities in Disposal Research | Status of UFD Campaign International Activities in Disposal Research | This is a report that summarizes the status of international collaboration within UFDC's disposal research program. | 2013-09-20 05:00 | 2014-01-31 12:00 |  | On track to meet revised finish date. | 2013 | Expected Late |  |  |  | None
M3FT-13OR0902029 Per Rob Howard: I could not find M3FT-13OR0902029; however, M3FT-16OR090201023 “Preliminary Siting Factors and Considerations v1_4-29-16_R2.pdf” is a revised and updated version of the same deliverable. OUO. Predecisional Draft. Deliberative Process Pre-Decisional Privileged and Confidential | M3 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | NFST Review of Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilitie | Revision 0 of Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilities | Conduct NFST Management Review of Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilities and issue Revision 0 of the document. | 2013-09-23 02:00 |  | 2013-09-23 | Milestone M3FT-13OR0902029 “Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilities.” This document updates information originally captured in the Preliminary Site Requirements and Considerations for a Monitored Retrievable Storage Facility (DOE/RW-315P) using input from current regulatory requirements, U.S. experience over the past two decades (e.g., PFS) international experience and the evolving policy for managing used nuclear fuel. | 2013 | Complete |  | Howard, Rob | Howard, Rob | OUO
M3FT-13PN0810023 Requested, but no response. | M3 |  | PNNL | FT-13PN081002 | ST Storage and Transportation Engineering Analysis - PNNL |  | Sorenson, Ken | Report on Inspection 2 | Report on Inspection 2 | Report on Inspection 2. | 2013-09-27 09:00 | 2014-01-30 06:00 |  | Because of the industry delays in performing the inspections, it was not possible to perform the modeling necessary for milestone M3FT-13PN0810023. This milestone will now be tracked as M3FT-14PN0810035 in FY14. | 2013 | Expected Late |  |  |  | None
M3FT-13SN0815021 Per Sam Durbin: No document is available. | M3 | 1.02.08.15.02 | SNL | FT-13SN081502 | ST Security - SNL | Duran, Felicia | Sorenson, Ken | Review of Security Strategies for Used Fuel Storage and Transportation for a Consolidated Storage Facility | Review of Security Strategies for Consolidated Storage and Transportation | Co-authored report with LLNL to review prior work and make recommendations to DOE for further analyses. | 2013-06-21 14:00 |  | 2013-06-21 04:00 |  | 2013 | Complete |  | Duran, Felicia | Duran, Felicia | OUO |  |  | used fuel storage and transportation security, safeguards and security
M3FT-13SN08180329 Christi and Kris think this was ULR. Can't find document. | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | International Benchmark Calculations of Field Experiments | International Benchmark Calculations of Field Experiments | Generic Salt Repository Benchmarking | Milestone is completed on schedule by due the due date. | 2013 | Complete |  |  |  |  | Arguello, Guadalupe | Leigh, Christi | None | International Benchmark Calc of Field Exp M3FT-13SN08180329.pdf | FCRD-UFD-2013-000322
M3FT-13SN08180339 superceded by FY14 Milestone M3FT-14SN0818017 - Thermomechanical Testing of Intact Salt Results for FY14. | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL |  | Mackinnon, Robert | Update to Coupled Thermal-Hydrological-Mechanical Processes in Salt | Update to Coupled Thermal-Hydrological-Mechanical Processes in Salt | This report updates the report due 11/15/12 funded under FY12. | 2013-09-20 04:00 | 2013-11-15 04:00 |  | This deliverable will be moved into the FY14 work package and tracked there | 2013 | Expected Late |  |  |  | None
M3FT-13SN0912033 Per Matt Brainard: Support "Plan for removing stranded fuel from shutdown sites - PRELIMINARY DRAFT L3 report" was marked Late with a Revised Finish Date stated of 9/30/2013, however the comment provided in September 2013 indicates the milestone was completed. The Deliverable Form was never populated or submitted for approval, therefore the Deliverable is missing. | M3 | 1.02.09.12.03 | SNL | FT-13SN091203 | TR Operational - Shutdown Sites - SNL |  | Feldman, Matt | Support "Plan for removing stranded fuel from shutdown sites - PRELIMINARY DRAFT L3 report" | PRELIMINARY DRAFT L3 report:: Plan for Removing Stranded Fuel from Shutdown Sites. | Draft report for removing stranded fuel from shutdown sites L2 report. | 2013-08-30 16:00 | 2013-09-30 04:00 |  | completed | 2013 | Late |  |  |  | None
M3FT-13SR0902042 Canceled. | M3 | 1.02.09.02.04 | SRNL | FT-13SR090204 | Systems Architecture - SRNL | Carter, Joe | Nutt, Mark | Evaluate Cask and fleet maintenance facility concepts | Cask and fleet maintenance facility concepts | Joint effort with ORNL describing cask/fleet maintenance facilities required for Consolidated Storage Facility. Develop cask and fleet maintenance facility concepts that could by integrated into a waste management system architecture. | 2013-05-31 02:00 |  | 2013-05-31 |  | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | Milestone #_ M3FT-13SR0902042.pdf |  | Email: To John Wagner and Mark Nutt
M3FT-13SR0908056 Per Matt Brainard: Deliverable not uploaded to PICS:NE. No notes indicating why. Document Author: “Joe T . Carter/Roger Duke”. Deliverable form submitted and approved blank. | M3 | 1.02.09.08.05 | SRNL | FT-13SR090805 | Technical Support for Storage Design Concepts Evaluation - SRNL | Smith, Pat | Wagner, John | Complete the initial draft of a Project Management Plan. | Complete the initial draft of a Project Management Plan. | Initiate development of a Project Management Plan. The plan is to be consistent with Project Management Institute (PMI) guidelines for successfuel projects. See Table 1 for the 16 elements that makes up the project management plan. | 2013-10-31 |  | 2013-10-31 | On Schedule. | 2013 | 90 Day |  | Carter, Joe | Carter, Joe | None
M3FT-14HQ0911023 Per Matt Brainard: Milestone was delayed into FY15 for completion on 10/31/2014. During the FY15 planning phase, this milestone appears to have been dropped as there is no clear crosswalk in milestone titles (e.g. potential supersede is “M3FT-15ID09110210-Update Routing Methodology Report with Input from Stakeholders” but the titles and due dates do not match). Therefore, there is no deliverable to provide for this milestone. | M3 | 1.02.09.11.02 | DOE-HQ | FT-14HQ091102 | TR: Institutional - Industry Contract (Northwind) - DOE-HQ | Bates, Melissa | Feldman, Matt | Draft Report documenting the routing analysis for shipments from shutdown reactor sites | Report documenting the routing analysis for shipments from shutdown reactor sites | Draft Report documenting the routing analysis for shipments from shutdown reactor sites | 2014-08-15 02:00 | 2014-10-31 |  | Revised into FY15. | 2014 | Late |  |  |  | None |  | FCRD-NFST-2014-000090
M3FT-14HQ0912053 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Narrative: “This deliverable was submitted on September 16, 2014. However, PICS system will not allow the deliverable to be uploaded (file size too large). Instructions for how to access the file has been included in the notes section below. The October 30, 2014 completion date shown only represents the date this information was uploaded into PICS.” Main Document Title: “Stakeholder Tool for Assessing Radioactive Transportation (START) Version 1.0 User Manual”. Notes: A full draft of the START, Version 1.0 user manual has been completed and is ready for review and comment. Due to the file size, the document can be retrieved at the following url: ftp://transp40.vuse.vanderbilt.edu/tdot_vulnerability/User_Manual.zip. i.d.: generic. p.w.: VUceeshare. If you do not presently have an active START account, you may apply for one by going to the START url and clicking on the Register option: http://ec2-54-80-251-230.compute-1.amazonaws.com/start/Account/Login. | M3 | 1.02.09.12.05 | DOE-HQ | FT-14HQ091205 | TR: Operational - DOE-HQ | Bates, Melissa | Feldman, Matt | Develop draft User's Manual documenting the process for using the routing analysis tool | Develop draft User's Manual documenting the process for using the routing analysis tool | Develop draft User's Manual documenting the process for using the routing analysis tool | 2014-08-29 04:00 | 2014-10-30 | 2014-10-30 02:00 | Completed on 10/30/2014. | 2014 | Late | Stakeholder Tool for Assessing Radioactive Transportation (START) Version 1.0 User Manual |  |  | None
M3FT-14ID0820011 Document not available in PICS:NE. Note: “No Document Produced” entered as Main Document Title on Deliverable Form. | M3 | 1.02.08.20.01 | DOE-ID | FT-14ID082001 | High Burnup Cask Demo Project - DOE-HQ | Larson, Ned | Couch, Brad | Public comments on the Draft Test Plan | Public comments on the Draft Test Plan | Public comments on the Draft Test Plan | 2013-12-20 06:00 |  | 2013-12-16 02:00 |  | 2014 | Complete | No document produced |  |  | None |  | FCRD-UFD-2014-000342
M3FT-14IN0805027 Carryover to FY15: M3FT-15IN0805023 | M3 | 1.02.08.05.02 | INL | FT-14IN080502 | Experiments - INL | Marschman, Steve | Sorenson, Ken | SST Vessel Conceptual Design | SST Vessel Conceptual Design | Report documenting the designs so they can be evaluated by other project participants and serve to obtain approval from customer to proceed with at least one of the designs. Develop two concepts for SST vessels (one for in-cell use and one for placement outside a building). This is a small task, so detailed construction designs cannot be developed. | 2014-09-26 16:00 | 2014-11-28 05:00 |  | This report will be completed at the end of November. Resources were not available to work on this report at the end of the fiscal year so it was deffered to FY15. | 2014 | Expected Late |  |  |  | None |  | FCRD-UFD-2014-000313
M3FT-14OR09030111 Per Josh Jarrell: Do NOT include in SP site - available through PICS/NE | M3 | 1.02.09.03.01 | ORNL | FT-14OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Nutt, Mark | CURIE User Manual | CURIE User Manual | Prepare a complete CURIE user manual to familiarize the users with the website and its functionality. | 2014-09-19 04:00 |  | 2014-09-19 | This manual highlights the capabilities in CURIE as well as provides information to users on how to use (upload documents, edit documents, register, etc.) CURIE. This document will be updated annually to ensure that future improvements in CURIE are captured. | 2014 | Complete | CURIE User Manual | Josh Jarrell | Josh Jarrell | None | 2014-09-19_FCRD-NFST-2014-000353_CURIE-User-Manual_final.pdf | FCRD-NFST-2014-000353
M3FT-14OR0904023 Per Josh Jarrell: Do NOT include in SP site. Not available through PICS/NE, but Josh can get through CURIE if needed. | M3 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Draft of Standardization Assessment Roadmap | Draft of Standardization Assessment Roadmap | Preliminary Draft to develop a systematic, technical work plan and approach for performing a quantitative evaluation of transitioning to standardized canisters. This roadmap will clearly define the objective of the assessment, the scenarios to be evaluated, the data and capabilities need to evaluate the scenarios, and other tasks required to achieve the objective. | 2014-01-24 04:00 |  | 2014-01-24 |  | 2014 | Complete |  | Josh Jarrell | Josh Jarrell | None |  | FCRD-NFST-2014-000355
M3FT-14OR0904024 Per Josh Jarrell: Do NOT include in SP site. Not available through PICS/NE, but Josh can get through CURIE if needed. | M3 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Draft of Preliminary Standardization Assessment | Draft of Preliminary Standardization Assessment | Draft of preliminary quantitative evaluation of transitioning to standardized canisters. This preliminary assessment is intended to document the status of the assessment, including preliminary findings, but is expected to be limited in terms of the completeness of the assessment due to time allowed to complete it and the available systems analysis capabilities and accuracy of require data. | 2014-07-25 02:00 |  | 2014-07-25 |  | 2014 | Complete | Initial Standardized Canister System Evaluation | Josh Jarrell | Josh Jarrell | None |  | FCRD-NFST-2014-000356
M3FT-14OR09050110 Per Matt Brainard: Import GC-859 data into UNF-ST&DARDS was originally planned for FY15 completion on 12/31/2014 and was superseded by Level 5 milestone M5FT-15OR0905017 - GC-859 implementation, which was completed on 9/30/2015. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Pre-released version of GC-859 has been implemented in UNF-ST&DARDS.” DMS Number: “FCRD-NFST-2015-000754”. Notes: “Pre-released version of GC-859 has been implemented in UNF-ST&DARDS. The official version of GC-859 has not been released by the Energy Information Administration (EIA) at this writing. The Unified Database will be updated with the official version of GC-859 when available. This activity will be included under FY16 Activity FT-16OR090105019, “Data collection and database synthesis in support of UNF characterization”. Please contact John M. Scaglione (scaglionejm@ornl.gov) or Kaushik Banerjee (banerjeek@ornl.gov) for additional information.” | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Import GC-859 data into UNF-ST&DARDS | Integration of GC-859 data into UNF-ST&DARDS database | Integration of GC-859 database into UNF-ST&DARDS | 2014-12-31 |  |  | Schedule is contingent upon release by EIA. | 2014 | On Schedule |  |  |  | None |  | FCRD-NFST-2014-000357
M3FT-14OR09050116 Per Matt Brainard: Status report on CDB update activities was originally planned for FY15 completion on 11/26/2014 and was superseded by M3FT-15OR09050119 - Report documenting status of characteristics database update activities, which was completed on 12/19/2014. | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Status report on CDB update activities | Status report on characteristics database update activities | Report documenting status of characteristics database update activities | 2014-11-26 |  |  | On schedule | 2014 | 90 Day |  |  |  | None
M3FT-14OR09050117 Per Matt Brainard: Assessment of newly acquired fuel characteristics data was originally planned for FY15 completion on 3/30/2015 and was superseded by M3FT-15OR09050120 Assessment of newly acquired fuel characteristics data, which was completed on 9/11/2015. | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Assessment of newly acquired fuel characteristics data | Assessment of fuel characteristics data and recommendations for further data supplements | Report document conclusions of efforts associated with the newly acquired data from the fuel vendors and small set of utilities, and recommendations regarding the need for, benefits of, and estimated costs associated with acquiring additional information, e.g. NDRs for remaining plants and/or cycles of operation, to inform any future data requests. | 2015-03-30 |  |  |  | 2014 | On Schedule |  |  |  | None
M3FT-14OR0905014 Per Matt Brainard: Draft UNF database requirements document was completed on 2/28/2014, however the Deliverable Form in PICS:NE was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Draft M2 document completed” Document Author: “Josh Peterson”. Document Owner: “John Scaglione”. Deliverable Description: “Draft M2 report documenting the requirements of the unified database”. DMS Number: “FCRD-NFST-2014-000359”. Lab ID No. (Other): “ORNL file system”. CAM Note at Approval: “L-3, which is draft of the L-2, is accepted for review.” | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Draft UNF database requirements document | Draft M2 report documenting the requirements of the UNF database | Draft M2 report documenting the requirements of the UNF database | 2014-02-28 |  | 2014-02-28 |  | 2014 | Complete |  | Peterson, Josh | Scaglione, John | None |  | FCRD-NFST-2014-000359
M3FT-14OR09130119 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Main Document Title: “AAR S-2043 Cask Railcar System Requirements Document.” DMS No. FCRD-NFST-2014-000377. Narrative: “Draft document submitted for review.” | M3 | 1.02.09.13.01 | ORNL | FT-14OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Draft S-2043 Compliant Railcar System Requirements Document | Provide draft S-2043 Compliant Railcar System Requirements Document for review | Provide draft S-2043 Compliant Railcar System Requirements Document for review | 2014-02-14 04:00 |  | 2014-02-14 |  | 2014 | Complete | AAR S-2043 Cask Railcar System Requirements Document | Feldman, Matt | Feldman, Matt | None |  | FCRD-NFST-2014-000377
M3FT-14PN0810032 Superseded by M3FT-15PN080100411. Per Matt Brainard: Originally planned for completion in FY15. Superseded by M3FT-15PN08100411 during FY15 work package planning. File attached. Note: “As a draft, this document will not be made publicly available. Rather, once comments are received and addressed, the document will be reissued as an M2 that will be publicly available.” | M3 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Draft of M2 Report | Draft of M2 Report | Submit draft M2 report for comment. | 2015-01-30 05:00 |  |  | On schedule. | 2014 | On Schedule |  |  |  | None |  | FCRD-UFD-2014-000322
M3FT-14PN0810035 Per Matt Brainard: Document does not exist in PICS:NE. Planned for FY15 completion. Possibly superseded by M3FT-15PN08100412 - Hope Creek Post-inspection Report (Deliverable: Hope Creek Analysis Report). | M3 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Hope Creek Analysis Report | Hope Creek Analysis Report | Hope Creek Analysis Report. Previously Fy13 M3FT-13PN0810023. | 2015-03-31 03:00 |  |  | On schedule. | 2014 | On Schedule |  | Hanson, Brady | Hanson, Brady | None |  | FCRD-UFD-2014-000323
M3FT-14PN0810038 From James Fort: I cannot find the first report on this list, “Post-inspection report”. I do have later versions from the end of that year, but the milestones are different: * M3FT-15PN08100412, “Hope Creek Post-Inspection Report” * M3FT-15PN080100413, “Diablo Canyon Post-Inspection Report” | M3 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Post-inspection report | Post-inspection report | Perform posttest analyses and provide report on the third inspection. | 2015-03-31 03:00 |  |  | On schedule. | 2014 | On Schedule |  |  |  | None |  | FCRD-UFD-2014-000324
M3FT-14PN0912026 Matt Brainard: Characterization and assessment of transportability of canisters was completed on 9/30/2014, however the Deliverable Form in PICS:NE was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “This report fulfills Milestone M3FT-14PN0912026.” Document Author/Owner: “Steve Maheras”. Deliverable Description: “Final Report for TR Operational - PNNL.”. Main Document Title: “Characterization and Assessment of Transportability of Canisters.” DMS Number: “FCRD-NFST-2014-000371”. Notes: “9/18/2017 - Deliverable report removed by Program Controls at WPM's request due to presence of proprietary information.” | M3 | 1.02.09.12.02 | PNNL | FT-14PN091202 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Characterization and assessment of transportability of canisters. | Characterization and assessment of transportability of canisters. | Develop transportation cask specific models. | 2014-09-30 15:00 |  | 2014-09-30 06:00 | This report fulfills Milestone M3FT-14PN0912026. | 2014 | Complete | Characterization and Assessment of Transportability of Canisters | Maheras, Steve | Maheras, Steve | None |  | FCRD-NFST-2014-000371 | canisters, modeling templates, COBRA-SFS
M3FT-14SN0912041 Per Matt Brainard: Document not available in PICS:NE. Additional information as follows: Completion Narrative: The Mac version of RADTRAN and the Windows version were bundled with the Java GUI. Download from the test site worked seamlessly for both versions when the security is set properly. Appropriate directions will be posted on the RADTRAN website. The task is, at this time, complete. Main Document Title: RADTRAN For Apple Products: Letter report. Lab ID No.: https://radtran.sandia.gov/radcat Deliverable Form Notes: This is a modification to an existing software program. Its existence is opaque to the user in that the Windows user sees the Windows version when he or she downloads RADTRAN bundled with RadCat, and the Mac user sees the Apple version of the same bundle. | M3 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Weiner, Ruth | Feldman, Matt | Executing RADTRAN on Apple computers | Apple verion of RADTRAN | a. Compile RADTRAN for an Apple computer. b. Test and debug the program, document changes in protocol and revised the user guide as needed. | 2014-03-27 02:00 | 2014-03-07 08:00 | 2014-03-06 06:00 |  | 2014 | Complete | RADTRAN For Apple Products: Letter report. | Weiner, Ruth | Weiner, Ruth | None |  | FCRD-NFST-2014-000373 | RADTRAN, Apple, Mac, PC, RadCat
M3FT-15AN0901012 Per Matt Brainard: Not available in PICS:NE. DMS Number FCRD-NFST-2015-000162. Note: Report is being maintained with the author. It will be transmitted to the Document Management System when Official Use Only questions related to DOE directed markings are resolved. | M3 | 1.02.09.01.01 | ANL | FT-15AN090101 | CX: Project Management - ANL | Nutt, Mark | Jarrell, Josh | DRAFT Update Nuclear Fuels Storage and Transportation Program Plan | DRAFT Update Nuclear Fuels Storage and Transportation Program Plan | DRAFT update of FY14 NFST program plan to support out-year budget planning, including preparation for FY 2016 work planning, factoring in recent accomplishments and any new guidance from DOE. | 2015-05-29 03:00 |  | 2015-05-28 01:00 |  | 2015 | Complete | NFST Near-Term Implementation Plan | W. Mark Nutt | W. Mark Nutt | None |  | FCRD-NFST-2015-000162
M3FT-15ID09110210 Per Matt Brainard: potentially supersedes M3FT-14HQ0911023 but the titles and due dates do not match. Per Matt Brainard: Update Routing Methodology Report with Input from Stakeholders was completed on 9/30/2015, however the Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “The client decided to not request stakeholder comment on the Routing Methodology Report in order to have the stakeholders work on each issue raised in the report.” Main Document Title: “Update Routing Methodology Report with Input from Stakeholders”. DMS Number: “FCRD-NFST-2015-000177”. NTD Comment at Approval: “Per e-mail from Matt Feldman, 11/2/15. For M3FT-15ID09110210 Update Routing Methodology Report with Input from Stakeholders, there was a significant delay in getting the report to the stakeholders due to internal technical and policy review issues. Due to this, NFST management, based on GC guidance, made the call to not ask the stakeholders to provide comments on the report itself, but rather to work on the questions and issues identified in the report through an on-going white-paper process that will contribute to a new DOE routing report at a later date. Thus, the intent of the milestone was met by North Wind due to circumstances that were beyond their control.” | M3 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Update Routing Methodology Report with Input from Stakeholders | Update Routing Methodology Report with Input from Stakeholders | Update Routing Methodology Report with Input from Stakeholders | 2015-09-30 06:00 |  | 2015-09-30 02:00 | The client decided to not request stakeholder comment on the Routing Methodology Report in order to have the stakeholders work on each issue raised in the report. | 2015 | Complete | Update Routing Methodology Report with Input from Stakeholders |  |  | None |  | FCRD-NFST-2015-000177
M3FT-15ID0911024 Per Matt Brainard: Submit Draft 180(c) Tabletop Exercise Lessons Learned Report was completed on 9/7/2015, however the Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “This was delivered late because the meeting with the stakeholders to gather necessary input did not occur until 8/12/2015.” Main Document Title: “Draft 180(c) Tabletop Exercise Lessons Learned Report”. DMS Number: “FCRD-NFST-2015-000178”. | M3 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Submit Draft 180(c) Tabletop Exercise Lessons Learned Report | Draft 180(c) Tabletop Exercise Lessons Learned Report | Submit Draft 180(c) Tabletop Exercise Lessons Learned Report | 2015-08-14 08:00 | 2015-09-07 04:00 | 2015-09-07 02:00 | This was delivered late because the meeting with the stakeholders to gather necessary input did not occur until 8/12/2015. | 2015 | Completed Late | Draft 180(c) Tabletop Exercise Lessons Learned Report |  |  | None |  | FCRD-NFST-2015-000178
M3FT-15ID0911025 Per Matt Brainard: Submit Draft National Transportation Plan, Revision 3 for review was completed on 2/13/2015, however the Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “This milestone was delivered on time on February 13, 2015.” Document Author: “Judith Holm”. Document Owner: “ORNL”. Main Document Title: “Draft National Transportation Plan, Revision 3”. DMS Number: “FCRD-NFST-2015-000179”. | M3 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Submit Draft National Transportation Plan, Revision 3 for review | Draft National Transportation Plan, Revision 3 | Submit Draft National Transportation Plan, Revision 3 for review | 2015-02-13 06:00 |  | 2015-02-13 02:00 |  | 2015 | Complete | Draft National Transportation Plan, Revision 3 | Judith Holm | ORNL | None |  | FCRD-NFST-2015-000179
M3FT-15ID0911026 Per Matt Brainard: Conduct Tabletop Exercise was completed on 5/29/2015, however the Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “This was completed on time at the NTSF annual meeting in Albuquerque, NM on May 11, 2015.” Main Document Title: “Meeting Summary of Tabletop Exercise”. DMS Number: “FCRD-NFST-2015-000180”. | M3 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Conduct Tabletop Exercise | Conduct Tabletop Exercise | Conduct Tabletop Exercise | 2015-05-29 06:00 |  | 2015-05-29 02:00 |  | 2015 | Complete | Meeting Summary of Tabletop Exercise |  |  | None |  | FCRD-NFST-2015-000180
M3FT-15ID0911028 Per Matt Brainard: Issue Lessons Learned Report on West Valley Shipments was completed on 8/11/2015, however the Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “This milestone was delivered late because the meeting at West Valley, to gather input for the report, was delayed due to the West Valley staff's schedule.” Main Document Title: “Lessons Learned Report on West Valley Shipments”. DMS Number: “FCRD-NFST-2015-000181”. | M3 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Issue Lessons Learned Report on West Valley Shipments | Lessons Learned Report on West Valley Shipments | Issue Lessons Learned Report on West Valley Shipments | 2015-03-31 06:00 |  | 2015-08-11 02:00 |  | 2015 | Completed Late | Lessons Learned Report on West Valley Shipments |  |  | None |  | FCRD-NFST-2015-000181
M3FT-15ID0912053 Per Matt Brainard: Release Beta Version of START Version 1.2 was marked complete on 3/27/2015, however the Deliverable Form in PICS:NE was never submitted. It is entirely blank. Deliverable is missing. | M3 | 1.02.09.12.05 | DOE-ID | FT-15ID091205 | TR: Operational - DOE-ID | Helvey, Elizabeth | Feldman, Matt | Release Beta Version of START Version 1.2 | Beta Version of START Version 1.2 | Release Beta Version of START Version 1.2 | 2015-03-27 06:00 | 2015-07-17 04:00 | 2015-03-27 04:00 |  | 2015 | Complete |  |  |  | None |  | FCRD-NFST-2015-000182
M3FT-15IN0802017 Per Matt Brainard: milestone not met. Narrative provided in PICS:NE indicates “This milestone will not be completed due to the illness and subsequent loss of the staff member needed for this work.” Deliverable is considered missing. | M3 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Progress on instruments, sensors, and deployment strategies for canisterized used nuclear fuel | Progress on instruments, sensors, and deployment strategies for canisterized used nuclear fuel | This activity will coordinate efforts to develop ways to detect cracking in SS canisters, and ti deploy instruments/sensors in those hostile environments. | 2015-09-14 15:00 | 2015-09-30 04:00 |  | This milestone will not be completed due to the illness and subsequent loss of the staff member needed for this work. | 2015 | Expected Late |  |  |  | None |  | FCRD-UFD-2015-000275
M3FT-15OR0805034 Per Matt Brainard: Report not uploaded into PICS:NE. Deliverable form approved without upload. Main Document Title “FY 2015 Status Report CIRFT Testing of High-Burnup Used Nuclear Fuel Rods from Pressurized Water Reactor and Boiling Water Reactor Environments”. DMS No. FCRD-UFD-2015-000432 referenced. Deliverable Description: “report provides data results of CIRFT testing on Zyr-4, M5 and Zy-2 (BWR) high burnup fuel. Finite element analysis is provided to support the testing. Report also provides out of cell results for hydride reorientation testing; in cell testing will be done the 1st quarter of FY16.” Document Owner: Jy-An Wang/Bruce Bevard (ORNL) | M3 | 1.02.08.05.03 | ORNL | FT-15OR080503 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Draft M2 Report on Experimental Testing Results | Draft Report on Experimental Testing Results | Preliminary draft of level 2 Milestone | 2015-08-21 |  | 2015-08-21 |  | 2015 | Complete | FY 2015 Status Report CIRFT Testing of High-Burnup Used Nuclear Fuel Rods from Pressurized Water Reactor and Boiling Water Reactor Environments | ORNL | Wang, Jy-An | None |  | FCRD-UFD-2015-000432 | CIRFT, High burnup fuel, vibration testing, hydride reorientation, S-N curve, pellet-clad bonding,
M3FT-15OR0904025 Per Josh Jarrell: Do NOT include in SP site - available through PICS/NE | M3 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Draft of FY15 Standardization Assessment Update | Draft of FY15 Standardization Assessment Update | Draft of the the standardization assessment update. | 2015-08-21 04:00 |  | 2015-08-21 |  | 2015 | Complete | Draft of Intermediate Standardized Canister System Evaluation | Josh Jarrell | Josh Jarrell | None | Prelim_STAD_Assess_M3_2015-08_21_draft-final.docx | FCRD-NFST-2015-000434
M3FT-15PN0805041 superseded by M3FT-16PN080202042 | M3 | 1.02.08.05.04 | PNNL | FT-15PN080504 | ST Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Effects of Hydrides on Mechanical Properties of Unirradiated Cladding | Effects of Hydrides on Mechanical Properties of Unirradiated Cladding | Document the results of testing on unirradiated cladding and providing the link to spent fuel cladding behavior. | 2015-09-30 11:00 | 2015-10-19 03:00 |  | Discovery of a calculation error required a lot of rework so the deliverable is late | 2015 | Expected Late |  |  |  | None |  | FCRD-UFD-2015-000489
M3FT-15PN0905021 Per Steve Maheras: Doc is OUO and not appropriate for the SP site. | M3 | 1.02.09.05.02 | PNNL | FT-15PN090502 | CX: Characterization and Assessment - PNNL | Maheras, Steve | Jarrell, Josh | Best Practices for SFS Thermal Analysis Modeling | Best Practices for SFS Thermal Modeling | Document specifying best practices for SFS thermal analysis modeling. | 2015-09-09 |  | 2015-09-28 06:00 | This report is an M3 report intended for use by thermal analysts developing COBRA-SFS models for spent fuel storage and transportation systems. It consists of advice distilled from many years of experience in this work, and is intended to help flatten the somewhat steep learning curve that confronts new users of the COBRA-SFS code. This document assumes that the reader is familiar with the COBRA-SFS Users Manual (or is in the process of gaining such familiarity), and is actively engaged in the process of learning how to use the code efficiently and effectively | 2015 | Completed Late | COBRA-SFS Model Development: Experience-Based Guidance and Suggested Best Practices | Steve Maheras | Steve Maheras | None |  | FCRD-NFST-2015-000496 | UNF-ST&DARDS, COBRA-SFS, thermal modeling, best practices
M3FT-15PN09120310 Per Steve Maheras: Doc is OUO and not appropriate for the SP site. | M3 | 1.02.09.12.03 | PNNL | FT-15PN091203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Final Cask Transportability Report | Final Cask Transportability Report | Final cask transportability report. | 2015-09-01 03:00 |  | 2015-09-01 09:00 | This report is a M3 final report and continues the investigation to define needed information and thermal modeling requirements and capabilities for evaluation of spent fuel thermal history in on-site storage, as related to transportability concerns. The main focus is on transfer operations, particularly vacuum drying, in consideration of determining peak fuel temperatures likely to have been actually experienced by the spent fuel. Results are presented showing validation of the main thermal modeling code, COBRA-SFS, cycle 4 of which is being incorporated into the UNF ST&DARDS tool, for vacuum drying conditions. This validation is based on TAN Facility testing in two spent fuel casks, the CASTOR-V/21 and the TN-24P. The CASTOR-V/21 was tested at a high decay heat load of 28 kW, with individual fuel assemblies ranging from 1.0 to 1.83 kW, reaching temperatures that exceeded 400°C in the vacuum test. The TN-24P was tested at a somewhat lower decay heat load of 20.5 kW, but this value is still a relatively high heat load, compared to typical initial loading of canisters at actual sites around the country, particularly the ISFSI-only sites. In comparison with both sets of data, the COBRA-SFS code is shown to give excellent agreement with the measured data, and gives great confidence that this modeling approach can be used to produce realistic estimates of peak cladding temperatures for vacuum drying conditions, without imposing excessive conservatisms, or at least, not any more excessive than a lack of information on actual operational conditions warrant. | 2015 | Complete | Characterization and Assessment of Transportability of Canisters - Thermal Issues | Steve Maheras | Steve Maheras | None |  | FCRD-NFST-2015-000497 | UNF-ST&DARDS, COBRA-SFS, thermal modeling, vacuum drying, dry storage casks, dry storage canisters
M3FT-15SN0909011 Per Matt Brainard: Deliverable not uploaded to PICS:NE. Note: “Report undergoing review and approval to receive Lab SAND #. Report will be uploaded when internal review completed.” Main Document Title: “Insights from Public Preference Surveys Related to Siting of Nuclear Waste Facilities”. DMS No. FCRD-NFST-2015-000521. | M3 | 1.02.09.09.01 | SNL | FT-15SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Howard, Rob | Insights from Public Perference Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Insights from Public Preference Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Complete documentation of public surveys, analysis of results, and insights gained in FY15. | 2015-09-30 |  | 2015-09-30 02:00 | Report completed on Insights from Public Preference Surveys Related to Transportation and Siting of Nuclear Waste Facilities | 2015 | Complete | Insights from Public Preference Surveys Related to Siting of Nuclear Waste Facilities | Rob P Rechard | Rob P Rechard | None |  | FCRD-NFST-2015-000521 | public preference survey, consent-based siting, interim storage facility, transportation of HLW
M3FT-15SR0902111 Per Matt Brainard: Revision 2 of the Functions and Requirements – Deliverable missing. Deliverable form submitted and subsequently approved without document upload. Additional deliverable form information: Narrative: “This report expands on Rev. 1 by adding two appendix which begin the process of identifying in detail regulatory requirements established by the NRC.” Document Author: NFST Requirements Team. Document Owner. Joe T. Carter. Deliverable Description: “FCRD-NFST-2013-000330, Revision 2, Nuclear Fuels Storage and Transportation Requirements Document . This report satisfy the Level 3 milestone, M3FT-15SR0902111, Revision 2 of the Functions and Requirements due 6/30/15.” Main Document Title: “Nuclear Fuels Storage and Transportation Requirements Document. DMS No. FCRD-NFST-2015-000535.” Notes: “Report is being maintained with the author. It will be transmitted to the Document Management System when Official Use Only questions related to DOE directed markings are resolved.” | M3 | 1.02.09.02.11 | SRNL | FT-15SR090211 | Waste Management Functional and Operational Requirements - SRNL | Carter, Joe | Jarrell, Josh | Revision 2 of the Functions and Requirements | Revised System Functional and Operational Requirements | Revision of the Waste Management System Functions and Requirements document | 2015-06-30 02:00 |  | 2015-06-30 |  | 2015 | Complete | Nuclear Fuels Storage and Transportation Requirements Document | NFST Requirements Team | Carter. Joe | None |  | FCRD-NFST-2015-000535 | NFST Requirements Document
M3FT-15SR0905031 Per Matt Brainard: Deliverable not uploaded to PICS:NE. Notes: “Report is being maintained with the author. It will be transmitted to the Document Management System when Official Use Only questions related to DOE directed markings are resolved.” Main Document Title: “Commercial Spent Nuclear Fuel and High-Level Radioactive Waste Inventory Report”. Document Author and Owner: Joe T. Carter/Dennis Vinson. DMS No. FCRD-NFST-2015-000536. | M3 | 1.02.09.05.03 | SRNL | FT-15SR090503 | CX: Characterization and Assessment - SRNL | Carter, Joe | Jarrell, Josh | NFST Inventory Report Rev 3 | NFST Planning Project Inventory Basis, Rev 3 | SRNL will update the NFST Inventory projections report documentation based on the new GC-859 data and fuel projection model. | 2015-06-30 03:00 |  | 2015-06-30 |  | 2015 | Complete | Commercial Spent Nuclear Fuel and High-Level Radioactive Waste Inventory Report | Joe T. Carter | Joe T. Carter | None |  | FCRD-NFST-2015-000536 | NFST Inventory Report
M3FT-16AN090101012 Per Matt Brainard: Not available in PICS:NE. DMS Number FCRD-NFST-2016-000447. Note: Draft document is being maintained by W.M. Nutt and will be finalized to meet Level-2 milestone M2FT-16AN090101011. Draft report being maintained by W.M. Nutt. | M3 | 1.02.09.01.01.01 | ANL | FT-16AN09010101 | CX: Project Management - ANL | Nutt, Mark | Jarrell, Josh | DRAFT FY15 NFST Accomplishments Report | DRAFT FY15 NFST Accomplishments Report | Draft of the FY15 NFST Accomplishments Report | 2015-11-18 06:00 |  | 2015-11-19 01:00 |  | 2016 | Completed Late | DRAFT FY15 NFST Accomplishments Report | W. Mark Nutt | W. Mark Nutt | None |  | FCRD-NFST-2016-000447
M3FT-16AN090102033 Software release - no documentation. | M3 | 1.02.09.01.02.03 | ANL | FT-16AN09010203 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM Release: Phase 2.1 - Prototype 2 | NGSAM Phase 2.1 Prototype 2 | Phase 2.1 - Prototype 2 software release will (1) extend the "At-ISF" logic/algorithms in Prototype 1; (2) support detailed step-by-step operational models of vertical storage; and (3) use the Unified Database, version 2 (released Sept. 30, 2015 - M2FT–15OR0905011). This NGSAM release will include a high-level generic ISF model; however, certain capabilities will NOT be included, such as: (1) Multiple ISF’s within a single simulation; (2) ISF Operation constraints [e.g. staffing/shift management, crane usage, other resources required]; and (3) Detailed step-by-step procedures for horizontal storage of SNF. | 2016-09-23 21:00 |  | 2016-09-23 01:00 | NGSAM Version 2.1.6.0 released to IWM System Architecture Analysts | 2016 | Complete | NGSAM Verstion 2.1.6.0 is a software release - no report necessary |  |  | None |  | FCRD-NFST-2016-000460
M3FT-16AN090302012 Per Matt Brainard: Deliverable not uploaded to PICS:NE. Note: “File not uploaded. It's too large for PICS and will be provided directly to DMS.” DMS No. FCRD-NFST-2016-000469. Main Document Title: “Environmental Considerations for the Consolidated Storage of Commercial Spent Nuclear Fuel and Associated Operations”. Narrative: “Draft report provided to NTD (M. Nutt) on schedule 5/31/2016, copying several others; feedback is anticipated by 6/14, toward completion of the level 2 milestone on schedule (submittal to DOE 6/30)” | M3 | 1.02.09.03.02.01 | ANL | FT-16AN09030201 | ST: NEPA - ANL | MacDonell, Margaret | Carter, Joe | Draft Environmental Considerations for an Interim Storage Facility and Associated Operations (Initial) | Draft Environmental Considerations for an Interim Storage Facility and Associated Operations (Initial) | Draft Initial Environmental Considerations Report. This draft report will be reviewed and comments incorporated to produce Environmental Considerations for an Interim Storage Facility and Associated Operations (Initial): M2FT-16AN0302011 | 2016-05-31 09:00 |  | 2016-06-01 02:00 |  | 2016 | Completed Late | Environmental Considerations for the Consolidated Storage of Commercial Spent Nuclear Fuel and Associated Operations |  | Margaret MacDonell | None |  | FCRD-NFST-2016-000469
M3FT-16ID090401041 Per Matt Brainard: 180(c) Implementation Exercise Draft Final Report - Deliverable missing. Deliverable form submitted and subsequently approved without document upload. Additional deliverable form information: Narrative: “This milestone was met on time.” Main Document Title: “180(c) Implementation Exercise Draft Final Report.” DMS No. FCRD-NFST-2016-000475.” | M3 | 1.02.09.04.01.04 | DOE-ID | FT-16ID09040104 | TR: Institutional - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | 180(c) Implementation Exercise Draft Final Report | Draft Final 180c Policy Implementation Exercise Report | This is a final report describing the Section 180(c) Implementation Exercise, the lessons learned from the activity and the next steps for implementing Section 180(c). | 2016-07-15 04:00 |  | 2016-07-15 02:00 |  | 2016 | Complete | 180(c) Implementation Exercise Draft Final Report |  |  | None |  | FCRD-NFST-2016-000475
M3FT-16ID090402056 Per Matt Brainard: User's Manual for START Version 2.0 - Deliverable missing. Deliverable form submitted and subsequently approved without document upload. Additional deliverable form information: Narrative: “This milestone is complete.” Main Document Title: “User's Manual for START version 2.0” DMS No. FCRD-NFST-2016-000473” | M3 | 1.02.09.04.02.05 | DOE-ID | FT-16ID09040205 | TR: Operational - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | User's Manual for START Version 2.0 | User's Manual for START Version 2.0 | Develop a User's Manual for START Version 2.0. | 2016-04-29 03:00 |  | 2016-05-02 02:00 |  | 2016 | Completed Late | User's Manual for START version 2.0 |  |  | None |  | FCRD-NFST-2016-000473
M3FT-16OR090101022 Per Matt Brainard: Critical Decision Process Needs Assessment – Deliverable missing. Delayed into FY17 for completion on 10/31/2016, however the FY17 follow-on work package did not contain any milestones. It appears that this milestone was dropped during the transition between FY16 and FY17. | M3 | 1.02.09.01.01.02 | ORNL | FT-16OR09010102 | CX: Project Management - ORNL | Howard, Rob | Jarrell, Josh | Critical Decision Process Needs Assessment | Critical Decision Process Needs Assessment | DReport describing when it may be necessary to begin the DOE Order 413.3 critical decision process and the necessary information that would be required. | 2016-04-08 02:00 | 2016-10-31 |  | Work was reprioritized based on project needs. | 2016 | Late |  |  |  | None |  | FCRD-NFST-2016-000450
M3FT-16OR090102055 Per Josh Jarrell: Do NOT include in SP site - available through PICS/NE | M3 | 1.02.09.01.02.05 | ORNL | FT-16OR09010205 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Draft of Consolidated Interim Storage from an Integrated Systems Perspective | Draft of Consolidated Interim Storage from an Integrated Systems Perspective | Draft of Level 2 Deliverable | 2016-05-13 |  | 2016-05-13 |  | 2016 | Complete | Draft of Consolidated Interim Storage from an Integrated Systems Perspective | Jarrell, Josh | Jarrell, Josh | None | 2016-05-13_ISF-Implications_final_M3.docx | FCRD-NFST-2016-000452
M3FT-16OR090104015 Per Josh Jarrell: Do NOT include in SP site - available through PICS/NE | M3 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Draft of Standardization Assessment Report | Draft of Standardization Assessment Report | Draft of Level 2 Milestone "Standardization Assessment Report." | 2016-04-29 |  | 2016-04-28 |  | 2016 | Complete | Draft of FY16 Standardized Canister System Evaluation | Jarrell, Josh | Jarrell, Josh | None | FY16_Standardization_Assess_M3_2016-04_29_Final.docx | FCRD-NFST-2016-000451
M3FT-16OR090201024 Per Rob Howard: M3FT-16OR090201024 and M4FT-16OR090201028 were not stand-alone documents; they were incorporated into M2FT-16AN090201011 | M3 | 1.02.09.02.01.02 | ORNL | FT-16OR09020102 | CB: Siting Process - ORNL | Howard, Rob | Howard, Rob | Siting Process Guiding Principles Document | Siting Process Guiding Principles | Develop the Siting Process Guiding Principles document based on input from stakeholder engagements and examples from international consent based siting programs. | 2016-07-29 06:00 |  | 2016-07-28 |  | 2016 | Complete | Project and Organizational Principles for Consent-Based Siting | Rob Howard | Rob Howard | OUO |  | FCRD-NFST-2016-000467
M3FT-16PN080202042 Supersedes M3FT-15PN0805041. per Matt Brainard: Document not uploaded into PICS:NE. Status as of 9/29/2016 – “Milestone M3FT-16PN080202042 is complete and meets the finish date of 9/28/16. The report has currently been released as a limited report until the zirconium cladding vendors can review the report according to NDA. The report will be loaded into PICS after their review cycle has been completed.” The report was never loaded into PICS:NE. Contact Brady Hanson or Wendy Erikson at PNNL for a copy. DMS Tracking No. FCRD-UFD-2016-000432. It’s possible the file has been loaded into DMS. Per Matt Brainard: Delayed into FY16 for completion. Revised Finish Date stated as 10/19/2015. Nothing with that date was entered into the FY16 work package, however a level 3 milestone titled “M3FT-16PN080202042-Finalize M3 Milestone” was listed with a due date of 9/28/2016. This milestone superseded the FY15 milestone as the following narrative indicates: “The purpose of this work is to build on the results reported in the M3 milestone M3FT-15PN0805041, document number FCRD-UFD-2015-000489 (Shimskey et al., 2015). In that work, baseline burst testing was completed on four different types of as-manufactured zirconium cladding acquired for the Used Fuel Disposition Campaign Storage and Transportation program. Weibull statistical analyses of the results showed the acquired material to be of high quality with little variability, demonstrating that the material is suitable for experimental work for the program.” That said, this Deliverable was never uploaded into PICS:NE. Instead, the following comment was entered: “Milestone M3FT-16PN080202042 is complete and meets the finish date of 9/28/16. The report has currently been released as a limited report until the zirconium cladding vendors can review the report according to NDA. The report will be loaded into PICS after their review cycle has been completed.” Deliverable is considered missing from PICS:NE. Document Owner: Brady Hanson. Deliverable Description: Reviewed in PNNL's ERICA document clearance system and submitted to the NTD and CAM. | M3 | 1.02.08.02.02.04 | PNNL | FT-16PN08020204 | ST Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Finalize M3 Milestone | Material Properties of Unirradiated Zircaloy Cladding with Hydride Reorientation | Peer review paper documenting the FY16 progress on clad properties testing. | 2016-09-28 03:00 |  | 2016-09-28 06:00 | The purpose of this work is to build on the results reported in the M3 milestone M3FT-15PN0805041, document number FCRD-UFD-2015-000489 (Shimskey et al., 2015). In that work, baseline burst testing was completed on four different types of as-manufactured zirconium cladding acquired for the Used Fuel Disposition Campaign Storage and Transportation program. Weibull statistical analyses of the results showed the acquired material to be of high quality with little variability, demonstrating that the material is suitable for experimental work for the program. | 2016 | Complete | Development of Radial Hydride Treatment of Prehydrided As-Manufactured Cladding | Shimskey, Rick | Hanson, Brady | None |  | FCRD-UFD-2016-000432 | Hydrides, cladding, zirconium, radial hydride treatment
M3SF-17ID020201072 Deliverable not uploaded into PICS:NE. Deliverable submitted and approved without attachment. Main Document Title: “30% generic design review”. Narrative: “CB&I presented the 30% generic design review to DOE”. Approval comment: “comments were provided to the contractor for incorporation into the 60% design review materials”. | M3 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | 30 Percent Generic Design Review | Design Criteria, Design Report, Annotated outline | 30 Percent Generic Design Review | 2017-05-10 |  | 2017-04-18 02:00 |  | 2017 | Complete | 30% generic design review |  |  | None |  | SFWD-IWM-2017-000229
M3SF-17ID020201073 Deliverable not uploaded into PICS:NE. Deliverable submitted and approved without attachment. Main Document Title: “TSAR 20% review”. Narrative: “CB&I presented a 20% TSAR to DOE for comments.” Approval comment: “Comments provided to CB&I”. | M3 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | 20 Percent TSAR Review | TSAR Annotated outline, Existing storage site technical specification summary | 20 Percent TSAR Review | 2017-05-30 |  | 2017-05-31 02:00 |  | 2017 | Completed Late | TSAR 20% review |  |  | None |  | SFWD-IWM-2017-000230
M3SF-17ID020201074 Deliverable not uploaded into PICS:NE. Deliverable submitted and approved without attachment. Main Document Title: “60% design review”. Narrative: “CB&I presented their 60% design review.” Approval comment: “The 60% TSAR package was reviewed on August 30 and 31. Comments were submitted verbally and written comments in in progress.” | M3 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | 60 Percent Project Review | Important to Safety design features, Aging Management Plans | 60 Percent Project Review | 2017-08-24 | 2017-08-30 02:00 | 2017-08-31 02:00 |  | 2017 | Completed Late | 60% design review |  |  | None |  | SFWD-IWM-2017-000231
M3SF-17ID020201075 Superseded by “M3SF-18ID020201041: 90 Percent Project Review” completed on 12/14/2017 under the follow on FY18 work package. | M3 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | 90 Percent Project Review | Pilot ISF Design Report (Section 4.2.1), TSAR (Section 4.2.2) | 90 Percent Project Review | 2017-12-14 |  |  | on schedule | 2017 | 90 Day |  |  |  | None |  | SFWD-IWM-2017-000232
M3SF-17ID0203030510 Superseded by “M4SF-18ID020303042-CLIN 2 Event 5: AAR Notice to Proceed” completed on 2/2/2018 under the follow on FY18 work package. | M3 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 5(a): AAR Notice to Proceed | Event 5(a): AAR Notice to Proceed | Event 5(a): AAR Notice to Proceed | 2017-07-31 | 2017-10-27 02:00 |  | The railcar design approval authority, the Association of American Railroads Engineering Equipment Committee, is taking longer than they did for previous reviews. They requested some more analysis and some changes in the report format | 2017 | Late |  |  |  | None |  | SFWD-IWM-2017-000063
M3SF-17ID020501031 Superseded by “M3SF-18ID020408031: Complete TO2 Phase 1: Prototype Ready for Testing” and completed on 10/25/2017 under the follow on FY18 work package. | M3 | 1.08.02.05.01.03 | DOE-ID | SF-17ID02050103 | Simultaneous Welding Task (Task Order 2) | Ford, Brayton | Nutt, Mark | Complete TO2 Phase 1: Prototype Ready for Testing | Complete TO2 Phase 1: Prototype Ready for Testing | Complete TO2 Phase 1: Prototype Ready for Testing | 2017-10-31 04:00 |  |  | on schedule | 2017 | 90 Day |  |  |  | None |  | SFWD-IWM-2017-000236
M3SF-17ID020501032 Superseded by M3SF-18ID020408032 | M3 | 1.08.02.05.01.03 | DOE-ID | SF-17ID02050103 | Simultaneous Welding Task (Task Order 2) | Ford, Brayton | Nutt, Mark | Complete TO2 Phase 2: Testing and Evaluation | Phase 2 Testing and Evaluation | Complete TO2 Phase 2: Testing and Evaluation | 2018-02-12 04:00 |  |  | on schedule | 2017 | On Schedule |  |  |  | None |  | SFWD-IWM-2017-000237
M3SF-17LA010303021 carried over to FY18: M3SF-18LA01030313 | M3 | 1.08.01.03.03.02 | LANL | SF-17LA01030302 | Salt R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Test Plan Document for Thermal Testing in Salt | Test Plan Document for Thermal Testing in Salt | LANL will work closely with SNL and LBNL to create a test plan to implement recommended thermal experiments in the underground at WIPP. This task will build on a March 2017 SNL deliverable that will outline a set of experiments and scientific goals. LANL will adapt the March 2017 deliverable to refine the initial set of experiments to include details of implementation in the underground (CAD, logistics, etc.). Details of the final experimental plan will be compiled in a test plan in accordance with Quality Assurance (QA) requirements. | 2017-09-30 10:00 | 2017-11-30 06:00 |  | We were informed on 9/8/17 that our final budget allocation has arrived for FY17. This will allow us to finish our Test Plan deliverable. We will shift resources back to work on this deliverable as soon as possible. | 2017 | Expected Late |  |  |  | None |  | SFWD-SFWST-2017-000043
M3SF-17LB010301061 File name says M3SF-17LB010301051 - Predecisional Draft. ULR? | M3 | 1.08.01.03.01.06 | LBNL | SF-17LB01030106 | Argillite International Collaborations - LBNL | Zheng, Liange | McMahon, Kevin | High temperature studies on bentonites and clays | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | The activities in Argillite international collaborations will be incorporated in the milestone for the Argillite disposal R&D | 2017-06-23 18:00 |  | 2017-06-23 03:00 |  | 2017 | Complete | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock: FY17 Progress | LBNL | Zheng, Liange | None | M3SF-17LB010301051.pdf | SFWD-SFWST-2017-000041 | Argillite, bentonite, clay, THMC modeling, THM modeling, fracture damage modeling, heater test modeling, coupled processes
M3SF-17OR020101022 Per Matt Brainard: Draft Combined Siting Considerations Document - Deliverable missing. Deliverable form submitted and subsequently approved without document upload. Additional deliverable form information: Narrative: “This document summarizes the key siting considerations for federal interim storage facilities and repositories as a draft stand-alone chapter in the Siting Process document per guidance in email from Mike Reim to Rob Howard October 5, 2016.” Document Author: Robert Howard. Document Owner. Robert Howard. Deliverable Description: “This document summarizes the key siting considerations for federal interim storage facilities and repositories as a draft stand-alone chapter in the Siting Process document per guidance in email from Mike Reim to Rob Howard October 5, 2016.” Main Document Title: “Initial Draft Siting Considerations for Federal Interim Storage Facilities and Repositories. DMS No. SFWD-IWM-2017-000050.” | M3 | 1.08.02.01.01.02 | ORNL | SF-17OR02010102 | Siting Process Design - ORNL (CLOSED) | Howard, Rob | Howard, Rob | Draft Combined Siting Considerations Document | Initial Draft Siting Considerations for Federal Interim Storage Facilities and Repositories | Draft Siting Considerations Document for integrated waste management facilities that includes siting considerations for repositories and interim storage facilities | 2016-11-18 |  | 2016-10-21 |  | 2017 | Complete | Initial Draft Siting Considerations for Federal Interim Storage Facilities and Repositories | Howard, Rob | Howard, Rob | Draft |  | SFWD-IWM-2017-000050 | Siting Considerations, criteria
M3SF-17OR020302028 Per Matt Brainard: UNF Standards Activities – Delayed into FY18 for completion on 10/31/2017. Deliverable missing. The follow-on FY18 work package does not contain a Level 3 Milestone titled “UNF Standards Activities”. The milestone appears to have been dropped between FY17 year end and FY18 execution. | M3 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | UNF Standards Activities | Updated Dose Rate Report on Selected Loaded Transportation Casks | Continued development of and analyses using the UNF Standards Analysis Tool | 2017-09-30 | 2017-10-31 |  | late. | 2017 | Expected Late |  |  |  | None |  | SFWD-IWM-2017-000183
M3SF-17OR020401051 Per Matt Brainard: Accelerated Transportation Deployment Study – Delayed into FY18 for completion on 11/30/2017. Deliverable missing. The follow-on FY18 work package does not exist. It appears as though the work package was dropped between FY17 year end and FY18 execution. | M3 | 1.08.02.04.01.05 | ORNL | SF-17OR02040105 | Special Study: Near-term Transportation - ORNL | Feldman, Matt | Jarrell, Josh | Accelerated Transportation Deployment Study | Accelerated Transportation Deployment Study | Evaluation of alternatives for the deployment of a minimal capability to accelerated the transportation of SNF from shutdown reactor sites to an interim storage facility. The evaluation will consider alternative approaches and quantify key uncertainties and risks. | 2017-08-31 | 2017-11-30 |  | 85% Complete through 9/30/2017. | 2017 | Late |  |  |  | None |  | SFWD-IWM-2017-000065
M3SF-17OR020501026 Per Matt Brainard: Compare 21P, 12P, and 4P system scenarios from an integrated system standpoint drawing upon past analysis work – Originally planned for FY18 completion on 11/8/2017. Deliverable missing. The follow-on FY18 work package does not exist. It appears as though the entire control account and work package were dropped between FY17 year end and FY18 execution. | M3 | 1.08.02.05.01.02 | ORNL | SF-17OR02050102 | Systematic Studies Involving Canisters- ORNL | Scaglione, John | Nutt, Mark | Compare 21P, 12P, and 4P system scenarios from an integrated system standpoint drawing upon past analysis work | Integrated systems analysis comparison for 21P, 12P, and 4P packages | Systems analysis evaluation that evaluates overall system impacts of the 21P relative to the 12P, and the 4x4P relative to the 12P. Report will include a discussion of system flexibility and contraints. | 2017-11-08 |  |  | On schedule | 2017 | 90 Day |  |  |  | None |  | SFWD-IWM-2017-000235
M3SF-17PN010201033 Per Matt Brainard: M3SF-17PN010201033 – Hydride Reorientation in Unirradiated Cladding was revised into FY18 due to “Staff availability limited being able to finish on time.” There is no clear cross-walk between this milestone and one in the FY18 work package, however the following FY18 M3 milestone is close and may have superseded the FY17 Milestone: M3SF-18PN010201033-Hydride Cooling Rate Study, which was planned for completion in FY19, and was superseded again by FY19 milestone M3SF-19PN010201031-Hydride Cooling Rate Study, which isn’t due until 8/30/2019. Therefore a deliverable for which, is not available yet. | M3 | 1.08.01.02.01.03 | PNNL | SF-17PN01020103 | Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Hydride Reorientation in Unirradiated Cladding | Hydride Reorientation in Unirradiated Cladding | Report on FY17 activities looking at the temperature and hoop stresses necessary to reorient hydrides | 2017-09-29 06:00 | 2017-10-30 03:00 |  | Staff availability limited being able to finish on time. | 2017 | Expected Late |  |  |  | None |  | SFWD-SFWST-2017-000031
M3SF-17PN010201035 Document not available in PICS:NE. Last performance status update on 10/13/2017 by Brady Hanson indicates “Changes to the scope and priorities decided by CAM and PI require additional changes to the test plan.” | M3 | 1.08.01.02.01.03 | PNNL | SF-17PN01020103 | Experiments - PNNL | Hanson, Brady | Sorenson, Ken | PNNL Sister Rod Test Plan | PNNL Sister Rod Test Plan | Draft test plan of sister rod testing planned at PNNL for review by external organizations. | 2017-09-29 06:00 | 2017-12-29 03:00 |  | Changes to the scope and priorities decided by CAM and PI require additional changes to the test plan. | 2017 | Expected Late |  | Hanson, Brady | Hanson, Brady | None |  | SFWD-SFWST-2017-000032 | Sister Rod
M3SF-17SN010201046 Per Charles Bryan: M3SF-17SN010201046 is an OUO draft report. It was never issued a SAND number. The final report was issued as a UUR report, M3SF-19N010201047, which does have a SAND number. | M3 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | A Probabilistic Model for Stress Corrosion Cracking | A Probabilistic Model for Stress Corrosion Cracking | This report will document work to develop a probabilistic model for stress corrosion cracking of SNF interim storage canisters. | 2018-09-21 06:00 |  |  | After a hiatus during the summer due to lack of funding, work has been restarted on the SCC probabilistic model. | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000225
M3SF-17SN010203042 Per Matt Brainard: Document not available in PICS:NE. The last performance status update on 10/13/2017 indicated that “This task will be initiated once funding is placed”. Checking the FY18 Analysis – SNL work package and this milestone no longer exists. It may have been dropped entirely. | M3 | 1.08.01.02.03.04 | SNL | SF-17SN01020304 | Analysis - SNL (Carryover Only) | Dingreville, Remi | Sorenson, Ken | Development of Uncertainty Quantification Methodology as Applied to Stress Corrosion cracking | M3 report on UQ methodology for SCC of welded canister | Factors affecting site susceptibility to SCC, and the identification of vulnerable sites. For these sites what are the recommended inspection schedules? SNL-T2.2- Depending on the site susceptibility, what is the most appropriate inspection (NDE) technology? Using site susceptibility to determine the type of inspection and % coverage required prior to canister transport. For low-risk sites, low probability of detection (visual?) inspections may be sufficient. For high-risk sites it may be necessary to develop techniques requiring a higher probability of detection (eddy current, ultrasonic?) and resolution. | 2017-09-22 02:00 | 2018-03-30 04:00 |  | This task will be initiated once funding is placed. | 2017 | Expected Late |  |  |  | None |  | SFWD-SFWST-2017-000037
M3SF-17SN010304032 Re-Plan. Canceled MS | M3 | 1.08.01.03.04.03 | SNL | SF-17SN01030403 | Inventory and Waste Charaterization - SNL | Sassani, David | MacKinnon, Robert | Status Report on Inventory and Waste Characterization | Status Report on Inventory and Waste Characterization | Report summarizing work activities on updates/revisions to DOE Managed HLW and SNF data sets | 2018-07-20 02:00 |  |  |  | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000226
M3SF-17SN010501015 Re-plan canceled MS | M3 | 1.08.01.05.01.01 | SNL | SF-17SN01050101 | Complete and Populate Online Waste Library (OWL) - SNL | Sassani, Dave | McMahon, Kevin | Update to Inventory and Waste Characterization Report | Update to Inventory and Waste Characterization Report | Report summarizing additional capabilities added to OWL and updates to the inventory and waste characteristics/performance data/information therein. | 2018-07-20 |  |  |  | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000227
M3SF-17SN020201031 Classified SAND Report | M3 | 1.08.02.02.01.03 | SNL | SF-17SN02020103 | Storage Design Concepts - SNL | Durbin, Sam | Carter, Joe | Estimation of a Security-Related Source Term from Spent Nuclear Fuel in Underground Storage | Estimation of a Source Term from Spent Nuclear Fuel in Underground Storage for Security-Related Events | Classified SAND report | 2017-05-26 14:00 |  | 2017-05-26 02:00 |  | 2017 | Complete | Study on Effects of Explosive Attacks on Belowground Spent Nuclear Fuel Storage Systems | Andrew Thompson | Andrew Thompson | None |  | SFWD-IWM-2017-000055 | spent nuclear fuel; dry storage cask; radiological sabotage
M3SF-17SN020201032 Classified SAND Report | M3 | 1.08.02.02.01.03 | SNL | SF-17SN02020103 | Storage Design Concepts - SNL | Durbin, Sam | Carter, Joe | Uncertainty Analysis of a Security-Related Source Term from Spent Nuclear Fuel in Underground Storage | Uncertainty Analysis of a Security-Related Source Term from Spent Nuclear Fuel in Underground Storage | Classified SAND Report | 2017-07-28 10:00 | 2017-11-17 04:00 |  | Modeling appears to have resolved previous restart issues. Completion expected by 11/17/17. | 2017 | Late |  | Samuel Durbin | SNL | None |  | SFWD-IWM-2017-000056 | spent nuclear fuel;
M3SF-17SN020402141 Raw video - ENSA Cask | M3 | 1.08.02.04.02.14 | SNL | SF-17SN02040214 | Videography for ENSA Cask Shipment - SNL | Sorenson, Ken | Howard, Rob | Draft digital videography of the ENSA/DOE Rail Cask Transport and Tests | ENSA/DOE Rail Cask Transport and Testing | Produce videography of the ENSA/DOE rail cask transport and testing. | 2017-09-30 06:00 |  | 2017-09-29 04:00 | The deliverable consists of two 1-Terabyte hard drives with the raw videography from the Baltimore operations and the TTCI tests. These hard drives were sent to ORNL. | 2017 | Complete | ENSA Transportation Cask Raw Video |  |  | None | EXTERNAL RE ENSA Transportation Cask Raw Video and CURIE Sorenson.msg | SFWD-IWM-2017-000233
M3SF-17SR0202010410 Per Matt Brainard: Private ISF Planning and Gap analysis – Originally planned for FY18 completion on 11/20/2017 and subsequently delayed until 1/31/2018. Deliverable missing. The follow-on FY18 work package does not contain a Level 3 Milestone titled “Private ISF Planning and Gap analysis”. The milestone appears to have been dropped between FY17 year end and FY18 execution. | M3 | 1.08.02.02.01.04 | SRNL | SF-17SR02020104 | Storage Design Concepts - SRNL | Carter, Joe | Carter, Joe | Private ISF Planning and Gap analysis | Commercial Interim Spent Fuel Storage Concept Gap and Impact Analysis | Commercial Interim Spent Fuel Storage Service Concept Gap and Impact Analysis | 2017-11-20 | 2018-01-31 |  | Milestone is being reprogrammed in FY-18 | 2017 | Expected Late |  |  |  | None
M3SF-17SR020403201 Per Matt Brainard: Nuclear Fuels Storage and Transportation Requirements Document - Originally planned for FY18 completion on 11/15/2017 and subsequently delayed until 1/31/2018. Deliverable missing. The follow-on FY18 work package does not exist. It appears as though the entire control account and work package were dropped between FY17 year end and FY18 execution. | M3 | 1.08.02.04.03.20 | SRNL | SF-17SR02040320 | Functional and Operational Requirements - SRNL | Carter, Joe | Jarrell, Josh | Nuclear Fuels Storage and Transportation Requirements Document | Nuclear Fuels Storage and Transportation Requirements Document | Up date the Nuclear Fuels Storage and Transportation Requirements Document to Rev 4, continueing to add detail based on the underlying licensing requirments | 2017-11-15 | 2018-01-31 |  | Milestone will be eliminated with FY-18 reprogramming | 2017 | Expected Late |  |  |  | None |  | SFWD-IWM-2017-000073
M3SF-18AN010301018 Note: the milestones M3SF-18AN010301018 and M3SF-18AN010302017 do not exist as separate reports - these milestones were reported in M3SF-19AN0103001012 and M3SF-19AN0103002012 respectively. | M3 | 1.08.01.03.01.01 | ANL | SF-18AN01030101 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Deliverable | 2019-03-19 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18AN010302017 Note: the milestones M3SF-18AN010301018 and M3SF-18AN010302017 do not exist as separate reports - these milestones were reported in M3SF-19AN0103001012 and M3SF-19AN0103002012 respectively. | M3 | 1.08.01.03.02.01 | ANL | SF-18AN01030201 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Deliverable | 2019-03-19 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18AN020402013 Per Matt Brainard: ESA Input to Facility Configuration Analysis - Originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M3SF-19AN020402012 - ESA Input to Facility Configuration Analysis, completed on 1/31/2019. | M3 | 1.08.02.04.02.01 | ANL | SF-18AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | ESA Input to Facility Configuration Analysis | ESA Development Report | Draft chapters describing the ESA model and analysis for input to the Facility Configuration Analysis | 2019-01-31 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M3SF-18AN020402025 Superseded by M3SF-19AN020402023 | M3 | 1.08.02.04.02.02 | ANL | SF-18AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | NGSAM Current and Future Capabilities | NGSAM FY2018 Status Report | Report of NGSAM-related accomplishments and activities supported by numerous DOE labs | 2019-01-31 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18ID020303049 Patrick Schwab: There is no deliverable document for this. It was just an invoice after all the other parts of CLIN 2 were completed. | M3 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 2 Event Final: Completion of CLIN 2 (Phase 2) | CLIN Completion Letter: CLIN 2 | CLIN 2 Event Final: Completion of CLIN 2 (Phase 2) | 2018-03-20 |  | 2018-03-08 |  | 2018 | Complete | Submission of Final Phase 2 Report | Orano (formerly Areva) Fed Services | Schwab | None | FS-18-0051 Submission of Phase 2 Report.docx |  | Railcar, cask car, buffer car, Atlas
M3SF-18IN020409016 Superseded by M4SF-19IN20409012 | M3 | 1.08.02.04.09.01 | INL | SF-18IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Evaluation of CPP-603 for handling, loading, and drying ATR fuel in a standardized canister | Evaluation of CPP-603 for handling, loading, and drying ATR fuel in a standardized canister |  | 2019-09-02 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18LA010303016 superceded by M3SF-19LA010303011 | M3 | 1.08.01.03.03.01 | LANL | SF-18LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Salt Thermal Testing in Heated Boreholes: Experiments and Simulations | Salt Thermal Testing in Heated Boreholes: Experiments and Simulations | Report summarizing progress in data and modeling for the WIPP experiments in heated boreholes. | 2019-03-31 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18LA010304023 superceded by M4SF-19LA010304021 | M3 | 1.08.01.03.04.02 | LANL | SF-18LA01030402 | GDSA - Geologic Modeling - LANL | Perry, Frank | Mackinnon, Robert | Prorgress report on development of geologic framework model capability to support GDSA | Prorgress report on development of geologic framework model capability to support GDSA | Report on progress in developing a geologic framework modeling capability of alternative geologic media. | 2019-04-26 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M3SF-18LB010301033 superceded by M3SF-19LB010301031 | M3 | 1.08.01.03.01.03 | LBNL | SF-18LB01030103 | Argillite Disposal R&D - LBNL | Rutqvist, Jonny | McMahon, Kevin | Argillite Disposal R&D at LBNL | Argillite Disposal R&D at LBNL | Report on Expanded Argillite Disposal R&D at LBNL | 2019-03-15 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18LB010303023 superceded by M3SF-19LB010303023 | M3 | 1.08.01.03.03.02 | LBNL | SF-18LB01030302 | Salt Disposal R&D - LBNL | Rutqvist, Jonny | MacKinnon, Robert | LBNL Salt Coupled THMC Research in Support of Small Borehole Test | LBNL Salt Coupled THMC Research in Support of Small Borehole Test | Report on LBNL Salt Coupled THMC Reasarch in Support of Small Borehole Test | 2019-02-15 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18LB010308023 M3SF-18LB010308023 is superseded by FY19 milestone M3SF-19LB010308022 Engineered Barrier System Research Activities at LBNL: FY19 Progress Report. | M3 | 1.08.01.03.08.02 | LBNL | SF-18LB01030802 | Engineered Barrier System R&D - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL: FY18-FY19 Progress Report | Engineered Barrier System Research Activities at LBNL: FY18-FY19 Progress Report | This activity includes - Expand thermal-hydrological-mechanical-chemical (THMC) modeling capabilities to assess engineering-barrier-system (EBS) responses by evaluating chemical-mechanical coupling via state surface approach. - Development of reduced order models for THMC processes for integration of process-based coupled THMC models into GDSA | 2019-05-31 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M3SF-18OR010201082 superceded by M3SF-19OR010201072 | M3 | 1.08.01.02.01.08 | ORNL | SF-18OR01020108 | Stress Corrosion Cracking - ORNL | Scaglione, John | Saltzstein, Sylvia | Summary Report on Aerosol Transport Through Cracks Modeling | SCC Aerosol Transport Model Summary Report | Report documenting model development and validation needs and gaps. | 2018-12-20 |  |  | On schedule | 2018 | 90 Day |  |  |  | None
M3SF-18OR010203013 Per Matt Brainard: Document not uploaded to PICS:NE: “Document is currently undergoing industry review in accordance with our NDA since some of the information generated was developed based on proprietary data.” Main Document Title: “Integrated Shielding Benchmark for a TN-32B Spent Nuclear Fuel Cask.” Deliverable Description: “This report documents a shielding analysis of the TN-32B High Burnup demonstration cask comparing the predicted radiation dose fields to the radiation detection measurement taken during the loading of the High Burnup demonstration cask. During the loading process, numerous dose rate measurements were recorded, and these data form the basis for development of a shielding benchmark.” Lab ID No. 115063. | M3 | 1.08.01.02.03.01 | ORNL | SF-18OR01020301 | Analysis - ORNL | Scaglione, John | Saltzstein, Sylvia | Document dose rate anaylsis and comparison to measured results for HBU demo cask | Dose rate measurement and modeling comparison for the HBU demo cask | This report will provide a detailed dose rate analysis of the HBU demo cask and compare against measured values. | 2018-08-31 |  | 2018-08-31 |  | 2018 | Complete | Integrated Shielding Benchmark for a TN-32B Spent Nuclear Fuel Cask | Cumberland | Scaglione, John | None
M3SF-18OR0103050110 superceded by M3SF-19OR010305015 | M3 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Multiphysics criticality consequence analysis capability development status report | Multiphysics criticality consequence analysis capability development status report | This deliverable captures the Multiphysics criticality excursion consequence analysis methodology status and reports path forward. | 2019-05-31 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18OR0103050112 Replaced with 2019 milestone M3SF-19OR010305016 | M3 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Neutronic and thermal hydraulic coupling for waste package | Neutronic and thermal hydraulic coupling for waste package | This deliverable includes a methodology to simulate DPC criticality and quantify various important parameters such as change in isotopic inventory, increase in temperature, and increase in pressure. The deliverable also includes the sensitivity of criticality excursion on various boundary conditions such as water flow rate. | 2019-03-29 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18OR0103050113 Replaced with M4SF-19OR010305017 | M3 | 1.08.01.03.05 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Initial structural performance analysis of waste package for various criticality scenarios | Structural performance analysis of waste package for various criticality scenarios |  | 2019-09-05 | 2019-12-31 |  |  | 2019 | Cancelled |  |  |  | None
M3SF-18OR010305018 superseded by M3SF-19OR010305013 | M3 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Update of DPC direct disposal criticality analysis report | DPC direct disposal criticality analysis report | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results including misload analysis results into the existing living document. | 2019-04-19 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18OR0203020411 Superseded by FY19 Milestone M3SF-19OR0203020310 - Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report, completed on 2/22/2019. | M3 | 1.08.02.03.02.04 | ORNL | SF-18OR02030204 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report | Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report | Report on analysis of various options for acceptance queues from pick-up of spent nuclear fuel from commercial nuclear power plants. | 2019-02-22 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M3SF-18OR020302045 Superseded by FY19 Milestone M3SF-19OR020302035 - Site Specific De-Inventory Report #7, which is not due until 8/23/2019 in the FY19 follow-on work package. Deliverable has not yet been produced. | M3 | 1.08.02.03.02.04 | ORNL | SF-18OR02030204 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #7 | Site Specific De-Inventory Report #7 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-01-11 | 2019-03-15 |  | On schedule for revised finish date. | 2018 | Expected Late |  |  |  | None
M3SF-18OR020302046 Per Matt Brainard: Superseded by FY19 Milestone M3SF-19OR020302036 - Site Specific De-Inventory Report #8, which is not due until 8/23/2019 in the FY19 follow-on work package. Deliverable has not yet been produced. | M3 | 1.08.02.03.02.04 | ORNL | SF-18OR02030204 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #8 | Site Specific De-Inventory Report #8 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-01-11 | 2019-03-29 |  | On schedule for revised finish date. | 2018 | Expected Late |  |  |  | None
M3SF-18OR020402062 Superseded by FY19 Milestone M3SF-19OR020402061 - System Architecture/NGSAM Results Summary, completed on 1/31/2019. | M3 | 1.08.02.04.02.06 | ORNL | SF-18OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | System Architecture/NGSAM Results Summary | FY18 System Architecture Report | Report of the analysis conducted to evaluate an integrated approach to the waste management system. This report incorporates the latest information provided through other program activities to update and augment strategies and approaches for managing SNF throughout the waste management system. | 2019-01-31 |  |  | on track | 2018 | On Schedule |  |  |  | None
M3SF-18OR020405015 Superseded by FY19 Milestone M3SF-19OR020405014 - Update UNF-ST&DARDS thermal report, completed on 5/31/2019. | M3 | 1.08.02.04.05.01 | ORNL | SF-18OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS thermal report | Update UNF-ST&DARDS thermal report | The deliverable includes development of new thermal model(s)(storage, transfer), and integration of new thermal model(s) into UNF-ST&DARDS. Under this deliverable, any PNNL developed thermal models will also be incorporated into UNF-ST&DARDS. Canister surface temperature will be included as a parameter of interest with peak cladding temperature, and cask surface temperature. | 2019-01-31 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18OR020405016 Per Matt Brainard: - Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data - Originally planned for FY19 completion on 2/28/2019. Superseded by FY19 Milestone M3SF-19OR020405015 - Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data, completed on 2/28/2019. | M3 | 1.08.02.04.05.01 | ORNL | SF-18OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | validation of UNF-ST&DARDS as-loaded analysis methodology | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18OR020405017 Update UNF-ST&DARDS shielding report - Originally planned for FY19 completion on 2/14/2019. Superseded by FY19 Milestone M3SF-19OR020405016 - Update UNF-ST&DARDS shielding report, completed on 6/28/2019. | M3 | 1.08.02.04.05.01 | ORNL | SF-18OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS shielding report | UNF-ST&DARDS shielding analysis capability | The deliverable includes development of new shielding model(s) (transport), and integration of new shielding model(s) into UNF-ST&DARDS. Under this deliverable, on-the-fly dose analysis methodology may be integrated into UNF-ST&DARDS if Shift Monte Carlo code is ready with complete hybrid variance reduction capability. | 2019-02-14 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M3SF-18PN010201033 superseded M3SF-17PN010201033, and was then superseded by M3SF-19PN010201031 | M3 | 1.08.01.02.01.03 | PNNL | SF-18PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | Hydride Cooling Rate Study | Cooling Rate Studies | Determine effect of cooling rate on hydride formation to inform sister rod testing | 2019-01-25 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18PN0102030212 Per Jim Fort: report is associated with a task that has been moved to 2020, “Thermal Modeling for Transportation System”. Per Matt Brainard: Thermal Models During Transportation – originally planned for FY19 completion on 3/29/2019. However there isn’t a clear cross-walk between this milestone and a FY19 one (Consider FY18 milestone missing): | M3 | 1.08.01.02.03.02 | PNNL | SF-18PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Thermal Models During Transportation | Thermal Modeling for Transportation System | Model the temperatures of structures, systems, and components when a canister is placed in a transportation package | 2019-03-29 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18PN010203028 superceded by M3SF-19PN010203022 | M3 | 1.08.01.02.03.02 | PNNL | SF-18PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | FAST/FRAPCON modeling of sister rods | FAST Models of Sister Rods | Use the FAST/FRAPCON code family to model end of life rod internal pressure, oxide layer and CRUD layer thicknesses, clad thinning, etc. and compare against NDE data from ORNL and rod puncture data. | 2018-10-26 |  |  | On schedule. | 2018 | 90 Day |  |  |  | None
M3SF-18PN010203029 superceded by M3SF-19PN010203023 | M3 | 1.08.01.02.03.02 | PNNL | SF-18PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Sensitivity of High Heat Load MAGNASTOR | Decay Heat Sensitivity Study | Determine cladding temperatures for various heat loadings to determine how short cooled assembly loading affects PCT and distributions | 2018-12-21 |  |  | On schedule. | 2018 | 90 Day |  |  |  | None
M3SF-18SN0102010413 superceded by M3SF-19SN010201047 | M3 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Final Report: Probabilistic Model for Stress Corrosion Cracking of Spent Nuclear Fuel Canisters | Final Report: Probabilistic Model for Stress Corrosion Cracking of Spent Nuclear Fuel Canisters | This final report will document the completed model for stress corrosion cracking of spent nuclear fuel canisters, summarizing the model development and use, and the final results. | 2019-03-22 |  |  | Work on this report continues on schedule. The level 2 milestone report due in September was submitted on time, and will provide feeds for this milestone. Improvements to the canister SCC model continue to be implemented. | 2018 | On Schedule |  |  |  | None
M3SF-18SN0102010414 superceded by M2SF-19SN010201048 | M3 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Initiation of crack growth experiments at SNL using RH controlled load frames (elevate to M2) | Initiation of crack growth experiments at SNL using RH controlled load frames | Sandia will purchase one or more load frames for performing SCC crack growth testing in controlled RH environments, and will, by 3/15/19, have initiated SC crack growth experiments under atmospheric conditions. | 2019-03-15 |  |  | Work on this milestone is on schedule. the load frames have been purchased and were delivered in September. they will be installed and tested over the next few months. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010202024 superseded by M3SF-19SN010202021 | M3 | 1.08.01.02.02.02 | SNL | SF-18SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | Shaker Table and 30cm Drop Tests | Transportation Tests | Preparing and conducting shaker table and 30cm drop tests. | 2019-03-29 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010203032 Per Matt Brainard: has been mapped into FY19 and elevated to an M2. It is now: “M2SF-19SN010203032 - Test Plan for Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator”. | M3 | 1.08.01.02.03.03 | SNL | SF-18SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator (Should be M2) | Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator | Results of T-H testing of a horizontal dry cask simulator | 2019-02-22 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010203033 superceded by M3SF-19SN010203033 | M3 | 1.08.01.02.03.03 | SNL | SF-18SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | 2019-03-29 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010205013 Per Matt Brainard: has been mapped into FY19 and is now: “M3SF-19SN010205012 - Assessment of Security-Related Issues for Spent Nuclear Fuel”. | M3 | 1.08.01.02.05.01 | SNL | SF-18SN01020501 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Assessment of Security-Related Issues for Spent Nuclear Fuel | Assessment of Security-Related Issues for Spent Nuclear Fuel | Investigations into security-related issues with continued use of dry casks | 2019-03-08 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010301093 superceded by M4SF-19SN010301091 | M3 | 1.08.01.03.01.09 | SNL | SF-18SN01030109 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | McMahon, Kevin | Expanded - Argillite Disposal R&D International Collaborations interim report - 2019 | Argillite Disposal R&D International Collaborations interim report - 2019 |  | 2019-05-24 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010304053 Emily Stein: When we did FY19 planning, this M3 went away and was replaced with an M2 that is due in September. It doesn’t exist. | M3 | 1.08.01.03.04.05 | SNL | SF-18SN01030405 | GDSA - Uncertainty and Sensitivity Analysis Methods - SNL | Stein, Emily | MacKinnon, Robert | Status Report on UQ/SA Tools in GDSA Framework | Status Report on UQ/SA Tools in GDSA Framework | M3 report documenting and demonstrating newly developed UQ/SA tools and the progress of UQ/SA tools during the UFD and SFWST campaigns | 2019-04-16 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010304063 superceded by M2SF-19SN010304041 | M3 | 1.08.01.03.04.06 | SNL | SF-18SN01030406 | GDSA - Framework Development - SNL | Mariner, Paul | MacKinnon, Robert | Disposal Research Integration | Status of Disposal Research | Integration of process modeling for the safety case | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010304063 superceded by M2SF-19SN010304041 | M3 | 1.08.01.03.04.06 | SNL | SF-18SN01030406 | GDSA - Framework Development - SNL | Mariner, Paul | Mackinnon, Robert | Disposal Research Integration | Status of Disposal Research | Integration of process modeling for the safety case | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010305029 superceded by M2SF-19SN010305021 | M3 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | Mackinnon, Robert | Accelerated Testing of Selected Filler Compositions | Results from Accelerated Testing of Selected DPC Fillers | Select one or more cement compositions for accelerated testing, optimizing the slurry recipe, and emphasizing evaluation of injectability, slurry pH, thermal setting, dewatering, and shrinkage. | 2019-06-26 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010305061 same as M3SF-19SN010305061 | M3 | 1.08.01.03.05.06 | SNL | SF-18SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | MacKinnon, Robert | Probabilistic Postclosure DPC Criticality Consequence Analysis - Scoping | Criticality Consequence Analysis for Geologic Disposal, Scoping | Develop technical and regulatory strategy for low consequence analyses, founded in regulations and existing generic PA models. Identify an appropriate set of criticality FEPs. Identify appropriate uses for simulation and enumeration approaches for repository performance assessment. Define key parameters and metrics. | 2019-01-22 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010305061 same as M3SF-19SN010305061 | M3 | 1.08.01.03.05.06 | SNL | SF-18SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Mackinnon, Robert | Probabilistic Postclosure DPC Criticality Consequence Analysis - Scoping | Criticality Consequence Analysis for Geologic Disposal, Scoping | Develop technical and regulatory strategy for low consequence analyses, founded in regulations and existing generic PA models. Identify an appropriate set of criticality FEPs. Identify appropriate uses for simulation and enumeration approaches for repository performance assessment. Define key parameters and metrics. | 43487 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SN010305072 not completed per Hardin | M3 | 1.08.01.03.05.07 | SNL | SF-18SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | MacKinnon, Robert | DPC Criticality Simulation Preliminary Phase | Preliminary Multiphysics Simulations for Disposal Criticality Scenarios | Perform and document a systematic approach to postclosure waste package criticality simulation, using external code coupling. | 2019-09-18 |  |  | Work planning is complete and procurement of services is underway. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010305072 not completed per Hardin | M3 | 1.08.01.03.05.07 | SNL | SF-18SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | Mackinnon, Robert | DPC Criticality Simulation Preliminary Phase | Preliminary Multiphysics Simulations for Disposal Criticality Scenarios | Perform and document a systematic approach to postclosure waste package criticality simulation, using external code coupling. | 43726 |  |  | Work planning is complete and procurement of services is underway. | 2018 | On Schedule |  |  |  | None
M3SF-18SN010309012 OUO Author: This is a rough draft version of the Final Report M2SF-18SN010309013 SAND2018_12352 R.pdf. Please point any users to that document. | M3 | 1.08.01.03.09.01 | SNL | SF-18SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, David | MacKinnon, Robert | Status Report on Inventory and Waste Characterization | Status Report on Inventory and Waste Characterization | Report summarizing work activities on updates/revisions to DOE Managed HLW and SNF data sets | 2018-07-20 |  | 2018-07-20 02:00 |  | 2018 | Complete | Status Report on Inventory and Waste Characterization | Sassani, David | Sassani, David | OUO |  |  | waste forms inventory repository DSNF DHLW
M3SF-18SN010309015 Pre-Plan canceled MS | M3 | 1.08.01.03.09.01 | SNL | SF-18SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, Dave | Mackinnon, Robert | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status report on expansion of OWL Capabilities for outputing canistered/packaged inventories that can be input to generic storage, transportation, or disposal studies. | 2019-04-30 |  |  | on track | 2018 | On Schedule |  |  |  | None
M3SF-18SN010309015 Pre-Plan canceled MS | M3 | 1.08.01.03.09.01 | SNL | SF-18SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, Dave | Mackinnon, Robert | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status report on expansion of OWL Capabilities for outputing canistered/packaged inventories that can be input to generic storage, transportation, or disposal studies. | 2019-04-30 |  |  | on track | 2018 | On Schedule |  |  |  | None
M3SF-18SN010401014 superceded by M3SF-19SN010401014 | M3 | 1.08.01.04.01.01 | SNL | SF-18SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Place contract with Cloud Vendor | Cloud Vendor Contract | Place contract with Cloud Vendor | 2018-08-03 |  | 2018-08-03 |  | 2018 | Complete | First Two Pages of the SNL Contract for the Cloud Vendor Services |  |  | None | NWM Cloud PO Pg 1.PNG NWM Cloud PO Pg 2.PNG
M3SF-18SR010201054 superceded by M3SF-19SR010201052 | M3 | 1.08.01.02.01.05 | SRNL | SF-18SR01020105 | Stress Corrosion Cracking - SRNL | Carter, Joe | Saltzstein, Sylvia | FY-18 Summary Report of Canister Corrosion Testing | FY-18 Summary Report of Canister Corrosion Testing | Summary Report of Canister Corrosion Testing | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18SR010202032 Per Matt Brainard: M3SF-18SR010202032: Sister Pin Transportation Summary Report was delayed into FY19 for completion on 11/13/2018, however the SF-18SR01020203 - Transportation - SRNL work package did not continue into FY19. Milestone appears to have been deleted between fiscal years. Consider deliverable missing. | M3 | 1.08.01.02.02.03 | SRNL | SF-18SR01020203 | Transportation - SRNL | Carter, Joe | Saltzstein, Sylvia | Sister Pin Transportation Summary Report | Sister Pin Transportation Summary Report | Sister Pin Transportation Summary Report | 2018-09-28 | 2018-11-13 |  | To be complete by 11/13/18. | 2018 | Expected Late |  |  |  | None
M3SF-18SR020405023 Superseded by FY19 Milestone M3SF-19SR020405022 - Inventory Report rev 6, completed on 3/27/2019. | M3 | 1.08.02.04.05.02 | SRNL | SF-18SR02040502 | Commercial SNF Characterization - SRNL | Carter, Joe | Howard, Rob | Inventory Report rev 6 | Inventory Report Rev 6 | Inventory Report rev 6 | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-19ID020303046 CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) - Deliverable missing from PICS:NE. Note entered on Deliverable Form: “The Atlas Railcar Phase 3 Final Report, including all the appendices, is now on the DOE website.” | M3 | 1.08.02.03.03.04 | DOE-ID | SF-19ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) | CLIN Completion Letter: CLIN 2 | CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) | 2019-05-20 |  |  | Railcars have finished fabrication and they are en route to the test site. | 2019 | 90 Day |  |  |  | None
M3SF-19SN010205012 SNSI | M3 | 1.08.01.02.05.01 | SNL | SF-19SN01020501 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Assessment of Security-Related Issues for Spent Nuclear Fuel | Assessment of Security-Related Issues for Spent Nuclear Fuel | Investigations into security-related issues with continued use of dry casks | 2019-03-08 |  | 2019-03-01 02:00 |  | 2019 | 90 Day | Unmanned Aerial Systems Threat Analysis for Isolated and Consolidated Spent Fuel Storage Configurations (SAND2019-1843) | Mancel Jordan Parks | Samuel Durbin | SNSI |  |  | unmanned aerial systems; vulnerability analysis; spent nuclear fuel; dry storage cask
M3SF-19SN010309012 Per Matt Brainard: M3SF-19SN010309012 – Document unavailable in PICS:NE. CUI Type “Other” prohibits upload to PICS:NE (comment: internal use only draft report). Note: This draft report is internal use only and represents completion of milestone deliverable M3SF-19SN010309012 “Status Report on OWL Capabilities Expansion” that reports interim status on FY2019 activities for the work package (WP) SF-19SN01030901. This report provides the draft status information for in process FY2019 work activities for WP SF-19SN01030901, and serves as a draft template for the milestone deliverable M2SF-19SN010309013 “Online Waste Library (OWL) and Waste Forms Characteristics Annual Report” due on August 2, 2019 for WP SF-19SN01030901. Internal SNL Tracking No. 960647 (Prog. Rev). Document is available through Dave Sassani, SNL. | M3 | 1.08.01.03.09.01 | SNL | SF-19SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, David | McMahon, Kevin | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status report on expansion of OWL Capabilities for outputing canistered/packaged inventories that can be input to generic storage, transportation, or disposal studies. | 2019-04-30 |  |  | milestone is on schedule | 2019 | 90 Day |  |  |  | None
M41UF030101 Per Mark Nutt: M41UF030101, ANL input to SNL L3 Milestone – I cannot find anything on this. Jim Cunnane was working this and may have sent an e-mail to Geoff Freeze. | M4 | 1.02.08.03 | ANL | FTAN11UF0301 | FEPS |  |  | ANL input to SNL L3 Milestone
M41UF030701 Per Mark Nutt: ANL Input to SNL L3 MS: Used Fuel Waste Form Degradation FY11 Summary Report – I don’t have a record on this and was not who was performing the work. It may have been Jim Cunnane. Carlos Jove Colon may have an email or the file. | M4 | 1.02.08.03 | ANL | FTAN11UF0307 | Repository Science/waste form degradation & RN mobilization |  |  | ANL Input to SNL L3 MS: Used Fuel Waste Form Degradation FY11 Summary Report
M41UF030901 Requested, but no response. | M4 | 1.02.08.03 | INL | FTIN11UF0309 | Generic Natural System Evaluation |  |  | Input from INL to SNL L2 milestone
M41UF031002 Requested, but no response. | M4 | 1.02.08.03 | INL | FTIN11UF0310 | Inventory |  |  | contribution report
M41UF031003 Requested, but no response. | M4 | 1.02.08.03 | INL | FTIN11UF0310 | Inventory |  |  | contribution report
M41UF031101 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0311 | Technical Bases / Lessons Learned |  |  | LANL Input to SNL L3 MS: System-Wide Integration and Site Selection Concepts for Future Disposition Options for HLW
M41UF031201 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0312 | FEPS |  |  | LANL input to SNL L3 milestone
M41UF031301 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0313 | Generic EBS Evaluation |  |  | LANL input to SNL L2 Milestone: Evaluation of THMC Processes at EBS Interfaces
M41UF031402 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0314 | Generic Natural System Evaluation |  |  | LANL input to SNL L2 Milestone
M41UF031501 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0315 | Generic Disposal System-Level Modeling |  |  | LANL input to SNL L2 MS: Report describing the integrated generic disposal system environment (GDSE) model
M41UF031601 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0316 | LLW Disposition |  |  | LANL Input to SRS Level 3 Milestone: LLW Disposal Issues and Alternatives
M41UF031801 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0318 | Repository Science/Engineered material performance |  |  | LANL Input to SNL L3 Milestone: Engineered Material Performance - EOFY Status Report
M41UF031901 Requested, but no response. | M4 | 1.02.08.03 | LANL | FTLA11UF0319 | Repository Science/flow and transport saturated media |  |  | LANL Input to SNL L3 MS: Synthesis report on progress made FY11 in flow and transport saturated media
M41UF032201 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0322 | FEPS |  |  | LBNL input to SNL L3 milestone
M41UF032301 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0323 | Generic EBS Evaluation |  |  | LBNL input to SNL L2 milestone: Evaluation of THMC Processes at EBS Interfaces
M41UF032401 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0324 | Generic Natural System Evaluation |  |  | Input from LBNL to SNL for SNL L2 milestone
M41UF032501 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0325 | Generic Disposal System-Level Modeling |  |  | LBNL Input to SNL L2 MS: Report describing the integrated generic disposal system environment (GDSE) model
M41UF032601 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0326 | Repository Science/flow and transport unsaturated media |  |  | FY11 Report on Unsaturated Flow and Transport
M41UF032701 Requested, but no response. | M4 | 1.02.08.03 | LBNL | FTLB11UF0327 | Repository Science/THCM near field |  |  | LBNL Input to SNL L3 MS: FY11 Development of TOUGH2-Based Repository THMC SImulation Tools
M41UF032901 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0329 | FEPS |  |  | LLNL input to SNL L3 milestone
M41UF033005 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0330 | Generic EBS Evaluation |  |  | DSEF Version 1.1 Progress Report
M41UF033101 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0331 | Generic Natural System Evaluation |  |  | LLNL input to SNL L2 milestone
M41UF033102 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0331 | Generic Natural System Evaluation |  |  | Pu solubility in goethite suspensions at 80 and 2C5.
M41UF033103 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0331 | Generic Natural System Evaluation |  |  | Pu solubility in clay suspensions at 80 and 25C
M41UF033201 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0332 | Repository Science/THCM near field |  |  | LLNL Input to SNL L3 MS: FY11 Development of Fully Coupled Repository THMC Simulation Tools report
M41UF033302 Requested, but no response. | M4 | 1.02.08.03 | LLNL | FTLL11UF0333 | Repository Science/Thermal load management & design concepts |  |  | LLNL input to SNL L3 MS: FY11 Investigations on Repository Near-Field Thermal Modeling
M41UF033403 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0334 | Repository Science/Criticality analysis |  |  | Spent Fuel Benchmark Evaluation
M41UF033404 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0334 | Repository Science/Criticality analysis |  |  | Degraded Model Benchmark Applicability
M41UF033405 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0334 | Repository Science/Criticality analysis |  |  | Criticality Consequence Whitepaper
M41UF033407 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0334 | Repository Science/Criticality analysis |  |  | Radiation Transport Analysis
M41UF033408 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0334 | Repository Science/Criticality analysis |  |  | Computational Analysis of Radiochemical Assays
M41UF033502 Requested, but no response. | M4 | 1.02.08.03 | PNNL | FTPN11UF0335 | Inventory |  |  | Contribution Report
M41UF034002 Requested, but no response. | M4 | 1.02.08.03 | SNL | FTSN11UF0340 | Generic Natural System Evaluation |  |  | Initiating natural system database design
M41UF034203 Requested, but no response. | M4 | 1.02.08.03 | SNL | FTSN11UF0342 | Inventory |  |  | Contribution Report (SNL Input to SRNL milestone report)
M41UF034401 Requested, but no response. | M4 | 1.02.08.03 | SNL | FTSN11UF0344 | LLW Disposition |  |  | SNL Input to SRNL Level 3 Milestone: LLW Disposal Issues and Alternatives
M41UF034901 Requested, but no response. | M4 | 1.02.08.03 | SNL | FTSN11UF0349 | Repository Science/Engineered material performance |  |  | Engineered material performance interim report - work plan
M41UF035103 Requested, but no response. | M4 | 1.02.08.03 | SNL | FTSN11UF0351 | Repository Science/System Level analysis |  |  | A design and user document for the sampling software including the sampling DLL
M41UF035601 Requested, but no response. | M4 | 1.02.08.03 | SRNL | FTSR11UF0356 | Perspectives on Nuclear Waste Management |  |  | SRS Input to SNL L3 MS: Evaluation of Possible Perspectives on Nuclear Waste Management
M41UF035802 Requested, but no response. | M4 | 1.02.08.03 | SRNL | FTSR11UF0358 | Repository Science/Thermal load management & design concepts |  |  | Pre-conceptual designs summary report
M41UF035902 Requested, but no response. | M4 | 1.02.08.03 | ORNL | FTOR11UF0359 | Repository Science/Thermal load management & design concepts |  |  | Provide input to SNL L3 milestone
M41UF040101 Per Mark Nutt: M41UF040101 and M41UF040102 (Concept Evaluations) – I have no record of any reports for these milestones. We were working with Ruth Weiner and Ken Sorenson on this project. Ruth had the lead and I have a hunch we satisfied the milestones by reviewing draft reports, etc. | M4 | 1.02.08.04 | ANL | FTAN11UF0401 | Concept Evaluations
M41UF040102 Per Mark Nutt: M41UF040101 and M41UF040102 (Concept Evaluations) – I have no record of any reports for these milestones. We were working with Ruth Weiner and Ken Sorenson on this project. Ruth had the lead and I have a hunch we satisfied the milestones by reviewing draft reports, etc. | M4 | 1.02.08.04 | ANL | FTAN11UF0401 | Concept Evaluations | [8 empty] | No input provided by WPM. | [6 empty] | ICEM2011_Aging_59067.pdf ICEM2011_ASurv_59032.pdf
M41UF040201 Per Mark Nutt: M41UF040201 and M41UF040202 (Transportation) – I have no record of any reports and cannot remember what they may have been for. PICS-NE won’t show me the work packages in FY11 to even have a clue. My hunch is that we supported Paul McConnell and satisfied the milestone via email. | M4 | 1.02.08.04 | ANL | FTAN11UF0402 | Transportation | [8 empty] | Assumed on schedule | [6 empty] | ANL_MYR_Transport_FY11.pdf
M41UF040202 Per Mark Nutt: M41UF040201 and M41UF040202 (Transportation) – I have no record of any reports and cannot remember what they may have been for. PICS-NE won’t show me the work packages in FY11 to even have a clue. My hunch is that we supported Paul McConnell and satisfied the milestone via email. | M4 | 1.02.08.04 | ANL | FTAN11UF0402 | Transportation | [8 empty] | No input provided by WPM. | [6 empty] | HBU_Test_Plan_ANL_42811.pdf
M41UF040701 Requested, but no response. | M4 | 1.02.08.04 | LLNL | FTLL11UF0407 | R&D Opportunities | [8 empty] | The LLNL Storage R&D level-4 milestone was completed on 3/30/2011 via email letter report to the Cost Account Manager and the activity lead.
M41UF040801 Requested, but no response. | M4 | 1.02.08.04 | LLNL | FTLL11UF0408 | Security | [8 empty] | Delayed to 8/12 to allow incorporation of results of, and/or inspired by, the multi-lab workshop at INL the last week of July. Further delayed to 8/18 due to additional DOE review requirements.
M41UF041101 Requested, but no response. | M4 | 1.02.08.04 | ORNL | FTOR11UF0411 | Security | [8 empty] | This milestone is currently expected to be completed ontime. | [6 empty] | UFDC_Security_Self-Protection-Report_01Aug11.pdf
M41UF041302 Requested, but no response. | M4 | 1.02.08.04 | PNNL | FTPN11UF0413 | Concept Evaluations | [8 empty] | Milestone completed 3/31/11. | [6 empty] | FCT-Report-PNNL March deliverable PR Concepts.docx FCT-Report-PNNL March deliverable PR Concepts.pdf FCT-Report-PNNL March deliverable PR Concepts.pdf FCT-Report-PNNL March deliverable PR Concepts.pdf FCT-Report-PNNL March deliverable PR Concepts_2.pdf FCT-Report-PNNL March deliverable PR Concepts_2.pdf FCT-Report-PNNL March deliverable Security_2.pdf
M41UF041402 Requested, but no response. | M4 | 1.02.08.04 | PNNL | FTPN11UF0414 | R&D Opportunities
M41UF041503 Requested, but no response. | M4 | 1.02.08.04 | PNNL | FTPN11UF0415 | Security | [8 empty] | Milestone completed 3/31/11. | [6 empty] | FCT-Report-PNNL March deliverable Security.pdf FCT-Report-PNNL March deliverable Security.pdf FCT-Report-PNNL March deliverable Security_2.pdf FCT-Report-PNNL March deliverable Security_2.pdf
M41UF041702 Requested, but no response. | M4 | 1.02.08.04 | SNL | FTSN11UF0417 | Concept Evaluations | [8 empty] | The milestone is on schedule. | [6 empty] | Final Report_Ageing Man.doc
M41UF041802 Requested, but no response. | M4 | 1.02.08.04 | SNL | FTSN11UF0418 | R&D Opportunities | [8 empty] | On schedule | [6 empty] | SNL M4 email.docx
M41UF042002 Requested, but no response. | M4 | 1.02.08.04 | SNL | FTSN11UF0420 | Transportation | [8 empty] | Status Report completion is on schedule. All six laboratories on the Transportation Team shall provide input that shall be collated into a single document. | [6 empty] | @@FCTP_Transportation_March312011_milestone.docx
M41UF042105 Requested, but no response. | M4 | 1.02.08.04 | SRNL | FTSR11UF0421 | Concept Evaluations | [8 empty] | Milestone on schedule
M41UF042106 Requested, but no response. | M4 | 1.02.08.04 | SRNL | FTSR11UF0421 | Concept Evaluations | [8 empty] | Alternative descriptions have been developed. Material will be included in the concept evaluation report. On schedule.
M41UF042201 Requested, but no response. | M4 | 1.02.08.04 | SRNL | FTSR11UF0422 | R&D Opportunities
M41UF042301 Requested, but no response. | M4 | 1.02.08.04 | SRNL | FTSR11UF0423 | Security | [8 empty] | New revised finish date for Level 4 Milestone (M41UF042301) from August 1, 2011 to August 12, 2011 in order incorporate comments from the UFD Security Team Meeting held in Idaho on July 26-27th, 2011 as directed by the SNL work package lead.
M41UF042401 Requested, but no response. | M4 | 1.02.08.04 | SRNL | FTSR11UF0424 | Transportation | [8 empty] | On Schedule.
M4508020201 Requested, but no response. | M4 | 1.5.08.02 | LLNL | LL1015080202 | External Interactions |  |  | LLNL Input to Summary of External Interactions - FY10
M4508020601 Requested, but no response. | M4 | 1.5.08.02 | LLNL | LL1015080206 | International - LLNL |  |  | LLNL Input to Summary of International Collaboration - FY10
M4508030201 Requested, but no response. | M4 | 1.5.08.03 | LLNL | LL1015080302 | Rapid Response - LLNL |  |  | Summary of Inquiries Addressed by LLNL FY10
M4508030301 Requested, but no response. | M4 | 1.5.08.03 | LANL | LA1015080303 | Rapid Response |  |  | Summary Report of Inquiries Addressed by LANL FY10
M4508030804 Requested, but no response. | M4 | 1.5.08.03 | SRNL | SR1015080308 | Technical Bases - Lessons Learned |  |  | Storage Support status report
M4508031001 Per Mark Nutt: M4508031001, Legal and Regulatory Framework Analysis – I cannot find anything on this. If I recall correctly (and this was nine years ago), we worked closely with Rob Rechard on the development of the final report. My bet is that we sent him an email with our input and claimed victory on the L4. Since it was rough input we didn’t want it on DMS. I do not have access to my Argonne emails and cannot look. Perhaps Rob can search back for something from me and find an email from me with a document – if you need to have it. | M4 | 1.5.08.03 | ANL | AN1015080310 | Legal and Regulatory Framework Analysis |  |  | Input to SNL for end of FY10 status report
M4508031101 Requested, but no response. | M4 | 1.5.08.03 | SRNL | SR1015080311 | Legal and Regulatory Framework Analysis |  |  | Input to SNL for end of FY10 status report
M4508031303 Requested, but no response. | M4 | 1.5.08.03 | PNNL | PN1015080313 | Storage - R&D Opportunities | [8 empty] | Final report contribution was submitted to Sandia and the project team ahead of schedule for incorporation into the consolidated report, which being prepared by Sandia for their Sept 30 milestone. | [6 empty] | Section_3_as-of-8_22 Hanson R1.docx
M4508031401 Requested, but no response. | M4 | 1.5.08.03 | SNL | SN1015080314 | Storage - R&D Opportunities
M4508032001 Requested, but no response. | M4 | 1.5.08.03 | SRNL | SR1015080320 | SNF/HLW Disposition - Waste Form and Inventory Determination |  |  | Quantities and Inventory of UNF and HLW
M4508032002 Requested, but no response. | M4 | 1.5.08.03 | SRNL | SR1015080320 | SNF/HLW Disposition - Waste Form and Inventory Determination |  |  | Alternative HLW forms for aqueous reprocessing
M4508032006 Requested, but no response. | M4 | 1.5.08.03 | SRNL | SR1015080320 | SNF/HLW Disposition - Waste Form and Inventory Determination |  |  | Alternative Fuel Cycle HLW forms
M4508032104 Requested, but no response. | M4 | 1.5.08.03 | INL | IN1015080321 | LLW Disposition - Quantities and Inventory |  |  | LLW Inventory for two processing scenarios
M4508032203 Requested, but no response. | M4 | 1.5.08.03 | PNNL | PN1015080322 | LLW Disposition - Quantities and Inventory |  |  | LLW generation waste estimates for additional fuel cycle alternatives
M4508032802 Requested, but no response. | M4 | 1.5.08.03 | PNNL | PN1015080328 | Storage - Security | [8 empty] | Milestone was completed ahead schedule. | [6 empty] | UFDStorageSecurity10Sep2010Final.pdf
M4508032901 Requested, but no response. | M4 | 1.5.08.03 | SNL | SN1015080329 | Storage - Security | [8 empty] | This work package required input from other related work packages that had later mid-year deliverable deadlines. A revised finish date of 3/15/2010 was approved and the milestone was delivered on hat date. | [6 empty] | M4508032901 Milestone Report.pdf
M4508041401 Requested, but no response. | M4 | 1.5.08.04 | LBNL | LB1015080414 | Disposal Systems Evaluations and Tool Development - Natural System Evaluation |  |  | Summary on the technical gap on clay repositories.
M4508041501 Requested, but no response. | M4 | 1.5.08.04 | LLNL | LL1015080415 | Disposal Systems Evaluations and Tool Development - Natural System Evaluation |  |  | Summary on the irreversibility of radionuclide sorption.
M4508041601 Requested, but no response. | M4 | 1.5.08.04 | LANL | LA1015080416 | Disposal Systems Evaluations and Tool Development - Natural System Evaluation |  |  | Summary on the key natural system attributes related to far field hydrology and radionuclide transport.
M4508041901 Requested, but no response. | M4 | 1.5.08.04 | LBNL | LB1015080419 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | Model results for clay swelling
M4508042001 Requested, but no response. | M4 | 1.5.08.04 | LLNL | LL1015080420 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | Test plan and preliminary results on radionuclide solubility at elevated temperatures
M4508042101 Requested, but no response. | M4 | 1.5.08.04 | LANL | LA1015080421 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | Model description and results for the granite environment.
M4508042202 Requested, but no response. | M4 | 1.5.08.04 | SNL | SN1015080422 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | Report on guidance for model development
M4508042301 Requested, but no response. | M4 | 1.5.08.04 | LANL | LA1015080423 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | Mid FY progress Report on Evaluation of EBS
M4508042302 Requested, but no response. | M4 | 1.5.08.04 | LANL | LA1015080423 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | End of FY progress report on Evaluation of EBS
M4508042401 Requested, but no response. | M4 | 1.5.08.04 | LBNL | LB1015080424 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | Mid FY progress report on Evaluation of EBS
M4508042402 Requested, but no response. | M4 | 1.5.08.04 | LBNL | LB1015080424 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | FY10 Report on EBS Evaluations
M4508042504 Requested, but no response. | M4 | 1.5.08.04 | LLNL | LL1015080425 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | FY10 Report on EBS evaluations
M4508042601 Requested, but no response. | M4 | 1.5.08.04 | SNL | SN1015080426 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | Mid FY10 Progress report
M4FT-12AN0808015 Per Matt Brainard: Nothing uploaded in PICS:NE. Deliverable form submitted and approved blank. No notes. DMS No. FCRD-USED-2012-000404 only. | M4 | 1.02.08.08.01 | ANL | FT-12AN080801 | Generic Disposal System Level Modeling - ANL | Nutt, Mark | McMahon, Kevin | Safety Case for the Generic Disposal of Nuclear Waste - ANL | Safety Case for the Generic Disposal of Nuclear Waste - ANL Input | This activity will develop and layout a case for the safety of a generic repository a holistic and comprehensive fashion, including transportation, interim storage, and post-closure. Some discussion of preclosure safety and operations including any interim storage will be provided as well. This will provide for the larger context of safety beyond what is achieved solely by performance assessment, which is one component of safety. ANL input to SNL Level-2 milestone M2FT-12SN0808041 A Safety Case for the Generic Disposal of Nuclear Waste | 2012-04-30 03:00 |  | 2012-04-30 01:00 |  | 2012 | Complete |  |  |  | None |  | FCRD-USED-2012-000404
M4FT-12IN0809012 Per Matt Brainard: Nothing uploaded in PICS:NE. Deliverable form submitted and approved blank. No notes. DMS No. FCRD-UFD-2012-000529 only. | M4 | 1.02.08.09.01 | INL | FT-12IN080901 | DR Inventory - INL | Birk, Sandy | McMahon, Kevin | M4 Contribution to Revision 5 of Inventory Estimate Report | M4 Inventory Update | Contribute to inventory Update | 2012-06-29 04:00 | 2012-09-28 04:00 | 2012-07-29 02:00 |  | 2012 | Completed Late |  | Birk, Sandy | Birk, Sandy | None |  | FCRD-UFD-2012-000529
M4FT-12LA0803073 Per Matt Brainard: Document not available in PICS:NE. Main Document title entered as “Unknown”. No files uploaded. | M4 | 1.02.08.03.07 | LANL | FT-12LA080307 | ST R&D Investigations - LANL | Perry, Frank | Sorenson, Ken | Recommendations for acoustic technologies to meet measurement and monitoring needs for long-term storage | Recommendations for acoustic technologies that meet facility requirements | End of year status report recommending acoustic technologies that meet measurement and monitoring needs for long-term storage. | 2012-09-03 06:00 | 2012-09-18 02:00 | 2012-09-18 02:00 | Actual submission date was Sept. 18, 2012 | 2012 | Completed Late | Unknown | Ulrich, Timothy |  | None
M4FT-12LA0807056 input for other reports - copy not available per Painter | M4 | 1.02.08.07.05 | LANL | FT-12LA080705 | Natural Systems Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Integrated tool development for natural system evaluation | Report on integrated tool development for natural system evaluation: LANL input | This activity will develop an integrated tool for natural system performance analysis. This tool will integrate detail process models with probabilistic analysis capability. The tool developed will be used to support prioritization and decision making related to natural system R&D activities. In FY12, we will initiate this activity and preliminarily demonstrate the capability. | 2012-08-01 08:00 |  | 2012-08-01 02:00 |  | 2012 | Complete |  | Painter, Scott | Painter, Scott | None | ITDforNSE_LANLinput.pdf | FCRD-UFD-2012-000570
M4FT-12LA0810022 Per Matt Brainard: Status Report on LANL Early Analysis Activities and Proposed Future Work is missing. The deliverable form was submitted and subsequently approved blank. The only other piece of information in PICS:NE on this milestone is a DMS number of FCRD-USED-2012-000406. Bruce Robinson was the WPM. Ken Sorenson was the CAM. | M4 | 1.02.08.10.02 | LANL | FT-12LA081002 | ST Engineering Analysis - LANL | Robinson, Bruce | Sorenson, Ken | Status Report on LANL Early Analysis Activities and Proposed Future Work | Status Report on LANL Early Analysis Activities and Proposed Future Work | Based on assessment of topics suitable for early analyses, LANL will conduct and document analyses it conducts, integrating with participants at the other Laboratories. | 2012-07-13 02:00 |  | 2012-07-13 02:00 |  | 2012 | Complete |  |  |  | None |  | FCRD-USED-2012-000406
M4FT-12LA0810026 Per Matt Brainard: Nothing was uploaded in PICS:NE on M4FT-12LA0810026, except DMS Number: FCRD-USED-2012-000410. Document is not available. | M4 | 1.02.08.10.02 | LANL | FT-12LA081002 | ST Engineering Analysis - LANL | Brown, Neil | Sorenson, Ken | Postclosure Aspects of Can in Can Concept | Operational Aspects of Can in Can Concept | Provide detailed analysis of operational aspects of the can in can concept to Oak Ridge for input into final report. | 2012-08-31 06:00 |  | 2012-08-30 02:00 |  | 2012 | Complete |  | Brown, Neil | Brown, Neil | None |  | FCRD-USED-2012-000410
M4FT-12LA08180114 superceded by M4FT-13LA0818015 | M4 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Status Report on LANL International Collaboration | Status Report on LANL International Collaboration | Submit a status on LANL international collaboration specific to SDI activities. These activities may include: 1) presentations at Pu-Futures Conference and meetings with the German program on HLW research, and 2) establishing research contribution to the First Nuclides. | 2012-10-31 06:00 |  |  | On schedule. | 2012 | 90 Day |  |  |  | None
M4FT-12LB0807065 superceded by M4FT-13LB0807052 | M4 | 1.02.08.07.06 | LBNL | FT-12LB080706 | Natural Systems Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Fluid flows in low permeability media: Non-Newtonian flow in clays | Report on fluid flows in clay formations | This activity will focus on the better understanding of multiphase fluid flows in both near field and far field environments and the improvement of existing experimental and modeling tools for uncertainty quantification and parameter estimation. LBNL work will include the development of non-Newtonian flow model in clay. FY12 work will include the preliminary model/method formulation, validation and demonstration. | 2012-11-15 09:00 |  |  | on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12LL0806042 Superseded by M4FT-13LL08060325 | M4 | 1.02.08.06.04 | LLNL | FT-12LL080604 | Engineered Barrier Systems (EBS) Evaluations - LLNL | Sutton, Mark | McMahon, Kevin | Thermodynamic Properties Report - Phase 2 | Thermodynamic Database Report | Continue populating the thermodynamic property database for materials found in the EBS of candidate geologic media | 2013-03-31 03:00 |  |  | On schedule | 2012 | On Schedule |  |  |  | None
M4FT-12LL0806044 Code Release Per Matt Brainard: DSEF Version 3.0 originally scheduled for FY13 completion on 3/31/2013. Superseded by M4FT-13LL08060323: DSEF v3.0, completed on 8/15/2013. | M4 | 1.02.08.06.04 | LLNL | FT-12LL080604 | Engineered Barrier Systems (EBS) Evaluations - LLNL | Greenberg, Harris | McMahon, Kevin | DSEF Version 3.0 | DSEF Version 3.0 | Release of DSEF Version 3.0 | 2013-03-31 03:00 |  |  | On schedule | 2012 | On Schedule |  |  |  | None
M4FT-12LL0807075 Per Matt Brainard: This one was mapped to FY13 and has a different milestone/deliverable number: “M4FT-13LL0807071 - International collaboration - Radionuclide interactions and transport in geologic repository environments – Pu interaction with clay”. It was actually completed in FY14, on 11/14/2013. | M4 | 1.02.08.07.07 | LLNL | FT-12LL080707 | Natural Systems Evaluations - LLNL | Kersting, Annie | McMahon, Kevin | Radionuclide Interaction & transport in representative geologic environments - Phase 3 | Interim report on Phase 3 testing of RN transport | Continue experimental investigation reported in Phase 2. Specific tests will be defined based on interim test results midway through Phase 2. | 2013-03-29 12:00 |  |  | 60% COMPLETE | 2012 | On Schedule |  |  |  | None
M4FT-12LL0807076 Per Matt Brainard: M4FT-12LL0807076 - Disposal system material properties - Phase 2 was originally planned for FY13 Completion on 2/28/2013. The only two milestones in the FY13 work package (identified below) do not appear to have anything to do with the FY12 milestone. It appears the FY12 milestone was dropped during the FY13 planning phase. M4FT-13LL0807071-International collaboration - Radionuclide interactions and transport in geologic repository environments – Pu interaction with clay, due 11/6/2013. M3FT-13LL0807072-Radionuclide interactions and transport in geologic repository environments – Intrinsic colloids, due 8/15/2013. There is nothing to provide on this FY12 milestone. | M4 | 1.02.08.07.07 | LLNL | FT-12LL080707 | Natural Systems Evaluations - LLNL | Wolery, Tom | McMahon, Kevin | Disposal system material properties - Phase 2 | Report on thermodynamic data collection & synthesis - Phase 2 | This continuing activity will focus on the development of disposal concepts for natural system components and the collection and management of critical technical data for natural system evaluation. The data collected in UFD and other related projects will be archived in a centralized data repository. In FY12 and FY13, a catalog of representative geologic media and the associated properties (e.g., groundwater chemistry) will be provided, improved, and used as boundary conditions for related UFD activities. LLNL work will focus on thermodynamic data collection and synthesis. | 2013-02-28 15:00 |  |  | 60.00 | 2012 | On Schedule |  |  |  | None
M4FT-12LL0814032 input to ANL L-2 Milestone M2FT-12AN0814012 Per Matt Brainard: M4FT-12LL0814032 - Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - LLNL Input Deliverable form submitted and approved blank. No file uploaded. Jim Blink listed as WPM, Document Author, and Document Owner. Mark Nutt listed as CAM. DMS No. FCRD-UFD-2012-000531 referenced. No other comments or notes. | M4 | 1.02.08.14.03 | LLNL | FT-12LL081403 | CX Perspectives on NW Management - LLNL | Blink, Jim | Nutt, Mark | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - LLNL Input | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - LLNL Input | Provide input to ANL L-2 Milestone M2FT-12AN0814012, Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | 2012-09-28 06:00 |  | 2012-09-28 03:00 | See Accomplishments block and deliverable module | 2012 | Complete |  | Blink, James | Blink, James | None |  | FCRD-UFD-2012-000531
M4FT-12LL0815023 Per Mark Sutton: report is marked OUO and since it was authored several years ago, I will need to have it reviewed as an abundance of caution to make sure it is still releasable as OUO. | M4 | 1.02.08.15.02 | LLNL | FT-12LL081502 | ST Security - LLNL | Blink, Jim | Sorenson, Ken | Support S&T security assessment activities | Progress report on material attractiveness | Extend material attractiveness FOM to transportation scenarios. Participate in Security working group meetings and joint product development. | 2012-07-13 14:00 | 2012-07-17 03:00 | 2012-07-30 03:00 |  | 2012 | Completed Late |  | Blink, Jim | Blink, Jim | OUO | LLNL_OUO_Security-2012July-R8-IM-Cover.pdf
M4FT-12LL0815024 Per Mark Sutton: report is not available to me and I was not able to find it on the server. Have you checked with then Mike Miller at LANL who was the NTD at that time? | M4 | 1.02.08.15.02 | LLNL | FT-12LL081502 | ST Security - LLNL | Blink, Jim | Sorenson, Ken | Continue support of Security evaluations for S&T | Input to multi-lab progress report | Continue Security evaluations for S&T. Assist in production and review of SNL September milestone | 2013-03-30 14:00 |  |  | On schedule | 2012 | On Schedule |  |  |  | None
M4FT-12OR0807031 Per Matt Brainard: M4FT-12OR0807031 - ORNL Year End Status Report in Support of Regional Geology and Tectonic Hazard Nothing uploaded in PICS:NE. Deliverable form submitted and approved blank. No notes. DMS No. FCRD-UFD-2012-000532 referenced. Gary Mays identified as Document author and owner. | M4 | 1.02.08.07.03 | ORNL | FT-12OR080703 | Regional Geology & Tectonic Hazard - ORNL | Howard, Rob | McMahon, Kevin | ORNL Year End Status Report in Support of Regional Geology and Tectonic Hazard | Year End Status Report in Support of Regional and Tectonic Hazards Work Package | Provide status report documenting support to Regional Tectonic Hazard work package. Report should cover tasks described in scope description | 2012-08-31 06:00 | 2012-09-28 | 2012-09-28 | This deliverable was completed on 9/29/12 | 2012 | Completed Late |  | Mays, Gary | Mays, Gary | None |  | FCRD-UFD-2012-000532
M4FT-12OR0822012 Per Matt Brainard: doc was not uploaded to PICS/NE. It was deemed sensitive by John Wagner, and therefore PICS:NE wouldn’t allow the upload. | M4 | 1.02.08.22.01 | ORNL | FT-12OR082201 | Characterization of Existing UNF | Wagner, John | Wagner, John | Revised Results on UNF Categorization | Revised Results for UNF Categorization | Provide revised results on UNF characterization based on input from SMEs, updated inventory data, and isotopic analyses. | 2012-07-31 |  | 2012-08-07 |  | 2012 | Completed Late |  | Wagner, John | Wagner, John |  |  | FCRD-UFD-2012-000533
M4FT-12OR08220215 Superseded by M4FT-13OR0914065: Beta version of UNF database, completed on 12/21/12. | M4 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | Wagner, John | Beta version of UNF database | Beta version of UNF database | This will be the second internal version of the database and will included additional data, as compared to the Sept version, and corrections, as needed. | 2012-11-30 |  |  | on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12OR08220226 Per Matt Brainard: Report documenting UNF assembly models – Originally due in FY13 on 11/30/2012. Milestone superseded by M4FT-13OR09140611: Report documenting UNF assembly models, attached. “This report documents prototype development of the automated fuel assembly modeling methodology component of the database system that will subsequently be refined and expanded upon as well as the development of preliminary ORIGEN/ARP BWR libraries to be used by the M&S Toolset.” | M4 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting UNF assembly models | Report documenting UNF assembly models | Report documenting UNF assembly models developed. | 2012-11-30 |  |  | Product is progressing and is still on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12OR08220227 Per Matt Brainard: Report documenting models for criticality safety analyses - Originally due in FY13 on 11/30/2012. Milestone superseded by M4FT-13OR09140612: Report documenting models for criticality safety analyses. This report was not uploaded into PICS:NE. Note: “This report presents a description of the methodology for automatic criticality model building and a description of specific dry storage canisters that have been developed as part of UNF-IDEAS. This report is considered a draft document that will be updated as new cask models and templates are developed and made available within the automation sequence. This document will be kept in-house and used to feed the M2-deliverable due in March.” - ORNL in-house, contact J. Scaglione | M4 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting models for criticality safety analyses | Report documenting models for criticality safety analyses | Report documenting models for criticality safety analyses | 2012-11-30 |  |  | Product is progressing and inital set of models is on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12OR08220228 Per Matt Brainard: Report documenting models for thermal analyses – Originally due in FY13 on 11/30/2012. Milestone superseded by M4FT-13OR09140613: Report documenting models for thermal analyses. This report was not uploaded into PICS:NE. Note: “This report represents an initial discussion of the thermal analysis models that are being developed for UNF-IDEAS. The development of UNF-IDEAS is a multi-laboratory effort. The thermal analysis models and associated documentation contained in this report was developed by Pacific Northwest National Laboratory (PNNL). This report will be updated as new cask model templates and site-specific characteristics (e.g., cask loading maps) are incorporated, hence it is considered a living document and will be maintained in-house. The intended use of this report is to document the cask model development for UNF-IDEAS and ultimately be incorporated into M2FT-13OR0914061, Complete Initial Commercial UNF Database and Documentation.” - ORNL in-house, contact J. Scaglione | M4 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting models for thermal analyses | Report documenting models for thermal analyses | Report documenting models for thermal analyses | 2012-11-30 |  |  | Product is progressing but is slightly behind schedule due to staff availability. Resources have been freed up to get back on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12OR08220234 Per Matt Brainard: Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities - Originally due in FY13 on 2/22/2013. Milestone superseded by M4FT-13OR09140619: Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities, attached. “This report documents a preliminary assessment of the realistic safety margin available in as-loaded casks at the decommissioned Maine Yankee Nuclear Power Plant. The analysis presented in this report considers three thermal performance criteria, total decay heat, maximum cladding temperature, and maximum cask surface temperature, as well as one criticality safety criterion, neutron multiplication factor (keff), to assess the available margin for the casks. More importantly, the analysis presented here demonstrates the feasibility of using tools currently under development for the integrated analysis of as-loaded casks stored at plants around the country.” | M4 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | Wagner, John | Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities | preliminary assessment of realistic safety margins | Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities | 2013-02-22 |  |  |  | 2012 | On Schedule |  |  |  | None
M4FT-12OR08220316 Per Matt Brainard: Summary report of data inputs to be used for multi-physics model - Originally due in FY13 on 11/30/2012. Exact milestone missing in FY13 follow on work package. No clear cross walk between titles or dates. Best guess from the list below is that the FY12 milestone was superseded by FY13 Milestone M4FT-13OR08220111 - Documentation of data, material properties, modeling inputs and proposed analytical approaches, which is attached – but this is only a guess. It might be worth checking with Rob Howard or considering this milestone missing in the database. Narrative provided in PICS:NE: “This document contains a compilation of structural material properties for each of the materials necessary to support modeling and simulation initiatives identified in Used Nuclear Fuel Loading and Structural Performance Under Normal Conditions of Transport - Draft Modeling, Simulation and Experimental Integration RD&D Plan” | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Summary report of data inputs to be used for multi-physics model | Summary report of data inputs to be used for multi-physics model | Summary report of data inputs to be used for multi-physics model | 2012-11-30 |  |  | on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12OR08220317 Superseded by M4FT-13OR08220110. | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Report documenting M&S, including UQ, development activities | Report documenting M&S development activities | Report documenting the M&S capabilities, including UQ, developed, V&V, limitations, and recommended future work. | 2013-02-28 |  |  |  | 2012 | On Schedule |  |  |  | None
M4FT-12OR08220318 Per Matt Brainard: Report documenting the experimental activities, originally planned for completion in FY13 on 2/28/2013. Milestone was superseded by M4FT-13OR08220112: Report documenting experimental activities, attached. Narrative provided in PICS:NE: “The purpose of this report is to document the results of a literature review conducted of studies related to the vibration and shock associated with the normal conditions of transport for rail shipments of used nuclear fuel from commercial light-water reactors. As discussed in Adkins (2013), the objective of this report is to determine if adequate data exist to realistically evaluate the impacts of the shock and vibration associated with the normal conditions of transport on commercial light-water reactor used nuclear fuel shipped in current-generation high-capacity rail transportation casks.” | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Report documenting the experimental activities | Report documenting the experimental activities | Report documenting the experimental data measurements, limitations, and recommended future work. | 2013-02-28 |  |  |  | 2012 | On Schedule |  |  |  | None
M4FT-12OR0822037 Per Matt Brainard: Conduct Core Team Meeting – delayed into FY13 for completion on 12/14/2012. However the milestone appears to have been dropped in between FY12 Year End and FY13 Work Package planning. There is no milestone with the same title in FY13. Deliverable is missing. | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Conduct Core Team Meeting | Conduct Core Team Meeting | Conduct Core Team Meeting. Prepare meeting summary report | 2012-08-10 | 2012-12-14 |  | on schedule for revised finish date | 2012 | Late |  |  |  | None
M4FT-12OR0822038 Per Matt Brainard: Conduct workshop on plan – delayed into FY13 for completion on 1/31/2013. However the milestone appears to have been dropped in between FY12 Year End and FY13 Work Package planning. There is no milestone with the same title in FY13. Deliverable is missing. | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Conduct workshop on plan | Conduct workshop on plan | Conduct workshop on plan. Prepare summary report on workshop. | 2012-09-21 | 2013-01-31 |  | on schedule for revised finish date | 2012 | Expected Late |  |  |  | None
M4FT-12OR0822039 Superseded by M3FT-13OR0822013. | M4 | 1.02.08.22.03 | ORNL | FT-12OR082203 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Finalize Draft RD&D Plan | Finalize Draft RD&D Plan | Finalize Draft RD&D Plan for Review | 2012-08-24 | 2012-12-21 |  | on schedule for revised finish date | 2012 | Late |  |  |  | None
M4FT-12SN0807085 Per Matt Brainard: Modeling hydrologic flows in representative geologic media: Parameter estimation and uncertainty analysis was originally planned for FY13 Completion on 11/15/2012. During the FY13 planning phase, the above milestone was superseded by M4FT-13SN0807089-Report on hydrologic flow modeling and characterization for FY14 completion on 11/4/2013. During the FY14 planning phase, the work package titled “Natural Systems Evaluations” that the milestone was associated with was dropped, therefore there is no report to provide as evidence for the FY12 milestone completion. | M4 | 1.02.08.07.08 | SNL | FT-12SN080708 | Natural Systems Evaluations - SNL | Arnold, Bill | McMahon, Kevin | Modeling hydrologic flows in representative geologic media: Parameter estimation and uncertainty analysis | Report on parameter estimation and uncertainty quantification of field testing data | This activity will focus on the better understanding of multiphase fluid flows in both near field and far field environments and the improvement of existing experimental and modeling tools for uncertainty quantification and parameter estimation. SNL will provide inputs on uncertainty quantification of field testing data. | 2012-11-15 02:00 |  |  | On schedule | 2012 | 90 Day |  |  |  | None
M4FT-12SN0808044 draft basis for M2FT-12SN0808042 Per Matt Brainard: M4FT-12SN0808044 - 1) Generic Performance Assessment Model: Architecture, Implementation, and Demonstration Nothing uploaded into PICS:NE. Deliverable form submitted and approved with the following note: “Report has not yet cleared SNL R&A. Will be uploaded once approval for unlimited release has been obtained.” The report was never uploaded into PICS:NE. Geoff Freeze is listed as the Document Author and Owner. DMS Tracking No. FCRD-UFD-2012-000255 referenced. The Deliverable Description is shows as “E-mail notification”. | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 1) Generic Performance Assessment Model: Architecture, Implementation, and Demonstration | 1) Generic Performance Assessment Model: Architecture, Implementation, and Demonstration | Draft report describing the improvements made to the GPAM and its use in evaluating the performance of generic repositories for waste form disposal alternatives. This report will serve as a basis for a chapter in the November Level 2 milestone report. | 2012-06-29 08:00 | 2012-08-31 22:00 | 2012-08-31 02:00 |  | 2012 | Completed Late |  | Freeze, Geoff | Freeze, Geoff | None |  | FCRD-UFD-2012-000255
M4FT-12SN0808047 Per Matt Brainard: 4) GDSM Database and Computation Environment Description and Implementation Deliverable form submitted and approved blank. No file uploaded. Palmer Vaughn listed as WPM with Geoff Freeze as his backup. Kevin McMahon listed as CAM. Document Author is Ralph Rogers. Document Owner is Jeralyn Prouty. DMS No. FCRD-UFD-2012-000239 referenced. Deliverable Description is “E-mail Notification”. No other comments or notes. | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 4) GDSM Database and Computation Environment Description and Implementation | 4) GDSM Database and Computation Environment Description and Implementation | Draft report describing the control computational database including a discussion of its use, description of features, interface to the GPAM and the identification of current baseline values and pedigree of information contained. Additionally, the approach and implementation of a configuration management system will be described. This report will serve as a basis for a chapter in the November Level 2 milestone report. | 2012-08-31 06:00 |  | 41152.0833 |  | 2012 | Complete |  | Rogers, Ralph | Prouty, Jeralyn | None |  | FCRD-UFD-2012-000239 | parameter database
M4FT-12SN08180221 Contained within M2FT-12SN08180223 | M4 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Bibliography of Delaware Basin Data for Bedded Salt | Bibliography of Data for Delaware Basin Bedded Salt | Summary of Existing Data from WIPP and the Delaware Basin and How it Supports the Safety Framework for Disposal of Heat-generating Waste in Salt. | 2012-09-28 12:00 |  | 41152.0833 |  | 2012 | Complete |  | Kuhlman, Kris | Kuhlman, Kris | None | SITED-bibliography-milestone.docx | FCRD-UFD-2012-000607
M4FT-12SN08180221 Contained within M2FT-12SN08180223 | M4 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | Mackinnon, Robert | Bibliography of Delaware Basin Data for Bedded Salt | Bibliography of Data for Delaware Basin Bedded Salt | Summary of Existing Data from WIPP and the Delaware Basin and How it Supports the Safety Framework for Disposal of Heat-generating Waste in Salt. | 2012-09-28 12:00 |  | 2012-08-31 02:00 |  | 2012 | Complete |  | Kris Kuhlman | Kris Kuhlman | None | SITED-bibliography-milestone.docx | FCRD-UFD-2012-000607
M4FT-12SN08180247 superceded by M3FT-13SN080180335 | M4 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | MacKinnon, Robert | MacKinnon, Robert | Evaluation of EBS THM Coupled Process in Salt | EBS THM Coupled Processes in Salt | This technical memo must summarize work on the associated activity and make recommendations for process models for TSPA | 2012-11-15 06:00 |  |  | The deliverable is on schedule | 2012 | 90 Day |  |  |  | None
M4FT-12SR0804044 this document is not included because it is still in “Pre-Decisional Draft Do Not Release or Distribute” FCRD-UFD-2012-000113, Rev. 1 “Costing Study for a Generic Salt Repository: Systems Engineering and Analysis in Support of a Policy Review of Comingling Decision and Related System Design Considerations” | M4 | 1.02.08.04.04 | SRNL | FT-12SR080404 | DR Thermal Load Management & Design Concepts - SRNL | Smith, Pat | McMahon, Kevin | Prepare Cost Estimate Report | Prepare Cost Estimate Report | Prepare Cost estimate report. | 2012-07-31 |  | 2012-07-31 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | Costing Study for a Generic Salt Repository Rev 1 7-31-12.pdf | FCRD-UFD-2012-000113 | Costing Study
M4FT-13AN0806011 supersedes by M4FT-14AN0807011 | M4 | 1.02.08.06.01 | ANL | FT-13AN080601 | DR Generic Engineered Barrier System Evaluations - ANL | Ebert, William | McMahon, Kevin | FY13 ANL Test Plan | ANL Test Plan for FY2013 | Test plan for experimental and model development activities to be conducted in FY13. Will summarize rationale and planned approach for modeling and experimental work, including support of collaboration with PNNL and SNL. | 2012-11-20 04:00 |  | 2012-11-19 01:00 |  | 2013 | Complete |  | Jerden, James | Ebert, William | None | ANL UO2 Test Plan.pdf | FCRD-UFD-2013-000034
M4FT-13AN09020123 Per Matt Brainard: Status Report: Assessment of Advanced Re-Packaging Techniques and R&D Gaps (Dry, Automated, Remote) – Deliverable missing in PICS:NE. Other Deliverable Form information: Narrative: “Electronic submission of draft report via e-mail to M. Nutt for inclusion in milestone M3FT-13AN09020127”. Document Author/Creator: “Young Soo Park”. Document Owner: “W.M. Nutt”. Deliverable Description: “Input section for M3FT13AN09020127. UNF repackaging technology assessment and gap analysis, survey and evaluation of the current UNF repackaging system technology options to identify the technology gaps, recent advances in enabling technologies, and R&D needs.” Other Tracking Info: “Subsumed into M3FT13AN09020127” | M4 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL | Nutt, Mark | Nutt, Mark | Status Report: Assessment of Advanced Re-Packaging Techniques and R&D Gaps (Dry, Automated, Remote) | Status Report: Assessment of Advanced Re-Packaging Techniques and R&D Gaps (Dry, Automated, Remote) | Status report on the assessment of advanced re-packaging techniques. | 2013-08-30 06:00 | 2013-09-30 02:00 | 2013-09-19 01:00 | Electronic submission of draft report via e-mail to M. Nutt for inclusion in milestone M3FT-13AN09020127 | 2013 | Completed Late |  | Park, Young | Nutt, Mark | None
M4FT-13LA08070411 Per Scott Painter: This was feed into another report, so there is no doc available. | M4 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Colloid Facilitated Transport. | Report on Colloid Facilitated Migration. | Input to SNL's Level 2 MS on radionuclide transport. | 2013-09-15 12:00 |  | 2013-09-29 08:00 | The report on colloid facilitated migration, a feed to another report, was sent to the relevant work package manager on 9/29/13. | 2013 | Completed Late |  | Reimus, Paul | Reimus, Paul | None |  |  | Radionuclide transport, colloid facilitated transport, uranium,
M4FT-13LA08070412 Per Matt Brainard: Summary of international collaborations on CFM. originally planned for FY14 completion on 12/7/2013. During the FY14 planning phase, the work package titled “Generic Natural Systems Evaluations - LANL” that the milestone was associated with was dropped, therefore there is no report to provide as evidence for the above FY13 milestone completion. | M4 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL |  | McMahon, Kevin | Summary of international collaborations on CFM. | Summary of International Collaborations on CFM. | Extended summary input for SNL's Level 2 milestone on international collaborations. | 2013-12-07 10:00 |  |  | work is no schedule | 2013 | 90 Day |  |  |  | None
M4FT-13LA08070414 Per Matt Brainard: Summary of international collaborations on modeling BRIE experiment. originally planned for FY14 completion on 12/7/2013. During the FY14 planning phase, the work package titled “Generic Natural Systems Evaluations - LANL” that the milestone was associated with was dropped, however the above milestone was mapped to the FY14 work package titled FT-14LA080706 - Crystalline Disposal R&D International – LANL and was superseded by: M4FT-14LA0807064-Summary of international collaborations on modeling BRIE experiment | M4 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL |  | McMahon, Kevin | Summary of international collaborations on modeling BRIE experiment | Report on international collaborations on modeling BRIE experiment | A summary will go into SNL's Level 2 milestone on international collaboration. The work will also be described in LANL's Level 2 milestone on 12/15/13. | 2013-12-07 06:00 |  |  | Work is on schedule | 2013 | 90 Day |  |  |  | None
M4FT-13LA0807047 Per Matt Brainard: PICS/NE entry shows that 1. Deliverable titled "An Experimental Methodology for Improving Radionuclide Transport Process Models using Uranium and Grimsel Granodiorite as a Case Study" was submitted. 2. Input to another report | M4 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on radionuclide transport in granite media | Report on radionuclide transport in granite media | Report on radionuclide transport in granite media and neutron scattering techniques | 2013-08-15 12:00 |  | 2013-08-28 04:00 |  | 2013 | Completed Late |  | Reimus, Paul | Reimus, Paul | None |  |  | Radionuclide transport, granite
M4FT-13LA0807049. Document not uploaded to PICS-NE and not available. A narrative was entered as: “Report on neutron scattering technique was submitted to work package manager on Sept 3.” | M4 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Neutron Scattering Techniques | Report on neutron scattering techniques | Input to Sandia National Laboratory's Level 2 milestone on radionuclide transport | 2013-08-15 12:00 | 2013-09-03 02:00 | 2013-09-03 02:00 | Report on neutron scattering technique was submitted to work package manager on Sept 3. | 2013 | Completed Late |  | Ding, Mei | Ding, Mei | None
M4FT-13LA0808052 input for other reports - copy not available per Painter | M4 | 1.02.08.08.05 | LANL | FT-13LA080805 | Advanced System Level Modeling - LANL | Painter, Scott | McMahon, Kevin | Document tests of Akuna/Amanzi | Report on tests of Akuna/Amanzi | Report describing tests of the Akuna/Amanzi framework will be provided as input to SNL's Level 3 milestone. | 2013-07-31 08:00 |  | 2013-07-31 04:00 |  | 2013 | Complete |  | Painter, Scott | Painter, Scott | None
M4FT-13LA0823031 Per Matt Brainard: Input to the UNF and HLW Disposal Option Evaluation Milestone shows 100% complete under performance, however the Deliverable Form was never submitted. No file uploaded. Mike Miller listed as WPM. Peter Swift as CAM and NTD. No other comments or notes. | M4 | 1.02.08.23.03 | LANL | FT-13LA082303 | UNF and HLW Disposal Option Evaluation - LANL |  | Swift, Peter | Input to the UNF and HLW Disposal Option Evaluation | UNF and HLW Disposal Option Evaluation Final Report | Used nuclear fuel and high level radioactive waste disposal option evaluation. | 2013-09-30 08:00 |  |  | complete | 2013 | 90 Day |  |  |  | None
M4FT-13LB0807054 Per Matt Brainard: Report on hydrologic flows in low permeability media. originally planned for FY14 completion on 11/13/2013. During the FY14 planning phase, the work package titled “Generic Natural Systems Evaluations - LBNL” that the milestone was associated with was dropped, however the above milestone was mapped to the FY14 work package titled FT-14LB080604 - Argillite Disposal R&D - LBNL and was superseded by: M4FT-14LB0806045-Report on hydrologic flows in low permeability media | M4 | 1.02.08.07.05 | LBNL | FT-13LB080705 | Generic Natural System Evaluations - LBNL |  | McMahon, Kevin | Report on hydrologic flows in low permeability media | Report on hydrologic flows in low permeability media | Study non-Darcy flow and its impact in clay reporsitory | 2013-11-13 05:00 |  |  | on schedule | 2013 | 90 Day |  |  |  | None
M4FT-13LB0807055 Per Matt Brainard: Report on international collaborations on FE heater and HG-A tests. originally planned for FY14 completion on 11/6/2013. During the FY14 planning phase, the work package titled “Generic Natural Systems Evaluations - LBNL” that the milestone was associated with was dropped, however the above milestone was mapped to the FY14 work package titled FT-14LB080606 - Argillite Disposal R&D International – LBNL and was superseded by: M4FT-14LB0806066-Report on international collaborations on FE heater and HG-A tests | M4 | 1.02.08.07.05 | LBNL | FT-13LB080705 | Generic Natural System Evaluations - LBNL |  | McMahon, Kevin | Report on international collaborations on FE heater and HG-A tests | Report on international collaborations on FE heater and HG-A tests | Document modeling activities for FE heater and HG-A tests | 2013-11-06 05:00 |  |  | on schedule | 2013 | 90 Day |  |  |  | None
M4FT-13OR0822017 Per Matt Brainard: Report documenting final data, material property, and M&S input information, milestone marked complete but deliverable form was submitted and subsequently approved blank. No deliverable was uploaded into PICS:NE. Deliverable is missing. No other identifying information provided in PICS:NE. | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Report documenting final data, material property, and M&S input information | Transportation & Storage M&S Supporting Material Property and Input Information | Develop report documenting final data, material property, and M&S input information intended to be implemented for demonstration of approach. This will represent the finalization of information feeding in to the deterministic evaluations that must be performed. | 2013-08-16 09:00 |  | 2013-08-16 02:00 |  | 2013 | Complete |  |  |  | None
M4FT-13OR0822018 Per Matt Brainard: Report documenting final M&S methodology, basis, approach, and results, milestone marked complete but deliverable form was submitted and subsequently approved blank. No deliverable was uploaded into PICS:NE. Deliverable is missing. No other identifying information provided in PICS:NE. | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Report documenting final M&S methodology, basis, approach, and results | Used Fuel Ttansportation & Storage M&S methodology, basis, and results | Report of data inputs to be used for multi-physics model and results stemming from scoping evaluations. | 2013-08-16 23:00 |  | 2013-08-16 02:00 |  | 2013 | Complete |  |  |  | None
M4FT-13OR0902024 Per Rob Howard: I could not fine M4FT-13OR0902024; however, “M4FT-14OR0902069_Worker_Exposure_Methodology_and_Parameters_30May2014.docx” is an updated version of that milestone. | M4 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | Complete Worker Exposure Methodology for Incorporation in System Architecture Studies | Worker Exposure Methodology for Incorporation in System Architecture Studies | This activity will develop a methodology for evaluating worker exposures incident to the various activities that may be conducted during the movement and handling of spent fuel in the course of operationg an integrated waste management system | 2013-04-30 02:00 |  | 2013-04-30 |  | 2013 | Complete |  | Robert Howard | ORNL | None |  |  | Worker Dose
M4FT-13OR09030111 Per Josh Jarrell: No report available | M4 | 1.02.09.03.01 | ORNL | FT-13OR090301 | Collaborative Document and Data Management System - ORNL | Jarrell, Josh | Nutt, Mark | Initial Document Database | Initial Document Database | Accumulate 100 searchable, accessible UNF documents. | 2013-04-26 02:00 |  | 2013-04-23 |  | 2013 | Complete |  | Josh Jarrell | Josh Jarrell | None
M4FT-13OR09140612 Per Matt Brainard: M4FT-12OR08220227: Report documenting models for criticality safety analyses - Originally due in FY13 on 11/30/2012. Milestone superseded by M4FT-13OR09140612: Report documenting models for criticality safety analyses. This report was not uploaded into PICS:NE. Note: “This report presents a description of the methodology for automatic criticality model building and a description of specific dry storage canisters that have been developed as part of UNF-IDEAS. This report is considered a draft document that will be updated as new cask models and templates are developed and made available within the automation sequence. This document will be kept in-house and used to feed the M2-deliverable due in March.” - ORNL in-house, contact J. Scaglione | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting models for criticality safety analyses | Report documenting models for criticality safety analyses | Report documenting models for criticality safety analyses | 2012-11-30 04:00 |  | 2012-11-30 |  | 2013 | Complete |  | Ilas, Dan | Scaglione, John | None
M4FT-13OR09140613 Per Matt Brainard: M4FT-12OR08220228: Report documenting models for thermal analyses – Originally due in FY13 on 11/30/2012. Milestone superseded by M4FT-13OR09140613: Report documenting models for thermal analyses. This report was not uploaded into PICS:NE. Note: “This report represents an initial discussion of the thermal analysis models that are being developed for UNF-IDEAS. The development of UNF-IDEAS is a multi-laboratory effort. The thermal analysis models and associated documentation contained in this report was developed by Pacific Northwest National Laboratory (PNNL). This report will be updated as new cask model templates and site-specific characteristics (e.g., cask loading maps) are incorporated, hence it is considered a living document and will be maintained in-house. The intended use of this report is to document the cask model development for UNF-IDEAS and ultimately be incorporated into M2FT-13OR0914061, Complete Initial Commercial UNF Database and Documentation.” - ORNL in-house, contact J. Scaglione | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting models for thermal analyses | Report documenting models for thermal analyses | Report documenting models for thermal analyses | 2012-11-30 04:00 |  | 2012-11-30 |  | 2013 | Complete |  | Cuta, | Scaglione, John | None
M4FT-13SN08070811 This milestone is carried over from FY12. The work was completed and already incorporated into M2FT-12LL0807071 | M4 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Modeling hydrologic flows in representative geologic media: Parameter estimation and uncertainty analysis | Report on parameter estimation and uncertainty quantification of field testing data | This milestone is carried over from FY12. The work was completed and already incorporated into M2FT-12LL0807071 milestone report. No carryover funding is needed. | 2012-11-15 10:00 |  | 2012-11-15 04:00 |  | 2013 | Complete |  | Arnold, Bill | Wang, Yifeng | None | Arnold_et_al_FCRD-UFD-2013-000029_with_cover.pdf | FCRD-UFD-2013-000029
M4FT-13SN08070811 work was completed and already incorporated into M2FT-12LL0807071 | M4 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Modeling hydrologic flows in representative geologic media: Parameter estimation and uncertainty analysis | Report on parameter estimation and uncertainty quantification of field testing data | This milestone is carried over from FY12. The work was completed and already incorporated into M2FT-12LL0807071 milestone report. No carryover funding is needed. | 2012-11-15 10:00 |  | 2012-11-15 04:00 |  | 2013 | Complete |  | Bill Arnold | Yifeng Wang | None | Arnold_et_al_FCRD-UFD-2013-000029_with_cover.pdf | FCRD-UFD-2013-000029
M4FT-13SN0807089 Per Matt Brainard: M4FT-12SN0807085: Modeling hydrologic flows in representative geologic media: Parameter estimation and uncertainty analysis was originally planned for FY13 Completion on 11/15/2012. During the FY13 planning phase, the above milestone was superseded by M4FT-13SN0807089-Report on hydrologic flow modeling and characterization for FY14 completion on 11/4/2013. During the FY14 planning phase, the work package titled “Natural Systems Evaluations” that the milestone was associated with was dropped, therefore there is no report to provide as evidence for the FY12 milestone completion. | M4 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL |  | McMahon, Kevin | Report on hydrologic flow modeling and characterization | Report on hydrologic flow modeling and characterization | This is a SNL's input to a LANL's level 3 milestone. This report will include (1) the continued development of an advanced method for parameter estimation and uncertainty quantification and (2) ROK KURT site fracture distribution data and site testing data. | 2013-11-04 08:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None
M4FT-13SN08180340 Delivery of core to Germans - no document. | M4 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Delivery of Core for Testing by the Germans | Delivery of Core to Germans | Delivery of Core for Testing by the Germans | 2013-02-15 06:00 |  | 2013-02-01 02:00 |  | 2013 | Complete |  | Schuhen, Michael | Schuhen, Michael | None |  |  | WIPP Core
M4FT-13SN08180340 Delivery of core to Germans - no document. | M4 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Delivery of Core for Testing by the Germans | Delivery of Core to Germans | Delivery of Core for Testing by the Germans | 2013-02-15 |  | 2013-02-01 |  | 2013 | Complete |  | Schuhen, Michael | Schuhen, Michael | None |  |  | WIPP Core
M4FT-13SR0823051 contribution to study draft. File was loaded in PICS/NE, but we're unable to retrieve. No copies are available. | M4 | 1.02.08.23.05 | SRNL | FT-13SR082305 | UNF and HLW Disposal Option Evaluation - SRNL | Smith, Pat | Swift, Peter | SRNL contribution to study draft | SRNL contribution to study draft | Examine the relationship bewtween various categories of existing used nuclear fuel (UNF) and high level radioactive waste (HLW) in the United States and future options for permanent geologic disposal. | 2013-08-30 |  | 41516 |  | 2013 | Complete |  | Marra, James | Marra, James | None | SRNL - Draft Study.pdf |  | Study Draft
M4FT-14AN0902111 Per Matt Brainard: Not available in PICS:NE. DMS Number FCRD-NFST-2014-000535 assigned. | M4 | 1.02.09.02.11 | ANL | FT-14AN090211 | Execution Strategy Analysis - ANL | Nutt, Mark | Nutt, Mark | Success Precedence Diagram | Success Precedence Diagram and Description | Completed Success Precedence Diagram and Description | 2013-10-31 07:00 |  | 2013-10-25 02:00 |  | 2014 | Complete | ?Success Precedence Diagram | William Nutt | William Nutt | None |  | FCRD-NFST-2014-000535
M4FT-14LA0807023 Per Matt Brainard: Note: Will form chapter in larger report. Submitted to main author. DMS No. FCRD-UFD-2014-000495 referenced. Report on Crystalline and Crystalline International Disposal Activities was submitted to work package manager on 8/26/2014. It was not uploaded into PICS:NE. | M4 | 1.02.08.07.02 | LANL | FT-14LA080702 | Crystalline Disposal R&D - LANL | Painter, Scott | McMahon, Kevin | Report on Crystalline and Crystalline International Disposal Activities | Summary of FY2014 Crystalline Disposal Activities | Report will summarize LANL activities in Crystalline and Crystalline-International Disposal activities. | 2014-08-15 10:00 |  | 2014-08-26 02:00 |  | 2014 | Completed Late | Crystalline and Crystalline International Disposal Activities |  |  | None |  | FCRD-UFD-2014-000495
M4FT-14OR0810011 Per Matt Brainard: Provide detailed thermal source terms for Hope Creek fuel assemblies to PNNL, milestone marked complete but deliverable form was submitted and subsequently approved without document upload. Deliverable is missing. Narrative provided: “Decay heat source term information was transmitted to PNNL via email for Hope Creek casks MPC144 and MPC145 as of August 1, 2013 on 4/25/2014.” DMS No. FCRD-UFD-2014-000501. Other Info: ORNL and PNNL, contact J. Scaglione or H. Adkins | M4 | 1.02.08.10.01 | ORNL | FT-14OR081001 | Analysis - ORNL | Scaglione, John | Sorenson, Ken | Provide detailed thermal source terms for Hope Creek fuel assemblies to PNNL | Thermal source terms for Hope Creek inspection comparison | Thermal source terms and distributions will be provided to PNNL for use in thermal models in support of PNNL deliverable regarding Hope Creek industry inspection. | 2014-06-06 |  | 2014-05-13 |  | 2014 | Complete | Hope Creek Decay Heat Data | Mueller, Don | Scaglione, John | None |  | FCRD-UFD-2014-000501
M4FT-14OR09030113 Per Josh Jarrell: Do NOT include in SP site. Not available through PICS/NE, but Josh can get through CURIE if needed. | M4 | 1.02.09.03.01 | ORNL | FT-14OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Nutt, Mark | Preliminary CURIE User Manual | Preliminary CURIE User Manual | Preliminary User Manual to familiarize the users with the website and its functionality. | 2014-04-25 04:00 |  | 2014-04-25 |  | 2014 | Complete | Preliminary CURIE User Manual | Josh Jarrell | Josh jarrell | None |  | FCRD-NFST-2014-000538
M4FT-14OR09040220 Per Josh Jarrell: No report available | M4 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Develop Performance Requirements for Canisters | Canister Performance Requirements Report | Develop performance requirements for the standardization scenarios recommended by the roadmap. For example, the canister performance operational requirements (those at the reactors) as well as the canister performance disposal requirements (those at a repository) should be clearly defined. | 2014-05-23 02:00 |  | 2014-05-23 |  | 2014 | Complete | Develop Performance Requirements for Canisters | Josh Jarrell | Josh Jarrell | None |  | FCRD-NFST-2014-000539
M4FT-15AN0902046 Merged into M2SF-17AN020403081 | M4 | 1.02.09.02.04 | ANL | FT-15AN090204 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM Phase 2 Prototype 1 Users Manual | NGSAM Phase 2 Prototype 1 Users Manual | NGSAM Phase 2 Prototype 1 Users Manual | 2015-02-20 05:00 |  | 2015-02-18 02:00 |  | 2015 | Complete | NGSAM User’s Manual (Release 0) |  |  | None |  | FCRD-NFST-2015-000559
M4FT-15AN0904012 Per Matt Brainard: Deliverable not uploaded to PICS:NE. Note: “No document attached because this submission will be included as part of M3 and later M2 by ORNL lead.” Deliverable Description: “Contributions to Draft of Intermediate Standardized Canister System Evaluation (FCRD-NFST-2015-000105 Rev. 0), including updated scenario descriptions and analysis of ISF and repackaging data.” DMS No. FCRD-NFST-2015-000561 | M4 | 1.02.09.04.01 | ANL | FT-15AN090401 | CX: Standardization and Integration - ANL | Fortner, Jeffrey | Jarrell, Josh | FY15 Standardization System Analysis | FY15 Standardization System Analysis | Conduct FY15 standardization system analyses for the identified scenarios. Describe the evaluation and results in a draft a section that will be included in M3FT-15OR0904025, Draft of FY15 Standardization Assessment Update. | 2015-07-31 07:00 |  | 2015-07-31 01:00 |  | 2015 | Complete | N/A | Jeffrey Fortner | Jeffrey Fortner | None |  | FCRD-NFST-2015-000561 | standardization STAD ISF
M4FT-15IN0805022 Per Matt Brainard: SCC Detection on Canisters – Milestone never completed and Deliverable is missing. September 2015 Monthly update on this milestone indicates: “This report will not be completed due to the terminal illness of the staff member who was to perform the work. INL has not found a replacement for this staff member.” | M4 | 1.02.08.05.02 | INL | FT-15IN080502 | ST Experiments - INL | Marschman, Steve | Sorenson, Ken | SCC Detection on Canisters | Stress Corrosion Cracking Detection on Canisters | INL's inspection processes developed to support Yucca Mountain canister weld inspections will be investigated for application to stainless steel canister inspections. To be investigated are the potential for detection of actual cracks and their precursors. | 2015-07-31 07:00 | 2015-09-30 04:00 |  | This report will not be completed due to the terminal illness of the staff member who was to perform the work. INL has not found a replacement for this staff member. | 2015 | Late |  |  |  | None |  | FCRD-UFD-2015-000591
M4FT-15OR0816011 Per Matt Brainard: Direct Disposal of DPC Reactivity and Criticality Evaluations Deliverable Title: Direct Disposal of DPC Reactivity and Criticality Status Report File marked OUO and not uploaded into PICS:NE. Document Author: Banerjee Document Owner: Scaglione Deliverable Description: Update to FY2014 report FCRD-UFD-2014-000520. New information was added: Appendix A is added. Appendix A contains (1) post-closure criticality results with principal set of 29 isotopes (recommended for post-closure criticality analysis) for eight sites (total 215 DPCs), (2) reactivity reduction study by groundwater species applied to as-loaded DPCs, and (3) reactivity impact of filler material applied to as-loaded DPCs. Main Document Title: Dual Purpose Canister Reactivity and Groundwater Absorption Analyses DMS No. FCRD-UFD-2015-000637 referenced. | M4 | 1.02.08.16.01 | ORNL | FT-15OR081601 | DR Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | McMahon, Kevin | Direct Disposal of DPC Reactivity and Criticality Evaluations | Direct Disposal of DPC Reactivity and Criticality Status Report | Develop realistic, efficient approaches for analyzing the potential reactivity of DPCs subject to degradation in the disposal environment. Study the nature of criticality events, should they occur, and the consequences to waste isolation. FY15 Reactivity Analyses will focus on analyses of specific "as-loaded" canisters using the as-loaded configurations in UNF-St&andards. 2) Study the nature of criticality events, should they occur, and the consequences to waste isolation. FY15 work on the nature of criticality events will focus on developing representative assumptions, boundary conditions, and scoping analyses as described in "Critcality Analysis Process for Direct Disposal of Dual Purpose Canisters" ORNL/LTR-2014/80. | 2015-03-30 04:00 |  | 42093 |  | 2015 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Banerjee, Kaushik | Scaglione, John | OUO |  | FCRD-UFD-2015-000637
M4FT-15OR0817042 ULR. PREDECISIONAL DRAFT Sassani, David: Hi Laura, this report is OUO and designated as "PREDECISIONAL DRAFT MATERIAL – DO NOT DISTRBUTE" There was an NDA associated with this that only a limited number of people were part of for the work. I have the file, but will need to check to see whether or not it can be put out for others to see at this point or not, before I send it. | M4 | 1.02.08.17.04 | ORNL | FT-15OR081704 | DR Deep Borehole Disposal - ORNL | Howard, Rob | Mackinnon, Robert | Develop Surface Siting Considerations for Deep Borehole Report | Surface Siting Considerations for Deep Borehole Demonstration | Use data and software developed to support siting of an interim storage demonstration facility in combination with criteria developed for surface considerations to support the evaluation of logistical factors for deep borehole field test siting. Document the results in a Level 4 milestone to be used as input to M2FT-15SN0817061 Site Selection Report due on 05/04/2015 | 2015-04-03 |  | 2015-03-26 |  | 2015 | Complete | Considerations for Characterizing a Deep Borehole Field Test Site Using a GIS-Based Analysis Tool | Belles, Randy | Howard, Rob | None | Borehole-ORSAGE Report Final.pdf | FCRD-UFD-2015-000639 | Deep Borehole
M4FT-15OR0903012 Per Robby Joseph: had no document as it was a demonstration. | M4 | 1.02.09.03.01 | ORNL | FT-15OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Jarrell, Josh | Demonstrate UNF-ST&DARDS data integration in CURIE to DOE sponsors | Demonstrate UNF-ST&DARDS data integration in CURIE to DOE sponsors | This deliverable will be satisfied by providing a demonstration to the DOE sponsors on the ability to access UNF data from the CURIE website. | 2015-02-20 01:00 |  | 2015-02-12 |  | 2015 | Complete | Demonstrate UNF-ST&DARDS data integration in CURIE to DOE Sponsors | Robert Joseph |  | None |  | FCRD-NFST-2015-000651
M4FT-15SN0810055 OUO. Per Matt Brainard: marked CUI Type OUO, which prohibits upload into PICS:NE. Remi or someone else at SNL with access to this document will need to provide it to you. | M4 | 1.02.08.10.05 | SNL | FT-15SN081005 | ST Analysis - SNL | Dingreville, Remi | Sorenson, Ken | Draft report of M2 | Draft of M2 report on uncertainty quantification | Draft report of M2 report | 2015-07-03 06:00 |  | 2015-07-24 02:00 |  | 2015 | Completed Late | Development of Uncertainty Quantification Methodologies as Applied to Storage and Transportation R&D: Study on Stress Corrosion Cracking of Canister Welds |  |  | OUO |  | FCRD-UFD-2015-000712
M4FT-15SN0819033 Email unavailable per Kuhlman. | M4 | 1.02.08.19.03 | SNL | FT-15SN081903 | DR Salt Field Testing - SNL | Kuhlman, Kris | MacKinnon, Robert | Completion and Review of Salt URL Framework and Field Test Plans | Support and Review of Field Tests in Salt | Complete input to URL framework and mine-by/thermal test plans. Provide input and support to LANL for their thermal test plan deliverable. Support internal/external review of test plans following URL framework document. | 2015-09-03 12:00 |  | 42193.0833 |  | 2015 | Complete | email from Phil Stauffer indicating support from Dave Sassani and Kris Kuhlman for M2 | Kuhlman, Kris | Kuhlman, Kris | None | stauffer-email-on-M2.pdf | FCRD-UFD-2015-000717
M4FT-15SN0902081 Per Matt Brainard: Note: “Report is being maintained with the author. It will be transmitted to the Document Management System when Official Use Only questions related to DOE directed markings are resolved.” DMS No. FCRD-NFST-2015-000720. Main Document Title: “Analysis of the effects of the repository thermal limits”. Narrative: “Completed preliminary draft.” | M4 | 1.02.09.02.08 | SNL | FT-15SN090208 | Waste Management System Architecture Analysis - SNL | Kalinina, Elena | Jarrell, Josh | Waste Management System Analyses - Emplacement Thermal Limits | Emplacement Thermal Limits Analysis Report | Evaluate the impacts of the repository emplacement thermal limits on the waste management system. | 2015-07-31 14:00 |  | 2015-07-31 02:00 |  | 2015 | Complete | Analysis of the effects of the repository thermal limits | Elena Kalinina | Elena Kalinina | None |  | FCRD-NFST-2015-000720 | Thermal management, interim storage, repackaging, repository media
M4FT-15SR0910032 Per Matt Brainard: Deliverable not uploaded to PICS:NE. No notes indicating why. Main Document Title: “60 % Review Lines of Inquiry”. Deliverable Description: “60% Review Lines of Inquiry. Note: Milestone was completed 10/30/14.” DMS No.: FCRD-NFST-2015-000744. | M4 | 1.02.09.10.03 | SRNL | FT-15SR091003 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | TO 16 60% Review Lines of Inquiry | TO16 60% design Review Lines of Inquiry | Consolidate LOI from all review team members | 2014-10-30 02:00 |  | 2014-11-01 |  | 2015 | Completed Late | 60 % Review Lines of Inquiry | Joe. T. Carter | Joe. T. Carter | None |  | FCRD-NFST-2015-000744 | Lines of Inquiry
M4FT-15SR0910036 Per Matt Brainard: Deliverable not uploaded to PICS:NE. No notes indicating why. Main Document Title: “Draft Statement of Work”. Deliverable Description: “Draft Statement of Work - Draft Statement of Work was complete October 15, 2014.” DMS No.: FCRD-NFST-2015-000746. | M4 | 1.02.09.10.03 | SRNL | FT-15SR091003 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | Draft Pilot Design and TSAR Statement of Work | Draft Statement of Work | Draft pilot design concepts and TSAR SOW | 2014-10-15 04:00 |  | 2014-11-01 |  | 2015 | Completed Late | Draft Statement of Work | Joe. T. Carter | Joe. T. Carter | None |  | FCRD-NFST-2015-000746 | Statement of Work
M4FT-16IN080308012 Glenn Russell: FCRD-UFD-2016-000631 is not associated with an actual document. 000631 is the activity for the web map application which is the product of this activity but not a document. | M4 | 1.02.08.03.08.01 | INL | FT-16IN08030801 | Deep Borehole Field Test - INL | Russell, Glenn | Mackinnon, Robert | Activity to support FY2015 Deep Borehole Web Map | Activity to support FY2015 Deep Borehole Web Map | Activity to support FY2015 Deep Borehole Web Map | 2016-09-30 14:00 |  | 2016-09-30 02:00 | Beta version of Regional Geology Application in Javascript is not published but still in development. This Javascript based version is version 2.0 of the Regional Geology Web Map Application. Go live date for published version 2.0 is set for May 2017. M4 Milestone was the efforts put for in development, not an actual published application. | 2016 | Complete | Regional Geology Web Application V2 |  |  | None |  | FCRD-UFD-2016-000631
M4FT-16OR080203021 OUO Per Matt Brainard: Generate detailed thermal source terms for as-loaded casks was marked OUO in PICS:NE, which prohibits upload into the system. Deliverable Description: “Electronic files containing detailed thermal source terms for the NAC-MAGNASTOR Transportable Storage Canister CNZ-078 calculated using the detailed reactor history and fuel design information supplied by Duke Energy. Because this information was developed using proprietary data, the files could only be shared with PNNL based on the multi-party NDA requirements. It should be able to be shared once the PNNL deliverable is reviewed by NAC and Duke.” Main Document Title: “Detailed thermal source terms for the NAC-MAGNASTOR Transportable Storage Canister CNZ-078” | M4 | 1.02.08.02.03.02 | ORNL | FT-16OR08020302 | ST Analysis - ORNL | Scaglione, John | Sorenson, Ken | Generate detailed thermal source terms for as-loaded casks | Detailed thermal source terms | Establish necessary NDAs and work with industry to acquire necessary data. Generate detailed thermal source terms for representative casks and work with PNNL to develop thermal sensitivity analyses for TN-40 and NAC-Magnastor systems | 2016-07-29 06:00 |  | 2016-07-27 |  | 2016 | Complete | Detailed thermal source terms for the NAC-MAGNASTOR Transportable Storage Canister CNZ-078 | Liljenfeldt, Henrik | Scaglione, John | OUO |  | FCRD-UFD-2016-000603
M4FT-16OR080307012 Per Matt Brainard: Update of DPC direct disposal criticality analysis report Deliverable Title: Updated DPC direct disposal criticality evaluation File marked OUO and not uploaded into PICS:NE. Document Author: Banerjee Document Owner: Scaglione Deliverable Description: Update of existing DPC direct disposal criticality analysis report. Detailed canister specific post-closure criticality results for 16 new sites (total 339 DPCs) were added to this update. Main Document Title: Dual Purpose Canister Reactivity and Groundwater Absorption Analyses DMS No. FCRD-UFD-2016-000616 referenced. | M4 | 1.02.08.03.07.01 | ORNL | FT-16OR08030701 | DR Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Update of DPC direct disposal criticality analysis report | Updated DPC direct disposal criticality evaluation | Report documenting updated DPC criticality analysis results | 2016-08-05 02:00 |  | 42587 |  | 2016 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Banerjee, Kaushik | Scaglione, John | OUO |  | FCRD-UFD-2016-000616
M4FT-16OR080308041 Per Rob Howard, this document was never produced. ELH: Don’t have this one—can’t even find a draft and that is searching every digital record I have for "Peretz". I recall this was separate from the engineering work package; Bob MacKinnon requested ORNL help with GIS for site selection. Dave Sassani may know about this one. | M4 | 1.02.08.03.08.04 | ORNL | FT-16OR08030804 | Deep Borehole Field Test - ORNL | Howard, Rob | Mackinnon, Robert | Near Surface and Surface Geoscience and GIS Data and Evaluation Supporting the Deep Borehole Field Test Site | Near Surface and Surface Geoscience and GIS Data and Evaluation Supporting the Deep Borehole Field Test Site | This report will describe the near surface and surface existing geoscience and GIS data for the DBFT site, including any additional collected site characterization data to support the development of a site geologic framework model. | 2016-07-15 04:00 |  | 2016-07-15 |  | 2016 | Complete | Input on DBFT Conceptual Design Report | Peretz, Fred | Peretz, Fred | None | Peretz CDR draft input May 11 (002).docx | FCRD-UFD-2016-000612
M4FT-16OR090201028 Per Rob Howard: M3FT-16OR090201024 and M4FT-16OR090201028 were not stand-alone documents; they were incorporated into M2FT-16AN090201011 | M4 | 1.02.09.02.01.02 | ORNL | FT-16OR09020102 | CB: Siting Process - ORNL | Howard, Rob | Howard, Rob | Develop Consent Based Siting Roadmap | Consent Based Siting Plan | The Roadmap will reflect a consent based, phased, and adaptive siting approach that is flexible and allows decisions to be reviewed and modified in response to new information or new technical, social, or political developments | 2015-12-11 06:00 |  | 2015-12-11 |  | 2016 | Complete | Consent Based Siting Project and Stakeholder Engagement Plan | Robert Howard | Robert Howard | None |  | FCRD-NFST-2016-000654
M4FT-16PN090105022 OUO. Doc should not be included in SP site per Steve Maheras. | M4 | 1.02.09.01.05.02 | PNNL | FT-16PN09010502 | Characterization and Assessment - PNNL | Maheras, Steve | Jarrell, Josh | Develop 1 canister system set of drying templates and results to support test case for confirmation of UNF-ST&DARDS implementation | Canister System Drying Templates | M4 report that documents development of 1 canister system set of drying templates and results to support test case for confirmation of UNF-ST&DARDS implementation. | 2016-05-27 |  | 2016-05-25 03:00 |  | 2016 | Complete | Characterization and Assessment of Transportability of Canisters – Recommendations for Site-Specific Thermal Evaluations | Harold Adkins | Steve Maheras | None |  | FCRD-NFST-2016-000648 | UNF ST&DARDS, thermal templates, Maine Yankee, SNF, drying, peak fuel temperature
M4FT-16PN0904020313 OUO. Document should not be included in the SP site per Steve Maheras. | M4 | 1.02.09.04.02.03 | PNNL | FT-16PN09040203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Canister Transportability Assessment | Canister Transportability Assessment | Continue development of transportation cask specific thermal template models and evaluate aspects that may impact the transportability of loaded canisters/casks, such as thermal load and vacuum drying conditions. | 2016-07-15 |  | 2016-07-13 03:00 |  | 2016 | Complete | Characterization and Assessment of Transportability of Canisters – COBRA-SFS Thermal Models for 24PT4 Canister, MP197HB Transportation Cask, and 24PT1 Canister | JM Cuta | Steve Maheras | None |  | FCRD-NFST-2016-000672 | Thermal template, thermal model, COBRA-SFS, San Onofre, 24PT1, 24PT4, MP197HB, MP187, UNF ST&DARDS, SONGS
M4FT-16SN080503032 ULR. Same as MFT-15SN0826011 | M4 | 1.02.08.05.03.03 | SNL | FT-16SN08050303 | Develop and implement operating procedures - SNL | Appel, Gordon | McMahon, Kevin | Identify and summarize operating procedures | DOE Managed HLW and SNF Research: Generic operating procedures | Develop Generic List of and Description of operating procedures for DOE Managed HLW and SNF disposal | 42629.75 |  | 42628.3333 | Report completed as scheduled | 2016 | Complete | DRAFT Operating Procedures for a Generic Repository Licensing Organization | Gordon Appel | Gordon Appel | None | 20160914_First Page of Procedures Report FY16_Final_with Appendix E.pdf | FCRD-UFD-2016-000638
M4SF-17AN020403084 Software only - no document. | M4 | 1.08.02.04.03.08 | ANL | SF-17AN02040308 | NGSAM Development and Application - ANL | St. Aubin, Jim | Jarrell, Josh | Release NGSAM (Version 2.2.3.0) | Release NGSAM (Version 2.2.3.0) | Enhanced NGSAM database / application software release - no report deliverable | 2017-09-26 16:00 |  | 2017-09-26 02:00 | On September 26, 2017, the NGSAM Development Team completed its testing and released this level 4 milestone software to the IWM management and system analysts. | 2017 | Complete | The attached document supports the NGSAM software release by describing FY 2017 enhancements | ANL | Argonne National Laboratory - software only not a document | None |  | SFWD-IWM-2017-000147
M4SF-17ID0203030511 Superseded by “M4SF-18ID020303043-CLIN 2 Event 5: Phase 2 Report including Conceptual Design Information for Simulated Cradle & Cask Test Loads” and completed on 3/7/2018 under the follow on FY18 work package | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 5(b): Phase 2 Report (includes ballast design; see Issues and Mitigating Actions Item #4) | Event 5(b): Phase 2 Report (includes ballast design; see Issues and Mitigating Actions Item #4) | Event 5(b): Phase 2 Report (includes ballast design; see Issues and Mitigating Actions Item #4) | 2017-09-14 | 2017-10-13 04:00 |  | The railcar design approval authority, the Association of American Railroads Engineering Equipment Committee, is taking longer than they did for previous reviews. They requested some more analysis and some changes in the report format | 2017 | Expected Late |  |  |  | None |  | SFWD-IWM-2017-000132
M4SF-17ID020303055 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Narrative: “Kasgro Rail completed finite modeling analysis for the Atlas HLRM Railcar Project’s cask railcar for DOE review and approval on 11/17/2016.” Main Document Title: “Event 1: Cask Railcar Finite Modeling”. No further notes. | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 1: Cask Railcar Finite Modeling Complete | Event 1: Cask Railcar Finite Modeling Complete | Event 1: Cask Railcar Finite Modeling Complete | 2017-01-30 |  | 2016-12-01 02:00 |  | 2017 | Complete | • Event 1: Cask Railcar Finite Modeling |  |  | None |  | SFWD-IWM-2017-000133
M4SF-17ID020303056 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Narrative: “Kasgro Rail completed finite modeling analysis for the Atlas HLRM Railcar Project’s buffer railcar for DOE review and approval on 11/17/2016.” Main Document Title: “Event 2: Buffer Railcar Finite Modeling”. No further notes. | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 2: Buffer Railcar Finite Modeling Complete | Event 2: Buffer Railcar Finite Modeling Complete | Event 2: Buffer Railcar Finite Modeling Complete | 2017-01-30 |  | 2016-12-01 02:00 |  | 2017 | Complete | • Event 2: Buffer Railcar Finite Modeling |  |  | None |  | SFWD-IWM-2017-000134
M4SF-17ID020303057 Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Narrative: “completed.” Main Document Title: “completed”. No further notes. | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 3: Dynamic Modeling Complete | Event 3: Dynamic Modeling Complete | Event 3: Dynamic Modeling Complete | 2017-05-10 | 2017-07-12 04:00 | 2017-08-04 04:00 |  | 2017 | Completed Late | completed |  |  | None |  | SFWD-IWM-2017-000135
M4SF-17ID020303058 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Narrative: “Fabrication estimate were submitted to DOE on 1/26/17.” Main Document Title: “Fabrication Estimate”. No further notes. | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 4(a): Fabrication Estimate Complete | Event 4(a): Fabrication Estimate Complete | Event 4(a): Fabrication Estimate Complete | 2016-12-30 | 2017-01-31 02:00 | 2017-01-26 04:00 |  | 2017 | Completed Late | Fabrication Estimate |  |  | None |  | SFWD-IWM-2017-000136
M4SF-17ID020303059 Per Matt Brainard: Deliverable not uploaded into PICS:NE. Deliverable form submitted and approved blank. Narrative: “Completed rail car document work package.” Main Document Title: “Railcar Document Package and Fabrication Estimate Complete”. No further notes. | M4 | 1.08.02.03.03.05 | DOE-ID | SF-17ID02030305 | Transportation: Hardware - DOE-ID | Ford, Brayton | Feldman, Matt | Event 4(b): Railcar Document Package | Event 4(b): Railcar Document Package | Event 4(b): Railcar Document Package | 2017-07-31 | 2017-09-29 02:00 | 2017-09-11 02:00 | Completed rail car document work package. | 2017 | Completed Late | Railcar Document Package and Fabrication Estimate Complete |  |  | None |  | SFWD-IWM-2017-000137
M4SF-17ID020501034 . Superseded by “M4SF-18ID020408033-Conduct Simultaneous Welding Test for DOE” and completed on 12/20/2017 under the follow on FY18 work package. | M4 | 1.08.02.05.01.03 | DOE-ID | SF-17ID02050103 | Simultaneous Welding Task (Task Order 2) | Ford, Brayton | Nutt, Mark | Conduct Simultaneous Welding Test for DOE | Conduct Simultaneous Welding Test for DOE | Conduct Simultaneous Welding Test for DOE | 2017-12-20 06:00 |  |  | on schedule | 2017 | 90 Day |  |  |  | None |  | SFWD-IWM-2017-000245
M4SF-17OR0102010210 superceded by M4SF-18OR010201022 | M4 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | Sorenson, Ken | Document RIP data and current DE test status | Status report on DE testing | Status report on current results of RIP measurements and any other DE exams to date | 2018-05-04 |  |  | work has not yet started on this activity | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000238
M4SF-17OR010305026 Replaced by Milestone M4SF-18OR010305013 | M4 | 1.08.01.03.05.02 | ORNL | SF-17OR01030502 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Update of DPC direct disposal criticality analysis report | Update to DPC Direct Disposal Criticality Analysis Report | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results into the exisiting living document. | 2018-04-27 |  |  |  | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000241
M4SF-17OR010305028 Replaced by Milestone M4SF-18OR010305015 | M4 | 1.08.01.03.05.02 | ORNL | SF-17OR01030502 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Summary status report of DPC filler demonstration project | Status update of DPC filler demonstration | Status update of DPC filler capabilities and results to date | 2018-09-28 |  |  |  | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000242
M4SF-17OR020402031 Per Rob Howard: computer animation (software), not a document. | M4 | 1.08.02.04.02.03 | ORNL | SF-17OR02040203 | Communications Support - ORNL | Howard, Rob | Jarrell, Josh | Computer Animation of Waste Management System Concept of Operations | Computer Animated Waste Management System Concept of Operations | Develop computer animation of Concept of Operations for the Waste Management System with focus on commercial spent fuel movement. The level of detail should be suitable for communication with the general public. | 2017-03-31 |  | 2017-03-31 |  | 2017 | Complete | Computer Animation of Waste Management System Concept of Operations | Robert Howard | Robert Howard | OUO |  | SFWD-IWM-2017-000139
M4SF-17OR020403118 Per Robby Joseph: had no document because it was only a collection of input (mostly emails) that were used in ANL’s M3 report. | M4 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | ORNL-input for ANL-led NGSAM Transition Status Update | Provide input for NGSAM Transition Status Update | This update will provide ANL text on NGSAM transition evaluation work performed at ORNL. It will not be a stand-alone report as it will be incorporated into ANL's M3 deliverable on NGSAM Transition Status Update, M3SF-17AN020403102, which is due on March 1, 2017. | 2017-02-17 |  | 2017-02-17 |  | 2017 | Complete | ORNL Input for NGSAM Transition and Benchmarking Report | Robby Joseph | Robby Joseph | None | Benchmarking_Report_Input_All_02_17_17.docx | SFWD-IWM-2017-000151
M4SF-17OR020403272 Per Rob Howard: M4SF-17OR020403272 and M4SF-17OR020403274 were not stand alone documents. These milestones were incorporated into M4SF-17OR020403273 “Monetized and Non-Monetized Impacts of an ISF on a Hypothetical Host Community.docx” | M4 | 1.08.02.04.03.27 | ORNL | SF-17OR02040327 | System Deployment Analysis - ORNL | Howard, Rob | Jarrell, Josh | Inputs and Assumptions for Hypothetical Community Impact Analyses | Inputs and Assumptions for Hypothetical Community Impact Analyses | Develop recommended inputs and assumptions for a preliminary Community Impact Analysis illustrating how an interim storage facility might impact a hypothetical host community. A nuclear waste management facility will carry with it a number of impacts that are carried by the host community and state. These impacts will vary significantly depending on a variety of factors, such as type of facility (ISF vs repository), the facility scope and design, geographic location, and phases of operation (i.e. construction, operation and decommissioning) | 2017-06-16 |  | 2017-06-16 |  | 2017 | Complete | Assessing the Impacts of an ISF on a Hypothetical Host Community: Inputs and Assumptions | Robert Howard | Robert Howard | OUO |  | SFWD-IWM-2017-000243
M4SF-17OR020403274 Per Rob Howard: M4SF-17OR020403272 and M4SF-17OR020403274 were not stand alone documents. These milestones were incorporated into M4SF-17OR020403273 “Monetized and Non-Monetized Impacts of an ISF on a Hypothetical Host Community.docx” | M4 | 1.08.02.04.03.27 | ORNL | SF-17OR02040327 | System Deployment Analysis - ORNL | Howard, Rob | Jarrell, Josh | Preliminary Economic Benefits/Incentives Source Document | Preliminary Economic Benefits/Incentives Source Document | Preliminary Economic Benefits/Incentives Source Document Develop a source document that describes work conducted by communities, states, Tribes, and other countries with regard to negotiating institutional controls and socio-economic benefits and other considerations for hosting a nuclear waste facility. Investigate the requirements from the Nuclear Waste Policy Act and other relevant policies and existing or proposed laws and with regard to DOE’s requirements for providing benefits during the site investigation, construction, and operations phases of a facility. Research other DOE siting efforts to learn what aspects may be relevant to siting a storage site or repository. Briefly describe the type of information and support DOE might consider providing to a community prior to negotiating a hosting agreement. | 2017-07-19 |  | 2017-07-19 |  | 2017 | Complete | Assessing the Impacts of an Interim Storage Facility on a Hypothetical Host Community: Inputs and Assumptions | Rob Howard | Rob Howard | OUO |  | SFWD-IWM-2017-000208
M4SF-17PN020302039 Per Steve Maherqas: Doc is OUO and not appropriate for the SP site. | M4 | 1.08.02.03.02.03 | PNNL | SF-17PN02030203 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | FY2017 UNF-ST&DARDS Transportation Cask Template Developments to Support Ongoing Shutdown Site Planning, Implementation, and Disposition | FY2017 UNF-ST&DARDS Transportation Cask Template Developments to Support Ongoing Shutdown Site Planning, Implementation, and Disposition | Documentation of FY2017 UNF-ST&DARDS transportation cask models and templates. | 2017-09-22 |  | 2017-09-16 03:00 | This report continues the investigation to define needed information and thermal modeling requirements and capabilities for evaluation of spent fuel thermal history in on-site storage, as related to transportability concerns. Two new COBRA-SFS models have been added to support template development for the UNF-ST&DARDS tool. These are the NUHOMS 61BT Dry Storage Canister (DSC), to further extend the database for boiling water reactor (BWR) sites, and the HI-TRAC on-site transfer cask, to continue the development of capabilities for steady-state and transient analysis of wet-to-dry storage operations utilizing the UNF-ST&DARDS tool. This model contains a fully detailed representation of the MPC-32 within the transfer cask, and could readily be extended to creation of templates for modeling other MPC configurations within the HI-TRAC, for site-specific evaluations of transfer operations, using the UNF-ST&DARDS tool. The report also includes a general summary of the current range of COBRA-SFS thermal models available for template development for the UNF-ST&DARDS tool. A summary is provided outlining the current capability for analysis of transfer operations, and a brief discussion of the types of analyses that can be done, as a function of available data from a specific site. The report concludes with a short list of recommendations for continued work in support of the thermal modeling capability in UNF-ST&DARDS. | 2017 | Complete | Template Development for Storage Canisters and On-site Transfer Cask Thermal Models to Support Origin Site Planning, Implementation, and Disposition | Steve Maheras | Steve Maheras | OUO |  | SFWD-IWM-2017-000131 | Shutdown sites, SNF, UNF, thermal modeling, thermal templates, 61BT, NUHOMS, COBRA-SFS, horizontal storage module, dry storage canister, UNF-ST&DARDS
M4SF-17SN010305013 same as M4SF-18SN010305022 | M4 | 1.08.01.03.05.01 | SNL | SF-17SN01030501 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Joint Workplan on Filler Investigations for DPCs | Joint Workplan on Filler Investigations for DPCs | Workplan with ORNL to produce a demonstration of filler emplacement (with post-test examination) in scaled models representing DPCs. | 2017-12-20 06:00 |  |  | Coordination with ORNL has begun. | 2017 | 90 Day |  |  |  | None |  | SFWD-SFWST-2017-000239
M4SF-17SN010305013 same as M4SF-18SN010305022 | M4 | 1.08.01.03.05.01 | SNL | SF-17SN01030501 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Joint Workplan on Filler Investigations for DPCs | Joint Workplan on Filler Investigations for DPCs | Workplan with ORNL to produce a demonstration of filler emplacement (with post-test examination) in scaled models representing DPCs. | 2017-12-20 06:00 |  |  | Coordination with ORNL has begun. | 2017 | 90 Day |  |  |  | None |  | SFWD-SFWST-2017-000239
M4SF-17SN010305015 not completed per Hardin | M4 | 1.08.01.03.05.01 | SNL | SF-17SN01030501 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Describe a complete laboratory testing program for filler composition, delivery, emplacement in surrogate canisters, and post-test examination. To the extent possible specify filler material and equipment sources. | 2018-03-30 04:00 |  |  | Coordination with ORNL, and investigation of filler options, have begun. | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000240
M4SF-17SN010305015 not completed per Hardin | M4 | 1.08.01.03.05.01 | SNL | SF-17SN01030501 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Describe a complete laboratory testing program for filler composition, delivery, emplacement in surrogate canisters, and post-test examination. To the extent possible specify filler material and equipment sources. | 2018-03-30 04:00 |  |  | Coordination with ORNL, and investigation of filler options, have begun. | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000240
M4SF-17SN010501012 ULR. Draft input. M4SF-17SN010501012 ULR. Draft input. Author: The content of this milestone is contained in the Report SFWD-SFWST-2017-000047 M3 final SAND_8621 R.pdf. Please point any users to that final document. | M4 | 1.08.01.05.01.01 | SNL | SF-17SN01050101 | Complete and Populate Online Waste Library (OWL) - SNL | Sassani, David | McMahon, Kevin | The Online Waste Library (OWL): Inventory Content Update, Status, and Waste Forms Performance Constraints | The Online Waste Library (OWL): Inventory Content Update, Status, and Waste Forms Performance Constraints | Report on the updated OWL including inventory information modifications and waste form performance revisions | 2017-08-18 08:00 |  | 42957.0833 |  | 2017 | Complete | See notes above and description | Sassani, David | Sassani, David | see SF-17SN01050102 |  | SFWD-SFWST-2017-000112 | OWL database waste form characteristics
M4SF-17SN010501013 OUO Author: This is a rough draft version of the final Report SFWD-SFWST-2017-000047 M3 final SAND_8621 R.pdf. Please point any users to that final document. | M4 | 1.08.01.05.01.01 | SNL | SF-17SN01050101 | Complete and Populate Online Waste Library (OWL) - SNL | Sassani, David | McMahon, Kevin | Inventory Update for GDSA Evaluations | Inventory Update for GDSA Evaluations | Assessment of changes to GDSA inventory from that used in FY16 | 2017-03-17 08:00 |  | 42811.0833 |  | 2017 | Complete | Draft Updates to Inventory Represented in GDSA for a Defense Waste Repository | Sassani, David | Sassani, David | OUO |  | SFWD-SFWST-2017-000113 | defense waste repository inventory GDSA
M4SF-17SN010504054 OUO The M4 about the site evaluation plan, M4SF-17SN010504071, was subsumed. It is now Section 5 of the M2 I just sent, M2SF-17SN010504081. | M4 | 1.08.01.05.04.05 | SNL | SF-17SN01050405 | Define Generic Safety/Performance Objectives - SNL | Sevougian, S. David | Mackinnon, Robert | Generic Safety/Performance Objectives for a Defense Waste Repository | Generic Safety/Performance Objectives for a Defense Waste Repository | Brief letter report defining safety and performance objectives appropriate for a repository for DOE-managed wastes, especially as related to choices to be made during the site selection and evaluation phases of repository development | 2017-08-29 09:00 |  | 42977.75 |  | 2017 | Completed Late | Safety Analysis for a Generic Deep Geologic Repository in Shale (Section 4) | Sevougian, S. David | Sevougian, S. David | OUO |  | SFWD-SFWST-2017-000118 | Safety criteria, geologic disposal, safety assessment
M4SF-17SN010504071 OUO The M4 about the site evaluation plan, M4SF-17SN010504071, was subsumed. It is now Section 5 of the M2 I just sent, M2SF-17SN010504081. | M4 | 1.08.01.05.04.07 | SNL | SF-17SN01050407 | Document Preliminary Technical Site Evaluation Plan - SNL | Sevougian, S. David | Mackinnon, Robert | Preliminary Technical Site Evaluation Plan for a Defense Waste Repository | Preliminary Technical Site Evaluation Plan for a Defense Waste Repository | Letter report outlining a technical site-evaluation plan and activities, perhaps drawing upon experience with the DBH R&D project, as well as considering pertinent regulations. | 2017-09-29 03:00 |  | 42977.75 |  | 2017 | Complete | Safety Analysis for a Generic Deep Geologic Repository in Shale (Section 5) | Sevougian, S. David | Sevougian, S. David | OUO |  | SFWD-SFWST-2017-000120 | Site evaluation, geologic disposal
M4SF-18IN020409013 Per Josh Jarrell: Do NOT include in SP site - available through PICS/NE | M4 | 1.08.02.04.09.01 | INL | SF-18IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Draft Multi-Year Project Plan | Draft Multi-Year Project Plan | Draft report to lay out multi-year (nominally 3 year) plan for what is required to prepared DOE-managed fuel for transportation. Specific information in this report will include objective, scope, system concept, and multi-year goals of this activity. | 2018-08-31 |  | 2018-08-31 02:00 |  | 2018 | Complete | Multi-Year Plan to Prepare DOE-managed Spent Fuel for Transportation | Josh Jarrell | Josh Jarrell | None | 2018-09_Standard-Canister-Path-Forward_DRAFT_rev5.docx
M4SF-18LA010301061 superceded by M4SF-19LA0301062 | M4 | 1.08.01.03.01.06 | LANL | SF-18LA01030106 | Argillite International Collaborations - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite International Collaborations - LANL | Further Chemical Analyses of Febex Samples | To expand existing R&D partnerships with international programs (Swiss, Japanese, NEA ) in nuclear waste disposal underground research laboratory (URL) activities. Further participation in FEBEX research. Participate in data sharing of present and previous experimental results, including bentonite mineral phase transformations and steel corrosion/interface mineralogy characterization. | 2019-03-29 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18LA010302026 superceded by M4SF-19LA010302023 | M4 | 1.08.01.03.02.02 | LANL | SF-18LA01030202 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Modeling and experimental activities for crystalline rock disposal to support GDSA | Modeling and experimental activities for crystalline rock disposal to support GDSA | Describe DFN, reduced order models, colloid experiments supporting GDSA | 2019-04-18 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18LA010308012 superceded by M4SF-19LA010308012 | M4 | 1.08.01.03.08.01 | LANL | SF-18LA01030801 | Engineered Barrier System R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Engineered Barrier System R&D - LANL - interim report | Engineered Barrier System R&D - LANL - interim report | Engineered Barrier System R&D - LANL - interim report | 2019-03-29 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M4SF-18LB010302033 superceded by M4SF-19LB010302031 | M4 | 1.08.01.03.02.03 | LBNL | SF-18LB01030203 | Crystalline Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | LBNL Crystalline Disposal R&D in FY18 and FY19 | LBNL Crystalline R&D progress: FY18-FY19 | This activity includes - Expanding pore scale modeling of gas bubble migration to better account for the long-term mass transfer between the clay matrix and fracture(s) - Laboratory and modeling studies on EDZ behavior in granitic rocks and shale. Induced damage in core samples will be examined for its geophysical (seismic velocities), AE signatures, and hydrological properties (permeability) Numerical modeling of the laboratory experiments will be conducted via discrete modeling of fracture growth. | 2019-05-31 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M4SF-18LB010302073 Per Matt Brainard: M4SF-18LB010302073: LBNL research in Crystalline disposal R&D via international collaboration: FY18-FY19 progress report. originally planned for FY19 completion on 5/31/2019. During the FY19 planning phase, the work package titled “SF-19LB01030207 - Crystalline International Collaborations - LBNL (Rev. 2)” only included a single activity and no milestones. Although not 100% certain, the above milestone may have been mapped into the FY19 work package titled SF-19LB01030203 - Crystalline Disposal R&D - LBNL and superseded by: M4SF-19LB010302031- LBNL Crystalline Disposal R&D in FY19 The FY19 Deliverable is attached. WPM: Liange Zheng (Cindy Tilton as backup) CAM: Kevin McMahon Narrative: Summary The Used Fuel Disposition Disposal R&D roadmap identified a number of key research priorities based on an analysis of key features, events, and processes that are important to the safety case for radioactive waste disposal. The highest ranked areas relevant to crystalline disposal include host rock properties, flow and transport pathways and processes in crystalline media, and the excavation disturbed zone. The R&D activities conducted at LBNL during FY19 related to crystalline disposal address these key issues. These activities include laboratory experiments and related numerical simulations to evaluate how THMC processes affect the evolution of excavation disturbed zone and the use of a crystalline basement analog site in Sweden to evaluate fracture transmissivity using unique borehole monitoring tool, called Step-rate Injection Method for Fracture In-situ Properties (SIMFIP) and compare identified flow zones with different fracture sets observed in the field with core studies in the laboratory. The results of these studies are presented in this report. | M4 | 1.08.01.03.02.07 | LBNL | SF-18LB01030207 | Crystalline International Collaborations - LBNL | Zheng, Liange | McMahon, Kevin | LBNL research in Crystalline disposal R&D via international collaboration: FY18-FY19 progress report | Crystalline R&D international progress report: FY18-FY19 | This activity include additional laboratory experiments and numerical modeling of flow (single and two-phase) in fractured cores from crystalline rock samples. Objective is to understand the degree of agreement between core investigations and field fluid logging measurements | 2019-05-31 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M4SF-18LB010304032 Rutqvist: GDSA collaboration with Sandia was supposed to start from early FY18, but postponed due to CR's and funding uncertainties. | M4 | 1.08.01.03.04.03 | LBNL | SF-18LB01030403 | GDSA - Modeling and Integration - LBNL | Birkholzer, Jens | MacKinnon, Robert | Summary of LBNL Activities Supporting Geologic Disposal Safety Assessment - Modeling and Integration | Summary of LBNL Activities Supporting Geologic Disposal Safety Assessment - Modeling and Integration | Summary of LBNL Activities Supporting Geologic Disposal Safety Assessment - Modeling and Integration | 2018-07-27 | 2018-10-01 |  |  | 2018 | Late |  |  |  | None
M4SF-18LB010305041 superceded by M4SF-19LB010305041 Is this carryover to FY19? | M4 | 1.08.01.03.05.04 | LBNL | SF-18LB01030504 | Direct Disposal of Dual Purpose Canisters - LBNL | Rutqvist, Jonny | Mackinnon, Robert | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | 2019-05-31 |  |  | On Schedule | 2018 | On Schedule |  |  |  | None
M4SF-18LL010301042 superceded by M4SF-19LL010301042 | M4 | 1.08.01.03.01.04 | LLNL | SF-18LL01030104 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Code development in support of the SFWST Thermodynamic database | Code development in support of the SFWST Thermodynamic database | Report on water code development | 2018-12-03 |  |  | effort is on schedule | 2018 | 90 Day |  |  |  | None
M4SF-18LL010301082 superceded by M4SF-19LL010301082 | M4 | 1.08.01.03.01.08 | LLNL | SF-18LL01030108 | Argillite International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | Surface complexation and ion exchange database development phase 1: Clay minerals | Surface complexation and ion exchange database development phase 1: Clay minerals | Report on surface complexation/ion exchange database development with an initial focus on clay minerals | 2018-12-03 | 2019-05-03 03:00 |  | We anticipate significant delays in this effort due to staffing delays. | 2018 | Expected Late |  |  |  | None
M4SF-18LL010302042 superceded by M4SF-19LL010302042 | M4 | 1.08.01.03.02.04 | LLNL | SF-18LL01030204 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Pu incorporation into reduced iron oxide phases | Pu incorporation into reduced iron oxide phases | report on Pu incorporation into reduced iron oxide phases | 2018-12-03 | 2019-03-08 03:00 |  | Delays in synchrotron beamtime is leading to delays in deliverable | 2018 | Expected Late |  |  |  | None
M4SF-18OR0102010214 supersedes M5SF-17OR0102010212, which was superceded by M4SF-19OR010201025. | M4 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Defuel and ship defueled cladding to ANL | Report detailing the specific cladding shipped to ANL | Defuel 3.5 inch segments of sister rod fuel and ship approximately 6 feet of defueled cladding to ANL | 2019-03-29 |  |  | the defueling is scheduled to start in November 2018, but other hot cell activities could cause delays in having the material ready to ship to ANL on schedule. this issue is currently being reviewed. | 2018 | On Schedule |  |  |  | None
M4SF-18OR0103050117 superceded by M4SF-19OR0103050110 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Status report summarizing GDSA/PFLOWTRAN simulation status on HPC environment | Summary status report of GDSA/PFLOWTRAN simulation on HPC environment | Develop a M4 Status report summarizing the above activities suitable for incorporation or reference by either M2SF-18SN010304065 “GDSA Framework Development and Process Model Integration” or M3SF-18SN010305072 “DPC Criticality Simulation Preliminary Phase” | 2018-11-16 |  |  | On Schedule | 2018 | 90 Day |  |  |  | None
M4SF-18OR0103050120 superceded by M4SF-19OR0103050113 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Prepare BWR data evaluation report | SFCOMPO BWR data evaluation report | • Draft evaluation reports for a boiling water reactor (BWR) dataset will be prepared by ORNL for independent peer review by the Technical Review Group for the SFCOMPO database. The report will include a detailed uncertainty analysis of the data. | 2018-12-28 |  |  | On Schedule | 2018 | 90 Day |  |  |  | None
M4SF-18OR0103050121 Milestone omitted during FY19 planning because it was subsumed into M4SF-19OR0103050113 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Evaluate additional datasets for inclusion as burnup benchmarks | Additional data sets evaluated for spent fuel benchmarks | Report documenting data sets reviewed by international experts in spent fuel analysis for several BWR fuel designs for inclusion in benchmark database | 2019-02-28 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18OR010305013 OUO. Supercedes M4SF-17OR010305026 Per Matt Brainard: Update of DPC direct disposal criticality analysis report Deliverable Title: Update to DPC Direct Disposal Criticality Analysis Report File marked OUO and not uploaded into PICS:NE. Document Author: Georgeta Radulescu Document Owner: John Scaglione Deliverable Description: Dual-purpose canister (DPC) criticality report supporting feasibility assessment of DPC direct disposal in a geological repository has been revised (revision 4). This revision includes (1) a description of the criticality models for the NUHOMS® 24PT1-DSC and NUHOMS® 32 PT-DSC DPCs; (2) post-closure criticality calculation results for five additional sites (total 60 DPCs); (3) reactivity reduction study results by groundwater species applied to as-loaded DPCs; (4) misload analyses assuming the worst fuel assembly configuration in an as-loaded canister; and (5) a filler height scoping calculation.. Main Document Title: Dual Purpose Canister Reactivity and Groundwater Absorption Analyses Lab ID No. 111330: Other - banerjeek@ornl.gov. Notes: For details, please contact Kaushik Banerjee (banerjeek@ornl.gov) | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Update of DPC direct disposal criticality analysis report | Update to DPC Direct Disposal Criticality Analysis Report | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results into the existing living document. | 2018-05-25 |  | 43245 |  | 2018 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Radulescu, Georgeta | Scaglione, John | OUO
M4SF-18OR020102014 Per Rob Howard: not a stand-alone document; it was incorporated into M2SF-18OR020102011 | M4 | 1.08.02.01.02.01 | ORNL | SF-18OR02010201 | Private Initiative Implementation Plan - ORNL | Howard, Rob | Howard, Rob | Annotated Outline for Private Initiative Implementation Plan | Annotated Outline for Private Initiative Implementation Plan | Annotated Outline for Private Initiative Implementation Plan | 2017-12-15 |  | 2017-12-12 |  | 2018 | Complete | Private Initiative Implementation Plan Annotated Outline | Rob Howard | Rob Howard | OUO
M4SF-18PN010201035 Per Matt Brainard: Receipt, Cutting, and Storage of 10 Sister Rods, milestone was never given a FY18 year-end status, therefore the Deliverable is missing. It does not exist in the follow-on FY19 work package, therefore the milestone is assumed complete, however it was never uploaded into PICS:NE. | M4 | 1.08.01.02.01.03 | PNNL | SF-18PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | Receipt, Cutting, and Storage of 10 Sister Rods | Results of Sister Pin Destructive Tests | Document that rods were received, punctured, cut, and stored. | 2018-09-28 | 2018-10-31 |  | No input from WPM. | 2018 | Expected Late |  |  |  | None
M4SF-18PN010206022 Per Matt Brainard: 8-AXLE railcar evaluation support, milestone was never given a FY18 year-end status, therefore the Deliverable is missing. It does not exist in the follow-on FY19 work package, therefore the milestone is assumed complete, however it was never uploaded into PICS:NE. | M4 | 1.08.01.02.06.02 | PNNL | SF-18PN01020602 | Rail Car Optimization - PNNL | Ross, Steven | Saltzstein, Sylvia | 8-AXLE railcar evaluation support | 8-axle Rail Car Conceptual Design Summary | Provide status of the 8-axle railcar conceptual design activities. | 2018-09-27 | 2018-10-31 |  | No input from WPM. | 2018 | Expected Late |  |  |  | None
M4SF-18PN010206023 Per Matt Brainard: 8-axle Railcar Review Support, milestone was originally planned for completion in FY19 on 9/29/2019. However, during the FY19 work package planning phase, this milestone did not get transferred to the follow-on work package, therefore the Deliverable is missing and the milestone is assumed cancelled. | M4 | 1.08.01.02.06.02 | PNNL | SF-18PN01020602 | Rail Car Optimization - PNNL | Ross, Steven | Saltzstein, Sylvia | 8-axle Railcar Review Support | 8-Axle Railcar Modeling Validation Suppport | Provide summary of 8-axle railcar design and modeling support | 2019-09-29 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M4SF-18PN010308073 Per Matt Brainard: Note: It appears that FY18 milestones M4SF-18PN010308073: PNNL Input to International Collaborations and M4SF-18PN010308074: PNNL R&D Input to International Collaboration have both been superseded by M4SF-19PN010308072: PNNL R&D Input to International Collaboration in FY19. The FY19 milestone is currently on schedule for completion on 9/30/20019. There is no Deliverable to provide at this time. | M4 | 1.08.01.03.08.07 | PNNL | SF-18PN01030807 | Engineered Barrier System International Collaborations - PNNL | Hanson, Brady | McMahon, Kevin | PNNL Input to International Collaborations | PNNL Input to International Collaborations | Summarize the results of the First DISCO meeting and the Spent Fuel Workshop. | 2018-08-31 | 2018-11-29 03:00 |  | August Status: Nothing to report in the M4 (M4SF-18PN010308073) as the WPM was not able to attend the meetings that were to be summarized in this report so it is now delayed to 11/29/2018. | 2018 | Late |  |  |  | None
M4SF-18PN010308074 Per Matt Brainard: M4SF-18PN010308074: PNNL R&D Input to International Collaboration was planned for FY19 completion on 3/1/2019. During the FY19 Planning phase, the above milestone was mapped into FY19 work package SF-19PN01030807 - Engineered Barrier System International Collaborations – PNNL and superseded by M4SF-19PN010308072: PNNL R&D Input to International Collaboration with a new Estimated Finish Date of 9/30/2019. Note: It appears that FY18 milestones M4SF-18PN010308073: PNNL Input to International Collaborations and M4SF-18PN010308074: PNNL R&D Input to International Collaboration have both been superseded by M4SF-19PN010308072: PNNL R&D Input to International Collaboration in FY19. The FY19 milestone is currently on schedule for completion on 9/30/20019. There is no Deliverable to provide at this time. | M4 | 1.08.01.03.08.07 | PNNL | SF-18PN01030807 | Engineered Barrier System International Collaborations - PNNL | Hanson, Brady | McMahon, Kevin | PNNL R&D Input to International Collaboration | PNNL R&D Input to International Collaborations | Results of R&D and other interactions with international collaborators. | 2019-03-01 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18SN0102010411 Scoping tests with the experimental system were completed in September and documented on schedule in the deliverable M3SF-18SN010201047. | M4 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Investigations of Aerosol Transmission through SCC | Investigations of Aerosol Transmission through SCC | This report will summarize experimental and modeling work evaluating potential gas and particle transport though SCC cracks. | 2019-03-15 |  |  | Work that will be documented in this milestone continues on schedule. Scoping tests with the experimental system were completed in September and documented on schedule in the deliverable M3SF-18SN010201047. | 2018 | On Schedule |  |  |  | None
M4SF-18SN010305055 not completed per Hardin | M4 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | MacKinnon, Robert | Engineering and Cost Analysis for DPC Disposal Solutions | Preliminary Cost Analysis for DPC Disposal Solutions | Produce ROM cost estimates for identified options and DPC modifications. | 2019-05-02 |  |  | Work planning is complete and technical service subcontract let. | 2018 | On Schedule |  |  |  | None
M4SF-18SN010305055 not completed per Hardin | M4 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Mackinnon, Robert | Engineering and Cost Analysis for DPC Disposal Solutions | Preliminary Cost Analysis for DPC Disposal Solutions | Produce ROM cost estimates for identified options and DPC modifications. | 2019-05-02 |  |  | Work planning is complete and technical service subcontract let. | 2018 | On Schedule |  |  |  | None
M4SF-18SN010308083 Per Matt Brainard: Document not available in PICS:NE. It was due on 3/29/2019, which is in FY19. Checking the FY19 EBS – SNL work package and this milestone no longer exists. It may have been dropped entirely. | M4 | 1.08.01.03.08.08 | SNL | SF-18SN01030808 | Engineered Barrier System International Collaborations - SNL | Matteo, Edward | McMahon, Kevin | Milestone to Report on Additional FY18 Activities for EBS Int'l | Milestone to Report on Additional FY18 Activities for EBS Int'l | Milestone to Report on Additional FY18 Activities for EBS Int'l | 2019-03-29 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18SN010401012 Sandia Proprietary | M4 | 1.08.01.04.01.01 | SNL | SF-18SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Evaluate cloud service vendors against project requirements and document the recommended cloud service provider based on the outcome of the vendor evaluation | Final Report on Recommended Cloud Service Provider | Evaluate cloud service vendors against project requirements and document the recommended cloud service provider based on the outcome of the vendor evaluation. | 2018-06-15 |  | 2018-06-21 02:00 |  | 2018 | Completed Late | Cloud Vendor Recommndation for a IT Cloud Envioroment Project | Cindy Huber | Sandia National Labs | Sandia Proprietary
M4SF-19LA010305032 Removed from list per Florie Caporuscio - milestone was canceled. | M4 | 1.08.01.03.05.03 | LANL | SF-19LA01030503 | Direct Disposal of Dual Purpose Canisters - LANL | Caporuscio, Florie | Freeze, Geoff | Dual puropose canister - BORAL solubility | Dual Purpose canister - BORAL solubility |  | 2019-07-30 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M4SF-19OR010205033 Per Matt Brainard: Local streaming over WiFi, a Deliverable does not exist for this milestone. Deliverable Description: “A physical demonstration of the capability was made”. Notes: “There is no report for this milestone other than the technology was successfully demonstrated.” Lab ID # Notes: “No document, technology development milestone.” | M4 | 1.08.01.02.05.03 | ORNL | SF-19OR01020503 | Security - ORNL | Scaglione, John | Saltzstein, Sylvia | Local streaming over WiFi | Proof of concept demonstration to technology integration | Technology demonstration for local video streaming using a high-power local Wi-Fi hotspot for on-scene personnel and cellular-denied environments. | 2019-03-29 |  |  | On schedule | 2019 | 90 Day |  |  |  | None
M5508031501 Requested, but no response. | M5 | 1.5.08.03 | ANL | AN1015080315 | Storage - Concept Evaluation | [8 empty] | WPM missed deadline for December reporting. Milestone status not provided.
M5508031503 Per Yung Liu: The FY10 M5 deliverable for ANL was to review/comment SNL M3 report on Storage Concept Evaluation which was completed on August 26, 2010. Ken Sorenson was the Account Manager. The three white papers are not deliverables. | M5 | 1.5.08.03 | ANL | AN1015080315 | Storage - Concept Evaluation | [8 empty] | Reviewed and provided comments on SNL L3 report Evaluation of Storage Concepts FY10 Final Report on August 26, 2010. Provided three white papers to SNL staff: 1) High-Burnup Fuel Transportation and Long-Term Dry-Cask Storage Issues (August 27, 2010) 2) Surveillance of Used Fuel in Transport and Storage with RFID Technology (August 31, 2010) 3) Managing Aging Effects on Used Fuel Dry Casks for Long-term Storage (September 2, 1010) This satisfies L-4 Milestone M5508031503
M5508040305 Requested, but no response. | M5 | 1.5.08.04 | LLNL | LL1015080403 | FEPs Categorization and Cross-Map |  |  | Provide support to the review and approval of the SNL L2 milestone
M5508040602 Per Mark Nutt: M5508040602, UFDC R&D Roadmap Workshop – We had the workshop (this is a level-5 milestone that was not a report). | M5 | 1.5.08.04 | ANL | AN1015080406 | R&D Roadmap and Workshop |  |  | UFDC R&D Roadmap Workshop
M5FT-12OR08220210 Per Matt Brainard: Document not available in PICS:NE. Deliverable form submitted without upload on 8/13/2012. DMS tracking number FCRD-UFD-2012-000538 entered. No other information available. | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Letter report describing the scope and requirements of the database | Letter report describing the scope and requirements of the database | Letter report describing the scope and requirements of the database | 2012-07-20 |  | 2012-07-20 |  | 2012 | Complete |  | Scaglione, John | Scaglione, John | None |  | FCRD-UFD-2012-000538
M5FT-12OR08220212 Per Matt Brainard: Letter report defining format of the database, Deliverable missing. Milestone marked complete, however the Deliverable Form in PICS:NE was submitted blank. Document Author: Rob LeFebvre. Document Owner: John Scaglione. Only other piece of information on the Deliverable Form is DMS No. FCRD-UFD-2012-000541. | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Letter report defining format of the database | Letter report defining format of the database | A letter report defining the format of the database | 2012-07-27 |  | 2012-07-27 |  | 2012 | Complete |  | LeFebvre, Rob | Scaglione, John | None |  | FCRD-UFD-2012-000541
M5FT-12SN08180251 Activity? No doc available. | M5 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Hansen, Frank | None | RESPEC Contract | Respec Contract | Sandia may need to issue a contract to RESPEC to support the Brine Migration Experimental Studies | 2012-09-28 10:00 |  | 2012-07-12 02:00 |  | 2012 | Complete |  |  |  | None |  | FCRD-UFD-2012-000547
M5FT-12SN08180251 Per Matt Brainard: RESPEC Contract Deliverable Form was submitted blank, however Milestone shows 100% complete under performance. No file uploaded. Frank Hansen listed as WPM. Robert Mackinnon CAM. No other comments or notes. DMS No. FCRD-UFD-2012-000547 referenced. ULR - Contract. | M5 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Hansen, Francis | None | RESPEC Contract | Respec Contract | Sandia may need to issue a contract to RESPEC to support the Brine Migration Experimental Studies | 2012-09-28 10:00 |  | 2012-07-12 02:00 |  | 2012 | Complete |  |  |  | None |  | FCRD-UFD-2012-000547
M5FT-14IN0802014 Per Sylvia Saltzstein: No document is available. | M5 | 1.02.08.02.01 | INL | FT-14IN080201 | Field Demonstration Support - INL | Marschman, Steve | None | Complete In-Service Inspections at Utilities | Complete In-Service Inspections at Utilities | The in-service inspections at Hope Creek and Diablo Canyon will be complete. Analysis of samples will continue at SNL. | 2014-03-31 06:00 |  | 2014-04-30 04:00 |  | 2014 | Completed Late | No report was required as part of this activity |  |  | None |  | FCRD-UFD-2014-000561
M5FT-15OR0810033 Per Matt Brainard: Provide thermal source term information to PNNL for inclusion in thermal analysis models, Deliverable marked OUO, which prohibits upload into PICS:NE. Other pertinent information: Narrative: “Source term data transmitted to PNNL.” Document Author: Henrik Liljenfeldt. Document Owner: John Scaglione. Deliverable Description: “Tabulated fuel assembly radial and axial thermal source term information transmitted electronically to PNNL for use in thermal analysis codes.” Main Document Title: “High burnup demonstration project thermal source term data.” Notes: “This is electronic information for use in building thermal analysis model input files.” OUO | M5 | 1.02.08.10.03 | ORNL | FT-15OR081003 | ST Analysis - ORNL | Scaglione, John | None | Provide thermal source term information to PNNL for inclusion in thermal analysis models | Thermal source terms for as-loaded casks | Calculate thermal source terms and transmit data to PNNL for use in thermal analysis models | 2015-03-27 | 2015-08-14 | 2015-08-14 |  | 2015 | Completed Late | High burnup demonstration project thermal source term data | Liljenfeldt, Henrik | Scaglione, John | OUO |  | FCRD-UFD-2015-000748
M5FT-15OR0905017 Per Matt Brainard: Import GC-859 data into UNF-ST&DARDS was originally planned for FY15 completion on 12/31/2014 and was superseded by Level 5 milestone M5FT-15OR0905017 - GC-859 implementation, which was completed on 9/30/2015. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Pre-released version of GC-859 has been implemented in UNF-ST&DARDS.” DMS Number: “FCRD-NFST-2015-000754”. Notes: “Pre-released version of GC-859 has been implemented in UNF-ST&DARDS. The official version of GC-859 has not been released by the Energy Information Administration (EIA) at this writing. The Unified Database will be updated with the official version of GC-859 when available. This activity will be included under FY16 Activity FT-16OR090105019, “Data collection and database synthesis in support of UNF characterization”. Please contact John M. Scaglione (scaglionejm@ornl.gov) or Kaushik Banerjee (banerjeek@ornl.gov) for additional information.” | M5 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | None | GC-859 implementation | GC-859 implementation | GC-859 implementation and automated depletion and decay calculations of all discharged assemblies | 2014-12-31 04:00 | 2015-09-30 | 2015-09-30 | Pre-released version of GC-859 has been implemented in UNF-ST&DARDS | 2015 | Completed Late | N/A |  |  | None |  | FCRD-NFST-2015-000754
M5FT-16AN090102049 There is no document to upload. | M5 | 1.02.09.01.02.05 | ORNL | FT-16OR09010205 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | None | Reference scenario to UDB validation | Reference Data into UNDB | Ensure that the data and details of the FY15 reference scenario are also included in the Unified Database. | 2015-12-18 03:00 | 2016-02-01 02:00 | 2016-02-01 01:00 |  | 2016 | Completed Late | There is no document to upload. |  |  | None |  | FCRD-NFST-2016-000704
M5FT-16OR090103013 Per Elena Kalinina: I don’t know who wrote the document. I was supporting the work, but I did not write this report (recommendations). | M5 | 1.02.09.01.02.07 | SNL | FT-16SN09010207 | Waste Management System Architecture Analysis - SNL | Kalinina, Elena | None | Support DOE by Developing Way to Display CURIE Map on DOE Website | Display CURIE map on the DOE website | Support DOE by developing way to display CURIE Map directly on the DOE website. A prerequisite to this milestone is DOE releasing their website and DOE having the ability to host the 'system' that is created to support the CURIE maps on DOE's website. | 2016-02-26 02:00 |  | 2016-02-26 |  | 2016 | Complete | Support DOE by Developing Way to Display CURIE Map on DOE Website |  |  | None |  | FCRD-NFST-2016-000706
M5FT-16OR0901050111 Per Josh Jarrell: No report available | M5 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | None | Dry run generation of inventory report from unified database | Draft inventory report generated through UNF-ST&DARDS | This milestone will generate the inventory report and identify gaps in data that need to be filled in to support the ability to dynamically generate an inventory report from the unified database at anytime. | 2016-03-18 04:00 | 2016-04-15 | 2016-04-30 |  | 2016 | Completed Late | This is a software capability | Josh Peterson | Scaglione, John | None |  | FCRD-NFST-2016-000709
M5SF-17OR0102010212 Per Matt Brainard: Complete defueling of rod segments for shipment to ANL, originally planned for FY18 completion on 8/31/2018. Milestone superseded by M4SF-18OR0102010214 - Defuel and ship defueled cladding to ANL, which was planned for FY19 completion on 3/29/2019. Milestone was re-superseded by M4SF-19OR010201025 - Defuel and ship defueled cladding to ANL, which was completed on 5/9/2019. Deliverable attached. | M5 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | None | Complete defueling of rod segments for shipment to ANL | Completed shipping of cladding to ANL | Milestone to complete sample preparation including defueling of cladding segments for ANL testing | 2018-08-31 |  |  | This work has not started and will be impacted by budget issues if adequate funding isn't provided to ORNL in a timely fashion | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000247
M4SF-19OR010304074 Per Matt Brainard: The Subject milestone was reported as cancelled during the September reporting period. There is no deliverable to collect | M4 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Prepare BWR data evaluation report | SFCOMPO BWR data evaluation report | Draft evaluation reports for a boiling water reactor (BWR) dataset will be prepared by ORNL for independent peer review by the Technical Review Group for the SFCOMPO database. The report will include a detailed uncertainty analysis of the data. | 2018-12-28 |  |  |  | 2019 | Cancelled |  |  |  | None
M3SF-19OR010304075 Per Matt Brainard: The Subject milestone was reported as cancelled during the September performance reporting period. There is no deliverable to collect. “Work on this deliverable has been terminated in order to preserve funding. No FY2020 funding for this work package is planned.” | M3 | 1.08.01.03.04.07 | ORNL | SF-19OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | Update Experimental Plan for Commercial SNF Degradation in Repository Environments | Updated Experimental Plan for Commercial SNF Degradation in Repository Environments | Collaborate with SNL, PNNL, and ANL to develop a draft experimental test plan for commercial SNF degradation in select repository environments. | 2019-08-30 |  |  |  | 2019 | Cancelled |  |  |  | None
M3SF-19PN010203028 Per Matt Brainard: During the FY20 work package planning phase, it was determined that the Analysis work package this milestone was linked to would no longer be supported in FY20, and therefore a FY20 follow on work package does not exist. All remaining Analysis funds were redirected to Thermal and Drying activities for FY20. Therefore this milestone may be deemed “canceled” unless otherwise noted by someone else. | M3 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Compare FAST/FRAPCON model with sister rod data | FAST/FRAPCON Model Validation Against Sister Rods | When data from ORNL and PNNL sister rod characterization becomes available (pressures, volumes, fission gas release, total hydrogen content, and oxide layer thickness) compare against blind predictions. | 2019-05-31 |  |  |  |  | Cancelled
M3SF-19LB010308064 Superseded by: M3SF-20LB010308062 | M3 | 1.08.01.03.08 | LBNL | SF-19LB01030806 | Engineered Barrier System International Collaborations - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19-FY20 progress report | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19-FY20 progress report |  | 2019-10-25 |  |  |  | 2019 | Cancelled |  |  |  | None
M4SF-19LA010308014 Per Florie Caporuscio: No interim report. It's included in the FY20 final report. | M4 | 1.08.01.03.08.01 | LANL | SF-19LA01030801 | Engineered Barrier System R&D - LANL | Caporuscio, Florie | McMahon, Kevin | interim report - EBS R&D - LANL | interim report - EBS R&D - LANL | interim report - EBS R&D - LANL | 2019-10-25 |  |  |  | 2019 | Cancelled |  |  |  | None
M4SF-19PN020408051- Superseded by: M4SF-20PN020408041 | M4 | 1.08.02.04.08.05 | PNNL | SF-19PN02040805 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - PNNL | Nutt, Mark | Howard, Rob | Friction Stir Weld Repair Demonstration Status | Friction Stir Weld Repair Demonstration Status | Friction Stir Weld Repair Demonstration Status | 2019-11-29 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-20SN010207017 Superseded by- M2SF-21SN010207055 | M2 | 1.08.01.02.07 | SNL | SF-20SN01020701 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | FY20 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | FY20 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations |  | 2020-11-11 |  |  |  | 2020 | In progress |  |  |  | None
M2SF-20OR010201023 Superseded by- M2SF-21OR010201032 | M2 | 1.08.01.02.01 | ORNL | SF-20OR01020102 | Sibling Pin Testing - ORNL | Montgomery, Rose | Saltzstein, Sylvia | FY2020 ORNL High Burnup Confirmatory Demo Sibling Rod Testing Results | ORNL Sibling Rod Testing Results (FY20) |  | 2020-11-30 |  |  | Note: Milestone superseded by "M2SF-21OR010201032 - FY2020 ORNL High Burnup Confirmatory Demo Sibling Rod Testing Results" under FY 2021 work package SF-21OR01020103 - Fuel Integrity Testing and Analysis - ORNL. The milestone remains due 11/30/2020. | 2020 | Postponed |  |  |  | None
M2SF-20PN010201036 Superseded by- M2SF-21PN010201055 | M2 | 1.08.01.02.01 | PNNL | SF-20PN01020103 | Sibling Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | FY20 Sibling Pin Testing Results | FY20 Sibling Pin Test Results |  | 2020-11-30 |  |  | Note: Milestone superseded by "M2SF-21PN010201055 - FY20 Sibling Pin Testing Results" under FY 2021 work package SF-21PN01020105 - Fuel Integrity Testing and Analysis - PNNL. The milestone remains due 11/30/2020. | 2020 | Postponed |  |  |  | None
M2SF-20SN010309013 Superseded by- M2SF-21SN010309012 | M2 | 1.08.01.03.09 | SNL | SF-20SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, Dave | Camphouse, Chris | Annual status update for OWL and Waste Form Characteristics | Annual status update for OWL and Waste Form Characteristics |  | 2020-11-30 |  |  | Note: Milestone superseded by "M2SF-21SN010309012 - Annual Status Update for OWL and Waste Form Characteristics" under FY 2021 work package SF-21SN01030901 - OWL - Inventory - SNL. The milestone is now due 1/29/2021. | 2020 | Postponed |  |  |  | None
M2SF-20OR0204050113 Superseded by- M2SF-21OR020401017 | M2 | 1.08.02.04.05 | ORNL | SF-20OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | UNF-ST&DARDS 4.1 Release | UNF-ST&DARDS 4.1 Release |  | 2020-12-18 |  |  | Note: Milestone superseded by "M2SF-21OR020401017 - UNF-ST&DARDS 4.1 Release" under FY 2021 work package SF-21OR02040101 - Commercial SNF Characterization - ORNL. The milestone remains due 12/18/2020. | 2020 | Postponed |  |  |  | None
M2SF-20SN010305062 Superseded by- M2SF-21SN010305061 | M2 | 1.08.01.03.05 | SNL | SF-20SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Repository-Scale Performance Assessment Incorporating Postclosure Criticality | Analysis of Repository Performance Including Postclosure Criticality |  | 2021-09-30 |  |  | Note: Milestone superseded by "M2SF-21SN010305061 - Repository-Scale Performance Assessment Incorporating Postclosure Criticality" under FY 2021 work package SF-21SN01030506 Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL. The milestone remains due 9/30/2021. | 2020 | Postponed |  |  |  | None
M5SF-20OR020303028- Superseded by M5SF-21OR020303052 | M5 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill |  | Letter Report on Organizational Coordination, Agreements, and Planning | Letter Report on Organizational Coordination, Agreements, and Planning | Letter report will describe the coordination effort that is a complex, major activity in this first phase. Project planning will need to be coordinated with multiple teams at national labs and the Navy as well as the management and programming teams at TRANSCOM and the remaining SMS design team at 3C Telemetry. Each organization will play an important role in developing a viable and workable project plan that will require funding from multiple sponsors and contracting actions for the subcontractors. A number of technical meetings will be needed for planning and coordination. | 2020-10-30 |  |  | On schedule. | 2020 | 90 Day |  |  |  | None
M4SF-20OR020402055- Superseded by M4SF-21OR020402101 | M4 | 1.08.02.04.02.05 | ORNL | SF-20OR02040205 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | Report Summarizing NGSAM Testing | Report Summarizing NGSAM Testing | Report summarizing NGSAM testing | 2020-11-30 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M4SF-19SN010101022- Superseded by M4SF-20SN010101022 | M4 | 1.08.01.01.01.02 | SNL | SF-19SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | Conduct KM Focus Group | Focus Group Report | Conduct Knowledge Management Focus Group with Staff | 2019-12-20 |  |  | Workshops held 9/30 & 10/1. Finalizing Report | 2019 | 90 Day |  |  |  | None
M4SF-19SN010101023- Superseded by M4SF-20SN010101023 | M4 | 1.08.01.01.01.02 | SNL | SF-19SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | KM Workshop | Briefing on KM Workshop | Plan and deliver KM Workshop | 2019-12-20 |  |  | Workshop dates Dec 17-19 | 2019 | 90 Day |  |  |  | None
M4SF-19SN010101024- Superseded by M4SF-20SN010101024 | M4 | 1.08.01.01.01.02 | SNL | SF-19SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | Conduct Deep Dives | Deep Dive Conducted | Conduct Deep Dive information sessions as a follow-on to the knowledge collection from Workshops | 2019-12-27 |  |  | Deep dives will be scheduled after the Workshop | 2019 | 90 Day |  |  |  | None
M3SF-20SN010304102- Superseded by M3SF-21SN010304112 | M3 | 1.08.01.03.04.10 | SNL | SF-20SN01030410 | GDSA - FEPs Reevaluation for ABD Glass - SNL | Price, Laura | Stein, Emily | Summary of FEP and preclosure safety reassessment for SRS ABD Glass Waste Form | Summary Report for Reassesment of ABD Glass WF | Report Summarizing the status of evaluations | 2020-11-30 |  |  | We anticipate completing this deliverable on time. | 2020 | 90 Day |  |  |  | None
M3SF-20OR0103050126- Superseded by M3SF-21OR010305125 | M3 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | DPC criticality analysis with fuel/basket modification | DPC criticality analysis with fuel/basket modification | Analyze various fuel loading and basket modification options geared towards criticality control in a repository including loading assemblies with disposal control elements, loading DPCs with additional neutron absorber inserts, and rechanneling BWR assemblies with neutron absorber materials. | 2020-11-06 |  |  | On Schedule | 2020 | 90 Day |  |  |  | None
M3SF-20OR0204050111- Superseded by M3SF-21OR020401015 | M3 | 1.08.02.04.05.01 | ORNL | SF-20OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Develop new criticality templates | Enhancement of UNF-ST&DARDS Criticality Analysis Capability | Develop 21-assembly PWR criticality template based on available TAD/STAD concepts. Perform sensitivity analysis on basket design parameters (e.g., basket neutron absorber). Develop an optimized loading approach from criticality standpoint using assemblies from the pool or already loaded dual-purpose canisters. Additionally, develop 2 commercial DPC criticality templates (subject to availability of drawings). | 2020-11-20 |  |  | On Schedule | 2020 | 90 Day |  |  |  | None
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | M3 Milestone report for the design concept for canister inspection and remediation facility at an ISF | 2019-08-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | M3 Milestone report for the design concept for canister inspection and remediation facility at an ISF | 2019-08-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 |  | SRNL | [7 empty] | due 11/30/2019 |  |  |  | 2019 |  |  |  |  | M2SF-18SR020201023 - Canister Inspection and Remediation Facility – Report, Originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M2SF-19SR020201022 - Canister Inspection and Remediation Facility – Report, which isn’t due until FY20 on 11/30/2019. No Deliverable to provide as of yet.
M3SF-19SR020201027- Superseded by M3SF-20SR020201027 | M3 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Leak Check Testing Status Report | Canister Leak Check Status Report | Provide a status report on the canister leak testing to date. | 2019-11-15 |  |  |  | 2019 |  |  |  |  | None
M3SF-19SR020201028- Superseded by M2SF-20SR020201022 | M3 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Repackaging Facility Concepts | Repackaging Facility Concept | Develop a Repackaging Facility concepts for SNF in existing DPC's to one more suitable to repository emplacement. | 2019-11-30 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M3SF-20PN0102070412 Supersedd by- M3SF-21PN010207025 | M3 | 1.08.01.02.07.04 | PNNL | SF-20PN01020704 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Updated Deposition Model Report | Updated Deposition Model | Update model with new phenomena and using input data provided by SNL | 2020-10-23 | 2020-12-15 18:00 | 2020-12-27 | Delayed due to COVID shutdown and staff being asked to accelerate deposition modeling to support the Lead Canister Field Demonstration task. | 2021 | Expected Late |  |  |  | None

## NE81 DR FY10-FY21
Milestone ID Number | Level | WBS | Site | WP Number | WP Title | FCTWPM | CAM | Milestone Title | Deliverable Title | Deliverable Description | Estimated Finish | Revised Finish | Actual Finish | Narrative | FY | Status | Main Document Title | Document Author/Creator | Document Owner | CUI Type | Uploaded Document Name | DMS Tracking Number | Keywords
M3FT-12LA0807013 | M3 | 1.02.08.07.01 | LANL | FT-12LA080701 | Regional Geology & Tectonic Hazard - LANL | Perry, Frank | McMahon, Kevin | Regional Geology and Tectonic Hazards - FY11 Status Report | Regional Geology and Tectonic Hazards - FY11 Status Report | FY11 Status Report on Regional Geology and Tectonic Hazards | 2011-10-28 02:00 |  | 2011-10-26 02:00 |  | 2012 | Complete |  | Perry, Frank | Perry, Frank | None | LANL UFCD Regional Geology Status Report 10-11.pdf | FCRD-USED-2012-000002
M4FT-12PN0806052 | M4 | 1.02.08.06.05 | PNNL | FT-12PN080605 | Engineered Barrier Systems (EBS) Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Waste Form Degradation and Radionuclide Mobilization Testing Plan | Waste Form Degradation and Radionuclide Mobilization Testing Plan | The testing plan will focus on radiolysis modeling development, the preparation of SimFuels (RADFUELS), the experiments that will be used in radiolysis modeling validation, corrosion tests to determine degradation mechanisms of used spent oxide and other fuels, and the release of important radionuclides. Collaboration between ANL, SNL and PNNL will ensure that key processes are being investigated. | 2011-12-02 14:00 |  | 2011-12-02 03:00 |  | 2012 | Complete |  | Buck, Edgar | Buck, Edgar | None | PNNL_UFD-Plan_FINAL_2011_Dec_2.pdf | FCRD-UFD-2012-000598
M4FT-12SN0808043 input to M2FT-14SN0804051 | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 6) Annotated Outline for Generic Safety Case | 6) Annotated Outline for Generic Safety Case | A draft report of a comprehensive annotated outline covering the information needed to produce a safety case for the safe disposal of nuclear waste in repositories mined in generic salt, crystalline rock, and clays/shales as well as in a deep borehole. This outline will serve as the basis for the Saftey Case report due in March. | 2011-12-15 06:00 |  | 2011-12-05 02:00 |  | 2012 | Complete |  |  |  | None | Generic Safety Case Annotated Outline_Milestone M4FT-12SN0808043.pdf | FCRD-UFD-2012-000603
M4FT-12AN0806011 | M4 | 1.02.08.06.01 | ANL | FT-12AN080601 | Engineered Barrier Systems (EBS) Evaluations - ANL | Ebert, William | McMahon, Kevin | Experimental plan for electrochemical corrosion studies | Experimental plan | Experimental plan to address issues identified by literature review and consulation with colleagues at PNNL and SNL. | 2012-01-06 02:00 | 2012-01-09 01:00 | 2012-01-06 01:00 |  | 2012 | Complete |  | Jerden, James | Swift, Peter | None | M4FT12AN0806011_UFD_test plan (2).pdf M4FT12AN0806011_UFD_test_plan.pdf | FCRD-USED-2012-000041 | uranium oxide, corrosion, oxidative dissoltuion
M3FT-12AN0814017 | M3 | 1.02.08.14.01 | ANL | FT-12AN081401 | CX Perspectives on NW Management - ANL | Vienna, John | Nutt, Mark | Initial Draft Set of Performance Metrics Relevant to the Used Fuel Disposition Campaign for the 2013 Screening | Initial Draft Set of Performance Metrics Relevant to the Used Fuel Disposition Campaign for the 2013 Screening | Milestone to prepare a draft set of Performance Metrics Relevant to the UFD for the 2013 screening assessment supporting Fuel Cycle Options. | 2012-01-31 02:00 |  | 2012-01-31 02:00 |  | 2012 | Complete |  |  |  | None | Waste Management Metrics - 2013 Fuel Cycle Evaluation (Final ITR).pdf | FCRD-UFD-2012-000061
M4FT-12LA0814021 Input to SNL L-2 milestone M2FT-12SN0814052 | M4 | 1.02.08.14.02 | LANL | FT-12LA081402 | CX Perspectives on NW Management - LANL | Robinson, Bruce | Nutt, Mark | Advanced Nuclear Fuel Cycle Affects on the Treatment of Uncertainty in the Long-Term Assessment of Geologic Disposal Systems - Natural System Input | Advanced Nuclear Fuel Cycle Affects on the Treatment of Uncertainty in the Long-Term Assessment of Geologic Disposal Systems - Natural System Input | Milestone will document the investigation of what aspects of quantifying, characterizing, and representing the uncertainty associated with geologic disposal are affected (i.e., reduced) by implementing different advanced nuclear fuel cycles (partitioning and transmutation scenarios) - focusing on the natural system. Input to SNL L-2 milestone M2FT-12SN0814052 | 2012-02-29 09:00 | 40984.25 | 40984.0833 |  | 2012 | Completed Late |  | Robinson, Bruce | Robinson, Bruce | None | LANL M4FT-12LA0814021.docx | FCRD-UFD-2012-000573
M4FT-12LL0814031 | M4 | 1.02.08.14.03 | LLNL | FT-12LL081403 | CX Perspectives on NW Management - LLNL | Blink, Jim | Nutt, Mark | Advanced Nuclear Fuel Cycle Effects on the Treatment of Uncertainty in the Long-Term Assessment of Geologic Disposal Systems - EBS Input | Advanced Nuclear Fuel Cycle Affects on the Treatment of Uncertainty in the Long-Term Assessment of Geologic Disposal Systems - EBS Input | Milestone will document the investigation of what aspects of quantifying, characterizing, and representing the uncertainty associated with geologic disposal are affected (i.e., reduced) by implementing different advanced nuclear fuel cycles (partitioning and transmutation scenarios) - focusing on the engineered barrier system. | 2012-02-29 12:00 |  | 2012-02-29 03:00 |  | 2012 | Complete |  | Sutton, Mark | Blink, James | None | M4FT-12LL0814031_FINAL.pdf | FCRD-UFD-2012-000576
M4FT-12SN0804033 | M4 | 1.02.08.04.03 | SNL | FT-12SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Parameter Uncertainty for Generic Design Concepts and Thermal Analysis | Parameter Uncertainty for Generic Disposal Concepts and Thermal Analysis | Develop uncertainty ranges for repository design concepts, thermal characteristics for engineered and natural materials (properties, temperature limits), and characteristics of the advanced waste streams selected for analysis (inventory, waste forms). | 2012-03-30 04:00 | 41010.0833 | 41017.0833 |  | 2012 | Completed Late |  | Hardin, Ernest | Hardin, Ernest | None | Parameter Uncertainty Report (FCRD-UFD-2012-000097 R0).pdf | FCRD-UFD-2012-000097 | repository thermal analysis
M2FT-12SN0814052 | M2 | 1.02.08.14.05 | SNL | FT-12SN081405 | CX Perspectives on NW Management - SNL | Rechard, Rob | Nutt, Mark | Report describing Advanced Nuclear Fuel Cycle Effects on the Treatment of Uncertainty in the Long-Term Assessment of Geologic Disposal Systems | Influence of Nuclear Fuel Cycle Options on Uncertainty of Long-Term Performance of Geologic Disposal Systems | This milestone will discuss what aspects of quantifying ,characterizing , and representing the uncertainty associated with geologic disposal are affected (i.e., reduced) by implementing different advanced nuclear fuel cycles (partitioning and transmutation scenarios). Key uncertainties associated with the performance of the natural barrier system, engineered barrier system , and total system for disposal system concepts in salt, clay/shale, crystalline, and deep borehole environments will be evaluated to identify how they are affected by different fuel cycle scenarios that result in different waste forms and radionuclide inventories. | 2012-03-30 19:00 | 2012-07-23 06:00 | 2012-07-23 02:00 |  | 2012 | Completed Late |  | Rechard, Rob | Rechard, Rob | None | Cover Sheet Appendix E for Uncertainty Report Signed Stockman Halsey Voegele.pdf Influence of Adv Fuel cycles on Uncertainty Final.docx | FCRD-UFD-2012-000088 | Uncertainty of geologic disposal
M3FT-12SR0814063 | M3 | 1.02.08.14.06 | SRNL | FT-12SR081406 | CX Perspectives on NW Management - SRNL | Smith, Pat | Nutt, Mark | Salt Study - Draft Results (2-3 Page Executive Summary-Type Format) | Salt Study - Draft Results (2-3 page executive summary-type format) | The Salt Study will support the evaluation of disposal of DOE high-level waste and spent nuclear fuel in a salt repository by examining a potential generic salt repository for the disposal of government-managed nuclear wastes. This Study will provide information to inform potential recommendations by the DOE's Management and Disposition Task Force. Desired outputs to include: scope and structure; cost and schedule of estimates for design, construction, startup, operation and closure of identified scenarios; and cost per waste package placement for each scenario. | 2012-04-20 |  | 2012-04-20 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | Defense Waste Salt Reporitory Exec Summary.pdf | FCRD-UFD-2012-000107 | Salt Study, Repository
M4FT-12LL0806041 Draft text and input for Level 2 ilestone. | M4 | 1.02.08.06.04 | LLNL | FT-12LL080604 | Engineered Barrier Systems (EBS) Evaluations - LLNL | Blink, James | McMahon, Kevin | Thermodynamic properties report | Input to SNL L2 milestone on Evaluation of Generic EBS Design Concepts | Provide draft text and input for the SNL L2 milestone in June | 2012-05-01 03:00 |  | 41030.125 |  | 2012 | Complete |  | Wolery, Tom | Wolery, Tom | None | M4FT-12LL0806041_f_TJW_UFDC_Clays_2012-5-1.pdf | FCRD-UFD-2012-000432
M3FT-12SR0814064 | M3 | 1.02.08.14.06 | SRNL | FT-12SR081406 | CX Perspectives on NW Management - SRNL | Carter, Joe | Nutt, Mark | Salt Study - Final Report | Salt Study - Final Report | The Salt Study will support the evaluation of disposal of DOE high-level waste and spent nuclear fuel in a salt repository by examining a potential generic salt repository for the disposal of government-managed nuclear wastes. Report to include: scope and structure similar to the 2011 Generic Study; cost and schedule estimates for design, construction, startup, operation and closure identified in scenarios; and cost per waste package placement for each scenario. | 2012-05-15 |  | 2012-05-15 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | FCRD-UFD-2012-000113.pdf | FCRD-UFD-2012-000113
M3FT-12LA0806021 ULR. DRAFT. | M3 | 1.02.08.06.02 | LANL | FT-12LA080602 | Engineered Barrier Systems (EBS) Evaluations - LANL | Caporuscio, Florie | McMahon, Kevin | EBS - LANL experimental clay metal studies | EBS - LANL experimental clay metal studies | Final report to include experimental activities will elucidate important aspects of clay-barrier interactions at elevated pressures and temperatures such as metal/barrier interface degradation, phase transformation, phase separation and transport, passivation layers and formation of secondary solids. Novel analytical techniques will be used to characterize fluid composition, phase identification of degradation products, and textural relations. | 2012-05-15 06:00 |  | 41040.0833 |  | 2012 | Complete |  | Caporuscio, Florie | Caporuscio, Florie | None | EBS LANL milestone draft deliverable.pdf | FCRD-UFD-2012-000675
M3FT-12LB0806034 | M3 | 1.02.08.06.03 | LBNL | FT-12LB080603 | Engineered Barrier Systems (EBS) Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Investigation of reactive transport and coupled THM processes in EBS: FY12 Report | Investigation of reactive transport and coupled THM processes in EBS: FY12 Report | The report will document progress made in the three LBNL activities | 2012-05-16 02:00 |  | 2012-05-18 03:00 |  | 2012 | Completed Late |  | Rutqvist, Jonny | Liu, Hui-Hai | None | FCRD- EBS FY12 LBNL Report (2).pdf | FCRD-UFD-2012-000125
M4FT-12LA0807054 | M4 | 1.02.08.07.05 | LANL | FT-12LA080705 | Natural Systems Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Radionuclide interaction and transport: CFM collaboration & column experiments | Report CFM collaboration & column experiments on U and Np transport | This activity will focus on better understanding of radionuclide transport in heterogeneous geologic media. The processes considered include radionuclide speciation/sorption and colloid-facilitated transport under a wide range of physical and chemical conditions (e.g., various disposal environments). LANL will provide inputs on international Colloid Formation and Migration (CFM) collaboration and column experiments on U and Np transport in saturated geologic media. | 2012-05-21 12:00 |  | 2012-06-04 02:00 |  | 2012 | Completed Late |  | Reimus, Paul | Reimus, Paul | None | UFD_Milestone_Reimus.pdf | FCRD-UFD-2012-000569
M4FT-12LB0807064 | M4 | 1.02.08.07.06 | LBNL | FT-12LB080706 | Natural Systems Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Modeling of radionuclide transport in clays | Report on radionuclide diffusion in clay formations | This activity will focus on better understanding of radionuclide transport in heterogeneous geologic media. The processes considered include radionuclide speciation/sorption and colloid-facilitated transport under a wide range of physical and chemical conditions (e.g., various disposal environments). LBNL will provide model inputs on evaluating how the THMC coupled processes impact radionuclide diffusion in clay formations. | 2012-05-21 13:00 |  | 2012-05-21 03:00 |  | 2012 | Complete |  | Zheng, Liange | Liu, Hui-Hai | None | M4FT-12LB0807064.pdf | FCRD-UFD-2012-000128
M3FT-12SN0807087 | M3 | 1.02.08.07.08 | SNL | FT-12SN080708 | Natural Systems Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Radionuclide interaction with clays and colloids | Report on radionuclide interactions with clays and colloids | This activity will focus on better understanding of radionuclide transport in heterogeneous geologic media. The processes considered include radionuclide speciation/sorption and colloid-facilitated transport under a wide range of physical and chemical conditions (e.g., various disposal environments). SNL will provide inputs on mechanistic understanding of radionuclide interactions with clays and colloids. | 2012-05-21 18:00 |  | 2012-05-21 02:00 |  | 2012 | Complete |  | Miller, Andy | Wang, Yifeng | None | Milestone M3FT-12SN0807087.pdf | FCRD-UFD-2012-000121 | iodine, caly, sorption, ion exchange, natural barrier system
M4FT-12LB0808032 input to M2FT-12SN0808042 | M4 | 1.02.08.08.03 | LBNL | FT-12LB080803 | Generic Disposal System Level Modeling - LBNL | Liu, Hui-Hai | McMahon, Kevin | Diffusion Modeling in a Generic Clay Repository: Impacts of heterogeneity and electro-chemical process | Diffusion Modeling in a Generic Clay Repository: Impacts of heterogeneity and electro-chemical process | this work is to contribute to Generic System Model Refinement activity (Work package FT-12SN080804) by (1) developing a defensible approach for incorporating effects of electro-chemical processes on diffusion in clay formations and (2) evaluating/incorporating impacts of subsurface heterogeneity. | 2012-05-29 08:00 |  | 2012-05-26 03:00 |  | 2012 | Complete |  |  |  | None | M4FT-12LB0808032.pdf | FCRD-UFD-2012-000127
M3FT-12SN08180226 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Test Plan Revision Based on External Review and Prioritized Test Matrix | Test plan for Hot Granular Salt Consolidation | A revision to the existing test plan will be made (a UFD Milestone) and will include a prioritized test matrix based on external review by international peers. | 2012-06-01 08:00 |  | 2012-06-01 02:00 |  | 2012 | Complete |  | Bauer, Stephen | Bauer, Stephen | None | 20120606_Final_SDI_Test_Plan_Crushed_Salt_Consolidation_Revision_1.pdf | FCRD-UFD-2012-000437
M4FT-12LL0804011 | M4 | 1.02.08.04.01 | LLNL | FT-12LL080401 | DR Thermal Load Management & Design Concepts - LLNL | Sutton, Mark | McMahon, Kevin | Input to SNL L3 and L2 milestones | LLNL input to SNL milestones | Report on progress in this area, including (1) TOPAZ3D FEM models to verify the FY11 analytical model and to explore the evolution of temperature in salt considering complex geometry and backfill consolidation, (2) Benchmark the analytical and TOPAZ3D models to the 3D salt repository calcs previously published, (3) Address uncertainties in thermal model inputs, including rock properties, engineered material properties, and design parameters, (4) Analyze additional reference concepts and waste streams | 2012-06-15 10:00 | 2012-06-12 03:00 | 2012-06-12 03:00 |  | 2012 | Complete |  | Greenberg, Harris | Sutton, Mark | None |  | FCRD-USED-2012-000405
M2FT-12SN0806061 | M2 | 1.02.08.06.06 | SNL | FT-12SN080606 | Engineered Barrier Systems (EBS) Evaluations - SNL | Jove-Colon, Carlos | McMahon, Kevin | Report on the Evaluation of Generic EBS Design Concepts and Process Models: Implications to EBS Design Optimization | Evaluation of Generic EBS Design Concepts and Process Models: Implications to EBS Design Optimization | This activity will comprise the description of key EBS process models to evaluate generic design concepts and their potential application as tools for repository design optimization. It will also include thermodynamic database development and preliminary studies on MD simulations in clay. | 2012-06-16 02:00 |  | 41075.0833 |  | 2012 | Complete |  | Jove Colon, Carlos | Jove Colon, Carlos | None | M2FT-12SN0806061_Milestone_Report_UFDC_EBS_FY12_R-A.pdf | FCRD-UFD-2012-000140
M2FT-12LL0807071 | M2 | 1.02.08.07.07 | LLNL | FT-12LL080707 | Natural Systems Evaluations - LLNL | Kersting, Annie | McMahon, Kevin | Report on Radionuclide interaction and transport in representative geologic environments | Report on radionuclide interaction with geologic media | This activity will focus on better understanding of radionuclide transport in heterogeneous geologic media. The processes considered include radionuclide speciation/sorption and colloid-facilitated transport under a wide range of physical and chemical conditions (e.g., various disposal environments). In FY12, the work will include radionuclide (e.g., Pu, Np, and I) sorption and colloid formation and stability in clay materials and initiate international collaboration. LLNL will focus on Pu interactions with clays and iron oxides and be responsible for submission of a level 2 milestone on radionuclide interaction and transport in geologic media. | 2012-06-20 07:00 |  | 2012-06-20 03:00 |  | 2012 | Complete |  | Kersting, Annie | Kersting, Annie | None | NS UFD M2 LLNL7-20-2012f.pdf | FCRD-UFD-2012-000154 | Radionuclides Pu colloids
M4FT-12OR0804021 Preliminary Draft. | M4 | 1.02.08.04.02 | ORNL | FT-12OR080402 | DR Thermal Load Management & Design Concepts - ORNL | Howard, Rob | McMahon, Kevin | Surface Facility Design Concepts | Preliminary Surface Facility Concepts for Waste Repositories | Develop descriptions of repository surface facilities and other repository infrastructure needed for each reference design concept, sufficient for cost estimation. | 2012-06-29 04:00 | 2012-07-13 | 2012-07-13 |  | 2012 | Completed Late |  | Howard, Rob | Howard, Rob | None | Surface Facilities Description_29_June_2012_Preliminary.docx | FCRD-UFD-2012-000586
M3FT-12SN08180219 This Users Guide is Appendix C in FCRD-UFD-2012-000380, M2FT-12SN08180223 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | User's Guide for Platform and organization structure for data management | User's Guide for Platform and organization structure for data management | By June 29, 2012 the database/platform for electronic filing of all of the technical information gathered in this task will be in place. | 2012-06-29 10:00 |  | 41089.0833 |  | 2012 | Complete |  | Kuhlman, Kris | Kuhlman, Kris | None | SITED-user-guide-and-data-management-organization.docx |  | User's Guide, SITED, Database, Salt Research
M2FT-12SN0808041 | M2 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | A Safety Case for the Generic Disposal of Nuclear Waste. | A Saftey Case for the Generci Disposal of Nuclear Waste | The case for the safety of a generic repository will be describe along with the objectives and necessary characteristic of a safety case. A comprehensive set of components and how these components contribute to the safety case will be provided | 2012-06-30 09:00 |  | 41090.0833 |  | 2012 | Complete |  | Vaughn, Palmer | Vaughn, Palmer | None | FCRD-UFD-2012-000146_Rev_0.pdf | FCRD-UFD-2012-000146 | Safety Case, Safety Assessment, Scenarios, Features, Events, and Processes, Dsiposal System, Dispoal of Nuclear Waste, Disposal Analogs
M3FT-12SN08180229 ULR. The current official version of this document is available on the Sandia National Laboratories FCT SharePoint site. A printed copy of this document may not be the version currently in effect. | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Develop Test plan for determining thermal conductivity of granular salt as a function of porosity and temperature | Test Plan for Thermal Conductivity as a Function of Porosity and Temperature | Test plan for determining thermal conductivity of granular salt as a function of porosity and temperature | 2012-07-09 06:00 |  | 2012-07-09 02:00 |  | 2012 | Complete |  | Bauer, Stephen | Bauer, Stephen | None | SAND2012-5987P.pdf
M4FT-12LA0808051 | M4 | 1.02.08.08.05 | LANL | FT-12LA080805 | Advanced Disposal System Modeling - LANL | Robinson, Bruce | McMahon, Kevin | Requirements and Assessment of Potential Framework Tools for Generic Disposal System Models | Requirements and Assessment of Potential Framework Tools for Generic Disposal System Models | Report summarizing the assessment conducted to identify requirements for future GDSM modeling tools, and the results of the gap analysis identifying the differences between what is required and what is available in existing codes and codes under development. | 2012-07-13 08:00 |  | 2012-08-09 02:00 |  | 2012 | Completed Late |  | Robinson, Bruce | Robinson, Bruce | None | Disposal Framework Report.pdf | FCRD-UFD-2012-000571
M4FT-12SN0808045 | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 2) Generic Natural System Conceptual Model and Numerical Architecture | 2) Generic Natural System Conceptual Model and Numerical Architecture | Draft report describing a generic conceptual model spanning the FEPS characteristic of the natural system in the host rock types of salt, clay/shale, crystalline rock, and the deep borehole concept. Develop numerical architecture and indentify numerical model implementations of the conceptual model in a manner that minimizes the number of interfaces, abstractions, and numbers of distinct numerical codes. This report will serve as a basis for a chapter in the November Level 2 milestone report. | 2012-07-16 06:00 |  | 41106.0833 |  | 2012 | Complete |  | Arnold, Bill | Arnold, Bill | None | GDSM_Natural_Systems_FY12_milestone_report_final.pdf | FCRD-UFD-2012-000179
M4FT-12SN0808046 Report shows as M4FT-12SN0808046-3 | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 3) Generic Engineered Barrier System Conceptual Model and System Architecture | 3) Generic Engineered Barrier System Conceptual Model and System Architecture | Draft report describing a generic conceptual model spanning the FEPS characteristic of the EBS and Near Field in the host rock types of salt, clay/shale, crystalline rock, and the deep borehole concept. Develop numerical architecture and indentify numerical model implementations of the conceptual model in a manner that minimizes the number of interfaces, abstractions, and numbers of distinct numerical codes. This report will serve as a basis for a chapter in the November Level 2 milestone report. | 2012-07-16 06:00 |  | 41106.0833 |  | 2012 | Complete |  | Hardin, Ernest | Hardin, Ernest | None | Generic EBS Model and System Architecture Final.pdf | FCRD-UFD-2012-000180 | Generic EBS Conceptual Model and Numerical Architecture, Engineered Barrier System, Waste Form, Waste Package, Sopurce Term, Inventory
M4FT-12LL0806043 | M4 | 1.02.08.06.04 | LLNL | FT-12LL080604 | Engineered Barrier Systems (EBS) Evaluations - LLNL | Blink, James | McMahon, Kevin | DSEF Version 2.0 Progress Report | DSEF Version 2.0 | Complete Version 2.0 of the DSEF, including improvements to the backbone and the thermal module(s), and the initial release of the cost module(s) | 2012-07-20 10:00 | 2012-08-31 12:00 | 2012-09-04 03:00 |  | 2012 | Completed Late |  | Greenberg, Harris | Greenberg, Harris | None |  | FCRD-UFD-2012-000495
M3FT-12PN0806051 | M3 | 1.02.08.06.05 | PNNL | FT-12PN080605 | Engineered Barrier Systems (EBS) Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Radiolysis Products Modeling Results for Scenarios | Radiolysis Products Modeling Results for Scenarios Report | A high-level waste repository environment will be a dynamic redox system because of the time-dependent generation of radiolytic oxidants and reductants and the corrosion of Fe- and Zr-bearing canister and cladding materials. A major difference between spent fuel and natural analogs, including unirradiated UO2, is the intense radiolytic field. The radiation emitted by used fuel can produce radiolysis products (including OH• and H• radicals, O2-, eaq, H2O2, H2, and O2) that may change the used fuel degradation rate and alter radionuclide behavior even within a locally reducing geological environment. This milestone will document the continued development of methodologies for conducting computer simulations of the formation of radiolytic species in more complex environments (carbonate, active secondary phase formation, chloride, elevated temperatures, etc.), the user-friendly graphical interface developed for the model, and a preliminary set of results based on the scenarios for Waste Form Degradation. | 2012-07-21 02:00 |  | 2012-07-27 03:00 |  | 2012 | Completed Late |  | Buck, Edgar | Buck, Edgar | None | Radiolysis Process Model_July 2012_FINAL.pdf | FCRD-UFD-2012-000199
M2FT-12SR0809051 | M2 | 1.02.08.09.05 | SRNL | FT-12SR080905 | DR Inventory - SRNL | Carter, Joe | McMahon, Kevin | Complete Revision 5 of the Inventory Estimate Report | Complete Revision 5 of the Inventory Estimate Report | Complete inventory estimates for alternative fuel cycles supporting the FY13 Systems options analysis. | 2012-07-31 |  | 2012-07-31 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | Fuel Cycle Potential Waste Inventory for Disposition R5 Final.pdf | FCRD-USED-2010-000031 | Fuel Cycle Waste Inventory
M4FT-12SN0811036 | M4 | 1.02.08.11.03 | SNL | FT-12SN081103 | CX International - SNL | McMahon, Kevin | Nutt, Mark | Status of R&D plan developed for work at KURT |  | A work plan for using KURT facility to conduct UFD R&D tests for the development of deep borehole and granite repository concept will be the content of this milestone report. | 2012-07-31 02:00 |  | 2012-07-31 02:00 |  | 2012 | Complete |  |  |  | None | Milestone M4FT-12SN081103.pdf | FCRD-UFD-2012-000212
M4FT-12SN0814101 | M4 | 1.02.08.14.10 | SNL | FT-12SN081410 | Siting Experience Database - SNL | Price, Laura | Nutt, Mark | Interim Status Review | Meeting with DOE | Meet with the DOE to provide an interim status update. | 2012-08-01 | 41183.375 | 41144.125 |  | 2012 | Completed Late |  | Price, Laura | Price, Laura | None | SEA_Meeting_Summary_082312.pdf | FCRD-UFD-2012-000606
M4FT-12PN0809031 | M4 | 1.02.08.09.03 | PNNL | FT-12PN080903 | DR Inventory - PNNL | Gastelum, Jason | McMahon, Kevin | Provide input to revision 5 of the Inventory report | Report Contributions | Provide input to revision 5 of the Inventory report to SRNL. | 2012-08-01 05:00 |  | 2012-07-17 03:00 |  | 2012 | Complete |  | Gastelum, Jason | Gastelum, Jason | None | Input to Inventory Report 20120716.pdf | FCRD-FUEL-2012-000138
M3FT-12SN08180235 ULR. Draft. | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Literature Survey and Analysis to Support Final Test Plan Development | Literature Survey and Analysis of Brine Migration Relevant to Nuclear Waste Disposal in Salt | Report will be a comprehensive review of thermally-driven brine migration | 2012-08-01 06:00 |  | 2012-07-19 02:00 |  | 2012 | Complete |  | Brush, Larry | Brush, Larry | None | Bru 2012 Revu of Bris Bri Mig 45 pp 07 02 2012.doc | FCRD-UFD-2012-000708
M4FT-12LL0807077 | M4 | 1.02.08.07.07 | LLNL | FT-12LL080707 | Natural Systems Evaluations - LLNL | Wolery, Tom | McMahon, Kevin | Disposal systems material properties | Report on thermodynamic data collection & synthesis | This activity will focus on the development of disposal concepts for natural system components and the collection and management of critical technical data for natural system evaluation. The data collected in UFD and other related projects will be archived in a centralized data repository. In FY12, a catalog of representative geologic media and the associated properties (e.g., groundwater chemistry) will be provided and will be used as boundary conditions for related UFD activities. LLNL work will focus on thermodynamic data collection and synthesis. | 2012-08-01 19:00 |  | 2012-08-01 03:00 |  | 2012 | Complete |  | Wolery, Tom | Wolery, Tom | None | TDB_report_8-1-12_g.pdf | FCRD-UFD-2012-000575
M4FT-12LB0807068 | M4 | 1.02.08.07.06 | LBNL | FT-12LB080706 | Natural Systems Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Disposal systems material properties | Report on technical data for near-field modeling of a clay repository | This activity will focus on the development disposal concept for natural system components and the collection and management of critical technical data for natural system evaluation. The data collected UFD and other related projects will be archived in a centralized data repository. In FY12, a catalog of representative geologic media and the associated properties (e.g., groundwater chemistry) will be provided and will be used as boundary conditions for related UFD activities. LBNL will be responsible for collecting technical data related to near-field modeling of a clay repository. | 2012-08-01 20:00 |  | 2012-08-01 03:00 |  | 2012 | Complete |  |  |  | None | LBNL M4FT-12LB0807068.pdf | FCRD-UFD-2012-000207
M3FT-12AN0806013 | M3 | 1.02.08.06.01 | ANL | FT-12AN080601 | Engineered Barrier Systems (EBS) Evaluations - ANL | Ebert, William | McMahon, Kevin | Waste form degradation model status report | Conceptual Models for Fuel Corrosion and Catalytic Behavior | Report describing conceptual model or models being developed to address corrosion and catalytic behaviors of fuel components under reducing conditions. | 2012-08-09 02:00 | 2012-08-08 01:00 | 2012-08-08 01:00 |  | 2012 | Complete |  | Jerden, James | Jerden, James | None | ANL_Fuel_Matrix_Degredation_Model_M3FT_12AN080601.pdf | FCRD-UFD-2012-000169 | used fuel, oxidation, degradation, mixed potential model
M4FT-12LL0817022 | M4 | 1.02.08.17.02 | LLNL | FT-12LL081702 | Deep Bore Hole - LLNL | Halsey, Bill | Mackinnon, Robert | Input/support to Deep Borehole Disposal RD&D Plan | Support for Deep Borehole Disposal RD&D Plan | Letter report via email to CAM summarizing LLNL input to (and/or review of) the SNL Deep Borehole Disposal Research, Development, & Demonstration Plan - as requested. | 2012-08-10 09:00 |  | 2012-08-08 03:00 |  | 2012 | Complete |  | Halsey, Bill | Halsey, Bill | None | LLNL_DBD_RD&D_Plan_M4_8-8-2012.docx | FCRD-UFD-2012-000577
M3FT-12SN0804032 FCRD-UFD-2013-000171 Rev. 1 Note: file name shows FCRD-UFD-2012-00219 | M3 | 1.02.08.04.03 | SNL | FT-12SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Generic Disposal Concepts and Thermal Analysis (FY12) | Generic Disposal Concepts and Thermal Analysis (FY12) | Milestone report that builds on the FY11 description of reference disposal concepts and their thermal results for selected waste streams, using contributions (M4 deliverables) from LLNL, ORNL, and SRS/SNL. | 2012-08-15 06:00 |  | 41137.0833 |  | 2012 | Completed Late |  | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2012-00219 (16Aug12).pdf | FCRD-UFD-2012-000219 | repository disposal concept thermal engineering cost
M2FT-12LB0807061 | M2 | 1.02.08.07.06 | LBNL | FT-12LB080706 | Natural Systems Evaluations - LBNL | Persoff, Peter | McMahon, Kevin | Report on Modeling coupled processes in the near field of a clay repository | Report on modeling coupled processes in the near field of a clay repository | It is well known that THMC process is important for the performance of a clay repository. This report documents the continued development of constitutive relationships and other capabilities for modeling THMC couplings and the further demonstration of the coupled modeling capabilities. | 2012-08-15 23:00 |  | 2012-08-14 02:00 |  | 2012 | Complete |  | Liu, Hui-Hai | Liu, Hui-Hai | None | LBNL M2FT-12LB0807061.pdf | FCRD-UFD-2012-000223 | Coupled Processes, Clay Repository, Constitutive Relationships, Model Validation
M4FT-12SR0812044 | M4 | 1.02.08.12.04 | SRNL | FT-12SR081204 | DR LLW Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Treatment/Management Trade Studies | LLW Treatment/Management Data Input | Provide support to identify treatment technologies for potential low level radioactive wastes from alternate fuel cycles and to evaluate their benefit for waste minimization and disposal. | 2012-08-17 |  | 2012-08-09 |  | 2012 | Complete |  | Jones, Robert | Jones, Robert | None | FCRD-USED-2012-000185 LLW Treatment-Management Data Input FINAL 8-9-12.pdf | FCRD-UFD-2012-000185
M3FT-12SN0808062 FCRD-USED-2012-000227. This report corresponds to DOE Document Number FCRD-UFD-2012-000227 and satisfies DOE Milestone Number M3FT-12SN0808062. SAND report format: SAND2012-10208 | M3 | 1.02.08.08.06 | SNL | FT-12SN080806 | Advanced Disposal System Modeling - SNL | Freeze, Geoff | McMahon, Kevin | Deliverable Report | Performance Assesment Framework Tools for Advanced Disposal System Modeling | Document gap analysis of candidate PA framework tools | 2012-08-24 02:00 |  | 2012-08-24 02:00 |  | 2012 | Complete |  | Freeze, Geoff | Freeze, Geoff | None | M3FT-12SN0808062_Final Approved.pdf | FCRD-USED-2012-000227 | performance assessment, advanced modeling
M4FT-12LA0811052 | M4 | 1.02.08.11.05 | LANL | FT-12LA081105 | CX International - LANL | Perry, Frank | Nutt, Mark | Status of Colloid-Facilitated Uranium Transport Experiments in Support of the CFM Project at Grimsel Test Site, Switzerland | Status of Colloid-Facilitated Uranium Transport Experiments in Support of the CFM Project at Grimsel Test Site, Switzerland | Status of Colloid-Facilitated Uranium Transport Experiments in Support of the CFM Project at Grimsel Test Site, Switzerland | 2012-08-24 02:00 |  | 2012-08-30 02:00 |  | 2012 | Completed Late |  | Reimus, Paul | Reimus, Paul | None | LANL_Reimus_M4FT-12LA0811052_&coverpage.pdf | FCRD-UFD-2012-000572
M4FT-12LA0811053 | M4 | 1.02.08.11.05 | LANL | FT-12LA081105 | CX International - LANL | Caporuscio, Florie | Nutt, Mark | Status of LANL investigation of temperature constraints in a clay or granite repository with backfill | Status of LANL investigations of temperature constraints on clay in repository environments | Status report on LANL investigations to support understanding of temperature constraints on clay in repository environments. | 2012-08-24 02:00 |  | 2012-08-23 02:00 |  | 2012 | Complete |  | Caporuscio, Florie | Caporuscio, Florie | None | FCRD-Report-LANL LBNL Intl clay work-deliverable 2012.pdf | FCRD-UFD-2012-000249 | mixed buffer material, recent EBS investigations, test plan
M4FT-12SN0811034 | M4 | 1.02.08.11.03 | SNL | FT-12SN081103 | CX International - SNL | McMahon, Kevin | Nutt, Mark | Status of Simulation and Uncertainty Quantification of Fractured Media Flow and Transport for the Bedrichov Tunnel Experiment Task in the DECOVALEX Project | Status of Simulation and Uncertainty Quantification of Fractured Media Flow and Transport for the Bedrichov Tunnel Experiment Task in the DECOVALEX Project | Status of Simulation and Uncertainty Quantification of Fractured Media Flow and Transport for the Bedrichov Tunnel Experiment Task in the DECOVALEX Project | 2012-08-24 02:00 |  | 2012-08-22 02:00 |  | 2012 | Complete |  | Gardner, Payton | McMahon, Kevin | None | DECOVALEX-2012_FY12_summary_UFD_style.pdf | FCRD-UFD-2012-000229
M4FT-12LB0811025 | M4 | 1.02.08.11.02 | LBNL | FT-12LB081102 | CX International - LBNL | Birkholzer, Jens | Nutt, Mark | Status of Diffusion-Reaction Modeling of the DR-A Field Experiment at Mont Terri, Switzerland | Status of Diffusion-Reaction Modeling of the DR-A Field Experiment at Mont Terri, Switzerland | Status of Diffusion-Reaction Modeling of the DR-A Field Experiment at Mont Terri, Switzerland | 2012-08-24 05:00 |  | 2012-08-29 03:00 |  | 2012 | Completed Late |  | Steefel, Carl | Birkholzer, Jens | None | LBNL M4FT-12LB0811025.pdf | FCRD-UFD-2012-000240 | Diffusion-Reaction Modeling
M4FT-12LB0811027 | M4 | 1.02.08.11.02 | LBNL | FT-12LB081102 | CX International - LBNL | Birkholzer, Jens | Nutt, Mark | Status of International Activities Supporting Clay or Granite Repositories | Status of International Activities Supporting Clay or Granite Repositories | Status of International Activities Supporting Clay or Granite Repositories | 2012-08-24 06:00 |  | 2012-08-23 03:00 |  | 2012 | Complete |  | Nakagawa, Seiji | Birkholzer, Jens | None | LBNL M4FT-12LB0811027.pdf | FCRD-UFD-2012-000241
M4FT-12PN0806053 | M4 | 1.02.08.06.05 | PNNL | FT-12PN080605 | Engineered Barrier Systems (EBS) Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Experimental Results for SimFuels | Experimental Results for SimFuels | Tests will be performed over the range of conditions to assess the role of radiolysis in used fuel degradation and radionuclide release. To have more effective control over the properties of the uranium oxide solids in the tests, unirradiated UO2 doped with various levels of radionuclides will be used. These SimFuel ceramics are termed radiolytically aged doped synthetic nuclear fuels (RADFUELs), which will help us elucidate the effect of doping on the fuel chemistry and the radiolysis effect. | 2012-08-24 11:00 |  | 2012-08-22 03:00 |  | 2012 | Complete |  | Buck, Edgar | Buck, Edgar | None | Radiolysis_Experimental_PNNL-21646.pdf | FCRD-UFD-2012-000247
M3FT-12SN08180241 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | MacKinnon, Robert | MacKinnon, Robert | Report on Safety Framework for Salt R&D Investigations | Safety Framework for Salt R&D Investigations | Report on Safety Framework for Salt R&D Investigations | 2012-08-30 04:00 | 2012-11-16 04:00 |  | The revised finish date was approved by DOE | 2012 | Late |  |  |  | None
M3FT-12SR0812043 | M3 | 1.02.08.12.04 | SRNL | FT-12SR081204 | DR LLW Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Radionuclide Inventory Data | Low Level Waste Radionuclide Inventory | Refine prior low level radioactive waste inventory estimates for alternate fuel cycles to include radionuclide concentration estimates. | 2012-08-31 02:00 |  | 2012-08-28 |  | 2012 | Complete |  | Jones, Robert | Jones, Robert | None | FCRD-UFD-2012-000186 LLW Radionuclide Inventory FINAL Rev 0 8-28-12.pdf | FCRD-UFD-2012-000186 | Low Level Waste Radionuclide Inventory
M3FT-12LA08180117 Note that Milestone numbers don't match - file name shows M3FT-12LA08180177 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Integrated Report on the Results of International Workshops | Integrated Report on the Results of International Workshops | Assess data needs for Actinide and Brine Chemistry to Support HLW in Salt and produce an integrated report based on the results of two international workshops. | 2012-08-31 04:00 |  | 2012-08-31 02:00 |  | 2012 | Complete |  | Reed, Don | Reed, Don | None | LANL Assessment Report - M3FT-12LA08180177 - redline with comment explanation.pdf LANL Assessment Report - M3FT-12LA08180177- rev 1 (2).pdf LANL Assessment Report - M3FT-12LA08180177.pdf | FCRD-UFD-2012-000238 | Research Actinide Brine Chemistry
M2FT-12SN0817031 | M2 | 1.02.08.17.03 | SNL | FT-12SN081703 | Deep Bore Hole - SNL | Mackinnon, Robert | Mackinnon, Robert | Deep Borehole Disposal Research, Development, and Demonstration Roadmap | Deep Borehole Disposal RD&D Plan | The Deep Borehole Disposal RD&D Plan will include: 1. Science needs roadmap, 2. Engineering needs analysis, 3.Borehole demonstration plan including organizational structure, schedule, milestones, and budget. | 2012-08-31 06:00 |  | 41152.0833 |  | 2012 | Complete |  |  |  | None | DBD_RDD_RM_M2FT-12SN0817031.pdf | FCRD-UFD-2012-000269
M4FT-12LA0806091 | M4 | 1.02.08.06.09 | LANL | FT-12LA080609 | Salt Disposal Investigations (SDI) Coupled Processes - LANL | Robinson, Bruce | McMahon, Kevin | LANL Activities in Model Benchmarking and Thermal Test Design Calculations | LANL Activities in Model Benchmarking and Thermal Test Design Calculations | Milestone will report on LANL participation in model benchmarking and thermal test design calculations | 2012-08-31 10:00 |  | 2012-08-30 02:00 |  | 2012 | Complete |  | Robinson, Bruce | Robinson, Bruce | None | M4FT-12LA0806091.pdf | FCRD-UFD-2012-000568
M4FT-12LA0808021 | M4 | 1.02.08.08.02 | LANL | FT-12LA080802 | Generic Disposal System Level Modeling - LANL | Chu, Shaoping | McMahon, Kevin | Generic system model refinement: (Granite) | Status report on generic granite system model improvements | Status report on improvements to the generic granite disposal system model in the GPAM | 2012-08-31 16:00 |  | 2012-08-27 02:00 |  | 2012 | Complete |  | Chu, Shaoping | Chu, Shaoping | None | M4FT-12LA0808021.pdf | FCRD-UFD-2012-000254 | granite, system level modeling
M2FT-12SN0807081 | M2 | 1.02.08.07.08 | SNL | FT-12SN080708 | Natural Systems Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Report on Integrated tool development for natural system evaluation | Report on integrated tool development for natural system evaluation: Preliminary results | This activity will develop an integrated tool for natural system performance analysis. This tool will integrate detail process models with probabilistic analysis capability. The tool developed will be used to support prioritization and decision making related to natural system R&D activities. This activity will also support the development of model parameter values for the total system performance assessments. In FY12, we will initiate this activity and preliminarily demonstrate the capability. | 2012-09-01 02:00 |  | 41148.0833 |  | 2012 | Complete |  | Wang, Yifeng | Wang, Yifeng | None | M2FT-12SN0807081_final.pdf | FCRD-UFD-2012-000229
M4FT-12IN0807041 | M4 | 1.02.08.07.04 | INL | FT-12IN080704 | Natural Systems Evaluations - INL | Simpson, Michael | McMahon, Kevin | Updated report on characterization of electrorefiner salt to assess direct disposal | Report on structural and compositional characterization of ER salt for direct disposal | With the experimental techniques developed in FY11, the FY12 work will focus on laboratory testing and collection of key experimental data for the leaching behavior of surrogate ER salt in simulated salt repository environments. Continue structural & compositional characterization of surrogate ER salt (INL). Continue characterization of the effect of radionuclide loading on salt encapsulation (SNL). | 2012-09-03 06:00 |  | 2012-08-31 02:00 |  | 2012 | Complete |  |  |  | None | FY12 report for milestone.docx
M4FT-12LB0807067 | M4 | 1.02.08.07.06 | LBNL | FT-12LB080706 | Natural Systems Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Development of critical field testing and site characterization techniques | Report on development of critical field testing and site characterization techniques: LBNL inputs | For FY12, this activity will review and assess new techniques for characterizing alternative rock types, with a particular focus on fracture characterization using a variety of techniques and fault/fracture identification using primarily geophysical techniques (LANL). The work will also evaluate the integrity of clay/shale as caprock based on the information drawn from petroleum industry (LBNL). | 2012-09-04 01:00 |  | 2012-08-28 03:00 |  | 2012 | Complete |  | Houseworth, James | Liu, Hui-Hai | None | LBNL M4FT-12LB0807067.pdf | FCRD-UFD-2012-000251
M4FT-12LA08180118 Input to M2FT-12SN08180223 | M4 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | LANL Report on the Non-Delaware Basin and International Program Salt Data | LANL Report on the Non-Delaware Basin and International Program Salt Data | This LANL approved report will evaluate the existing salt data collected for the non-Delaware Basin data compilation exercises in the context of demonstrating repository safety and will identify data gaps and needs. This milestone will be input to a SNL owned Level 2 milestone (M2FT-12SN08180223) in work package FT-12SN081802. | 2012-09-07 12:00 | 2012-10-01 02:00 | 2012-10-01 02:00 | Complete as of Monday 10/1/2012. | 2012 | Expected Late |  | Callahan, G. | Guerin, Dave | None | LANL Synthesis Report on Salt Studies - Activity 1 FINAL10012012.pdf | FCRD-UFD-2012-000312
M2FT-12SN0806062 | M2 | 1.02.08.06.06 | SNL | FT-12SN080606 | Engineered Barrier Systems (EBS) Evaluations - SNL | Jove-Colon, Carlos | McMahon, Kevin | Integration of EBS Models with Generic Disposal System Models. | Integration of EBS Models with Generic Disposal System Models | This milestone will document the preliminary integration of generic EBS modeling with generic system level models for NW disposal. It will describe the integration approaches and limitationsin passing information between various models. | 2012-09-07 22:00 |  | 41159.0833 |  | 2012 | Complete |  | Sassani, David | Jove Colon, Carlos | None | M2FT-12SN0806062 Integration EBS Models Used Fuel Degradation.pdf | FCRD-UFD-2012-000277
M4FT-12LB0818032 M2FT-12SN1204031.pdf M4FT-12LB0818032.pdf | M4 | 1.02.08.18.03 | LBNL | FT-12LB081803 | Salt Disposal Initiative - LBNL | Birkholzer, Jens | MacKinnon, Robert | Report on THM Coupled Process Modeling with TOUGH-FLAC to Evaluate the Fate and Transport of Water in a Salt-Based Repository | THM Coupled Process Modeling with TOUGH-FLAC to Evaluate the Fate and Transport of Water in a Salt-Based Repository | Develop a report on the THM model development and analysis with TOUGH-FLAC. | 2012-09-14 08:00 |  | 41166.125 | Report was delivered on time. | 2012 | Complete |  | Rutqvist, Jonny | Birkholzer, Jens | None | M2FT-12SN1204031.pdf M4FT-12LB0818032.pdf | FCRD-UFD-2012-000297
M4FT-12LB0807021 | M4 | 1.02.08.07.02 | LBNL | FT-12LB080702 | Regional Geology & Tectonic Hazard - LBNL | Liu, Hui-Hai | McMahon, Kevin | Status of shale geology: information on extent, thickness and depth of shale deposits | Status of shale geology: information on extent, thickness and depth of shale deposits | The L4 milestone will document information on the geometry of selected shale formations in the U.S. This information will be shared throughout the year with LANL for incorporation into a GIS database. | 2012-09-14 09:00 |  | 2012-09-14 03:00 |  | 2012 | Complete |  | Dobson, Patrick | Liu, Hui-Hai | None | LBNL M4FT-12LB0807021.pdf | FCRD-UFD-2012-000296
M2FT-12LB0811021 | M2 | 1.02.08.11.02 | LBNL | FT-12LB081102 | CX International - LBNL | Birkholzer, Jens | Nutt, Mark | Report on UFD Campaign International Activities in Disposal Research | International Activities in Disposal Research | International Activities in Disposal Research | 2012-09-15 08:00 |  | 2012-09-14 03:00 | Milestone was completed and submitted on 09/14/2012. | 2012 | Complete |  | Birkholzer, Jens | Birkholzer, Jens | None | M2FT-12LB0811021.pdf | FCRD-UFD-2012-000295
M4FT-12SN0808048 | M4 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | 5) Demonstration of Comparative Analysis of Disposal Options in Support of Systems Engineering Prioritization | 5) Demonstration of Comparative Analysis of Disposal Options in Support of Systems Engineering Prioritization | Draft report describing a preliminary application of the GPAM demonstrating it’s use in supporting the analysis of disposal option for the Systems Engineering Prioritization using selected fuel cycle/host Rock options. This will include identifying criteria and associated metrics appropriate for the evaluation of the disposal aspects of the Systems Engineering Fuel Cycle prioritization along with how the metrics will be evaluated and measured. This report will serve as a basis for a chapter in the November Level 2 milestone report. | 2012-09-17 06:00 | 2012-10-12 02:00 | 2012-10-12 02:00 | completed | 2012 | Expected Late |  | Vaughn, Palmer | Vaughn, Palmer | None | metrics milestone.pdf | FCRD-UFD-2012-000535
M3FT-12AN0806015 | M3 | 1.02.08.06.01 | ANL | FT-12AN080601 | Engineered Barrier Systems (EBS) Evaluations - ANL | Ebert, William | McMahon, Kevin | Report results of electrochemical experiments | Results of Electrochemical Experiments with Fuel Components | Report compiling experimental results, data interpretation, and insights provided to modeling activities. | 2012-09-21 02:00 |  | 2012-09-21 01:00 | Completed on Schedule | 2012 | Complete |  | Ebert, William | Ebert, William | None | USED2012_000201_Ebert.pdf | FCRD-UFD-2012-000201
M3FT-12LA0806072 | M3 | 1.02.08.06.07 | LANL | FT-12LA080607 | Salt Disposal Investigtions (SDI) THM Processes - LANL | Caporuscio, Florie | McMahon, Kevin | Test Plan to develop hydrological laboratory methods | Test Plan to Develop Hydrologic Laboratory Methods | Develop hydrological laboratory methods to examine water liberation, brine migration, and mineral reactions relevant to the water budget | 2012-09-21 04:00 |  | 2012-09-21 02:00 | deliverable submitted on 9/21/21 | 2012 | Complete |  | Caporuscio, Florie | Caporuscio, Florie | None | SDI THM experiment test plan-FCRD-Report-092112.pdf | FCRD-UFD-2012-000346
M4FT-12SR0812045 | M4 | 1.02.08.12.04 | SRNL | FT-12SR081204 | DR LLW Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Disposal History Update | History of LLW Disposal in the United States FY 2012 Update | Update the history of low level radioactive waste disposal in the United States for significant events that occurred in FY 2012. | 2012-09-28 |  | 2012-09-26 | Closure Document: FCRD-UFD-2012-000260, History of LLW Disposal in the US-FY2012 Update | 2012 | Complete |  | Seitz, Roger | Low Level Waste Disposal Update | None | FCRD-UFD-2012-000260 History of LLW Disposal in the US-FY2012 Update FINAL 9-26-12.pdf | FCRD-UFD-2012-000260
M2FT-12AN0814013 | M2 | 1.02.08.14.01 | ANL | FT-12AN081401 | CX Perspectives on NW Management - ANL | Nutt, Mark | Nutt, Mark | Revision to the UFDC Disposal R&D Roadmap Report | Report - Revision to the UFDC Disposal R&D Roadmap | Revision to the UFDC Disposal R&D Roadmap | 2012-09-28 02:00 |  | 2012-09-20 01:00 |  | 2012 | Complete |  | Nutt, Mark | Nutt, Mark | None | UFD RD Roadmap Appendix A - Rev 1.pdf UFD RD Roadmap Appendix B - Rev 1.pdf UFD_Disposal_R&D_Roadmap_(Rev_1).pdf | FCRD-USED-2011-000065
M2FT-12SN0801021 | M2 | 1.02.08.01.02 | SNL | FT-12SN080102 | CX Campaign Management - SNL | McMahon, Kevin | Nutt, Mark | Update of the UFD Campaign Implementation Plan | Update of the UFD Campaign Implementation Pla | Update of the UFD Campaign Implementation Plan | 2012-09-28 02:00 |  | 2012-09-17 02:00 |  | 2012 | Complete |  | McMahon, Kevin | Swift, Peter N | None | FCRD-UFD-2012-000334.pdf | FCRD-UFD-2012-000334
M4FT-12SR0814061 input to ANL L-2 Milestone M2FT-12AN0814012 | M4 | 1.02.08.14.06 | SRNL | FT-12SR081406 | CX Perspectives on NW Management - SRNL | Smith, Pat | Nutt, Mark | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - SRNL Input | Used Nuclear Fuel - Waste Management System Architecture Study Report | Provide input to ANL L-2 Milestone M2FT-12AN0814012, Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | 2012-09-28 02:00 |  | 2012-09-28 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | UFD- System Architecture Cost Study (Rev 0).pdf | FCRD-UFD-2012-000372
M3FT-12SN08180237 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Test Plan for Investigation of Material Interactions In Heated Salt | Test Plan for Investigation of Material Interactions in Heated Salt | Test Plan for Investigation of Material Interactions In Heated Salt | 2012-09-28 06:00 | 2012-10-31 06:00 | 2012-10-31 02:00 | On schedule for new delivery date | 2012 | Expected Late | Test Plan for Investigation of Material Interactions in Heated Salt | Stockman, Christine | Stockman, Christine | None | Test Plan for Materials in Salt final.pdf
M2FT-12SN08180243 ULR. Draft. | M2 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Develop TSPA Model and Implement Sensitivity Analysis of Processes Affecting Performance of a Salt Repository for Disposal of Heat-Generating Nuclear Waste | TSPA Model Development and Sensitivity Analysis of Processes Affecting Performance of a Salt Repository for Disposal of Heat-Generating Nuclear Waste | Report on TSPA Model Development and Sensitivity Analysis of Processes Affecting Performance of a Salt Repository for Disposal of Heat-Generating Nuclear Waste | 2012-09-28 06:00 |  | 41180.0833 | The document is undergoing final Sandia R&A. Do not distribute until corporate R&A is complete. | 2012 | Complete |  | Sevougian, S. David | Sevougian, S. David | None | FCRD-UFD-2012-000320 Rev 0 (28Sep12) Salt RD TSPA.pdf | FCRD-UFD-2012-000320
M3FT-12SN08180239 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Test Plan for Investigation of Thermodynamic Properties Of Brines, Minerals And Corrosion Products In High Temperature Systems | Test Plan for Study of Thermodynamic Properties Of Brines, Minerals And Corrosion Products In High Temperature Systems | Test Plan for Investigation of Thermodynamic Properties Of Brines, Minerals And Corrosion Products In High Temperature Systems | 2012-09-28 06:00 |  | 2012-09-28 02:00 | The test plan is undergoing through final Sandia R&A. The uploaded version should not be distributed outside of DOE until such time as final Corporate R&A is given. | 2012 | Complete |  | Xiong, Yongliang | Xiong, Yongliang | None | M3FT-12SN08180239.pdf | FCRD-UFD-2012-000339
M4FT-12OR0814041 input to ANL L-2 Milestone M2FT-12AN0814012 | M4 | 1.02.08.14.04 | ORNL | FT-12OR081404 | CX Perspectives on NW Management - ORNL | Howard, Rob | Nutt, Mark | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - ORNL Input | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - ORNL Input | Provide input to ANL L-2 Milestone M2FT-12AN0814012, Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | 2012-09-28 06:00 |  | 41180 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | UFD- System Architecture Cost Study (Rev 0).pdf | FCRD-UFD-2012-000372
M2FT-12SN08180223 Contains M3FT-12SN08180219, M4FT-12LA08180118 and M4FT-12SN08180221 | M2 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Review and Evaluation of Salt R&D Data for Disposal of Nuclear Waste in Salt | Review and Evaluation of Salt R&D Data for Nuclear Waste Disposal in Bedded Salt | This report will evaluate the existing salt data collected for the Delaware and non-Delaware Basin data compilation exercises in the context of demonstrating repository safety and will identify data gaps and needs. | 2012-09-28 10:00 |  | 2012-09-28 02:00 | The version we are uploading is still going through final Sandia R&A. Please do not distribute outside of DOE. We will up load final version and remove this caveat when Sandia Corporate review is complete. | 2012 | Complete |  | Kuhlman, Kris | Kuhlman, Kris |  | FCT Cover Sheet M2FT-12SN08180223.pdf Review and Evaluation of Salt R&D Data M2FT-12SN08180223.pdf SAND2012-8808P.pdf | FCRD-UFD-2012-000380
M3FT-12LA08180110 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Report on Assessment of the Utility of Neutron Measurements for the Characterization of Water in Salt | Report on Assessment of the Utility of Neutron Measurements for the Characterization of Water in Salt | Report on the investigation of the utility of conducting Small Angle Neutron Scattering (SANS) experiments at the Los Alamos Neutron Science Center (LANSCE) for the study of salt behavior. Neutron measurements on salt specimens will be conducted and assessed to determine the utility of this technique for probing the meso-scale pore structural variations due to water/moisture migration in salt. This study will be used to recommend whether similar measurements for salt and other media should be conducted in a larger, future experimental campaign. | 2012-09-28 10:00 | 2012-10-01 02:00 | 2012-10-01 02:00 | Complete as of Oct 1. | 2012 | Expected Late |  | Ding, Mei | Ding, Mei | None | FCRD-UFD-2012-000310.pdf | FCRD-UFD-2012-000310
M3FT-12LA0818016 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Development of Final Test Plan for FY2013 Experiments | Development of Final Test Plan for FY2013 Experiments | Develop an approved test plan for the brine migration experimental studies at LANL and upgrade the laboratory including purchasing ancillary equipment, materials, and fabricating dedicated reaction vessels. | 2012-09-28 10:00 |  | 2012-09-28 02:00 | Deliverable complete as described. | 2012 | Complete |  | Boukhalfa, Hakim | Caporuscio, Florie | None | Salt R&D test plan-FCRD-Report-092812 LANL.pdf | FCRD-UFD-2012-000364
M3FT-12LA0818018 | M3 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Weaver, Doug | MacKinnon, Robert | Test Plan for Radionuclide Solubility Measurements | Test Plan for Radionuclide Solubility Measurements | Develop a test plan to establish the magnitude of the temperature effect on radionuclide solubility to guide future performance assessment models. Once the test plan is approved under LANL-CO processes, experimental work will be initiated for the remainder of the FY. | 2012-09-28 10:00 | 2012-10-04 02:00 | 2012-10-04 02:00 | Completed on October 4, 2012. | 2012 | Expected Late |  | Reed, Don | Reed, Don | None | M3FT-12LA0818018 - Effect of Temperature on the Solubility of Multivalent Actinides.pdf | FCRD-UFD-2012-000660
M2FT-12LA08180112 | M2 | 1.02.08.18.01 | LANL | FT-12LA081801 | Salt Disposal Initiative - LANL | Robinson, Bruce | MacKinnon, Robert | Report on Model Development and Analysis of the Fate and Transport of Water in a Salt-Based Repository | Report on Model Development and Analysis of the Fate and Transport of Water in a Salt-Based Repository | Develop a report on the model development and analysis related to the fate and transport of water in a salt-based repository. | 2012-09-28 12:00 |  | 2012-09-28 02:00 | Complete as of Thursday 9/28/2012. | 2012 | Complete |  | Robinson, Bruce | Robinson, Bruce | None | M2FT-12LA08180112 submitted.pdf | FCRD-UFD-2012-000386
M3FT-12SN08180245 | M3 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Report on Benchmarking Studies for TMH Process Models | Benchmarking Studies for TMH Processes | Report on Benchmarking Studies for TMH Process Models | 2012-09-28 12:00 |  | 2012-09-28 02:00 | This is in Sandia R&A and should not be distributed outside of DOE. | 2012 | Complete |  | Arguello, Guadalupe | Arguello, Guadalupe | None | Cover Sheet Draft Rpt on Salt Benchmarking.pdf Intl benchmark calculations M3FT-12SN08180245 092612.pdf | FCRD-UFD-2012-000374
M4FT-12SN0814053 Input to ANL L-2 Milestone M2FT-12AN0814012 | M4 | 1.02.08.14.05 | SNL | FT-12SN081405 | CX Perspectives on NW Management - SNL | Rechard, Rob | Nutt, Mark | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - SNL Input | Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal - SNL Input | Provide input to ANL L-2 Milestone M2FT-12AN0814012, Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | 2012-09-28 15:00 |  | 41092.0833 |  | 2012 | Complete |  | Weck, Philippe | Rechard, Rob | None | System Architecture--At Reactor Logistics Final.docx | FCRD-UFD-2012-000605
M3FT-12LA0807057 | M3 | 1.02.08.07.05 | LANL | FT-12LA080705 | Natural Systems Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Development of critical field testing and site characterization techniques | Report on development of critical field testing and site characterization techniques | For FY12, this activity will review and assess new techniques for characterizing alternative rock types, with a particular focus on fracture characterization using a variety of techniques and fault/fracture identification using primarily geophysical techniques (LANL). The work will also evaluate the integrity of clay/shale as caprock based on the information drawn from petroleum industry (LBNL). | 2012-09-28 18:00 |  | 2012-09-27 02:00 |  | 2012 | Complete |  | Huang, Lianjie | Huang, Lianjie | None | M3FT-12LA0807057.pdf | FCRD-UFD-2012-000306 | site characterization, geophysics
M3FT-12SN0807082 | M3 | 1.02.08.07.08 | SNL | FT-12SN080708 | Natural Systems Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Direct disposal of ER salt in a salt repository: Laboratory testing | Report on direct disposal of ER waste in a salt repository: Laboratory testing | With the experimental techniques developed in FY11, the FY12 work will focus on laboratory testing and collection of key experimental data for the leaching behavior of surrogate ER salt in simulated salt repository environments. Continue structural & compositional characterization of surrogate ER salt (INL). Continue characterization of the effect of radionuclide loading on salt encapsulation (SNL). | 2012-09-28 18:00 |  | 2012-09-28 02:00 |  | 2012 | Complete |  | Wang, Yifeng | Wang, Yifeng | None | M3FT-12SN0807082.pdf | FCRD-UFD-2012-000339
M3FT-12SN0814102 same as M3FT-13SN0905023 | M3 | 1.02.08.14.10 | SNL | FT-12SN081410 | Siting Experience Database - SNL | Price, Laura | Nutt, Mark | Status Memo | Interim Status of Siting Experience Archive | A memo to DOE that provides the status of the archive and database. | 2012-09-29 | 2012-11-26 10:00 |  | The start of this project was delayed two months because of a delay in receiving funding. All milestones have thus been delayed two months. | 2012 | Expected Late |  |  |  | None
M4FT-12AN0808011 Per Matt Brainard: Also included FCRD-UFD-2012-000142, Benchmarking a New Closed-Form Thermal Analysis Technique Against a Traditional Lumped Parameter, Finite-Difference Method on this deliverable form. This report is not an identified milestone in PICS-NE, but was completed under this work package to benchmark the semi-analytic thermal model developed by LLNL with a numerical model. | M4 | 1.02.08.08.01 | ANL | FT-12AN080801 | Generic Disposal System Level Modeling - ANL | Nutt, Mark | McMahon, Kevin | Clay GDSM Model Development, Demonstration, Analysis | ANL Iput to Generic Disposal System Model: Architecture, Implementation, and Demonstration | This activity will provide needed technical sophistication pedigree by implementing additional process modeling fundamentals developed by Natural System and EBS SMEs into the clay GDSM. This will increase the defensibility of the disposal system risk information provided to UFD and System Engineering decision makers. This activity will provide input to SNL Level-2 milestone M2FT-12SN0808042 Generic Disposal System Model: Architecture, Implementation, and Demonstration | 2012-09-30 02:00 | 2012-07-13 01:00 | 2012-07-13 01:00 |  | 2012 | Complete |  | Huff, K.D. | Nutt, Mark | None | ANL FY12 Clay GDSM Input Milestone.doc LLNL-SINDA Thermal Benchmark.doc | FCRD-UFD-2012-000142
M4FT-12SN08180252 | M4 | 1.02.08.18.02 | SNL | FT-12SN081802 | Salt Disposal Initiative - SNL | Leigh, Christi | MacKinnon, Robert | Participate in US/German Workshops | US/German Workshop Presentations | Scope includes active follow-up to the International Salt Mechanics VII conference, with the intent to hold the next such conference in the USA and participation in the European Commission’s “Implementing Geological Disposal Technology Platform” (IGD-TP), which includes all repository media and a wide range of potential R&D. International collaboration builds upon collaboration to co-author state-of-the-art position papers. | 2012-10-10 06:00 |  | 2012-10-04 02:00 | The workshop is a week away. All presentations are complete and we will be there with bells on. | 2012 | 90 Day |  | Leigh, Christi | Leigh, Christi | None | Arguello_US_German_3rd_WS.pptx Bean_US_German_Salt_THM_final.pptx Hardin_Disposal concepts large packages (Hardin) V.1.pptx Leigh FEP Catalog U S -German 3rd Salt Workshop 10-9-2012_cdl_sds.pptx Sallaberry_3rd_US_German_Meeting_Salt_v1.2.pptx Sevougian PA U.S.-German 3rd Salt Workshop 10-9-2012 R&A version.pptx
M2FT-13OR08220311 | M2 | 1.02.08.22.03 | ORNL | FT-13OR082203 | Characterization of Existing UNF - ORNL | Wagner, John | Wagner, John | Final Report and Results for UNF Categorization | Final Report and Results for UNF Categorization | Final report on UNF categorization Prepare, finalize and submit report - Categorization of Used Nuclear Fuel Inventory in Support of a Comprehensive National Nuclear Fuel Cycle Strategy | 2012-10-31 04:00 |  | 41213.0833 |  | 2013 | Complete |  |  |  | None |  | FCRD-FCT-2012-000232
M2FT-12SN0814057 | M2 | 1.02.08.14.05 | SNL | FT-12SN081405 | CX Perspectives on NW Management - SNL | Rechard, Rob | Nutt, Mark | Status of Stranded Used Nuclear Fuel | Status of Stranded Used Nuclear Fuel | Project management of PNNL and SRNL conducting Stranded Nuclear Fuel Activity | 2012-10-31 08:00 |  |  | Report is on schedule and will be completed by the end of the month | 2012 | 90 Day |  |  |  | None
M2FT-12AN0814012 | M2 | 1.02.08.14.01 | ANL | FT-12AN081401 | CX Perspectives on NW Management - ANL | Nutt, Mark | Nutt, Mark | Report describing Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | Report - Waste Management Integration - Interfaces Between Long-Term Storage and Permanent Disposal | This milestone will describe an integrated approach to transportation, storage, and disposal in the waste management system with an emphasis of providing flexibility to respond to unknown situations and developments. This task will evaluate the implications of the current (de-facto) strategy for on-site storage of used nuclear fuel in large dry storage systems on the subsequent direct disposal of the stored used nuclear fuel in salt, clay/shale, and crystalline mined geologic repositories and in deep boreholes. Alternative strategies and approaches for managing the used nuclear fuel will be identified and evaluated to identify potential benefits in cost and flexibility. Factors including emplacement capability, thermal constraints, the need for re-packaging techniques, storage alternatives, transportation, impacts on utility operations, etc. will be considered. Measures for flexibility and rough order of magnitude cost factors associated with each alternative included in the evaluation. | 2012-10-31 14:00 |  |  | On schedule | 2012 | 90 Day |  |  |  | None
M4FT-13SR0804042 | M4 | 1.02.08.04.04 | SRNL | FT-13SR080404 | DR Thermal Load Management & Design Concepts - SRNL | Smith, Pat | McMahon, Kevin | Letter Report - Responses to peer review comments | Letter Report - responses to peer review comments | Prepare responses to review comments in preparing the M2 deliverable. | 2012-11-01 |  | 2012-11-01 |  | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | Responses.pdf
M4FT-13OR0804021 | M4 | 1.02.08.04.02 | ORNL | FT-13OR080402 | DR Thermal Load Management & Design Concepts - ORNL | Howard, Rob | McMahon, Kevin | Letter Report- Responses to Peer Review Comments - ORNL Input | Letter Report - Responses to Peer Review Comments- ORNL Input | Prepare responses to review comments in the discipline areas that LLNL contributed to in the FY12 report. Submit a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use by SNL in preparing the M2 deliverable. | 2012-11-01 02:00 |  | 2012-12-01 |  | 2013 | Completed Late |  | Howard, Rob | Howard, Rob | None | Transmittal_Letter_M4FT-12OR0804021_Nov_01_2012.pdf
M4FT-13LL0804014 | M4 | 1.02.08.04.01 | LLNL | FT-13LL080401 | DR Thermal Load Management & Design Concepts - LLNL | Sutton, Mark | McMahon, Kevin | Letter Report: Responses to Peer Review Comments | Responses to peer review comments | Prepare responses to review comments in the discipline areas that LLNL contributed to in the FY12 report. Submit a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use by SNL in preparing the M2 deliverable. | 2012-11-01 13:00 |  | 2012-12-01 05:00 |  | 2013 | Completed Late |  | Greenberg, Harris | LLNL | None | Draft comment response and proposed text revisions (LLNL assigned comments) Rev. B_MS.pdf LLNL-TR-491099-Rev._2_final_-_update.pdf
M2FT-12SN0806081 Replaces M3FT-12SN08180227 and M2FT-13SN08180341 | M2 | 1.02.08.06.08 | SNL | FT-12SN080608 | Salt Disposal Investigations (SDI) THM Processes - SNL | Hansen, Francis | McMahon, Kevin | Coupled Thermal-Hydrological-Mechanical Processes in Salt | Thermomechanical properties and model for hot granular salt consolidation | This report will report and evaluate the laboratory results, microprocesses, and the suitability of the constitutive model. | 2012-11-15 08:00 |  |  | On schedule. | 2012 | 90 Day |  |  |  | None
M2FT-13SN0804031 | M2 | 1.02.08.04.03 | SNL | FT-13SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Reference Disposal Concepts: Description and Thermal Analysis | Disposal Concepts and Thermal Load Management | Report describing the full set of UFD reference disposal concepts (including updated description of concepts identified in FY11 and FY12), with description of surface facilities, subsurface facilities, and waste packaging. Identify selected waste forms, and develop generic repository thermal analysis, and disposal system cost estimates. Summarize all disposal concept/thermal load management (DC/TLM) development activities conducted in FY11 and FY12, and finalize the results from the overall project in FY11 and FY12. | 2012-11-15 11:00 |  | 41228.0833 |  | 2013 | Complete |  |  |  | None | FCRD-UFD-2012-00219 Rev. 2.pdf | FCRD-UFD-2012-00219
M4FT-13LB0807052 supercedes M4FT-12LB0807065 | M4 | 1.02.08.07.05 | LBNL | FT-13LB080705 | Generic Natural System Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Fluid flows in low permeability media: Non-Newtonian flow in clays | Report on fluid flows in clay formations | This activity will focus on the better understanding of multiphase fluid flows in both near field and far field environments and the improvement of existing experimental and modeling tools for uncertainty quantification and parameter estimation. LBNL work will include the development of non-Newtonian flow model in clay. FY12 work will include the preliminary model/method formulation, validation and demonstration. | 2012-11-15 14:00 | 2012-11-14 09:00 | 2013-02-01 06:00 |  | 2013 | Completed Late |  | Liu, Hui-Hai | Liu, Hui-Hai | None | M4FT-13LB0807052 - LBNL.pdf | FCRD-UFD-2013-000028
M2FT-12SN0808042 includes M4FT-12LB0808032 and M2FT-12SN0808044 as input. | M2 | 1.02.08.08.04 | SNL | FT-12SN080804 | Generic Disposal System Level Modeling - SNL | Vaughn, Palmer | McMahon, Kevin | Generic Disposal System Model: Architecture, Implementation, and Demonstration. | Generic Perfromance Assessment Model System: Implementation and Application | This report will describe and document the model formulations and improvements, data used, and FEPs included for each host rock type and waste form option considered. The architecture and its implementation including the interface to the database will be described. A relevant demonstration of its use with results will be included. | 2012-11-15 15:00 |  | 41228.1667 | THis milestone is not due until 11/15. It is on schedule for that date. so it is about 90% complete. | 2012 | 90 Day |  | Vaughn, Palmer | Vaughn, Palmer | None |  | FCRD-UFD-2012-000430 | performance assessment, generic disposal system models
M3FT-13SN08180342 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Test Plan for Material Interactions | Test Plan for Material Interactions | Replaces test Plan for Material Interactions from FY12 | 2012-11-16 06:00 |  | 2012-11-16 02:00 |  | 2013 | Complete |  |  |  | None | Test Plan for Materials in Salt final.pdf | FCRD-USED-2013-000030
M4FT-12IN0802091 | M4 | 1.02.08.02.09 | INL | FT-12IN080209 | Dry Storage Demonstration Program Preliminary Program Execution Plan | Marschman, Steve | Wagner, John | Dry Storage Demonstration Program Functional Requirements | Dry Storage Demonstration Program Functional Requirements | Dry Storage Demonstration Program Functional Requirements | 2012-11-23 04:00 |  |  | On Schedule | 2012 | 90 Day |  |  |  | None
M3FT-12LA0807011 | M3 | 1.02.08.07.01 | LANL | FT-12LA080701 | Regional Geology & Tectonic Hazard - LANL | Perry, Frank | McMahon, Kevin | Distribution of alternative host rock formations and siting factors that potentially influence siting and site characterization activities. | Alternative host rock formation distributions and siting factors that potentially influence siting and site characterization activities | Milestone describes a GIS database and documentation of alternative host rock formation distributions and siting factors that potentially influence siting and site characterization activities. | 2012-12-09 12:00 |  | 2012-12-19 02:00 | on schedule for 12/9/2012 completion | 2012 | 90 Day |  | Perry, Frank | Perry, Frank | None | Regional_Geology_LANL_M3FT-12LA0807011.pdf | M3FT-12LA0807011 | Regional Geology
M3FT-13SN08180335 supercedes M4FT-12SN08180247 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Evaluation of EBS THM Coupled Process in Salt | EBS THM Coupled Processes in Salt | This technical memo must summarize work on the associated activity and make recommendations for process models for TSPA | 2012-12-14 04:00 |  | 41257.0833 |  | 2013 | Complete |  | Jove Colon, Carlos | Jove Colon, Carlos | None | FT-13SN08180330_FINAL.docx | FCRD-UFD-2013-000064
M2FT-12LA0807051 same as M2FT-13LA0807041 | M2 | 1.02.08.07.05 | LANL | FT-12LA080705 | Natural Systems Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Fluid flow model development for representative geologic media | Report on fluid flow model development for representative geologic media | The report documents (1) the mathematical formulation and preliminary implementation of the discrete fracture network (DFN) model, (2) the model development and preliminary validation of non-Newtonian flow in low permeability geologic formation, and (3) an improved method for field testing data analysis. | 2012-12-15 16:00 |  |  | On schedule | 2012 | 90 Day |  |  |  | None
M2FT-13LA0807043 | M2 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on Fluid flow model development for representative geologic media | Report on fluid flow model development for representative geologic media | The report documents (1) the mathematical formulation and preliminary implementation of the discrete fracture network (DFN) model, (2) the model development and preliminary validation of non-Newtonian flow in low permeability geologic formation, and (3) an improved method for field testing data analysis. | 2012-12-16 08:00 | 2012-12-14 02:00 | 2012-12-12 02:00 |  | 2013 | Complete |  | Painter, Scott | Painter, Scott | None | M2FT-13LA0807043.pdf | FCRD-UFD-2013-000058
M3FT-13AN0806013 | M3 | 1.02.08.06.01 | ANL | FT-13AN080601 | DR Generic Engineered Barrier System Evaluations - ANL | Ebert, William | McMahon, Kevin | ANL MPM version 1 archive | ANL MPM version 1 | Archive version of ANL MPM version 1 in TIO document management system. This version was validated by comparisons to the original Canadian model and data. It is being archived to distinuish extensions and modifications to be made in FY13. Sections of version 1 that have been modified and/or expanded in version 2 will be identified. | 2012-12-20 07:00 |  | 2012-12-19 01:00 |  | 2013 | Complete |  | Jerden, James | Ebert, William | None | M3FT13AN0806013_ANL_MPM_V1_Archive_2012.pdf | FCRD-UFD-2013-000057
M4FT-13OR0816101 Draft. | M4 | 1.02.08.16.10 | ORNL | FT-13OR081610 | Dual Purpose Canisters - ORNL | Howard, Rob | Nutt, Mark | Survey of Available Technologies | Letter Report: Survey of Available Technologies to Support Direct Disposal of DPCs | Survey available technologies to ensure that proposed disposal concepts incorporate an appropriate range of potential design solutions (see workplan FCRD-UFD-2012-000106). Consider technologies instead of overall disposal concepts. Focus on critical elements (e.g., hoisting), and use input from diverse international disposal programs and other applications (e.g., mining and tunneling). Provide a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use in concept development | 2013-01-31 02:00 |  | 2013-01-31 |  | 2013 | Complete |  | Howard, Rob | ORNL | None |  |  | Dual Purpose Canister
M3FT-12SN0814105 same as M3FT-13SN0905025 | M3 | 1.02.08.14.10 | SNL | FT-12SN081410 | Siting Experience Database - SNL | Price, Laura | Nutt, Mark | Provide a report describing the archive, its content, and its use | US Nuclear Facility Siting Experience Archive | Produce a report describing the archive, its content, and how it is used. The report will include a short synopsis of each facility for which documentation has been obtained and a summary of the siting information identified in the data base. | 2013-01-31 04:00 | 2013-03-29 12:00 |  | The start of this project was delayed two months because of a delay in receiving funding. All milestones have thus been delayed two months. | 2012 | Expected Late |  |  |  | None |  | FCRD-UFD-2012-000088
M2FT-13SN0808041 | M2 | 1.02.08.08.04 | SNL | FT-13SN080804 | Generic Disposal System Level Modeling - SNL | Freeze, Geoff | McMahon, Kevin | Generic Safety Case Report | Generic Deep Geologic Disposal Safety Case | Finalize Generic Safety Case Report | 2013-01-31 08:00 |  | 2013-01-31 02:00 |  | 2013 | Complete |  | Freeze, Geoff | Freeze, Geoff | None |  | FCRD-UFD-2012-000146 Rev 1 | safety case, deep geologic disposal
M2FT-12SN0814051 | M2 | 1.02.08.14.05 | SNL | FT-12SN081405 | CX Perspectives on NW Management - SNL | Rechard, Rob | Nutt, Mark | Report documenting analysis of Public and State Preferences Related to Siting, Characterization, and Operation of Radioactive Waste Management Facilities for Storage and Disposal | Public Preferences Related to Siting, Characterization, and Operation of Radioactive Waste Management Facilities for Storage and Disposal | Analysis of Public and State Preferences Related to Siting, Characterization, and Operation of Radioactive Waste Management Facilities for Storage and Disposal | 2013-01-31 16:00 |  |  | Presentation made to "SNL on FY12 survey results. Presentation to DOE HQplanned for Nov 6th. Writting of report text has begun. | 2012 | On Schedule |  |  |  | None
M4FT-13SN0816115 | M4 | 1.02.08.16.11 | SNL | FT-13SN081611 | Dual Purpose Canisters - SNL | Hardin, Ernest | Nutt, Mark | Letter report: Media-Specific Alternative DPC Disposal Concepts | Letter Report: Media-Specific Alternative DPC Disposal Concepts | Combine information on technologies discussed above, and international experience with deep geologic disposal, to develop a set of alternatives for direct disposal of DPCs. Provide concept description, as this will be the working set of DPC disposal alternatives that supports the remainder of the FY13 activities in this area. Note that DPC disposal concepts need not specify a particular geologic medium, but can give a range of suitable media characteristics if the concept is amenable. Specify representative package and drift spacings, ventilation duration, temperature limits, and other aspects needed for thermal analysis. Provide a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use in follow-on activities. | 2013-02-28 02:00 |  | 2013-02-28 02:00 |  | 2013 | Complete |  | Hardin, Ernest | Hardin, Ernest | None | DPC disposal alternatives FCRD-UFD-2013-000102 R0 Final.pdf | FCRD-UFD-2013-000102
M4FT-13LA0818015 supercedes M4FT-12LA08180114 | M4 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Status Report on LANL International Collaboration | Status Report on LANL International Collaboration | Submit a status on LANL international collaboration specific to SDI activities. These activities may include: 1) presentations at Pu-Futures Conference and meetings with the German program on HLW research, and 2) establishing research contribution to the First Nuclides. | 2013-02-28 06:00 |  | 41214.1667 |  | 2013 | Complete |  | Reed, Don | Reed, Don | None | Reed - International Progress - 10-31-2012 Rev.pdf | FCRD-UFD-2013-000021
M3FT-13PN0806054 | M3 | 1.02.08.06.05 | PNNL | FT-13PN080605 | DR Generic Engineered Barrier System Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Archive Radiolysis Model V1.0 into the document management system | Radiolysis Model Code V1.0 | Provide useable version of the radiolysis model to the program. | 2013-03-08 06:00 |  | 2013-03-07 03:00 |  | 2013 | Complete |  | Buck, Edgar | Buck, Edgar | OUO
M4FT-13OR0816102 Draft | M4 | 1.02.08.16.10 | ORNL | FT-13OR081610 | Dual Purpose Canisters - ORNL | Howard, Rob | Nutt, Mark | Performance Allocation for Engineered and Natural Barriers | Letter Report: Peformance Allocation for Engineered and Natural Barriers | Describe the major elements of the postclosure safety case for each alternative DPC disposal concept. Address the waste isolation functions, if any, of overpacks, buffer and/or backfill, plugs and seals, host rock and other natural barriers, etc. Identify what elements will be used to disposition postclosure criticality FEPs. Provide a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use in follow-on activities. | 2013-03-15 |  | 41348 |  | 2013 | Complete |  | Howard, Rob | Howard, Rob | None | DPC_Disposal_alternavies Performance Allocation Draft031513 Rev0.pdf
M4FT-13PN0806055 Journal Paper | M4 | 1.02.08.06.05 | PNNL | FT-13PN080605 | DR Generic Engineered Barrier System Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Submission of Journal Paper on Radiolysis Modeling | Submission of Journal Article | Submit paper to peer-reviewed journal on the subject of radiolysis. | 2013-03-15 06:00 |  | 41348.125 |  | 2013 | Complete |  | Buck, Edgar | Buck, Edgar | None
M4FT-13SN08180343 | M4 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Readiness Review for High Temperature Experiments in Brine | Rediness review for High Temperature Experiments in brines | Rediness Review | 2013-03-29 04:00 | 2013-10-31 02:00 | 2013-09-27 02:00 | Deliverable originally due 03/29/13 | 2013 | Completed Late |  | Xiong, Yongliang | Leigh, Christi | None | M4FT-13SN08180343.pdf | FCRD-UFD-2013-000302
M4FT-13SN0818036 ULR. No DMS or SAND numbers on report. | M4 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Forensic Studies of Material Recovered from the WIPP Experimental Area | Forensic Studies of Material Recovered from the WIPP Experimental Area | SNL will compile information about the benefits to be gained for re-entry into old WIPP test rooms. | 2013-03-29 10:00 | 2013-08-15 02:00 | 2013-08-26 02:00 |  | 2013 | Completed Late |  | Brady, Patrick | Schuhen, Michael | None | M4FT-13SN0818036 Forensic Studies of Material Recovered from the WIPP Experimental Area.pdf |  | Forensic Plan
M2FT-13SN08180338 | M2 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Proceedings: 3rd US/German Workshop on Salt Repository Research, Design, and Operation | Proceedings: 3rd US/German Workshop on Salt Repository Research, Design, and Operation | Scope includes active follow-up to the International Salt Mechanics VII conference, with the intent to hold the next such conference in the USA and participation in the European Commission’s “Implementing Geological Disposal Technology Platform” (IGD-TP), which includes all repository media and a wide range of potential R&D. International collaboration builds upon collaboration to co-author state-of-the-art position papers. | 2013-03-29 12:00 |  | 2013-02-15 02:00 |  | 2013 | Complete |  | Hansen, Francis | Hansen, Francis | None | appendix e.JPG combined 021413.pdf | FCRD-UFD-2013-000100
M4FT-13AN0816086 | M4 | 1.02.08.16.08 | ANL | FT-13AN081608 | Dual Purpose Canisters - ANL | Nutt, Mark | Nutt, Mark | Letter report: Logistics Simulation of DPC Aging, Selection, Transport and Disposal | Letter report: Logistics Simulation of DPC Aging, Selection, Transport and Disposal | Describe the simulation of a SNF management system that relies on direct disposal of DPCs. Develop assumptions consistent with Miller et al. (2012, in review) that define the criteria to select DPCs for disposal (e.g., schedule to begin disposal operations). Describe the order in which DPCs are disposed, the heat output, age, and burnup for DPCs selected for disposal, and the progressive ages of all DPCs that remain in storage. Provide a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use in follow-on activities, particularly thermal analysis. | 2013-04-12 04:00 | 2013-07-01 02:00 | 2013-07-01 01:00 |  | 2013 | Completed Late |  | Nutt, Mark | Nutt, Mark | None | Preliminary DPC Disposal Feasibility System Analysis (final).pdf | FCRD-UFD-2013-000184
M4FT-13OR0816103 | M4 | 1.02.08.16.10 | ORNL | FT-13OR081610 | Dual Purpose Canisters - ORNL | Howard, Rob | Nutt, Mark | Criticality scoping analysis | Postclosure Criticality Scoping Analysis for Alternative DPC Disposal Concepts | Perform criticality calculations sufficient to assess whether postclosure DPC criticality is likely for representative disposal concepts (particularly those offering water exclusion as a defensible boundary condition). Evaluate initial and crushed configurations. These are scoping calculations intended to address one of the most important potential barriers to direct disposal (BSC 2003). Submit a deliverable report for incorporation in the FY13 M2 project deliverable | 2013-04-30 | 2013-06-14 | 2013-06-17 |  | 2013 | Completed Late |  | Scaglione, John | Howard, Rob | None | M4_Deliverable_Feasibility of Direct Disposal_June_17_2013_r5.pdf
M3FT-13SR0809034 | M3 | 1.02.08.09.03 | SRNL | FT-13SR080903 | DR Inventory - SRNL | Carter, Joe | McMahon, Kevin | Supporting DOE-NE - Provide a comparison report of the task order estimates | Provide a Comparison Report of the task order estimates | Provide support to DOE-NE to evaluate estimates of primary and secondary wastes from LWR recycling and MOX fuel fabrication. | 2013-04-30 | 2013-06-30 | 2013-06-24 |  | 2013 | Completed Late |  | Jones, Robert | Jones, Robert | None | FCRD-UFD-2013-000178 Waste Comparison Summary.pdf | FCRD-UFD-2013-000178
M3FT-13SN0807087 | M3 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Revised R&D implementation plan for natural system evalaution and tool development | Revised R&D implementation plan for natural system evaluation and tool development | This report will update the R&D goal and research topics and summarize the accomplishments for each research topic. | 2013-04-30 06:00 |  | 2013-04-24 02:00 |  | 2013 | Complete |  | Wang, Yifeng | Wang, Yifeng | None | UFDC natural system evaluation RD plan rev 1 0 final.pdf | FCRD-UFD-2013-000144
M4FT-13LL0804012 | M4 | 1.02.08.04.01 | LLNL | FT-13LL080401 | DR Thermal Load Management & Design Concepts - LLNL | Sutton, Mark | McMahon, Kevin | Continue thermal analyses for disposal concepts | Supporting thermal analyses for disposal concepts | Perform and document supporting thermal analyses for disposal concepts, integrated with the Disposal System Evaluation Framework (i.e., using DSEF as the source of input data and repository of results). Perform thermal analysis of additional cases, for example, variations of the “design test case” (FY12), and disposal of large packages containing low-burnup SNF. | 2013-05-24 20:00 |  | 2013-06-11 06:00 |  | 2013 | Completed Late |  | Greenberg, Harris | Greenberg, Harris | None |  | FCRD-UFD-2013-000243
M2FT-13SN08180327 | M2 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | RD&D for the Advancement of Science and Engineering Supporting Geologic Disposal in Bedded Salt - March 2013 Workshop Outcomes | Conceptual Models for a Safety Assessment of Disposal of Heat-Generating Waste in Salt | Conceptual Models and description of their implementation for a Safety Assessment of Disposal of Heat-Generating Waste in Salt | 2013-05-31 04:00 |  | 41425.0833 |  | 2013 | Complete |  | Sevougian, S. David | Sevougian, S. David | None | FCRD-UFD-2013-000161 Rev. 0 Salt RDD Mar2013 Workshop.pdf FCT Transmittal FCRD-UFD-2013-000161 Rev. 0.pdf | FCRD-UFD-2013-000161
M3FT-13LA0806022 | M3 | 1.02.08.06.02 | LANL | FT-13LA080602 | DR Generic Engineered Barrier System Evaluations - LANL | Caporuscio, Florie | McMahon, Kevin | EBS Report - LANL Experimental update of buffer/backfill at elevated P,T | EBS Report - LANL Experimental update of buffer/backfill at elevated P,T | EBS Report - LANL Experimental update of buffer/backfill at elevated P,T | 2013-06-17 04:00 | 2013-06-28 02:00 | 2013-06-26 02:00 |  | 2013 | Completed Late |  | Caporuscio, Florie | Caporuscio, Florie | None | FCRD-Report EBS FY13-FINAL.pdf FY-13 EBS App E Cover sheet.pdf | FCRD-UFD-2013-000207
M4FT-13SR0816122 | M4 | 1.02.08.16.12 | SRNL | FT-13SR081612 | Dual Purpose Canisters - SRNL | Carter, Joe | Nutt, Mark | Letter report: Action Plans for Key Performance and Engineering Issues for DPC Disposal | Letter report: Action Plans for Key Performance and Engineering Issues for DPC Disposal | Identify primary regulatory and engineering issues associated with disposal of DPCs that will need to be resolved or specifically accommodated in the disposal concept. Include in the evaluation of potential issues, those concepts that rely heavily on engineered barriers, or that rely on developmental technologies or materials that are difficult or expensive to obtain. Include risks associated with failure of engineered components such as excavations, ventilation systems, and conveyances. Estimate the scope of activities to address or resolve the issues, and the resources needed to accomplish that scope. Provide a letter report (i.e., of limited length, with minimal frontmatter and formatting) for use in the M2 deliverable. | 2013-06-28 |  | 2013-06-27 |  | 2013 | Complete |  | Severynse, Tom | Severynse, Tom | None | Dual Purpose Canister -FT-13SR081612 (Letter Report L4 Milestone.pdf |  | Dual Purpose Canisters, Critical Issues
M3FT-13SN08180325 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Safety Framework for Disposal of Heat-Generating Waste in Salt | Safety Framework for Disposal of Heat-Generating Waste in Salt | Update of the Safety Framework for Disposal of Heat-Generating Waste in Salt | 2013-06-28 02:00 |  | 2013-06-28 02:00 |  | 2013 | Complete |  | Freeze, Geoff | Freeze, Geoff | None | M3FT-13SN08180325 Salt Safety FEPs_062713_Final.pdf | FCRD-UFD-2013-000191
M4FT-13SN0816116 | M4 | 1.02.08.16.11 | SNL | FT-13SN081611 | Dual Purpose Canisters - SNL | Hardin, Ernest | Nutt, Mark | FEP Crosswalks and PA Scenarios for Alternative DPC Disposal Concepts | FEP Crosswalks and PA Scenarios for Alternative DPC Disposal Concepts | Develop a technical plan for follow-on performance assessments for each alternative DPC disposal concept, or group of similar concepts. Identify which PA scenarios are important, and describe which FEPs would be included and excluded. Describe the calculation procedure and which software and data will be used. Submit a deliverable report for incorporation in the FY13 M2 project deliverable. | 2013-06-28 04:00 | 41465.0833 | 41465.0833 |  | 2013 | Completed Late |  |  |  | None | DPC FEPs Scenarios FCRD-UFD-2013-000172 Final.pdf | FCRD-UFD-2013-000172
M4FT-13LL08060325 Supersedes M4FT-12LL0806042 | M4 | 1.02.08.06.03 | LLNL | FT-13LL080603 | DR Generic Engineered Barrier System Evaluations - LLNL | Sutton, Mark | McMahon, Kevin | Evaluation of Thermodynamic Data | Evaluation of Thermodynamic Data | Evaluation of thermodynamic data, may include... | 2013-06-28 20:00 |  | 2013-06-28 06:00 |  | 2013 | Complete |  | Wolery, Tom | Sutton, Mark | None |  | FCRD-UFD-2013-000242
M4FT-13LL0816091 | M4 | 1.02.08.16.09 | LLNL | FT-13LL081609 | Dual Purpose Canisters - LLNL | Sutton, Mark | Nutt, Mark | Scoping Thermal Analysis of Alternative DPC Disposal Concepts | Scoping Thermal Analysis of Alternative DPC Disposal Concepts | Analyze peak temperatures (waste package, host rock, and/or other locations as appropriate) for each DPC disposal concept, using representative fuel burnup, age, and other characteristics from the concept descriptions deliverable. Perform parameter studies to estimate the minimum fuel age and maximum heat output at closure, or at emplacement for concepts that use preclosure ventilation, so that thermal limits can be met subject to documented assumptions (Miller et al. 2012, in review). | 2013-06-30 11:00 |  | 2013-06-27 03:00 |  | 2013 | Complete |  | Greenberg, Harris | Greenberg, Harris | None |  | FCRD-UFD-2013-000241
M3FT-13SN08180316 same as M3FT-14SN0818014 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Granular Salt Thermal Conductivity as a Function of Porosity and Temperature | Granular Salt Thermal Conductivity as a Function of Porosity and Temperature | Report on Granular Salt Thermal Conductivity as a Function of Porosity and Temperature | 2013-07-05 02:00 | 2013-11-15 04:00 | 2014-03-17 02:00 | This deliverable will be moved into the FY14 work package and tracked there | 2013 | Late | Thermal Conductivity of Salt as a Function of Porosity |  |  | None | M3FT-14SN0818014 Thermal Conductivity of Salt as a Function of Porosity.pdf
M4FT-13LL08060323 Supersedes M4FT-12LL0806044 | M4 | 1.02.08.06.03 | LLNL | FT-13LL080603 | DR Generic Engineered Barrier System Evaluations - LLNL | Sutton, Mark | McMahon, Kevin | DSEF v3.0 | DSEF v3.0 Update | DSEF v3.0 spreadsheet and user guide | 2013-07-12 20:00 | 2013-08-15 03:00 | 2013-08-15 03:00 |  | 2013 | Completed Late |  | Greenberg, Harris | Greenberg, Harris | None | LLNL-TR-629812 Rev. 1 - DSEF Version 3.0 User Manual August 2013.pdf
M4FT-13LB0806045 | M4 | 1.02.08.06.04 | LBNL | FT-13LB080604 | DR Generic Engineered Barrier System Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Investigation of reactive transport and coupled THMC processes in EBS: FY13 Report | Investigation of reactive transport and coupled THMC processes in EBS | Document lab tests and modeling studies on reactive transport and coupled THMC processes in EBS | 2013-07-16 08:00 |  | 2013-07-16 08:00 |  | 2013 | Complete |  | Liu, Hui-Hai | Liu, Hui-Hai | None | EBS Report_July 19 2013.pdf | FCRD-UFD-2013-000216
M4FT-13SN0804036 | M4 | 1.02.08.04.03 | SNL | FT-13SN080403 | DR Thermal Load Management & Design Concepts - SNL | Hardin, Ernest | McMahon, Kevin | Collaborative Report on Disposal Concepts | Collaborative Report on Disposal Concepts | Document strategies for disposal of large packages (e.g., up to 32-PWR size) and for postclosure criticality, in Germany and the U.S. Identify technology developments needed, and potential engineering feasibility and safety analysis issues with handling, packaging, conveyance, and final disposal. Include results from analyses performed to support and defend reference disposal concepts in the U.S. | 2013-07-19 04:00 | 41529.0833 | 41529.0833 | Collaborative report submitted. Late because letting of the DBE TEC subcontract was delayed by approx. 6 weeks, such that the report came together during a time period when other products (including an M2 deliverable) were being prepared. | 2013 | Completed Late |  | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2013-000170 R0 Collab. Rpt SAND2013-7665P.pdf | FCRD-UFD-2013-000170
M2FT-13SN0818034 | M2 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Establishing the Technical Basis for Disposal of Heat-generating Waste in Salt | Establishing the Technical Basis for Disposal of Heat-generating Waste in Salt | Level 2 Milestone: Establishing the Technical Basis for Disposal of Heat-generating Waste in Salt; QRL3, 6/28/2013. | 2013-07-29 02:00 |  | 2013-07-25 02:00 |  | 2013 | Complete |  | Kuhlman, Kris | Kuhlman, Kris | None | Kuhlman-Sevougian-Technial-Basis-for-Salt.pdf | FCRD-UFD-2013-000233
M4FT-13LB0808032 | M4 | 1.02.08.08.03 | LBNL | FT-13LB080803 | Generic Disposal System Level Modeling - LBNL | Liu, Hui-Hai | McMahon, Kevin | Diffusion modeling in a generic clay repository: FY13 report | Diffusion modeling in a generic clay repository: FY13 report | Diffusion modeling in a generic clay repository: FY13 report | 2013-07-30 08:00 |  | 2013-07-29 03:00 |  | 2013 | Complete |  | Bianchi, Marco | Liu, Hui-Hai | None | M4FT-13LB0808032 Diffusion Modeling in a Clay Repository FY 13 Report.pdf | FCRD-UFD-2013-000228
M3FT-13SR0809033 | M3 | 1.02.08.09.03 | SRNL | FT-13SR080903 | DR Inventory - SRNL | Carter, Joe | McMahon, Kevin | Complete Revision 6 of the Inventory Estimate Report | Complete Revision 6 of the Inventory Estimate Report | Complete inventory estimates revision 6 to reflect the results of the task order. | 2013-07-31 |  | 2013-07-30 |  | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | FC for Potential Waste Inventory for Dispositon R6.pdf | FCRD-USED-2010-000031
M3FT-13SN08070813 | M3 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | South Dakota shale research plan and database development | Report on South Dakota shale research | This MS will include (1)the development of South Dakota shale research plan and (2) the development of shale research literature database. | 2013-07-31 04:00 |  | 2013-07-30 04:00 |  | 2013 | Complete |  | Roggenthen, William |  | None | SDSMT Concepts and Literature 1.pdf SDSMT Preliminary Planning for Development of URL in Shale 1.pdf | FCRD-UFD-2013-000224 & 000225
M4FT-13SN0808045 | M4 | 1.02.08.08.04 | SNL | FT-13SN080804 | Generic Disposal System Level Modeling - SNL | Freeze, Geoff | McMahon, Kevin | Generic Modeling of Deep Borehole and Salt | PA Modeling of Generic Deep Borehole and Salt Disposal Systems | Reference cases and conceptual models for deep borehole and salt disposal systems | 2013-07-31 06:00 |  | 2013-07-31 06:00 |  | 2013 | Complete |  | Freeze, Geoff | Freeze, Geoff | None | M4FT-13SN0808045 Salt PA Outline_073013_Final2.pdf |  | generic modeling, performance assessment modeling
M4FT-13SN08070810 is Section 3 of M3FT-13LA0807046 | M4 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Report on integrated tool development for natural system evaluation | Report on integrated tool development for natural system evaluation | This is an input to a LANL's level 3 milestone. This report will document (1) the continued integrated tool development for natural system sensitivity analysis and (2) the initiation of hydrothermal experiment for host rock thermal limit studies. | 2013-08-12 06:00 |  | 2013-08-30 02:00 |  | 2013 | Completed Late |  | Hadgu, Teklu | Wang, Yifeng | None | Far_field_Flow_Transpot_Modeling_Using_DAKOTA-PFLOTRAN_August_2013 (3).docx
M4FT-13LB0807053 | M4 | 1.02.08.07.05 | LBNL | FT-13LB080705 | Generic Natural System Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Report on THMC effects on radionuclide transport in a clay repository | Report on THMC effects on radionuclide transport in a clay repository | Report on THMC effects on radionuclide transport in a clay repository | 2013-08-15 05:00 |  | 2013-08-15 03:00 |  | 2013 | Complete |  | Zheng, Liange | Liu, Hui-Hai | None | M4FT-13LB0807053.pdf | FCRD-UFD-2013-0000245
M3FT-13LL0807072 | M3 | 1.02.08.07.07 | LLNL | FT-13LL080707 | Generic Natural System Evaluations - LLNL | Kersting, Annie | McMahon, Kevin | Radionuclide interactions and transport in geologic repository environments – Intrinsic colloids | Report on Pu colloid formation and interactions with representative geologic media | In past two years it has been found that the stability of intrinsic Pu colloids depends on the initial form of Pu that is introduced into the system. FY13 work will continue to focus on the stability of intrinsic Pu colloids as a function of aqueous solubility, temperature, and aging in the presence and absence of inorganic colloids. | 2013-08-15 13:00 |  | 2013-08-15 02:00 |  | 2013 | Complete |  | Zhao, Pihong | Wang, Yifeng | None | Zhao et al. intrinsic colloids UFD f.pdf
M2FT-13LB0807051 | M2 | 1.02.08.07.05 | LBNL | FT-13LB080705 | Generic Natural System Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | Report on THMC modeling of the near field evolution of a generic clay repository: Model validation and demonstration | THMC modeling of the near field evolution of a generic clay repository, model validation and demonstration | Report on THMC modeling of the near field evolution of a generic clay repository: Model validation and demonstration | 2013-08-15 18:00 |  | 2013-08-15 03:00 |  | 2013 | Complete |  | Liu, Hui-Hai | Liu, Hui-Hai | None | M2FT-13LB0807051.pdf | FCRD-UFD-2013-000244
M4FT-13AN0811012 | M4 | 1.02.08.11.01 | ANL | FT-13AN081101 | CX International - ANL | Nutt, Mark | Nutt, Mark | ANL Report on the Status of UFD Campaign International Activities in Disposal Research | ANL Report on the Status of UFD Campaign International Activities in Disposal Research | This is a report that provides input from ANL to a L3 milestone at LBNL entitled "Status of UFD Campaign International Activities in Disposal Research." | 2013-08-20 04:00 | 2013-09-03 01:00 | 2013-09-03 01:00 | ANL Report on the Status of UFD Campaign International Activities in Disposal Research | 2013 | Completed Late |  | Nutt, Mark | Nutt, Mark | None | M4FT-13AN0811012.pdf
M4FT-13SN0811031 | M4 | 1.02.08.11.03 | SNL | FT-13SN081103 | CX International - SNL | McMahon, Kevin | Nutt, Mark | SNL Report on the Status of UFD Campaign International Activities in Disposal Research | SNL Report on the Status of UFD Campaign International Activities in Disposal Research | This is a report that provides input from SNL to a L3 milestone at LBNL entitled "Status of UFD Campaign International Activities in Disposal Rsearch." | 2013-08-20 04:00 |  | 2013-08-19 02:00 |  | 2013 | Complete |  | McMahon, Kevin | McMahon, Kevin | None | M4FT-13SN0811031 SNL International FY13.docx | FCRD-UFD-2013-000260 | international; disposal research
M3FT-13SN0808062 | M3 | 1.02.08.08.06 | SNL | FT-13SN080806 | Advanced System Level Modeling - SNL | Freeze, Geoff | McMahon, Kevin | Advanced Modeling Report | Evaluation of PA Model Frameworks for Implementing an Advanced Disposal System Modeling Capability | Summary of progress in developing and applying an advanced PA modeling capability to generic disposal system models | 2013-08-23 06:00 |  | 2013-08-22 02:00 |  | 2013 | Complete |  | Freeze, Geoff | Freeze, Geoff | None | M3FT-13SN0808062 ADSM FY13 Outline_082113_Final.pdf | FCRD-UFD-2013-000218
M2FT-13SN0816112 | M2 | 1.02.08.16.11 | SNL | FT-13SN081611 | Dual Purpose Canisters - SNL | Hardin, Ernest | Nutt, Mark | Preliminary Report on DPC Disposal Alternatives | Preliminary Report on DPC Disposal Alternatives | Provide technical support and input to development of key elements of the M2 deliverable, especially concept development, actions plans, and peer review. | 2013-08-30 04:00 |  | 41515.0833 |  | 2013 | Complete |  | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2013-000171 R0 Final.pdf | FCRD-UFD-2013-000171
M3FT-13PN0806058 | M3 | 1.02.08.06.05 | PNNL | FT-13PN080605 | DR Generic Engineered Barrier System Evaluations - PNNL | Buck, Edgar | McMahon, Kevin | Issue report documenting development of PNNL-Radiolysis Model Integration with the Argonne Mixed Potential Model and Discussion of Experimental Testing on SimFuels | The effect of brine radiolysis on used fuel corrosion | Complete report on modeling and experimental work. | 2013-08-30 06:00 |  | 2013-08-27 03:00 |  | 2013 | Complete |  | Buck, Edgar | Buck, Edgar | None | FCRD-Num Request Form_Buck_27Aug13 (2) (3)-signed.pdf FCT Document Cover Sheet_Buck_27Aug13 (3)-signed.pdf M3FT-PN0806058_UFD_report_Buck_2013-signed.pdf | FCRD-UFD-2013-000290
M3FT-13SN0807084 | M3 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Report on performance assessment of direct disposal of electrochemical refinery salt waste | Report on performance assessment of direct disposal of electrochemical refinery salt waste | This report will document the result of a performance assessment calculation for the direct dispsoal concept. | 2013-08-30 06:00 |  | 2013-08-29 02:00 |  | 2013 | Complete |  | Lee, Joon | Wang, Yifeng | None | M3FT-13SN0807084 (SAND2013-7304P ER salt disposal feasibility study).pdf | FCRD-UFD-2013-000275
M4FT-13LA0808021 | M4 | 1.02.08.08.02 | LANL | FT-13LA080802 | Generic Disposal System Level Modeling - LANL | Chu, Shaoping | McMahon, Kevin | Reference Case and Improved Generic Disposal System Modeling in Granite | Update and Improvements to the System Modeling of Generic Disposal in Granite | This report will document updates to the generic granite modeling and subsequent analyses. Additionally, a reference case will be established that documents high-level information and assumptions to provide some consistency and common basis for generic disposal system model design, numerical modeling, and analyses. | 2013-08-30 10:00 |  | 2013-08-29 02:00 |  | 2013 | Complete |  | Chu, Shaoping | Chu, Shaoping | None | M4FT-13LA0808021.pdf | FCRD-UFD-2013-000235 | granite, repository, system model
M4FT-13SR0812012 | M4 | 1.02.08.12.01 | SRNL | FT-13SR081201 | DR Low Level Radioactive Waste Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Treatment/Management Trade Studies | LLW Treatment/Management Data Input | Provide support to the Separations and Waste Form Campaign and the Fuel Cycle Options Campaign to identify and evaluate the effects of LLW treatment on waste parameters such as volume and classification. | 2013-08-31 02:00 |  | 2013-06-24 |  | 2013 | Complete |  | Jones, Robert | Jones, Robert | None | FCRD-UFD-2013-000195 LLW Treatment and Mgt.pdf | FCRD-UFD-2013-000195
M3FT-13AN0806015 | M3 | 1.02.08.06.01 | ANL | FT-13AN080601 | DR Generic Engineered Barrier System Evaluations - ANL | Ebert, William | McMahon, Kevin | ANL Mixed Potential Model with Experimental Results | ANL Mixed Potential Model with Test Data | Report showing integration of experimental results into used fuel matrix degradation model. Results of expanding model to include additional redox reactions, catalyzed reactions, and experimentally measured kinetic parameters. Documents experimental results and scientific bases for model development, which will be summarized in M2FT-SN0806062. | 2013-09-10 05:00 |  | 2013-09-10 01:00 | Status report for mixed potential model to calculate the electrochemical potential established by solution redox reactions controlling UO2 dissolution rate. Highlights incorporation of H2 reactions catalyzed by noble metal particles on fuel surface. | 2013 | Complete |  | Jerden, James | Ebert, William | None | FCRD_UFD_2013_000305_Jerden.pdf | FCRD-UFD-2013-000305 | oxide fuel, fuel matrix, corrosion, oxidative dissolution, mixed potential model
M4FT-13LB0818022 | M4 | 1.02.08.18.02 | LBNL | FT-13LB081802 | DR Salt R&D - LBNL | Birkholzer, Jens | MacKinnon, Robert | Report on Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | Develop a Report on Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | 2013-09-13 05:00 |  | 2013-09-11 03:00 | Milestone M4FT-13LB0818022 submitted on schedule | 2013 | Complete |  | Rutqvist, Jonny | Birkholzer, Jens | None | LBNL_M4FT-13LB0818022.pdf |  | Salt, nuclear waste repository, thermal, hydrological, mechanical, modeling
M2FT-13SN0807081 | M2 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL | Wang, Yifeng | McMahon, Kevin | Report on modeling radionuclide interaction and transport in representative geologic media | Report on modeling radionuclide interaction and transport in representative geologic media | This milestone report will describe the FY13 work accomplished at at LANL, LBNL, LLNL and SNL on radionuclide interaction with representative geologic media, specifically on radionuclide (mainly Pu, Np, U, and I) sorption and colloid formation and stability in clay, granite and other related materials. The report will provide a key list of parameter values for radionuclide transport in the natural system for generic repository performance assessments. | 2013-09-15 10:00 |  | 41530.1667 | This milestone documents the FY13 progress in the study of radionuclide interactions with clay and granitic materials. | 2013 | Complete |  | Wang, Yifeng | Wang, Yifeng | None | M2FT-13SN0807081.pdf | FCRD-UFD-2013-000314
M3FT-13LA0818017 supercedes M3FT-12LA08180116 | M3 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Summary Report on Salt Instrumentation Development | Summary Report on Salt Instrumentation Development | Develop a summary report on the development of the generic salt measurement and data collection techniques and to make usefully benefit of the unique skill sets and resources currently available from past WIPP studies, the Yucca Mountain Project, and from salt testing performed internationally. This milestone as listed in the referenced study plan is scheduled for 9/16/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-09-16 08:00 | 2013-10-31 02:00 | 2013-09-25 02:00 | The instrumentation and data collection of any future thermal test in salt is expected to be a complex process. Gages need to be selected, designed, and tested that can accurately measure the anticipated range of responses in a salt test and withstand the anticipated harsh test environment for several years. The purpose of this document is to summarize the activities conducted over the past 18 months to develop generic salt measurement and data collection techniques for a future thermal test. The scope of this document is limited to those activities conducted by the LANL-CO and does not include the recent work being funded by the DOE – Environmental Management (EM) and accomplished by the national laboratories related to the assessment of geophysical techniques. This report satisfies the level-3 milestone M3FT-13LA0818017 in Work Package FT-13LA081801. | 2013 | Completed Late |  | Otto, Shawn | Otto, Shawn | None | Instrumentation Development Report 09-25-13 FINAL Reduced Cover Page.pdf
M2FT-13LA0818019 | M2 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Brine Migration Experimental Studies for Salt Repositories Report - FY13 | Brine Migration Experimental Studies for Salt Repositories Report - FY13 | This deliverable will document the results of elevated P,T experiments performed on samples of salt, clay and sulfates. It will also detail the results of the SANS experiments. Finally, data extracted from the experiments will be cataloged for use in modeling efforts of the UFD campaign. | 2013-09-25 14:00 |  | 2013-09-25 04:00 | For the US Department of Energy Used Fuel Disposition Campaign generic repository studies we examined water content in Permian salt samples (Salado Formation) collected from the WIPP site. These samples were obtained because of ease of in-situ sample collection and known field relations. With these representative samples, we established the profile of water release and movement as a function of temperature from 30 to 275 deg C. This was performed using classical gravimetric methods, which measure weight loss as a result of heating. Weight loss measured was assumed to be water. The amount of water released from salt as a result of heating was found to be correlated with the salts accessory mineral content. Gravimetric analyses of salt rich in clay and other secondary minerals lost up to 3 wt % while pure halite salt lost less than 0.5 wt % water. Water released from salt at lower temperature was reversible and is attributed to clay hydration and dehydration processes. This was confirmed by heated stage X-Ray diffraction analysis of the clay component of the salt as a function of temperature. | 2013 | Complete |  | Caporuscio, Florie | Caporuscio, Florie | None | UFD-Brine Migration in Salt - Deliverable- 092513 R1 .pdf | FCRD-UFD-2013-000204
M2FT-13OR08220311 same as M2FT-12OR0822014 Submittal of milestone deliverable EBS Model Development and Evaluation Report (M2FT-13SN0806061) | M2 | 1.02.08.06.06 | SNL | FT-13SN080606 | DR Generic Engineered Barrier System Evaluations - SNL | Jove-Colon, Carlos | McMahon, Kevin | EBS Model Development and Evaluation Report | EBS Model Development and Evaluation | EBS Model Development and Evaluation Report. This report will be built from M3 and M4 level contributions from various national laboratory teams. The laboratory teams contributing to this milestone are LBNL, SNL, LANL, and LLNL encompassing R&D activities on model development and applications to assess barrier performance (e.g., THMc coupled processes) and experimental work on barrier material interactions with fluids and their stability at repository conditions. | 2013-09-27 02:00 |  | 41544.1667 | Submittal of milestone deliverable EBS Model Development and Evaluation Report (M2FT-13SN0806061) | 2013 | Complete |  | Jove Colon, Carlos | Jove Colon, Carlos | None | M2FT-13SN0806061_Milestone_Report_UFDC_EBS_FY13_Final - Copy.pdf | FCRD-UFD-2013-000312
M4FT-13SN08180344 | M4 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Update to the Salt R&D Reference Case | Update to the Salt R&D Reference Case | Update to the Salt R&D Reference Case | 2013-09-27 02:00 |  | 2013-09-27 02:00 | Deliverable complete on schedule. | 2013 | Complete |  | Sevougian, S. David | Leigh, Christi | None | M4FT-13SN08180344 Update Salt Ref Case 9-26-2013.pdf |  | Salt Repository
M3FT-13LA08180111 | M3 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Status Report on Radionuclide Solubility Experimental Studies | Status Report on Radionuclide Solubility Experimental Studies | This deliverable will document the results of the FY13 radionuclide solubility measurements to establish the magnitude of the temperature effect on radionuclide solubility. | 2013-09-27 06:00 |  | 2013-09-30 06:00 | This report documents the continued laboratory efforts to establish the magnitude of the temperature effect on radionuclide solubility to guide future performance assessment models. These data would become important in any repository scenario in which water contacts the waste and mobilizes radionuclides. It is likely that in any future repository program, these scenarios will need to be investigated regardless of how robust the scientific evidence is for encapsulation of the waste by the deforming salt medium. | 2013 | Completed Late |  | Reed, Don | Reed, Don | None | Final project report - 093013 with Cover.pdf
M3FT-13LA0818012 Carried over from FY12: M3FT-12LA0818013 | M3 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Test Plan for Forensic Analysis in the North Experimental Area of WIPP | Test Plan for Forensic Analysis in the North Experimental Area of WIPP | The Salt Disposal Investigations (SDI) test coordination office will develop a test plan that will determine the type, location and number of tests to examine during the re-entry of the North Experimental Area of WIPP. This milestone as listed in the referenced study plan is scheduled for 9/27/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-09-27 08:00 | 2013-10-31 06:00 | 2013-09-18 08:00 | This test strategy plan summarizes and consolidates the information necessary for the planning and development of a test bed in the WIPP for the coring, sampling, test equipment removal, data collection, and in-situ testing associated with historic thermal tests in WIPP Rooms A-1 and B. This plan summarizes the goals and anticipated test activities associated with these investigations and defines the detailed approach for access and obtaining this information. | 2013 | Complete |  | Weaver, Doug | Weaver, Doug | None | Test Plan for WIPP North Area Forensics 09232013 FINAL with COVER and SWIFT COMMENT.pdf
M4FT-13LA0818013 supercedes M3SF-12LA0818014 | M4 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Re-entry Plan for Mining into the North Experimental Area of WIPP | Re-entry Plan for Mining into the North Experimental Area of WIPP | WIPP M&O personnel and LANL will identify the process for planning a reentry into the north experimental area; this plan will be coordinated with the test planning. This milestone as listed in the referenced study plan is scheduled for 9/27/2013. Limitations within PICS dictate it be set at the end of March 2013. This milestone will need to be re-evaluated and potentially re-forecast during FY2013 planning. The completion of the milestone is contingent upon funding allocation in FY2013. | 2013-09-27 08:00 |  | 2013-07-01 02:00 |  | 2013 | Complete |  | Nuclear Waste Partnership LLC | Nuclear Waste Partnership LLC | None | M4FT-13LA0818013 - Mining Plan for Re-entry.pdf | FCRD-UFD-2013-000202
M3FT-13SN08180317 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Unconfined Compression Experiments on Bedded Salt at Elevated Temperature | Unconfined Compression Experiments on Bedded Salt at Elevated Temperature | Final Report for Thermomechanical Testing | 2013-09-27 12:00 |  | 2013-09-24 02:00 | Report delivered 3 day early. | 2013 | Complete |  | Hansen, Francis | Leigh, Christi | None | M3FT-13SN08180317_Unconfined_Comp_Exp_09242013.pdf
M3FT-13SN08180322 | M3 | 1.02.08.18.03 | SNL | FT-13SN081803 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures | 2013-09-27 12:00 |  | 2013-09-27 02:00 | Deliverable completed on schedule. | 2013 | Complete |  | Xiong, Yongliang | Leigh, Christi | None | M3FT-13SN08180322.pdf | FCRD-UFD-2013-000318
M3FT-13LA0807046 M4FT-13SN08070810 is Section 3 of this milestone report. | M3 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL | Painter, Scott | McMahon, Kevin | Report on integrated tool development for natural system evaluation | Integrated tool development for natural system evaluation | Report on integrated tool development | 2013-09-30 |  | 2013-09-30 | Report was delivered to UFD Campaign management on 9/30/2013. | 2013 | Complete |  | Painter, Scott | Painter, Scott | None | M3FT-13LA0807046.pdf | FCRD-UFD-2013-000375
M3FT-13SR0823052 same as M2FT-13SN0806061 | M3 | 1.02.08.23.05 | SRNL | FT-13SR082305 | UNF and HLW Disposal Option Evaluation - SRNL | Carter, Joe | Swift, Peter | SRNL final contribution to complete study | SRNL final contribution to complete study | SRNL will support developing the inventory and waste characteristics for defense and research reactor used fuel, vitrified HLW, and other miscellaneous wastes that may be targeted for geologic disposal. In addition support evaluation of group waste in various disposal environments. SRNL will write sections and conduct reviews as appropriate. | 2013-09-30 |  | 2013-09-30 | M2FT-13SN0806061, “Draft Evaluation of Options for Permanent Geologic Disposal of Used Nuclear Fuel and High-Level Radioactive Waste in Support of a Comprehensive National Nuclear Fuel Cycle Strategy.” | 2013 | Complete |  | Marra, James | Marra, James | None | Fw_ Completion of M2FT-13SN0806061-Draft Disposal Options Evalu.pdf |  | SRNL Final Complete Study
M4FT-13AN0808012 | M4 | 1.02.08.08.01 | ANL | FT-13AN080801 | Generic Disposal System Level Modeling - ANL | Nutt, Mark | McMahon, Kevin | Status of Clay/Shale GDSM Sensitivity Analysis for DPC Feasibility Evaluation | Enhancements to the Clay Generic Disposal System Modeling Capabilities | Report describing updates to the UFD Clay GDSM | 2013-09-30 01:00 |  | 2013-09-27 01:00 | The present report includes the model description from the previous report [Ref. 2] and presents new calculations using the UFDC Clay GDSM “Baseline” Model for a selected set of hypothetical clay repository conditions and with waste packages each containing 32 PWR fuel assemblies having a variety of burnups. | 2013 | Complete |  | Morris, Edgar | Nutt, Mark | None | ANL Clay GDSM - FY13 32 PWR Canister Sensitivity .docx | FCRD-UFD-2013-000390
M3FT-13SR0812011 | M3 | 1.02.08.12.01 | SRNL | FT-13SR081201 | DR Low Level Radioactive Waste Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Radionuclide Inventory Data | LLW Radionuclide Inventory Data | Update the LLW Radionuclide Inventory model developed in FY 2012 as directed by the Separations and Waste Form Campaign and Fuel Cycle Options Campaign. Potential updates include incorporation of additional fuel types (e.g. BWR, SFR, etc.), modification to reflect the results of the Industry Task Order for Improving the Estimates of Waste from Recycling, incorporation of an alternative waste classification system (i.e. other than strict adherance to 10CFR61) and modification for additional fuel cycle processes (e.g. electrochemical). | 2013-09-30 02:00 |  | 2013-09-25 | Revision 2 of the report, FCRD-UFD-2012-000186, "Low Level Waste Disposition - Low Level Waste Radionuclide Inventory". This report satisfies the UFD Level 3 Milestone, M3FT-13SR0812011, LLW Radionuclide Inventory Data. FCRD-UFD-2013-000362, "History of LLW Disposal in the United States - FY 2013 Update". This report satisfies the UFD Level 4 Milestone, M4FT-13SR0812013, LLW Disposal History Update. | 2013 | Complete |  | Jones, Robert | Jones, Robert | None | FCRD-UFD-2012-000186 LLW Radionuclide Inventory Rev 2 FINAL 9-25-13.pdf FCRD-UFD-2013-000362.pdf | FCRD-UFD-2013-000362
M4FT-13SR0812013 | M4 | 1.02.08.12.01 | SRNL | FT-13SR081201 | DR Low Level Radioactive Waste Disposition - SRNL | Jones, Robert | McMahon, Kevin | LLW Disposal History Update | History of LLW Disposal in the United States - FY 2012 Update | Update the history of low level radioactive waste disposal in the United States for significant events that occurred in FY 2013. | 2013-09-30 02:00 |  | 2013-09-25 | FCRD-UFD-2013-000362, "History of LLW Disposal in the United States - FY 2013 Update". This report satisfies the UFD Level 4 Milestone, M4FT-13SR0812013, LLW Disposal History Update. This report provides a summary of significant events related to commercial and Federal LLW disposal activities in FY 2013. This report supplements the original UFD LLW history report issued in FY 2010 (FCRD-USED-2010-000183, Update of Low-Level Radioactive Waste Disposal History in the United States). Additional updates previously issued in FY 2011 (FCRD-USED-2011-000300, Update of Low-Level Radioactive Waste Disposal History in the United States - FY-2011) and FY 2012 (FCRD-UFD-2012-000260, History of Low Level Radioactive Waste Disposal in the United States - FY 2012 Update) also supplement the original report. | 2013 | Complete |  | Jones, Robert | Jones, Robert | None | FCRD-UFD-2013-000362.pdf |  | Low Level Waste
M2FT-13SN0823012 ULR. Draft. DRAFT OF M2FT-13SN0823012 body of report is available in Non-Public NE 81 Milestones. Appendices only are available in Public NE-81 Milestones library. | M2 | 1.02.08.23.01 | SNL | FT-13SN082301 | UNF and HLW Disposal Option Evaluation - SNL | Swift, Peter | Swift, Peter | Draft report on evaluation of the potential impacts of existing UNF and HLW on the feasibility and performance of various disposal options | Draft report on evaluation of the potential impacts of existing UNF and HLW on the feasibility and performance of various disposal options | Draft report on evaluation of the potential impacts of existing UNF and HLW on the feasibility and performance of various disposal options | 2013-09-30 04:00 |  | 41547.0833 | Milestone met by delivery of a draft report to NE-53 and NE-5, ready for external peer review. | 2013 | Complete |  | Swift, Peter | Swift, Peter |  |  | FCRD-UFD-2013-000592
M5FT-13IN0807062 | M5 | 1.02.08.07.06 | INL | FT-13IN080706 | Generic Natural System Evaluations - INL | Simpson, Michael | None | Document information used to support electrorefiner salt PA | Document information used to support electrorefiner salt PA Report | This will be a report that describes all of the assumptions that go into the PA calculations. | 2013-09-30 06:00 | 2013-10-07 02:00 | 2013-10-07 02:00 | Draft report submitted on 10/7 | 2013 | Expected Late |  | Simpson, Michael | Simpson, Michael | None | Update on Assessment of Direct Disposal of Electrorefiner Salt v2.docx |  | electrorefiner salt
M3FT-13SN0823011 | M3 | 1.02.08.23.01 | SNL | FT-13SN082301 | UNF and HLW Disposal Option Evaluation - SNL | Swift, Peter | Swift, Peter | Evaluation of Options for Permanent Geologic Disposal of Used Nuclear Fuel and HIgh-Level Radioactive Waste in Support of a Comprehensive National Nuclear Fuel Cycle Strategy | Evaluation of Options for Pernament Disposal of Used Nuclear Fuel and High-Level Radioactive Waste In Support of A Comprehensive National Nuclear Fuel Cycle Strategy | Milestone will be fulfilled by delivery of the report in draft form to the DOE-NE Office of Fuel Cycle Technologies. | 2013-09-30 08:00 |  | 2013-09-30 02:00 | This M3 is the work activity that led to the M2FT-13SN0823012, delivery of draft report to NE-5. Both this M3 and the upper-level M2 are fullfilled by delivery of the M2 today. | 2013 | Complete |  | Swift, Peter | Swift, Peter | Draft held internally pending DOE review |  |  | Waste Form Inventory Disposal Options
M2FT-13LA08180113 | M2 | 1.02.08.18.01 | LANL | FT-13LA081801 | DR Salt R&D - LANL | Weaver, Doug | MacKinnon, Robert | Coupled Model for Heat and Water Transport in a HLW Repository | Coupled Model for Heat and Water Transport in a HLW Repository | This deliverable will be a comprehensive summary of results from the coupled THMC simulations for FY13. | 2013-09-30 10:00 |  | 41547.0833 | This report is organized as follows. It begins by presenting a summary of the coupled processes that are used in the simulations, including new algorithms implemented in FEHM specifically for this project (e.g., porosity change as salt dissolves and/or precipitates, water vapor pressure as a function of both salt concentration and temperature). Next, benchmarking exercises are presented that compare simulation results to recent LANL experiments on the thermal behavior of salt and water release from clay dehydration (FY13), as well as1980’s era non-heated and heated experimental data from WIPP. Next, the numerical model is used to make predictions of temperatures, porosity changes, and saturations that may occur for waste emplaced using the in-drift concept. These simulations are presented in order of increasing complexity, from thermal (T), to thermal hydrologic (TH), to thermal-hydrologic chemical (THC) in order to illustrate the relative importance of each process. These calculations are presented in the context of a future field test, and include, the most complex analyses, full THC calculations with initial results from clay dehydration simulations. Next, uncertainties in parameters such as initial saturation, depth of RoM backfill, and thermal diffusivity of drift air are addressed through uncertainty analyses for a generic salt repository. The report with chapters that begin the process of linking small scale observations of fluid inclusion migration to recent LANL experiments, and a brief discussion of the impacts of stress on short term calculations of heat and fluid flow. | 2013 | Complete |  | Stauffer, Philip | Stauffer, Philip | None | LANL_MILESTONE-M2FT-13LA08180113-final w Cover.pdf | FCRD-UFD-2013-000206
M4FT-13LB0806046 | M4 | 1.02.08.06.04 | LBNL | FT-13LB080604 | DR Generic Engineered Barrier System Evaluations - LBNL | Liu, Hui-Hai | McMahon, Kevin | THM and reactive transport model development and evaluation: International activities | THM and reactive transport model development and evaluation: International activities | Document international activities for THM and reactive transport model development and evaluation. The data sets from HE and DR-A tests (Mont Teri site) will be used for model evaluation. | 2013-10-16 08:00 |  | 2013-10-16 03:00 | on schedule | 2013 | 90 Day |  | Rutqvist, Jonny | Liu, Hui-Hai | None | M4FT-13LB0806046_final.pdf |  | EBS; International; THMC modeling; Reactive Transport
M2FT-13SN0806062 | M2 | 1.02.08.06.06 | SNL | FT-13SN080606 | DR Generic Engineered Barrier System Evaluations - SNL | Jove-Colon, Carlos | McMahon, Kevin | Used Fuel Degradation: Experimental and Modeling Report | Used Fuel Degradation: Experimental and Modeling Study | Used Fuel Degradation: Experimental and Modeling Report. This report will be based on contributions from SNL, PNNL, and ANL national laboratory teams. Integration of these efforts with those in other related UFD work packages (e.g., within EBS, GDSE) will be investigated along with those in the areas of criticality, inventory, and storage. | 2013-10-17 12:00 |  | 41564.0833 | Milestone deliverable is on schedule | 2013 | 90 Day |  | Sassani, David | Jove Colon, Carlos | None | M2FT-13SN0806062_Used_Fuel_Degradation_Experimental_Modeling_Report_FINAL.pdf | FCRD-UFD-2013-000404
M4FT-13OR0807031 Per Matt Brainard: Note: A .zip file was also uploaded into PICS:NE in support of this Deliverable. Please visit PICS:NE to review the details in the .zip file, if necessary. | M4 | 1.02.08.07.03 | ORNL | FT-13OR080703 | Regional Geology - ORNL | Howard, Rob | McMahon, Kevin | ORNL- Integration of GIS Data to Support Used Fuel Disposition | ORNL- Integration of GIS Data to Support Used Fuel Disposition | ORNL will combine the GIS population data layer from its FY12 work on this project with selected LANL GIS layers such as seismic, slope, groundwater sources, and federal lands use to generate GIS maps reflecting the combined visualization and display of these several GIS layers. ORNL shall verify the selected layers with LANL for processing and generate new maps using its OR-SAGE tool. The format for display will be coordinated with LANL. | 2013-10-21 04:00 |  | 2013-10-10 | This deliverable has been completed. | 2013 | 90 Day |  | Omitaou, Olufemi | Belles, Randy | None | ExclusionLayers.gdb.zip Population Exclusion Methodology.docx |  | Population Exclusion Layer
M2FT-13SN0817051 Final Report, supercedes M2FT-14SN0817022 | M2 | 1.02.08.17.05 | SNL | FT-13SN081705 | DR Deep Borehole Disposal - SNL | Arnold, Bill | Mackinnon, Robert | Deep Borehole Disposal Research: RD&D Needs and Criteria and Alternatives for Demonstration Site Selection | Deep Borehole Disposal Research: RD&D Needs and Criteria and Alternatives for Demonstration Site Selection | The report will describe set of technical siting criteria to screen sites that are clearly unsuitable or inappropriate for a deep borehole disposal (DBD) demonstration. Technical criteria will focus on factors that are potentially important to waste isolation in the DBD concept and to the successful implementation of the DBD demonstration, including relevant regional-scale characteristics. The report will also include a literature survey to identify relevant existing information on time-dependent properties of candidate seal materials under a range of environmental conditions. The report will also develop a safety framework for DBD by organizing the existing information and analyses for DBD and implement a systematic systems engineering approach to prioritizing the identified science and engineering needs for the DBD demonstration. | 2013-10-25 04:00 |  | 41572.0833 | Draft milestone report is complete and going into technical review during the second week of October. | 2013 | 90 Day |  |  |  | None | DBD_FY13_milestone_report_final_SAND2013-9490P.pdf
M4FT-14SN0816034 | M4 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Revise Assumptions | Assumptions for Evaluating Feasibility of Direct Geologic Disposal of Existing Dual-Purpose Canisters | Update the assumptions document produced in FY12 (FCRD-UFD-2012-000352 Rev. 0) to reflect needed changes identified in FY13 (FCRD-UFD-2013-000171 Rev. 0). | 2013-10-31 10:00 | 2013-11-20 02:00 | 2013-11-14 02:00 |  | 2014 | Completed Late | Assumptions for Evaluating Feasibility of Direct Geologic Disposal of Existing Dual-Purpose Canisters | Hardin, Ernest | Hardin, Ernest | None | Dual-Purpose Canister Disposal Catalog and Analysis Assumptions Rev. 1.pdf | FCRD-UFD-2014-000516
M4FT-14LB0804034 | M4 | 1.02.08.04.03 | LBNL | FT-14LB080403 | Waste Form Degradation Modeling - LBNL | Steefel, Carl | McMahon, Kevin | Nano-Continuum Modeling of a Nuclear Glass Specimen Altered for 25 Years | Nano-Continuum Modeling of a Nuclear Glass Specimen Altered for 25 Years | Simulation of results from isotopic exchange experiments in gel layer of corroded borosilicate glass conducted by PNNL. | 2013-11-01 02:00 | 2014-01-06 03:00 | 2014-01-06 03:00 |  | 2014 | Completed Late | Nano-Continuum Modeling of a Nuclear Glass Specimen Altered for 25 Years | Steefel, Carl | Steefel, Carl | None | M4FT-14LB0804034 LBNL.pdf | FCRD-UFD-2014-000480
M3FT-14LB0804033 | M3 | 1.02.08.04.03 | LBNL | FT-14LB080403 | Waste Form Degradation Modeling - LBNL | Steefel, Carl | McMahon, Kevin | Simulation of the corrosion rate of archaeological glass | Simulation of the corrosion rate of archaeological glass | The objective of this activity is to simulate the corrosion rate of the Ancient French Glass that has been now under study for many years. | 2013-11-01 08:00 | 2014-01-06 03:00 | 2014-01-06 03:00 |  | 2014 | Completed Late | Preliminary Simulation of the Corrosion Rate of Archaeological Glass | Steefel, Carl | Steefel, Carl | None | M3FT-14LB0804033 LBNL.pdf | FCRD-UFD-2014-000311
M4FT-14LB0806066 supersedes M4FT-13LB0807055 | M4 | 1.02.08.06.06 | LBNL | FT-14LB080606 | Argillite Disposal R&D International - LBNL | Liu, Hui-Hai | McMahon, Kevin | Report on international collaborations on FE heater and HG-A tests | Report on international collaborations on FE heater and HG-A tests | Document modeling activities for FE heater and HG-A tests | 2013-11-06 02:00 |  | 2013-11-06 08:00 |  | 2014 | Complete | Report on International Collaboration Involving the FE Heater and HG-A Tests at Mont Terri | Houseworth, James | Liu, Hui-Hai | None | M4FT-14LB0806066 LBNL.pdf | FCRD-UFD-2014-000002
M4FT-13LL0807071 supersedes M4FT-12LL0807075 | M4 | 1.02.08.07.07 | LLNL | FT-13LL080707 | Generic Natural System Evaluations - LLNL | Zavarin, Mavrik | McMahon, Kevin | International collaboration - Radionuclide interactions and transport in geologic repository environments – Pu interaction with clay | Progress report on international collaboration: Pu interactions with bentonite MS supports SNL’s L2 (11/6/13) | Batch experiments will be conducted on Pu interaction with and desorption from bentonite particles at temperatures of 25 and 80 oC. This is part of LLNL’s international efforts with KIT for CFM in NS; work to be performed at LLNL is complimentary to what KIT is doing. | 2013-11-06 15:00 | 2014-03-31 03:00 | 2013-11-14 03:00 | LLNL is shutting down due to budget impasse. In addition this deliverable was expanded and extended to August 15th to better feed into a MS2 International | 2013 | Expected Late |  |  | Zavarn, Mavrik | None | M4FT-13LL0807071_FINAL.pdf
M4FT-14LB0806045 supersedes M4FT-13LB0807054 | M4 | 1.02.08.06.04 | LBNL | FT-14LB080604 | Argillite Disposal R&D - LBNL | Liu, Hui-Hai | McMahon, Kevin | Report on hydrologic flows in low permeability media | Report on hydrologic flows in low permeability media | Study non-Darcy flow and its impact in clay reporsitory | 2013-11-13 02:00 |  | 2013-11-13 03:00 |  | 2014 | Complete | Report on Hydrologic Flow in Low- Permeability Media | Liu, Hui-Hai | Liu, Hui-Hai | None | M4FT-14LB0806045 LBNL.pdf | FCRD-UFD-2014-000001
M4FT-13LB0807021 | M4 | 1.02.08.07.02 | LBNL | FT-13LB080702 | Regional Geology - LBNL |  | McMahon, Kevin | Report on Inventory of Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Report on Inventory of Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Compile any additional available information on the extent, thickness and depth of shale formations. Initiate efforts to compile data on the hydrological, mechanical, and thermal properties and mineral and aqueous geochemical compostions of shale formations. Also initiate efforts to compile information on the geologic history of shale basins including timing and depth of maximum burial, evidence of past seismic activity, evidence of past episodes of fracturing and faulting, and aspects of the geologic environment such as the character of overlying and underlying formations. | 2013-11-15 14:00 |  |  | on schedule | 2013 | 90 Day |  |  |  | None
M2FT-13SN0808043 Per Matt Brainard: Carried over from FY13 to FY14 and was completed and uploaded under FY14 FCR&D. It is attached. The FY14 Milestone Number assigned to it is M2FT-14SN0808033 | M2 | 1.02.08.08.04 | SNL | FT-13SN080804 | Generic Disposal System Level Modeling - SNL |  | McMahon, Kevin | Generic Disposal System Modeling Report | Enhancements to Generic Disposal System Modeling Capabilities | Enhance the capability to develop and run PA models of generic disposal systems Prepare Generic Disposal System Modeling Report | 2013-11-16 08:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None
M4FT-14LB0814022 | M4 | 1.02.08.14.02 | LBNL | FT-14LB081402 | Regional Geology R&D - LBNL | Dobson, Patrick | McMahon, Kevin | Report on Inventory of Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Report on Inventory of Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Compile any additional available information on the extent, thickness and depth of shale formations. Initiate efforts to compile data on the hydrological, mechanical, and thermal properties and mineral and aqueous geochemical compostions of shale formations. Also initiate efforts to compile information on the geologic history of shale basins including timing and depth of maximum burial, evidence of past seismic activity, evidence of past episodes of fracturing and faulting, and aspects of the geologic environment such as the character of overlying and underlying formations. | 2013-11-27 02:00 |  | 2013-11-22 03:00 |  | 2014 | Complete | Inventory of Shale Formations in the US Including Geologic, Hydrological, and Mechanical Characteristics | Dobson, Patrick | Dobson, Patrick | None | M4FT-14LB0814022 LBNL.pdf | FCRD-UFD-2014-000513
M2FT-13SN0807086 | M2 | 1.02.08.07.08 | SNL | FT-13SN080708 | Generic Natural System Evaluations - SNL |  | McMahon, Kevin | Natural System Evaluations: International Collaborations Progress Report | Natural System Evaluations: International Collaborations Progress | The international collaborations at SNl will include (1) development of in-situ geophysical and geochemical characterization techniques at ROK KURT and (2)using Czech Bedrichov Tunnel testing data. The work will also include obtaining fracture mapping data at KURT for discrete fracture model development and demonstration. Natural System Evaluations: International Collaborations Progress Report | 2013-12-09 08:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None |  | FCRD-UFD-2013-000628
M2FT-14SN0806054 supercedes M2FT-13SN0806063 | M2 | 1.02.08.06.05 | SNL | FT-14SN080605 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | International Collaborations on Engineered Barrier Systems: Experimental and Modeling Investigations Report | International Collaborations on Engineered Barrier Systems: Experimental and Modeling Investigations | International Collaborations on Engineered Barrier Systems. This report will be based on the collaborations with international partners (e.g., DECOVALEX, Mt. Terri site) on (1) experimental and modeling investigations on EBS materials and concepts, and (2) field-scale research on cement - opalinus clay (CI) interaction experiment at the Mt. Terri site. | 2013-12-11 08:00 |  | 41619.0833 |  | 2014 | Complete | International Collaborations on Engineered Barrier Systems: Experimental and Modeling Investigations Report | Rutqvist, Jonny | Rutqvist, Jonny | None | M2FT-14SN0806054_Final.pdf | FCRD-UFD-2014-000058
M4FT-14LA0807064 supersedes M4FT-13LA08070414 | M4 | 1.02.08.07.06 | LANL | FT-14LA080706 | Crystalline Disposal R&D International - LANL | Painter, Scott | McMahon, Kevin | Summary of international collaborations on modeling BRIE experiment | Summary of international collaborations on modeling BRIE experiment | Summary of international collaborations on modeling BRIE experiment. | 2013-12-15 12:00 |  | 2013-11-27 02:00 |  | 2014 | Complete | Status of International Collaborations on Modeling the Bentonite Rock Interaction Experiment | Painter, Scott | Painter, Scott | None | M4FT-14LA0807064.pdf | FCRD-UFD-2014-000498
M2FT-13LA0807041 same as M2FT-12LA0807051 | M2 | 1.02.08.07.04 | LANL | FT-13LA080704 | Generic Natural System Evaluations - LANL |  | McMahon, Kevin | Report on modeling fluid flows in natural system, model validation and demonstration | Modeling fluid flows in natural system, model validation and demonstration | Report on modeling fluid flows in natural system, model validation and demonstration | 2013-12-15 22:00 |  |  | Work is on schedule | 2013 | 90 Day |  |  |  | None
M3FT-14SN0816032 same as M3FT-14SN0816037 | M3 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | DPC Disposal Concept Baseline Report | DPC Disposal Concepts Baseline Report | In support of the DPC disposal feasibility determination, specify the range of disposal concepts under consideration, including functional descriptions for overpacks and other engineered components. Provide system description information for several medium-specific disposal concepts including (but not limited to) salt, hard rock unsaturated “open,” and sedimentary backfilled “open.” Present information to clearly represent technical approaches to disposability and their dependence on geology, for possible use in work on standardized packaging, and by the cask/canister industry. | 2013-12-19 18:00 |  | 41628.0833 |  | 2014 | Completed Late | Spent Fuel Canister Disposability Baseline Report Prepared | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2014-000330 R0 final baseline disposability.pdf | FCRD-UFD-2014-000330
M3FT-14SN0818014 same as M3FT-13SN08180316 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Thermal Conductivity of Salt as a Function of Porosity | Thermal Conductivity of Salt as a Function of Porosity | Thermal Conductivity of Salt as a Function of Porosity | 2014-01-15 14:00 | 2014-03-28 04:00 | 2014-03-12 04:00 |  | 2014 | Completed Late | Thermophysical Properties of Reconsolidating Crushed Salt | Bauer, Stephen | Bauer, Stephen | None | M3FT-14SN0818014 Thermal Conductivity of Salt as a Function of Porosity.docx TCSAND07.doc | FCRD-UFD-2014-000337 | Thermal Conductivity, Crushed Salt
M4FT-14PN0804063 Literature search for Journal Paper | M4 | 1.02.08.04.06 | PNNL | FT-14PN080406 | Radiolysis Model Development - PNNL | Buck, Edgar | McMahon, Kevin | Journal Paper on 5-Metal Particle | Nanostructure of metallic particles in high burn-up light water reactor used fuel | Work on literature search and write up on journal paper. Work on radiolysis results and program. Submit journal paper on metallic particle analysis from used fuel. | 2014-01-17 23:00 |  | 41655.25 |  | 2014 | Complete | Implication of the presence of silver iodide in used nuclear fuel | Buck, Edgar | Buck, Edgar | None | JNM format update - Implication on the presence of silver iodide in used nuclear fuel.pdf | FCRD-UFD-2014-000485
M2FT-14LA0814012 supercedes M2FT-13LA0807012 | M2 | 1.02.08.14.01 | LANL | FT-14LA081401 | Regional Geology R&D - LANL | Perry, Frank | McMahon, Kevin | Report on a GIS Database for Alternative Host Rocks and Potential Siting Guidelines | GIS Database for Alternative Host Rocks and Sensitivity to Potential Siting Guidelines | Activity will support continued development of a GIS database for regional geology and siting guidelines tool development, as well as support completion of a Level 2 Milestone. | 2014-01-24 02:00 |  | 2014-01-22 02:00 |  | 2014 | Complete | Regional Geology: A GIS Database for Alternative Host Rocks and Potential Siting Guidelines | Perry, Frank | Perry, Frank |  | LANL.Perry.M2FT-14LA0814012-REVISED.pdf | FCRD-UFD-2014-000068
M3FT-14SN08180114 replaces M3FT-14SN08180110 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Results from The 4th US German Workshop on Salt | Results from The 4th US German Workshop on Salt | xxx | 2014-01-31 08:00 |  | 2013-12-23 02:00 |  | 2014 | Complete | Proceedings of the 4th US/German Workshop on Salt Repository Research, Design, and Operation | Hansen, Francis | Hansen, Francis | None | M3FT-14SN08180114 hansen.pdf | FCRD-UFD-2014-000335
M2FT-14LA0807024 | M2 | 1.02.08.07.02 | LANL | FT-14LA080702 | Crystalline Disposal R&D - LANL | Painter, Scott | McMahon, Kevin | Report on Modeling Fluid Flow in Natural Systems, Model Validation and Demonstration | Modeling Fluid Flow in Natural Systems, Model Validation and Demonstration | Report on modeling fluid flows in natural system, model validation and demonstration | 2014-01-31 12:00 |  | 2014-01-30 02:00 |  | 2014 | Complete | Modeling Fluid Flow in Natural Systems: Model Validation and Demonstration | Painter, Scott | Painter, Scott | None | M2FT-14LA0807024.pdf | FCRD-UFD-2014-000059
M3FT-14SN0818013 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Analysis of Data from Salt Reconsolidation Experiments at Sandia National Laboratories in FY12 and FY13 | Analysis of Data from Salt Reconsolidation Experiments at Sandia National Laboratories in FY12 and FY13 | Analysis of Data from Salt Reconsolidation Experiments at Sandia National Laboratories in FY12 and FY13 | 2014-02-12 16:00 | 2014-04-24 02:00 | 2014-03-13 04:00 |  | 2014 | Completed Late | Reconsolidation of Crushed Salt to 250°C Under Hydrostatic and Shear Stress Conditions | Broome, Scott | Broome, Scott | None | Broome_et_al.-6959.pdf M3FT-14SN0818013 Analysis of Data From Salt Reconsolidation Experiments at SNL in FY12 and FY13.docx | FCRD-UFD-2014-000336
M4FT-14OR0816042 | M4 | 1.02.08.16.04 | ORNL | FT-14OR081604 | DR Disposal of Dual Purpose Canisters - ORNL | Howard, Rob | Mackinnon, Robert | Revise workplan | Work Plan for Direct Disposal of Dual Purpose Canister Feasibility Studies | Revise to reflect FY13 analysis results and recommendations (from report FCRD-UFD-2013-000171 Rev. 0) and to remove existing Standardized Canister workscope. | 2014-02-28 02:00 | 2014-05-21 | 2014-05-31 |  | 2014 | Completed Late | Feasibility Evaluation for Direct Disposal of Dual Purpose Canisters: Study Plan | Howard, Rob | Howard, Rob | None | Feasibility_of_Direct_Disposal_PlanSched31May2014.pdf | FCRD-UFD-2014-000518 | Dual Purpose Canister, Disposal
M3FT-14SN0818015 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Modified Test Plan For Salt Reconsolidation Experiments at Sandia National Laboratories | Modified Test Plan For Salt Reconsolidation Experiments at Sandia National Laboratories | Test plan to be updated based on previous testing. | 2014-03-12 10:00 | 2014-06-26 08:00 | 2014-06-30 02:00 |  | 2014 | Completed Late | Test Plan SNL-FCT-TP-14-002 Experimental Investigation of Two-Phase Flow in Rock Salt | Malama, Bwalya | Malama, Bwalya | None | Final Test Plan_Two-Phase-Flow-Test-Plan_SNL-FCT-TP-002_Rev 0_20140630 (3).pdf | FCRD-UFD-2014-000338 | Two-Phase Flow ; Consolidated Rock Salt
M4FT-14OR0816044 | M4 | 1.02.08.16.04 | ORNL | FT-14OR081604 | DR Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Criticality Analysis Approach for DPC Direct Disposal Feasibility Evaluation | Criticality Analysis Approach for DPC Direct Disposal Feasibility Evaluation | The M4 deliverable will document an approach to analyzing the potential for postclosure criticality of DPCs in different disposal environments that considers environment-specific conditions with degradation scenario development, and exploits reactivity margin that may be implicit in current DPC design basis certificates of compliance for transportation. The deliverable will identify new cases (e.g., different representations of basket and package degradation), recommend an analysis approach (e.g., tailored to different DPC types and geologic settings),comment on the corresponding regulatory approach, and include a Criticality Analysis Roadmap that will depict the evolution of our criticality analysis approach through the phases of the DPC Direct Disposal Feasibility Study. This will ensure transparency regarding those considerations required in the early phases of the Study versus those later in the Study which will require, to the extent practicable, a certain degree of rigor and further considerations taken into account in order to support any future DOE decision regarding the feasibility of direct disposal of DPCs in a future repository. | 2014-03-14 |  | 2014-03-14 |  | 2014 | Complete | Criticality Analysis Process for Direct Disposal of Dual Purpose Canisters | Scaglione, John | Scaglione, John | None | Crit analysis process for direct disposal of DPCs 3-12-2014.pdf | FCRD-UFD-2014-000519 | criticality, disposal, feasibility
M2FT-14IN0801011 | M2 | 1.02.08.01.01 | INL | FT-14IN080101 | Mgmnt & Integration - INL | Bragg-Sitton, Shannon | Bragg-Sitton, Shannon | UFD Campaign Implementation Plan Update | UFD Campaign Implementation Plan Update | UFD Campaign Implementation Plan Update | 2014-03-28 08:00 |  | 2014-03-27 02:00 |  | 2014 | Complete | Update of the Used Fuel Disposition Campaign Implementation Plan | Bragg-Sitton, Shannon | Bragg-Sitton, Shannon | None |  | FCRD-UFD-2014-000047
M4FT-14SN0816036 | M4 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | System-Level Logistics, Cost Estimation and Fuel Selection for DPC Disposal (FY14) | Letter Report: Logistics, Cost Estimation and Fuel Selection Analysis for DPC Direct Disposal | Document logistical studies to evaluate DPC direct disposal scenarios as discussed in the FY13 deliverable (FCRD-UFD-2013-000171 Rev. 0, Section 10) and including the impacts from alternative fuel selection strategies. | 2014-04-30 10:00 | 41793.25 | 41793.0833 |  | 2014 | Completed Late | System-Level Logistics for Dual-Purpose Canister Disposal | Kalinina, Elena | Kalinina, Elena | None | System-Level Logistics for DPC Disposal June 3 2014.pdf | FCRD-UFD-2014-000517
M3FT-14SN0816037 same as M3FT-14SN0816032 | M3 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Letter Report: Underground Opening Stability Survey for Argillaceous Media | Letter Report: Underground Opening Stability Survey for Argillaceous Media | Document a survey of the observed long-term opening stability of underground openings in shale and other argillaceous rock types, researching rail and highway tunnels, and other excavations, and their ground support systems. | 2014-05-23 08:00 | 41801.0833 | 41801.0833 |  | 2014 | Completed Late | Review of Underground Construction Methods and Opening Stability for Repositories in Clay/Shale Media | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2014-000330 UG Opening Stability Final.pdf | FCRD-UFD-2014-000331 | repository excavation support clay shale
M4FT-14SR0816052 | M4 | 1.02.08.16.05 | SRNL | FT-14SR081605 | DR Disposal of Dual Purpose Canisters - SRNL | Carter, Joe | Mackinnon, Robert | Investigation of DPC filler materials | Potential DPC Filler Materials | SRNL will prepare a level 4 milestone report on potential DPC filler materials. | 2014-05-30 |  | 2014-05-28 |  | 2014 | Complete | Potential Dual Purpose Canister (DPC) Filler Material | Severynse, Tom | Severynse, Tom | None | FCRD-UFD-2014-000522 - DPC Fill Materials Rev 0.pdf | FCRD-UFD-2014-000522 | Dual Purpose Canister Filler Materials
M4FT-14SN0804071 | M4 | 1.02.08.04.07 | SNL | FT-14SN080407 | Waste Package Performance - DPC Overpacks and Internal Workings - SNL | Rechard, Rob | McMahon, Kevin | Experimental plan for DPC/overpack performance in repository | Experimental plan for evaluating DPC/overpack performance in repository | Develop an experimental plan for evaluating the performance of a DPC with overpack in several generic repository environments | 2014-05-30 06:00 | 2014-09-30 02:00 | 2014-09-30 02:00 | Completed report of the experimental plan for evaluating the performance of a DPC and its overpack in a repository | 2014 | Completed Late | Experimental Plan for DPC/Overpack Performance in a Repository | Ilgen, Anastasia | Rechard, Rob | None | Experimental plan for DPC-overpack performance in repository Ilgen 09-30-14.pdf |  | Dual-Purpose Canister, Corrosion Experiments, Spent Nuclear Fuel Disposal
M3FT-14SN0818017 supercedes M3FT-13SN08180339 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Thermomechanical Testing of Intact Salt Results for FY14 | Thermomechanical Testing of Intact Salt Results for FY14 | Test plan for Thermomechanical Testing of Intact Salt Results for FY14 | 2014-06-16 10:00 | 2014-09-30 12:00 | 2014-09-26 02:00 | This Test Plan describes scientific procedures for completing confined, triaxial, constant strain rate strength tests of intact salt at temperatures ranging from about 27°C to about 100°C. Laboratory studies allow generic salt properties (mechanical, thermal, hydrological, and chemical) to be measured in a controlled environment. There is a large body of laboratory data that describes the phenomenology of salt across a broad range of temperatures expected in a heat-generating waste disposal system. Laboratory studies currently underway in Germany are being conducted using salt samples provided by Sandia National Laboratories that were obtained from the WIPP site and those test results will add substantively to that body of knowledge. When combined, the total database of laboratory results will be used to develop input parameters for models, to assess adequacy of existing models, and to predict material behavior. These laboratory studies are also consistent with the aims of international salt repository research programs. | 2014 | Completed Late | Adjunct Laboratory Tests in Support of US/German Salt Characterization Program | Buchholz, Stuart | Stuart A. Buchholz | None | M3FT-14SN0818017.pdf | FCRD-UFD-2014-000339
M4FT-14LB0816021 | M4 | 1.02.08.16.02 | LBNL | FT-14LB081602 | DR Disposal of Dual Purpose Canisters - LBNL | Birkholzer, Jens | Mackinnon, Robert | Impact of High Waste Package Temperature on Near-Field Argillaceous Host Rock | Impact of High Waste Package Temperature on Near-Field Argillaceous Host Rock | LBNL will submit a letter report (M4; 30 June 2014) suitable for incorporation in a M2 deliverable in August. | 2014-06-30 03:00 |  | 2014-06-30 03:00 |  | 2014 | Complete | Model Evaluation of the Thermo-Hydrological-Mechanical Response in Argillaceous Sedimentary Rock Repository for Direct Disposal of Dual-Purpose Canisters | Zheng, Liange | Birkholzer, Jens | None | M4FT-14LB0816021 page iii signed.pdf ZhengL-M4FT-14LB0816021.pdf | FCRD-UFD-2014-000515 | argillite, THM, modeling, DPC
M4FT-14OR0816045 | M4 | 1.02.08.16.04 | ORNL | FT-14OR081604 | DR Disposal of Dual Purpose Canisters - ORNL | Howard, Rob | Mackinnon, Robert | DPC Reactivity and Groundwater Absorption Analyses | DPC Reactivity and Groundwater Absorption Analyses | Document the impacts on reactivity for flooding of representative DPCs with groundwater of different compositions. Identify additional DPCs with potentially low reactivity (following up on FY13 activities) for which criticality analyses indicate disposability. In addition, identify possible loading modifications for future DPCs (using existing designs) that would facilitate disposability. | 2014-06-30 06:00 |  | 41820 |  | 2014 | Complete | DPC Reactivity and Groundwater Absorption Analyses | Banerjee, Kaushik | Scaglione, John | None | FCRD-Report_Groundwater_Final.pdf | FCRD-UFD-2014-000520 | Dual Purpose Canister Criticality
M4FT-14LA0816011 | M4 | 1.02.08.16.01 | LANL | FT-14LA081601 | DR Disposal of Dual Purpose Canisters - LANL | Perry, Frank | Mackinnon, Robert | Assessment of saline groundwater environments for alternative geologic media and geologic settings | Assessment of saline groundwater environments for alternative geologic media and geologic settings | Report will describe assessment of data availability for saline aquifers in alternative host media and geologic environments and methods of inputting that data and information into a GIS framework. | 2014-06-30 08:00 |  | 2014-06-30 02:00 |  | 2014 | Complete | Survey of Chloride Concentrations in Formation (Pore) Waters of Crystalline Rocks and Shale | Perry, Frank | Perry, Frank | None | DPC_Criticality_Chloride_M4FT-14LA0816011_Perry_LANL.pdf | FCRD-UFD-2014-000514
M4FT-14AN0804013 input to M2FT-14SN0804051 | M4 | 1.02.08.04.01 | ANL | FT-14AN080401 | Waste Form Degradation Modeling - ANL | Zapol, Peter | McMahon, Kevin | provide input for Model Integration for Engineered Materials Performance | input for Model Integration for Engineered Materials Performance | provide results of calculations of hydrolysis reactions for inclusion into integrating framework specified by SNL | 2014-07-11 05:00 |  | 2014-07-11 01:00 |  | 2014 | Complete | Reaction Barriers for Glass Corrosion from First Principles Calculations |  |  | None | zapol_M4FT-14AN080401.pdf | FCRD-UFD-2014-000477
M4FT-14LA0804024 | M4 | 1.02.08.04.02 | LANL | FT-14LA080402 | Waste Form Degradation Modeling - LANL | Liu, Ben | McMahon, Kevin | Corrosion mechanisms for metal alloy waste forms- experiment and theory | Corrosion mechanisms for metal alloy waste forms- experiment and theory | Provide input for the M2 milestone from SNL on progress made year to date. This input will be based on the interactions between candidate metal alloy waste forms, primarily designed for the disposition of technetium, and a range of environmental conditions that may lead to corrosion. | 2014-07-11 10:00 |  | 2014-07-11 02:00 |  | 2014 | Complete | Corrosion mechanisms for metal alloy waste forms – experiment and theory | Liu, Xiang-Yang (Ben) | Liu, Xiang-Yang (Ben) | None |  | FCRD-UFD-2014-000478
M4FT-14PN0804061 | M4 | 1.02.08.04.06 | PNNL | FT-14PN080406 | Radiolysis Model Development - PNNL | Buck, Edgar | McMahon, Kevin | Report on Radiolysis Modeling of Used Fuel Disposal | Radiolytic Effects in a Chloride Brine: Model Sensitivity and Comparison with Experiments | Milestone report that describes modeling efforts for saline conditions and comparison with experiment. | 2014-07-11 17:00 |  | 2014-07-09 06:00 |  | 2014 | Complete | Radiolysis Model Formulation for Integration with the Mixed Potential Model | Buck, Edgar | Buck, Edgar | None | RM-UFD-Integration-Buck.pdf | FCRD-UFD-2014-000484
M4FT-14PN0804045 Contribution to L2 Milestone: SNL Overall Control Account” Milestone: M4FT-14PN0804045 | M4 | 1.02.08.04.04 | PNNL | FT-14PN080404 | Waste Form Degradation Modeling - PNNL | Smith, Frannie | McMahon, Kevin | Contribution to L2 Milestone: SNL overall Control Account | Contribution to L2 Milestone SNL | Provide input for the M2 milestone from SNL on progress made year to date. This input will be based on metal corrosion mechanisms focusing on the continued development, validation, and demonstration of simulation tools to lead the understanding of metal alloy corrosion over long-time periods. | 2014-07-11 19:00 |  | 41831.25 |  | 2014 | Complete | Letter Report on Completion of Milestone – “Contribution to L2 Milestone: SNL Overall Control Account” Milestone: M4FT-14PN0804045 | Rieke, Peter | Rieke, Peter | None | M4FT-14PN0804045 Rieke 11Jul2014.pdf | FCRD-UFD-2014-000483
M4FT-14PN0804041 | M4 | 1.02.08.04.04 | PNNL | FT-14PN080404 | Waste Form Degradation Modeling - PNNL | Rieke, Peter | McMahon, Kevin | Contribution to L2 Milestone: SNL overall Control Account | Contribution to L2 Milestone: SNL overall Control Account | Provide input for the M2 milestone from SNL on progress made year to date. This input will be based on developing a tool capable of analyzing available models of glass dissolution against existing glass dissolution databases. | 2014-07-12 08:00 |  | 2014-07-22 03:00 |  | 2014 | Completed Late | Contribution to L2 Milestone: SNL overall Control Account | Smith, Frances | Smith, Frances | None | M4FT-14PN0804041 Report-Smith-final.pdf | FCRD-UFD-2014-000481
M4FT-14AN0806011 | M4 | 1.02.08.06.01 | ANL | FT-14AN080601 | Argillite Disoosal R&D - ANL | Ebert, William | McMahon, Kevin | Fuel degradation in argillite media | Fuel degradation in argillite media | Results of applying mixed potential model (and radiolysis model) to conditions representing disposal system in argillite media provided for inclusion in SNL summary report. | 2014-07-14 10:00 |  | 2014-07-14 02:00 |  | 2014 | Complete | ANL Mixed Potential Model for Used Fuel Degradation: Application to Argillite and Crystalline Rock Environments. | Jerden, James | Ebert, William | None | ANL_MPM_FCRD-UFD-2014-000490.pdf | FCRD-UFD-2014-000490 | UO2; degradation model; mixed potential model
M4FT-14LA0806021 | M4 | 1.02.08.06.02 | LANL | FT-14LA080602 | Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | argillite EBS experimental program 2014 | argillite EBS experimental program 2014 | Experimental investigations focused on three major studies: Evaluating interactions with repository wall rock (argillite), conduct long-term (i.e., six-month) experiments to reproduce the thermal pulse event of a repository, and further experiments to elucidate the conditions for the formation of illite under depository conditions. | 2014-07-15 08:00 |  | 2014-07-15 02:00 |  | 2014 | Complete | LANL Argillite EBS Experimental Program 2014 | Caporuscio, Florie | Caporuscio, Florie | None | 2014 FCRD-Report EBS-LANL-Final.pdf | FCRD-UFD-2014-000491 | bentonite, EBS, zeolites, high temperature, steel corrosion inhibitors
M4FT-14OR0816046 | M4 | 1.02.08.16.04 | ORNL | FT-14OR081604 | DR Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | DPC Filler Literature Review | Whitepaper on DPC filler materials | Whitepaper surveying available concepts and materials that might be suitable for filling existing or future DPCs, to mitigate the potential for postclosure criticality. | 2014-07-17 |  | 41836 |  | 2014 | Complete | Potential DPC Filler Materials | Jubin, Robert | Scaglione, John | None | DPC Fill Materials M4 Report - Rev 0i.docx | FCRD-UFD-2014-000521
M4FT-14LB0804031 | M4 | 1.02.08.04.03 | LBNL | FT-14LB080403 | Waste Form Degradation Modeling - LBNL | Steefel, Carl | McMahon, Kevin | Micro-Continuum Modeling of Nuclear Glass Corrosion | Micro-Continuum Modeling of Nuclear Waste Glass Corrosion | Contribute report on long term micro-continuum and nano-continuum model of nuclear glass corrosion, with an emphasis on 1) simulation of the 26 year SON68 glass, and 2) simulation of the isotope exchange experiments. | 2014-07-24 23:00 | 2014-08-15 03:00 | 2014-08-12 03:00 |  | 2014 | Completed Late | Micro-Continuum Modeling of Nuclear Waste Glass Corrosion | Steefel, Carl | Steefel, Carl | None | M4FT-14LB0804031 LBNL.pdf | FCRD-UFD-2014-000479 | Glass corrosion, Waste form modeling, SON 68 glass
M4FT-14LL0817019 | M4 | 1.02.08.17.01 | LLNL | FT-14LL081701 | DR Deep Borehole Disposal - LLNL | Sutton, Mark | Mackinnon, Robert | Deep Borehole Material Degradation and Effects Report | Deep Borehole Material Degradation Report | Deep borehole material degradation report including degradation mode survey evaluation and initial assessment of vertical near-field thermal-hydrologic processes. | 2014-08-01 03:00 |  | 2014-08-01 03:00 |  | 2014 | Complete | FY14 Progress Report on Deep Borehole Material Degradation and Effects | Sutton, Mark | Sutton, Mark | None | LLNL Input to Deep Borehole Disposal Research_r1.docx | FCRD-UFD-2014-000523 | Deep Borehole, Cesium-137, Strontium-90
M4FT-14LL0806039 | M4 | 1.02.08.06.03 | LLNL | FT-14LL080603 | Argillite Disposal R&D - LLNL | Sutton, Mark | McMahon, Kevin | Thermodynamic Evaluations Progress Report | Thermodynamic Data Progress Report | Progress report on thermodynamic evaluations | 2014-08-02 16:00 |  | 2014-08-01 06:00 |  | 2014 | Complete | Thermodynamic Evaluations Progress Report | Zavarin, Mavrik | Zavarin, Mavrik | None | M4FT-4LL0806039rev2.pdf | FCRD-UFD-2014-000492 | uranium, neptunium, sorption, diffusion, clay, shale, modeling, experiment
M3FT-14LB0808021 | M3 | 1.02.08.08.02 | LBNL | FT-14LB080802 | DR Generic Disposal System Analysis - LBNL | Birkholzer, Jens | Mackinnon, Robert | Modeling Studies Supporting Generic Disposal System Analysis in Argillites | Modeling Studies Supporting Generic Disposal System Analysis in Argillites | Report describing (1) important subsystem processes, (2) how to include them in a system-level model, and (3) a generic reference case for a generic argillite disposal system. | 2014-08-08 13:00 |  | 2014-08-08 03:00 |  | 2014 | Complete | Modeling Studies Supporting Generic Disposal System Analysis in Argillites | LBNL | Birkholzer, Jens | None | M3FT-14LB0808021 LBNL.pdf | FCRD-UFD-2014-000319 | reference case, argillite, repository, bentonite, EBS
M4FT-14LA0808012 | M4 | 1.02.08.08.01 | LANL | FT-14LA080801 | DR Generic Disposal System Analysis - LANL | Painter, Scott | Mackinnon, Robert | Report on Analyses of a Generic Granite Repository System | Analyses of Generic Granite Disposal System | Report describing (1) important subsystem processes, (2) how to include them in a system-level model, (3) a generic reference case, and (4) system-level simulations for a generic granite disposal system. | 2014-08-08 14:00 | 2014-08-12 02:00 | 2014-08-15 02:00 |  | 2014 | Completed Late | Generic Crystalline Disposal Reference Case | Painter, Scott | Painter, Scott | None | M4FT-14LA0808012.pdf | FCRD-UFD-2014-000500
M4FT-14SN0818052 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Granular Salt Summary | Granular Salt Summary | Granular Salt Summary | 2014-08-11 04:00 |  | 2014-07-24 02:00 |  | 2014 | Complete | Granular Salt Summary: Reconsolidation Principles and Applications | Hansen, Francis | Kuhlman, Kris | None | FCRD-UFD-2014-000590_Rev0_Granular-Salt-Summary.pdf |  | salt, crushed salt, reconsolidation, healing
M4FT-14AN0807011 supersedes M4FT-13AN0806011 | M4 | 1.02.08.07.01 | ANL | FT-14AN080701 | Crystalline Disposal R&D - ANL | Ebert, William | McMahon, Kevin | Fuel degradation in crystalline media | Fuel degradation in crystalline media | Results of applying mixed potential model (and radiolysis model) to conditions representing disposal system in crystalline media provided for inclusion in SNL summary report. | 2014-08-15 05:00 |  | 2014-07-14 02:00 |  | 2014 | Complete | ANL Mixed Potential Model for Used Fuel Degradation: Application to Argillite and Crystalline Rock Environements | Jerden, James | Ebert, William | None | ANL_MPM_FCRD-UFD-2014-000490.pdf | FCRD-UFD-2014-000494 | UO2; fuel degradation; mixed potential model
M4FT-14SN0807081 | M4 | 1.02.08.07.08 | SNL | FT-14SN080708 | Crystalline Disposal R&D International - SNL | Wang, Yifeng | McMahon, Kevin | Report on international collaboration on fluid flow in fractured crystalline rocks | Report on fluid flows in fractured crystalline rocks: International collaboration | This milestone report will describe the international work to be performded through collaborations with DECOVALEX and KARI. | 2014-08-15 08:00 |  | 41866.0833 |  | 2014 | Complete | International Collaborations on Fluid Flows in Fractured Crystalline Rocks: FY14 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M4FT-14SN0807081.pdf | FCRD-UFD-2014-000499 | International collaboration, fracture crystalline rocks, fluid flow
M4FT-14LB0807041 | M4 | 1.02.08.07.04 | LBNL | FT-14LB080704 | Crystalline Disposal R&D - LBNL | Houseworth, James | McMahon, Kevin | Investigation of coupled THMC process, reactive transport and upscaling: FY14 progress | Investigation of coupled THMC process, reactive transport and upscaling: FY14 progress | Documents FY14 progress in investigation of coupled THMC process, reactive transport and upscaling. | 2014-08-15 10:00 |  | 2014-08-15 03:00 |  | 2014 | Complete | Investigation of Coupled THMC Processes and Reactive Transport: FY14 Progress | LBNL | Houseworth, James | None | M4FT-14LB0807041 LBNL.pdf | FCRD-UFD-2014-000497 | TOUGH-FLAC simulation, coupled processes, reactive transport, clay, molecular dynamics
M2FT-14SN0816031 | M2 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Update the initial version of Preliminary Report on Dual-Purpose Canister Disposal Alternatives (FY13) | Preliminary Report on Dual-Purpose Canister Disposal Alternatives (FY14) | Preliminary Report on Dual-Purpose Canister Disposal Alternatives (FY14) | 2014-08-15 14:00 |  | 41866.0833 |  | 2014 | Complete | Investigations of Dual-Purpose Canister Direct Disposal Feasibility (FY14) | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2014-000069 R0 M2 Submittal.pdf | FCRD-UFD-2014-000069 | DPC dual-purpose-canister disposal overpack criticality repository fillers clay shale
M4FT-14LB0806061 | M4 | 1.02.08.06.06 | LBNL | FT-14LB080606 | Argillite Disposal R&D International - LBNL | Houseworth, James | McMahon, Kevin | Investigation of coupled processes and Impact of High Temperature Limits in Argillite Rock | Investigation of coupled processes and Impact of High Temperature Limits in Argillite Rock | Documents FY14 Progress in investigation of coupled processes, reactive transport, and impacts of high temperature limits in Argillite rock through laboratory, theoretical, and modeling studies. This report will cover LBNL's research activities in both this and another work package entitled "Argillite Disposal R&D" (FT-14LB080604). | 2014-08-15 17:00 |  | 2014-08-15 03:00 |  | 2014 | Complete | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | LBNL | Houseworth, James | None | M4FT-14LB0806061 LBNL Argillite.pdf | FCRD-UFD-2014-000493 | Argillite, Stress-dependence of permeability and porosity, Discrete fracture network, Heater experiment, THMC modeling, high temperature, diffusion, Electrical Double Layer.
M3FT-14LB0818044 | M3 | 1.02.08.18.04 | LBNL | FT-14LB081804 | DR Salt R&D - LBNL | Birkholzer, Jens | MacKinnon, Robert | Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | Summary milestone for three activities | 2014-08-15 19:00 |  | 2014-08-14 03:00 |  | 2014 | Complete | Modeling Coupled THMC Processes and Brine Migration in Salt at High Temperatures | LBNL | Birkholzer, Jens | None | M3FT-14LB0818044 LBNL Salt.pdf | FCRD-UFD-2014-000341 | salt, nuclear waste, modeling, coupled processes
M4FT-14LL0807031 | M4 | 1.02.08.07.03 | LLNL | FT-14LL080703 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Pu sorption, desorption and intrinsic colloid stability under granitic chemical conditions | Report on determining the long-term stability of intrinsic Pu colloids (PuO2) under granitic chemical conditions | Report summarizing experimental results | 2014-08-16 06:00 |  | 2014-09-01 03:00 | Milestone document delivered to NE | 2014 | Completed Late | Plutonium Adsorption and Desorption from Bentonite: Progress Report FT-14LL0807071 | Begg, J.D. | Zavarin, Mavrik | None | FT-14LL0807071_REV1.pdf | FCRD-UFD-2014-000496 | bentonite, sorption, plutonium
M4FT-14SN0811031 | M4 | 1.02.08.11.03 | SNL | FT-14SN081103 | Information Exchanges, Workshops - SNL | McMahon, Kevin | McMahon, Kevin | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | This is a report that provides input from SNL to a L2 milestone at LBNL entitled "Status of UFD Campaign International Activities in Disposal Research." | 2014-08-16 14:00 |  | 41866.0833 |  | 2014 | Complete | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | McMahon, Kevin | McMahon, Kevin | None | M4FT-14SN0811031 SNL International FY14 FINAL.docx | FCRD-UFD-2014-000510 | Disposal Research, International
M4FT-14LB0814021 | M4 | 1.02.08.14.02 | LBNL | FT-14LB081402 | Regional Geology R&D - LBNL | Dobson, Patrick | McMahon, Kevin | Report on Data for Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Report on Data for Shale Formations in the US Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics. | Milestone will document information on shales that can be incorporated into the LANL GIS database. This information includes the physical, mineralogical and hydrologic characteristics of selected major shale units in the U.S. | 2014-08-22 13:00 | 2014-09-10 06:00 | 2014-09-10 03:00 | Milestone report submitted on revised due date. | 2014 | Completed Late | Inventory of Shale Formations in the US, Including Geologic, Geochemical, Hydrological, Mechanical, and Thermal Characteristics | Dobson, Patrick | Dobson, Patrick | None | M4FT-14LB0814021 LBNL Shale complete.pdf | FCRD-UFD-2014-000512 | regional geology, shale, GIS, sonic log
M2FT-14SN0804051 includes M4FT-14AN0804013 as input | M2 | 1.02.08.04.05 | SNL | FT-14SN080405 | Waste Form Degradation Modeling - SNL | Sassani, David | McMahon, Kevin | Model Integration for Engineered Materials Performance | Model Integration for Engineered Materials Performance | Model Integration for Engineered Materials Performance | 2014-08-22 18:00 |  | 41873.0833 |  | 2014 | Complete | Waste Form Degradation Model Integration for Engineered Materials Performance | Sassani, David | Sassani, David | None | M2FT_14SN0804051 Report final.pdf | FCRD-UFD-2014-000051 | waste form glass metallic degradation model performance assessment engineered materials
M3FT-14LA0818031 | M3 | 1.02.08.18.03 | LANL | FT-14LA081803 | DR Salt R&D - LANL | Caporuscio, Florie | MacKinnon, Robert | Salt R&D Brine migration experimental studies in salt 2014 | Salt R&D Brine migration experimental studies in salt 2014 | In FY14 the experimental test program to investigate brine migration appropriate for generic salt repository pressure and temperature (P,T) conditions will focus on hydrous mineral phases interactions at higher temperatures (200-300 oC). | 2014-08-25 16:00 |  | 2014-08-25 10:00 |  | 2014 | Complete | "BRINE MIGRATION EXPERIMENTAL STUDIES FOR SALT REPOSITORIES" | Caporuscio, Florie | Caporuscio, Florie | None | UFD-Brine Migration-2014-FINAL- 08-25-2014.pdf | FCRD-UFD-2014-000340
M2FT-14SN0806051 | M2 | 1.02.08.06.05 | SNL | FT-14SN080605 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of used fuel disposition in clay-bearing rock | Evaluation of used fuel disposition in clay-bearing rock | Evaluation of used fuel disposition in clay-bearing rock | 2014-08-29 12:00 |  | 41880.0833 |  | 2014 | Complete | Evaluation of Used Fuel Disposition in Clay-Bearing Rock | Jove Colon, Carlos | Jove Colon, Carlos | None | M2FT-14SN080605_Milestone_Report_UFDC_ARG_FY14_FCRD-UFD-2014-000056_Final.pdf | FCRD-UFD-2014-000056
M4FT-14SN0818057 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Low-Strain Rate Deformation in a Salt Repository | Feasibility Study of Monitoring Low-Strain Rate Deformation in a Salt Repository | This activity will conduct a feasibility study of measuring very low strain-rate deformability of bedded Permian Basin salt and other materials, at dry and in situ moisture conditions, both confined and unconfined. | 2014-09-05 08:00 |  | 2014-09-05 02:00 | Attached feasibility study report satisfies M4 on time. | 2014 | Complete | Technical Feasibility of Measuring Low-Stress, Low Strain-Rate Deformation Relevant to a Salt Repository | Hardin, Ernest | Kuhlman, Kris | None | Feasibility Study Final.pdf
M3FT-14SN0817021 | M3 | 1.02.08.17.02 | SNL | FT-14SN081702 | DR Deep Borehole Disposal - SNL | Arnold, Bill | Mackinnon, Robert | Geological Data Evaluation, Alternative Waste Forms, and Seals for Deep Borehole Disposal Demonstration | Geological Data Evaluation, Alternative Waste Forms, and Seals for Deep Borehole Disposal Demonstration | Report on RD&D activities supporting deep borehole disposal demonstration project. | 2014-09-05 10:00 |  | 2014-09-05 02:00 | Level 3 milestone report on deep borehole disposal research for FY2014 delivered on schedule on 09/05/2014. | 2014 | Complete | Deep Borehole Disposal Research: Geological Data Evaluation, Alternative Waste Forms, and Borehole Seals | Arnold, Bill | Arnold, Bill | None | DBD_FY14_milestone_report_final_SAND2014-17430R.pdf | FCRD-UFD-2014-000332 | deep borehole disposal radioactive waste
M4FT-14LA0818064 | M4 | 1.02.08.18.06 | LANL | FT-14LA081806 | Salt R&D to support Field Studies - LANL | Robinson, Bruce | MacKinnon, Robert | Summary of current THMC modeling results supporting large-scale thermal testing | Summary of current THMC modeling results supporting large-scale thermal testing | Report synthesizes the modeling that has been performed previous to the initiation of this activity as well as new modeling in support of the design of thermal tests | 2014-09-12 04:00 |  | 2014-09-30 04:00 | This report summarizes ongoing efforts to simulate coupled thermal-hydrological-chemical(THC) processes occurring within a hypothetical high-level waste (HLW) repository in bedded salt. | 2014 | Completed Late | Thermo-Hydrological and Chemical (THC) Modeling to Support Field Test Design | Robinson, Bruce | Robinson, Bruce | None | 2014_Sept30_LANL_MILESTONE-M4FT-14LA0818064_SimulationUdpate_FINAL.pdf |  | salt; coupled modeling; THMC
M3FT-14SN0808032 | M3 | 1.02.08.08.03 | SNL | FT-14SN080803 | DR Generic Disposal System Analysis - SNL | Freeze, Geoff | Mackinnon, Robert | Generic Disposal System Analyses | Performance Assessment Modeling and Sensitivity Analysis of Generic Disposal System Concepts | Summary report describing the capability development and system-level model application for analysis of generic disposal system concepts | 2014-09-12 16:00 |  | 2014-09-12 02:00 | Submitted | 2014 | Complete | Performance Assessment Modeling and Sensitivity Analysis of Generic Disposal System Concepts | Sevougian, S. David | Freeze, Geoff | None | FY14 GDSA Report SAND2014-17658.pdf | FCRD-UFD-2014-000320 | performance assessment
M4FT-14SN0816039 | M4 | 1.02.08.16.03 | SNL | FT-14SN081603 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Letter Report on Materials Used in DPCs and in Potential Direct Disposal Overpacks (FY14) | Letter Report on Materials Used in DPCs and in Potential Direct Disposal Overpacks (FY14) | Summarize current understanding of the corrosion behavior of materials used in existing dual-purpose (storage and transportation) canisters, in a range of disposal environments particularly sedimentary geologic host media and contacting clay-based engineered buffer materials. Also identify and summarize behavior of corrosion allowance and corrosion resistant materials available for use in disposal overpacks for existing DPCs. | 2014-09-15 10:00 | 41912.1667 | 41915.0833 | PICSNE is not letting me close this item. | 2014 | Expected Late | Letter Report on Materials Used in DPCs and in Potential Direct Disposal Overpacks (FY14) | Ilgen, Anastasia | Hardin, Ernest | None | Oct-3-2014-Ilgen-DPC-Materials-REPORT-Final.pdf |  | dual-purpose canister DPC disposal criticality corrosion
M3FT-14AN0804011 | M3 | 1.02.08.04.01 | ANL | FT-14AN080401 | Waste Form Degradation Modeling - ANL | Zapol, Peter | McMahon, Kevin | Provide report documenting progress in first principles model development for glass dissolution | Provide report documenting progress in first principles model development for glass dissolution | computational results for reaction barriers and energies | 2014-09-15 15:00 |  | 2014-09-30 01:00 | report submitted (pdf) | 2014 | Completed Late | Reaction Barriers for Glass Corrosion from First Principles Calculations | Zapol, Peter | Zapol, Peter | None | zapol_M3FT-14AN0804011report.pdf | FCRD-UFD-2014-000310 | modeling glass hydrolysis
M4FT-14LA0818062 | M4 | 1.02.08.18.06 | LANL | FT-14LA081806 | Salt R&D to support Field Studies - LANL | Robinson, Bruce | MacKinnon, Robert | Draft Test Plan for Brine Migration Intermediate-Scale Experimental Studies in Run-of-Mine Salt Backfill | Draft Test Plan for Brine Migration Intermediate-Scale Experimental Studies in Run-of-Mine Salt Backfill | Draft description of an intermediate-scale laboratory experiment and test plan to provide data to support field test planning. | 2014-09-19 06:00 |  | 2014-09-19 06:00 | The primary objective of the experimental effort described here is to aid in understanding the complex nature of liquid, vapor, and solid transport occurring around heated nuclear waste in bedded salt. In order to gain confidence in the predictive capability of numerical models, experimental validation must be performed to ensure that (a) hydrological and physiochemical parameters and (b) processes are correctly simulated. The experiments proposed here are designed to study aspects of the system that have not been satisfactorily quantified in prior work. In addition to exploring the complex coupled physical processes in support of numerical model validation, lessons learned from these experiments will facilitate preparations for larger-scale experiments that may utilize similar instrumentation techniques. | 2014 | Complete | Draft Test Plan for Brine Migration Experimental Studies in Run-of-Mine Salt Backfill | Robinson, Bruce | Robinson, Bruce | None | LANL_MILESTONE-M4FT-14LA0818062.pdf |  | salt, brine migration
M4FT-14SN0818051 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Transport Properties of Run-of-Mine Salt Backfill – Unconsolidated to Consolidated | Summary of initial test results for Transport Properties of Run-of-Mine Salt Backfill | The goal of this activity is conduct laboratory tests to determine flow and transport parameters in unconsolidated and reconsolidated granular salt as a function of porosity, time, water content, and temperature. | 2014-09-19 08:00 |  | 2014-09-17 02:00 | Level-4 Milestone completed on schedule | 2014 | Complete | Summary of Initial Test Results for Transport Properties of Run-of-Mine Salt Backfill | Schuhen, Michael | Kuhlman, Kris | None | FCRD-UFD-2014-000619-Two-phase-flow-2014-progress-FINAL.pdf
M5FT-14IN0818021 | M5 | 1.02.08.18.02 | INL | FT-14IN081802 | DR Salt R&D - INL | Frank, Steve | None | Provide input data to Sandia for PA calculations and transportation criticality issues | Milestone M5 Summary Report | Investigate primary salt packaging transportation criticality and salt/container interaction concerns. Provide input to Sandia for updated PA caluclations. Summary report for PA calculation input, packaging information and salt/container interactions. | 2014-09-19 12:00 |  | 2014-09-30 02:00 | Summary report outlining SNL calculations on criticality and transportation issues with direct disposal of ER salt completed. | 2014 | Completed Late | Summary Report - Criticality Analysis of Disposal and Transportation | Frank, Steve | Frank, Steve | None | Summary Report - Criticality Analysis of Disposal and Transportation.pdf |  | Direct Disposal, ER salt
M2FT-14LA0814011 | M2 | 1.02.08.14.01 | LANL | FT-14LA081401 | Regional Geology R&D - LANL | Perry, Frank | McMahon, Kevin | Database for Regional Geology, Phase 1– A Tool for informing Regional Evaluations of Alternative Geologic Media and Decision Making | Database for Regional Geology, Phase 1– A Tool for informing Regional Evaluations of Alternative Geologic Media and Decision Making | Report on Database for Regional Geology, Phase 1– A Tool for informing Regional Evaluations of Alternative Geologic Media and Decision Making | 2014-09-24 12:00 |  | 2014-09-23 02:00 | Milestone report describing the data contained within the UFD GIS Database for alternative geologic disposal media and siting guidelines. Description of implementation of a FY14 website and plans for a FY15 interactive mapping tool to allow online manipulate of data within the GIS database. | 2014 | Complete | Database for Regional Geology, Phase 1– A Tool for informing Regional Evaluations of Alternative Geologic Media and Decision Making | Perry, Frank | Perry, Frank | None | Regional_Geology_M2FT-14LA0814011_LANL_PERRY.pdf | FCRD-UFD-2014-000067 | Regional Geology, Disposal, Crystalline Basement, Shale, Salt, Granite
M2FT-14SN0818011 | M2 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Summary Results for Brine Migration Modeling Performed by LANL, LBNL and SNL for the Used Fuel Disposition Program | Summary Results for Brine Migration Modeling Performed by LANL, LBNL and SNL for the Used Fuel Disposition Program | Summary Results for Brine Migration Modeling Performed by LANL, LBNL and SNL for the Used Fuel Disposition Program | 2014-09-25 16:00 |  | 2014-09-23 02:00 | This report summarizes laboratory and field observations and numerical modeling related to coupled processes involving brine and vapor migration in geologic salt, focusing on recent developments and studies conducted at Sandia, Los Alamos, and Berkeley National Laboratories. Interest into the disposal of heat-generating waste in salt has led to interest into water distribution and migration in both run-of-mine crushed and intact geologic salt. Ideally a fully coupled thermal-hydraulic-mechanical-chemical simulation is performed using numerical models with validated constitutive models and parameters. When mechanical coupling is not available, mechanical effects are prescribed in hydraulic models as source, boundary, or initial conditions. This report presents material associated with developing appropriate initial conditions for a non-mechanical hydrologic simulation of brine migration in salt. Due to the strong coupling between the mechanical and hydrologic problems, the initial saturation will be low for the excavation disturbed zone surrounding the excavation. Although most of the material in this report is not new, the author hopes it is presented in a format making it useful to other salt researchers. This | 2014 | Complete | Summary Results for Brine Migration Modeling Performed by LANL, LBNL, and SNL for the UFD Program | Kuhlman, Kris | Kuhlman, Kris | None | brine-migration-UFD-M2-final.pdf | FCRD-UFD-2014-000071 | Brine Migration; Salt
M4FT-14LA0818068 | M4 | 1.02.08.18.06 | LANL | FT-14LA081806 | Salt R&D to support Field Studies - LANL | Robinson, Bruce | MacKinnon, Robert | Draft Test Plan for Phased Large-Scale Thermal Testing | Draft Test Plan for Phased Large-Scale Thermal Testing | Draft Test Plan that will include thermal test objectives for each phase, the test strategy for each phase, the parameters to be monitored, the test configuration, and test controls. | 2014-09-26 04:00 | 2014-10-10 02:00 | 2014-10-10 02:00 | Milestone completed | 2014 | Expected Late | Draft report: Test Plan for Phased Large-Scale Thermal Testing | Robinson, Bruce | Robinson, Bruce | None | LANL_Milestone-M4FT-14LA0818068.pdf |  | salt, URL, thermal testing
M4FT-14LA0818066 | M4 | 1.02.08.18.06 | LANL | FT-14LA081806 | Salt R&D to support Field Studies - LANL | Robinson, Bruce | MacKinnon, Robert | Framework for Underground Research | Framework for Underground Research | Document describes a framework by which a generic field-testing research strategy can be successfully developed and deployed, leading to actionable Test Plans. Jointly developed with SNL and LBNL | 2014-09-26 04:00 |  | 2014-09-01 06:00 | Input to the Framework document for research in a salt URL, final version to be completed by Sandia National Laboratories | 2014 | Complete | Framework for Underground Research in a Salt URL | Robinson, Bruce | Robinson, Bruce | None | LANL_Milestone_M4FT-14LA0818066.pdf |  | salt, URL, framework
M4FT-14LA08180610 | M4 | 1.02.08.18.06 | LANL | FT-14LA081806 | Salt R&D to support Field Studies - LANL | Robinson, Bruce | MacKinnon, Robert | Draft report, Test Plan for Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | Draft report, Test Plan for Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | Test Plan will describe how to measure undisturbed initial and boundary conditions (e.g., undisturbed permeability) prior to any type of transient test, such as a large-scale thermal test, and how to measure deformation/strain and permeability changes during the evolution of a transient test such as the LSTT. Developed jointly with SNL and LBNL. | 2014-09-26 06:00 | 2014-10-03 02:00 | 2014-10-03 06:00 | Milestone completed | 2014 | Expected Late | Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | Robinson, Bruce | Robinson, Bruce | None | LANL_MILESTONE-M4FT-14LA08180610.pdf
M4FT-14LB0818076 | M4 | 1.02.08.18.07 | LBNL | FT-14LB081807 | Salt R&D to support Field Studies - LBNL | Birkholzer, Jens | Mackinnon, Robert | Summary of LBNL Modeling and Field Test Planning Activities in Support of Disposal of Heat-Generating Waste in Salt | Summary of LBNL Modeling and Field Test Planning Activities in Support of Disposal of Heat-Generating Waste in Salt | This report summarizes the several activities in this work package: Thermomechanical-Hydrological and Chemical (TMHC) Modeling to Support Field Test Design; Brine Migration Modeling; Framework for Underground Research Planning; Thermal Testing Planning; Planning for Testsing the Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | 2014-09-26 06:00 |  | 2014-09-26 03:00 | Milestone data delivered on due date. | 2014 | Complete | Modeling and Field Test Planning Activities in Support of Disposal of Heat-Generating Waste in Salt | Rutqvist, Jonny | Birkholzer, Jens | None | M4FT-14LB0818076_Modeling and Field Test Planning Activities_Sep 2014.pdf |  | salt, nuclear waste, modeling, coupled processes, field test
M4FT-14SN0818055 Uploaded draft input for their thermal test plan milestone (M4FT-14LA0818068) for on-time completion of milestone | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | Mackinnon, Robert | Thermal Testing | Draft report, Test Plan for Phased Large-Scale Thermal Testing | A phased set of in situ thermal tests in bedded salt will be designed to support a number of generic safety case objectives. | 2014-09-26 08:00 |  | 2014-09-25 02:00 | Uploaded draft input for their thermal test plan milestone (M4FT-14LA0818068) for on-time completion of milestone | 2014 | Complete | Field-scale Thermal Testing in a Generic Salt Disposal Environment Underground Research Laboratory (URL): Delineation of Principal Purpose, Objectives, and Hypotheses | Sassani, David | Kuhlman, Kris | None | draft objectives field scale thermal testing final clean.pdf
M4FT-14SN0818056 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | Draft report, Test Plan for Mechanical and Hydrological Behavior of the Near-field Host Rock Surrounding Excavations | ). This test will provide data to characterize and quantify the time-dependent mechanical behavior and hydrologic response of test-room near-field host rock and establish boundary conditions for any test that might be executed in an excavation. A Test Plan will be developed to identify instrumentation and their arrangements for making rock displacement and strain measurements at locations that will also measure gas or brine fluid flow so that unambiguous correlations can be established between rock deformation/strain and permeability changes. | 2014-09-26 08:00 |  | 2014-09-22 02:00 | Finished level-4 deliverable ahead of schedule. | 2014 | Complete | Mechanical and Hydrological Characterization of the Near-field Surrounding Excavations in a Geologic Salt Formation | Howard, Cliff | Kuhlman, Kris | None | TestPlanMechanicalResponse-Generic-Salt-final.pdf
M4FT-14SN0818054 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Framework for Underground Research | Framework for Underground Research | This document describes a framework by which a generic field-testing research strategy can be successfully developed and deployed, leading to actionable Test Plans. | 2014-09-26 10:00 |  | 2014-09-18 02:00 | Level-4 deliverable is completed ahead of schedule | 2014 | Complete | Framework for Underground Research for Generic Repository Investigations in Salt | Sassani, David | Kuhlman, Kris | None | draft framework milestone final.pdf
M2FT-14SN0807051 | M2 | 1.02.08.07.05 | SNL | FT-14SN080705 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Used fuel disposal in crystalline rocks: status and FY14 progress | Used fuel disposal in crystalline rocks: status and FY14 progress | Used fuel disposal in crystalline rocks: status and FY14 progress | 2014-09-26 12:00 |  | 41907.0833 | This report summarizes the status and FY14 progress for work package of Crystalline Disposal R&D. | 2014 | Complete | Used fuel disposal in crystalline rocks: status and FY14 progress | Wang, Yifeng | Wang, Yifeng | None | M2FT-14SN0807051x.pdf | FCRD-UFD-2014-000060 | Crystalline repository
M2FT-14LB0811011 From Matt Brainard: Note: Work package FT-13LB081102 - CX International – LBNL appears to have been cancelled for FY14 and work package FT-14LB081101 - International Collaborations Integration & Coordination - LBNL initiated, in which M2FT-14LB0811011: International Collaboration Activities in Different Geologic Disposal Environments may have superseded M3FT-13LB0811022: LBNL Report on the Status of UFD Campaign International Activities in Disposal Research, but I’m not positive. There is no clear cross-walk between the two. FY14 M2 deliverable attached. | M2 | 1.02.08.11.01 | LBNL | FT-14LB081101 | International Collaborations Integration & Coordination - LBNL | Birkholzer, Jens | McMahon, Kevin | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | 2014-09-26 21:00 |  | 2014-09-26 03:00 | Milestone document submitted on due date. | 2014 | Complete | International Collaboration Activities in Different Geologic Disposal Environments | Birkholzer, Jens | Birkholzer, Jens | None | M2FT-14LB0811011_International Collab Activities_Sep 2014.pdf | FCRD-UFD-2014-000065 | underground research laboratory, disposal research, international
M4FT-14SN0818053 | M4 | 1.02.08.18.5 | SNL | FT-14SN081805 | Salt R&D to support Field Studies - SNL | Kuhlman, Kris | MacKinnon, Robert | Thermomechanical-Hydrological and Chemical (TMHC) Modeling to Support Field Test Design | Summarize current THMC modeling results supporting testing of mechanical and hydrological behavior of the near-field host rock surrounding excavations | This activity will use existing computational models to support the design of a large-scale thermal test (LSTT) and the design of a test for monitoring mechanical and hydrological behavior of the near-field host rock surrounding excavations (MHBNF) during the LSTT. To be documented in SNL Milestone M3FT-14SN08180110-Results from the US-German Benchmark Initiative for FY14 | 2014-09-30 08:00 |  | 2014-09-24 02:00 | milestone met by two reports already submitted into PICS:NE | 2014 | Complete | document is just a pointer to 2 other documents that satisfy this level-4 milestone | Kuhlman, Kris | Kuhlman, Kris | None | M4FT-14SN0818053-pointer.pdf
M4FT-14SN0817031 | M4 | 1.02.08.17.03 | SNL | FT-14SN081703 | DR Deep Borehole Experimental Test Support - SNL | Freeze, Geoff | Mackinnon, Robert | Develop Planning Documents | Draft Project Execution Plan | Planning documents for site selection and implementation of a deep borehole disposal experimental test include: a draft Project Execution Plan (PEP); a draft Project Schedule; and plans to address legal and regulatory requirements (e.g., permits and environmental assessments). | 2014-09-30 08:00 |  | 2014-09-30 06:00 | Submitted to DOE. | 2014 | Complete | Project Plan: Deep Borehole Field Test | Freeze, Geoff | Freeze, Geoff | None | DBH Field Test Project Plan_Final.pdf |  | deep borehole
M3FT-14SN08180110 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Results from the US-German Benchmark Initiative for FY14 | Results from the US-German Benchmark Initiative for FY14 | Results from the US-German Benchmark Initiative for FY14 | 2014-09-30 10:00 |  | 2013-12-23 02:00 |  | 2014 | Complete | Proceedings of the 4th US/German Workshop on Salt Repository Research, Design, and Operation | Hansen, Francis | Hansen, Francis | None | M3FT-14SN08180114 hansen.pdf | FCRD-UFD-2014-000333
M4FT-14PN0804044 | M4 | 1.02.08.04.04 | PNNL | FT-14PN080404 | Waste Form Degradation Modeling - PNNL | Rieke, Peter | McMahon, Kevin | Preparation of a beta phase user manual | Preparation of a beta phase user manual | The project will deliver a single level 4 milestone. The delivery date is assumed to be Sept. 31st. Given the uncertainty in budget appropriations and the possibility of a June end date, we plan to be flexible in the reporting as more budget information becomes available. Milestone Description – “Preparation of a beta phase user manual”. A report will be prepared and submitted to the project manager and other personnel as appropriate. The report will predominately comprise a “user manual” allowing selected outside users to independently evaluate the tool. The manual will contain examples of typical applications, description of the available glass dissolution models and explanation of the database interfaces. | 2014-09-30 11:00 |  | 2014-09-23 03:00 | This report describes the work performed to meet milestone M4FT-14PN0804044 “Preparation of a Beta Phase User Manual” for the FT-14PN0804043 – Comprehensive Corrosion Model Evaluation Tool – PNNL project. The Glass Corrosion Modeling Tool or GCMT allows the user to evaluate the goodness of a glass alteration model by fitting the model to a selected experimental database. The GCMT can implement the models proposed by various workers in the glass chemistry community and adds new models or variations as they become available. Extensive databases of glass dissolution data can be accessed. The GCMT can be used to understand the strengths and weaknesses of a particular model and propose new or adapted models. Given a specific model, the GCMT can be used to validate the choice of parameters used in the model for the targeted application. The GCMT should be of value in choosing a glass dissolution source term for the Performance Assessment (PA) nuclear waste repository model. | 2014 | Complete | Preparation of a Beta Phase User Manual | Rieke, Peter | Rieke, Peter | None | M4FT-14PN0804044 Report Final.pdf | FCRD-UFD-2014-000482
M3FT-14SN08180113 | M3 | 1.02.08.18.01 | SNL | FT-14SN081801 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY14 Results | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY14 Results | xxx | 2014-09-30 12:00 |  | 2014-09-25 02:00 | This work is conducted under Task 2.5, Development of a Chemical Model/database up to 200 oC with High Internal Consistency, in the TP Test Plan for Determining Thermodynamic Properties of Brines, Minerals and Corrosion Products for High Level Radioactive Waste Disposal in Salt (FCRD-UFD-2012- 00033). While the current actinide model does not extend to alkaline regions, an actinide model valid for alkaline to hyperalkaline regions, and for high ionic strengths, is required for management of a number of nuclear waste types including high level waste (HLW) glasses, cementitious materials, and tank wastes at the DOE Hanford and Savannah River sites. In this work, speciation and solubility of actinides [An(III) and An(IV)] in alkaline and hyperalkaline solutions with high ionic strengths are evaluated. In this work, a preliminary Pitzer model is developed for Am(OH)3(s) in alkaline and hyperalkaline solutions to ionic strengths up to ~15 mol•kg–1. This preliminary model is subject to revision when additional experimental data become available. Also in this work, using tetravalent metal ions such as Zr(IV) and Hf(IV) as analogs, and Pu(IV) data from various sources, a speciation analysis suggests that tetravalent plutonium could be speciated as Pu(OH)5 – and Pu(OH)6 2– in alkaline to hyperalkaline solutions. This preliminary conclusion should be revisited when new experimental data on Pu(IV) is available. In this case, future experimental studies are recommended. | 2014 | Complete | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY 14 Results | Xiong, Yongliang | Xiong, Yongliang | None | M3FT-14SN08180113.pdf | FCRD-UFD-2014-000334
M4FT-15AN0806012 Per Matt Brainard: Narrative: Attached is a short report communicating the Prototype Fortran Version of Mixed Potential Process Model for Used Fuel Degradation (MPM). The source code of the Fortran version is now available for download. Access to the ANL file share site is through e-mail invitation. Glenn and Paul will be receiving the link to the code today. If others would like access please send me an e-mail request. This is the first “hands-on” step towards integrating the MPM with the PA model and I anticipate a number of iterations. We will therefore carefully track any changes to the Fortran MPM as version numbers and communicate that information to anyone who has access to the file share. Please keep in mind that the Fortran MPM code is a working prototype for ironing out inputs and outputs; it is not the final fuel degradation process model. In parallel with the code integration work we will continue to improve the accuracy of MPM through experiments and ongoing literature reviews. This report and associated material meet ANL’s (10/15/2014) milestones M4FT-15AN0806012 and M4FT-15AN0807012 for the Crystalline and Argillite work packages FT-15AN080601 and FT-15AN080701. | M4 | 1.02.08.06.01 | ANL | FT-15AN080601 | DR Argillite Disposal R&D - ANL | Ebert, William | McMahon, Kevin | Draft of Fortran version of Mixed Potential Model | Draft of Fortran version of Mixed Potential Model | Draft version of MPM to support discussions addressing integration with PA. | 2014-10-15 04:00 |  | 2014-10-15 01:00 |  | 2015 | Complete | Prototype Fortran Version of the Mixed Potential Process Model for Used Fuel Degradation |  |  | None | M4FT15AN0806012_Prototype Fortran Version of Mixed Potential Model.pdf | FCRD-UFD-2015-000549
M4FT-15AN0807012 Per Matt Brainard: Narrative: Attached is a short report communicating the Prototype Fortran Version of Mixed Potential Process Model for Used Fuel Degradation (MPM). The source code of the Fortran version is now available for download. Access to the ANL file share site is through e-mail invitation. Glenn and Paul will be receiving the link to the code today. If others would like access please send me an e-mail request. This is the first “hands-on” step towards integrating the MPM with the PA model and I anticipate a number of iterations. We will therefore carefully track any changes to the Fortran MPM as version numbers and communicate that information to anyone who has access to the file share. Please keep in mind that the Fortran MPM code is a working prototype for ironing out inputs and outputs; it is not the final fuel degradation process model. In parallel with the code integration work we will continue to improve the accuracy of MPM through experiments and ongoing literature reviews. This report and associated material meet ANL’s (10/15/2014) milestones M4FT-15AN0806012 and M4FT-15AN0807012 for the Crystalline and Argillite work packages FT-15AN080601 and FT-15AN080701. | M4 | 1.02.08.07.01 | ANL | FT-15AN080701 | DR Crystalline Disposal R&D - ANL | Ebert, William | McMahon, Kevin | Draft verison of Fortran code for meeting with PA modelers | Draft verison of Fortran code for meeting with PA modelers | Fortran code of MPM to support discussions with PA modelers. | 2014-10-15 04:00 |  | 2014-10-15 08:00 |  | 2015 | Complete | Prototype Fortran Version of the Mixed Potential Process Model for Used Fuel Degradation |  |  |  | M4FT15AN0806012_Prototype Fortran Version of Mixed Potential Model.pdf | FCRD-UFD-2015-000551
M4FT-15OR0816013 | M4 | 1.02.08.16.01 | ORNL | FT-15OR081601 | DR Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | McMahon, Kevin | Validation Basis for Cl Reactivity Suppression In Groundwater | Validation Basis for Cl and Li Reactivity Suppression in Groundwater | To supplement the criticality groundwater composition analysis work area, a literature review of the validation basis for Cl will be conducted to support crediting it in the groundwater and to identify how much credit (i.e., estimate bias and uncertainty) should be expected. This task would include evaluating existing critical benchmark experiments and their applicability to the DPC configurations involving groundwater compositions containing Cl. The benchmark experiment applicability assessment and bias and uncertainty determination will follow the process outlined in NUREG/CR-7109. | 2014-12-19 04:00 |  | 41992 |  | 2015 | Complete | Validation Study for Crediting Chlorine in Criticality Analyses for US Spent Nuclear Fuel Disposition | Sobes, Vlad | Scaglione, John | None | FCRD-Report-Chlorine.pdf | FCRD-UFD-2015-000638
M3FT-15AN0806014 This document and associated materials meets milestones: M3FT-15AN0806014 and M3FT-15AN0807014: | M3 | 1.02.08.06.01 | ANL | FT-15AN080601 | DR Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Mixed Potential Model for Used Fuel Dissolution- Fortran Code | Mixed Potential Model for Used Fuel Dissolution- Fortran Code | Document Fortran code for mixed potential model for used fuel dissolution. | 2015-01-13 03:00 |  | 2015-01-13 01:00 |  | 2015 | Complete | Mixed Potential Model for Used Fuel Dissolution - Fortran Code | Jerden, James | Jerden, James | None | FCRD-UFD-2015-000159_Fortran Version of Mixed Potential Model_R3.pdf | FCRD-UFD-2015-000159
M3FT-15AN0807014 This document and associated materials meets milestones: M3FT-15AN0806014 and M3FT-15AN0807014: | M3 | 1.02.08.07.01 | ANL | FT-15AN080701 | DR Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Issue Fortran code of Mixed potential model | Issue Fortran code of Mixed potential model | Document Fortran code for MPM with discussion of technical basis of model. | 2015-01-13 04:00 |  | 2015-01-13 01:00 |  | 2015 | Complete | Mixed Potential Model for Used Fuel Dissolution - Fortran Code | Jerden, James | Jerden, James | None | FCRD-UFD-2015-000159_Fortran Version of Mixed Potential Model_R3.pdf | FCRD-UFD-2015-000160
M3FT-15SN08180210 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Proceedings from 5th US German Workshop | Proceedings from 5th US German Workshop | Proceedings from 5th US German Workshop | 2015-01-30 08:00 |  | 2015-01-29 02:00 |  | 2015 | Complete | Proceedings of 5th US/German Workshop on Salt Repository Research, Design and Operation | Hansen, Francis | Hansen, Francis | None | reduced size M3FT-15SN08180210 hansen.pdf | FCRD-UFD-2015-000514
M4FT-15SN0816023 | M4 | 1.02.08.16.02 | SNL | FT-15SN081602 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | McMahon, Kevin | Review International Cavern/Vault Disposal Concepts and Extend Thermal Calcs. | Letter Report: Cavern/Vault Disposal Concepts and Extended Thermal Calculations for DPC Direct Disposal | Develop and evaluate cavern-retrievable and underground vault type disposal concepts, as they may be applicable to DPC direct disposal. Extend thermal calculations from FY13, to larger waste packages (e.g., 37-PWR/89-BWR). | 2015-02-27 08:00 | 42065.0833 | 42065.0833 |  | 2015 | Completed Late | Cavern/Vault Disposal Concepts and Thermal Calculations for Direct Disposal of 37-PWR Size DPCs | Hadgu, Teklu | Hardin, Ernest | None | FCRD-UFD-2015-000715 Thermal vault report Final.pdf | FCRD-UFD-2015-000715
M3FT-15SN0818026 ULR. No SAND number on report. | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Test Plan for I, Sr, and Cs Studies at Elevated Temperature and Pressure | Test Plan for I, Sr, and Cs Studies at Elevated Temperature and Pressure | In FY2015 experiments will be conducted to determine the thermodynamics of basic elements (Na, Ca, K, Mg) in brines. In addition, larger scale testing equipment will come on-line. Test Plan for I, Sr, and Cs Studies at Elevated Temperature and Pressure | 2015-02-27 10:00 |  | 2015-03-10 02:00 |  | 2015 | Completed Late | Test Plan for I, Sr, and Cs Studies at Elevated Temperature and Pressure | Icenhower, Jonathan | Icenhower, Jonathan | None | Fission Product Test Plan.docx | FCRD-UFD-2015-000517
M4FT-15SR0816031 | M4 | 1.02.08.16.03 | SRNL | FT-15SR081603 | DR Disposal of Dual Purpose Canisters - SRNL | Carter, Joe | McMahon, Kevin | Generic Repository Cost Estimates | Generic Repository Cost Estimates | Extend cost estimates for reference enclosed and open concepts, to include disposal of waste packages based on DPCs and standardized canisters of specific sizes. This information will be used as input to system level analyses that include DPC direct-disposal, repackaging, and standardized container options. | 2015-03-31 06:00 |  | 2015-03-30 |  | 2015 | Complete | Generic Repository Cost Estimates | Severynse, Tom | Carter, Joe | None | FCRD-UFD-2015-000740 - Generic Repository Cost Estimates.pdf | FCRD-UFD-2015-000740 | Cost Estimate
M4FT-15SN0816022 | M4 | 1.02.08.16.02 | SNL | FT-15SN081602 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | McMahon, Kevin | Letter Report on Review of Waste Package Reliability Estimates for Geologic Disposal | Letter Report on Review of Waste Package Reliability Estimates for Geologic Disposal | SNL will review the early failure analysis for YM licensing, to identify any significant opportunities for improving overpack reliability. Apply insights from current approaches to human factors engineering, to recommend whether previous reliability estimates can be improved by one of more orders of magnitude. | 2015-03-31 06:00 | 42109.0833 | 42122.0833 |  | 2015 | Completed Late | Letter Report: Report on Review of Waste Package Reliability Estimates for Geologic Disposal | Groth, Katrina | Hardin,Ernest | None | Overpack reliability FCRD-UFD-2015-000714 Final.pdf | FCRD-UFD-2015-000714 | radioactive waste, packaging, reliability, early failure, human error
M4FT-15LA0817021 | M4 | 1.02.08.17.02 | LANL | FT-15LA081702 | DR Deep Borehole Disposal - LANL | Perry, Frank | Mackinnon, Robert | Analysis and documentation of regional technical factors to support the site selection report | Documentation and Analayis of Technical Factors to Support Site Selectio of a Deep Borehole Demstration | Report on the analysis and documentation of technical data (geophysics, hydrology, geology, borehole information) that will support selection of a site for a deep borehole demonstration | 2015-04-06 04:00 |  | 2015-04-06 02:00 |  | 2015 | Complete | A GIS Database to Support the Application of Technical Siting Guidelines to a Deep Borehole Field Test | Perry, Frank | Perry, Frank | None | Deep_Borehole_M4FT-15LA0817021_LANL_Perry.pdf | FCRD-UFD-2015-000603 | Deep Borehole, GIS, Siting Guidelines
M4FT-15LB0817032 | M4 | 1.02.08.17.03 | LBNL | FT-15LB081703 | DR Deep Borehole Disposal - LBNL | Birkholzer, Jens | Mackinnon, Robert | Analysis and Documentation of Site Selection and Characterization Activities | Analysis and Documentation of Site Selection and Characterization Activities | Analysis and Documentation of Site Selection and Characterization Activities, Level 4, Due Date: April 6, 2015 This milestone will feed into SNL milestone on Site selection due May 4, 2015. Title: Site Selection for Deep Borehole Field Test | 2015-04-06 15:00 |  | 2015-04-06 03:00 |  | 2015 | Complete | Analysis and Documentation of Site Selection and Characterization Activities | Houseworth, James | Birkholzer, Jens | None | M4FT-15LB0817032 Deep Borehole Siting.pdf | FCRD-UFD-2015-000607 | deep borehole, siting considerations
M2FT-15LA0819016 | M2 | 1.02.08.19.01 | LANL | FT-15LA081901 | DR Salt Field Testing - LANL | Stauffer, Philip | MacKinnon, Robert | Draft Test Plan for Phased Large-Scale Thermal Testing | Draft Test Plan for Phased Large-Scale Thermal Testing | Planning activity to write a high-level thermal test plan at a level of detail sufficient to support an independent peer review. Draft plan will include thermal test objectives for each phase, the test strategy for each phase, the parameters to be monitored, and the test configuration. | 2015-04-30 14:00 |  | 42124.0833 |  | 2015 | Complete | Test Proposal Document for Phased Field Testing in Salt | Stauffer, Philip | Stauffer, Philip | None | 2015_April_30_M2FT-15LA0819016_FCRD-UFD-2015-000077.pdf | FCRD-UFD-2015-000077 | Salt Field Testing
M2FT-15SN0816021 | M2 | 1.02.08.16.02 | SNL | FT-15SN081602 | DR Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | McMahon, Kevin | Summary of Investigations on Technical Feasibility of Direct Disposal of Dual-Purpose Canisters | Summary of Investigations on Technical Feasibility of Direct Disposal of Dual-Purpose Canisters | Summarize completed and in-progress R&D activities addressing safety, engineering feasibility, thermal management, and postclosure criticality control. | 2015-05-15 08:00 |  | 42138.25 |  | 2015 | Complete | Summary of Investigations on Technical Feasibility of Direct Disposal of Dual-Purpose Canisters | Hardin, Ernest | Hardin, Ernest | None | FCRD-UFD-2015-000129 Rev 1 DPC Summary.pdf | FCRD-UFD-2015-000129 | spent fuel,nuclear waste,geologic repository,dual-purpose canister
M4FT-15LA0819015 | M4 | 1.02.08.19.01 | LANL | FT-15LA081901 | DR Salt Field Testing - LANL | Stauffer, Philip | MacKinnon, Robert | Coupled Thermal-Hydrologic-Chemical Coupled Model for In-Drift Disposal Test | Coupled Thermal-Hydrologic-Chemical Coupled Model for In-Drift Disposal Test | A description of a THC model of an in-drift disposal experiment for the purposes of supporting a future test design activity. | 2015-06-30 04:00 | 2015-09-25 12:00 | 2015-09-25 02:00 | Submitted 9/25/2015 | 2015 | Completed Late | Coupled Thermal-Hydrologic-Chemical Coupled Model for In-Drift Disposal Test | Stauffer, Philip | Stauffer, Philip | None |  | FCRD-UFD-2015-000605 | Salt multiphase heat dissolution vapor
M2FT-15HQ0817072 https://www.fedconnect.net/FedConnect/default.aspx?ReturnUrl=%2fFedConnect%2f%3fdoc%3dDE-SOL-0008071%26agency%3dDOE&doc=DE-SOL-0008071&agency=DOE | M2 | 1.02.08.17.07 | DOE-HQ | FT-15HQ081707 | DR Deep Borehole Disposal - DOE-HQ | Couch, Brad | Mackinnon, Robert | Site Acquisition Activities Initiated | Site Acquisition Activities Initiated | Initiate activities to acquire the site for the Field Test. | 2015-07-01 06:00 |  | 42180.0833 |  | 2015 | Complete | Deep Borehole Draft RFP issued April 7, 2015 DE-SOL-0008071 |  |  | None | Deep Borehole Draft RFP issued April 7 2015 DE-SOL-0008071 (1).pdf | FCRD-UFD-2015-000017
M4FT-15AN0806016 | M4 | 1.02.08.06.01 | ANL | FT-15AN080601 | DR Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Progress report on development of mixed potential model and integration with PA | Progress report on development of mixed potential model and integration with PA | Experiments to measure effects of bromide and sulfide on catalytic activity of noble metal alloy (epsilon phase) affecting fuel dissolution and modeling to include in MPM. | 2015-07-21 03:00 |  | 2015-07-21 01:00 |  | 2015 | Complete | Fuel Matrix Degradation Model: Integration with Performance Assessment and Canister Corrosion Model Development | Jerden, James | Jerden, James | None | ANL_MPM_FCRD-UFD-2015-000550 R1.pdf | FCRD-UFD-2015-000550
M4FT-15AN0807016 | M4 | 1.02.08.07.01 | ANL | FT-15AN080701 | DR Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Technical progress and accomplishments report for activities to develop MPM | Technical progress and accomplishments report for activities to develop MPM | Progress report for activities in argillite and crystalline control accounts to continue developing mixed potential model and its integration into PA. Experiments to measure poisoning effects of bromide and sulfide solutions on noble metal particle catalysis of H2 and H2O2 redox reactions | 2015-07-21 03:00 |  | 2015-07-21 01:00 |  | 2015 | Complete | Fuel Matrix Degradation Model: Integration with Performance Assessment and Canister Corrosion Model Development | Jerden, James | Jerden, James | None | ANL_MPM_FCRD-UFD-2015-000550 R1.pdf | FCRD-UFD-2015-000552
M4FT-15LA0807021 | M4 | 1.02.08.07.02 | LANL | FT-15LA080702 | DR Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Modeling and experimental activities for crystalline rock disposal | Modeling and experimental activities for crystalline rock disposal | This report will describe | 2015-07-21 04:00 |  | 2015-07-21 02:00 |  | 2015 | Complete | Crystalline and Crystalline International Disposal Activities | Viswanathan, Hari | Viswanathan, Hari | None | M4FT_15LA080702.pdf | FCRD-UFD-2015-000602 | discrete fracture network, colloid-facilitated transport
M4FT-15LL0807052 | M4 | 1.02.08.07.05 | LLNL | FT-15LL080705 | DR Crystalline Disposal R&D - LLNL | Sutton, Mark | McMahon, Kevin | Progress Report on FY15 Crystalline Experiments | FY15 Progress Report on UFD Crystalline Interactions with Radionuclides | FY15 progress report on experimental studies evaluating radionuclide interaction on crystalline rock | 2015-07-21 15:00 | 2015-08-20 03:00 | 2015-08-28 03:00 |  | 2015 | Completed Late | Progress Report on FY15 Crystalline Experiments M4FT-15LL0807052 | Zavarin, Mavrik | Zavarin, Mavrik | None | M4T-15LL080752_FINAL.pdf | FCRD-UFD-2015-000612
M3FT-15LB0807042 | M3 | 1.02.08.07.04 | LBNL | FT-15LB080704 | DR Crystalline Disposal R&D - LBNL | Houseworth, James | McMahon, Kevin | Laboratory Experiments on Bentonite Samples: FY14 Progress | Laboratory Experiments on Bentonite Samples: FY14 Progress | Laboratory Experiments on Bentonite Samples: FY14 Progress, Level 3, Due Date: July 24, 2015 | 2015-07-24 18:00 |  | 2015-07-24 03:00 |  | 2015 | Complete | Laboratory Experiments on Bentonite Samples: FY15 Progress | Tinnacher, Ruth | Houseworth, James | None | M3FT-15LB0807042 LBNL.pdf | FCRD-UFD-2015-000365 | uranium, sorption, diffusion, clay, montmorillonite, bentonite, nuclear waste
M3FT-15LB0806052 input for M3FT-15LB0806032 | M3 | 1.02.08.06.05 | LBNL | FT-15LB080605 | DR Argillite GIS Database Support - LBNL | Dobson, Patrick | McMahon, Kevin | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock" | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock" | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock," Level 3, Due Date: July 31, 2015 (this is a milestone listed under the DR Argillite Disposal R&D Workpackage). | 2015-07-31 06:00 |  | 2015-07-31 03:00 |  | 2015 | Complete | N/A | LBNL |  | None |  | FCRD-UFD-2015-000364
M3FT-15LB0806042 input for M3FT-15LB0806032 | M3 | 1.02.08.06.04 | LBNL | FT-15LB080604 | DR Argillite International Collaborations - LBNL | Houseworth, James | McMahon, Kevin | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock" | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock" | Input for "Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock," Level 3, Due Date: July 31, 2015 (this is a milestone listed under the DR Argillite Disposal R&D Workpackage). | 2015-07-31 09:00 |  | 2015-07-31 03:00 |  | 2015 | Complete | N/A | LBNL |  | None |  | FCRD-UFD-2015-000363
M3FT-15LB0806032 | M3 | 1.02.08.06.03 | LBNL | FT-15LB080603 | DR Argillite Disposal R&D - LBNL | Houseworth, James | McMahon, Kevin | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock, Level 3, Due Date: July 31, 2015 This milestone will feed into SNL milestone due 9/4/2015. Title: Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks Site: SNL, Level: M2, QA Rigor: QRL3, Estimated Completion Date: 9/4/2015 Title: Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | 2015-07-31 23:00 |  | 2015-07-31 03:00 |  | 2015 | Complete | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | LBNL | Houseworth, James | None | M3FT-15LB0806032 LBNL.pdf | FCRD-UFD-2015-000362 | argillite, bentonite, clay, THMC modeling, THM modeling, fracture damage modeling, heater test modeling, coupled processes
M3FT-15SN0818028 File name shows same SAND number (SAND2015-6273R) as for M3FT-15SN0818029 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Summary of FY15 Results of Benchmark Modeling | Summary of FY15 Results of Benchmark Modeling | Summary of FY15 Results of Benchmark Modeling | 2015-08-03 08:00 |  | 42220.0833 |  | 2015 | Completed Late | Summary of FY15 Results of Benchmark Modeling Activities | Arguello, Guadalupe | Arguello, Guadalupe | None | SAND2015-6273 R ARGUELLO 2015_FCRD-Report..pdf | FCRD-UFD-2015-000519
M4FT-15LL0806062 | M4 | 1.02.08.06.06 | LLNL | FT-15LL080606 | DR Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | LLNL Thermodynamic and Sorption Data FY15 Progress Report | LLNL FY15 Progress Report on Thermodynamic and Sorption Data Development and Evaluation | Progress report documenting LLNL development and evaluation of thermodynamic and sorption data. | 2015-08-04 06:00 |  | 2015-09-01 03:00 | M4FT-15LL0806062-LLNL Thermodynamic and Sorption Data FY15 Progress Report | 2015 | Completed Late | M4FT-15LL0806062-LLNL Thermodynamic and Sorption Data FY15 Progress Report | Zavarin, Mavrik | Zavarin, Mavrik | None | IM-800066-3.pdf | FCRD-UFD-2015-000611
M3FT-15LA0806021 | M3 | 1.02.08.06.02 | LANL | FT-15LA080602 | DR Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | argillite EBS experimental program 2015 | Argillite Disposal experimental R&D LANL | deliverable -LANL experimental research | 2015-08-04 12:00 |  | 2015-08-04 02:00 |  | 2015 | Complete | Argillite Disposal R&D - LANL 2015 | Caporuscio, Florie | Caporuscio, Florie | None | EBS FY15 Deliverable-FINAL.docx.pdf | FCRD-UFD-2015-000356 | EBS, Argillite
M3FT-15SN08180212 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | FY15 Report on Lab Thermomechanical Testing | FY15 Report on Lab Thermomechanical Testing | Report from RESPEC on testing of WIPP salt cores | 2015-08-12 02:00 |  | 2015-08-28 02:00 |  | 2015 | Completed Late | FY15 Report on Lab Thermomechanical Testing | Hansen, Francis | Leigh, Christi | None | M3FT-15SN08180212 Hansen 2015_FCRD Report 082815.docx | FCRD-UFD-2015-000516
M4FT-15LB0811015 | M4 | 1.02.08.11.01 | LBNL | FT-15LB081101 | DR International Disposal R&D - LBNL | Birkholzer, Jens | McMahon, Kevin | Update on Fifth Worldwide Review | Update on Fifth Worldwide Review | Update on Fifth Worldwide Review, Level 4, Due Date: August 14, 2015 | 2015-08-14 14:00 |  | 2015-08-13 03:00 |  | 2015 | Complete | Challenging Issues for Nuclear Waste Disposal in Deep Geological Formations: Status Report on Fifth Worldwide Review | Faybishenko, Boris | Birkholzer, Jens | None | M4FT-LB0811015 Update on Fifth Worldwide Review.pdf | FCRD-UFD-2015-000606 | nuclear waste, geological disposal, worldwide review
M4FT-15LB0817033 | M4 | 1.02.08.17.03 | LBNL | FT-15LB081703 | DR Deep Borehole Disposal - LBNL | Birkholzer, Jens | Mackinnon, Robert | Field Test Characterization and Monitoring Design | Field Test Characterization and Monitoring Design | Field Test Characterization and Monitoring Design, Level 4, Due Date: August 14, 2015 This milestone will feed into SNL milestone M2FT-15SN08170xx, Deep Borehole Field Test Specifications, September 15 2015. Title: Deep Borehole Field Test Specifications (this report will document what characterization and monitoring activities will take place) | 2015-08-14 15:00 |  | 2015-08-13 03:00 |  | 2015 | Complete | Memo RE: M4FT-15LB0817033 |  |  | None |  | FCRD-UFD-2015-000608
M4FT-15SN0811021 | M4 | 1.02.08.11.02 | SNL | FT-15SN081102 | DR International Disposal R&D - SNL | McMahon, Kevin | McMahon, Kevin | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | This is a report that provides input from SNL to a L2 milestone at LBNL entitled "Status of UFD Campaign International Activities in Disposal Research." | 2015-08-15 06:00 |  | 2015-08-24 02:00 |  | 2015 | Completed Late | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | McMahon, Kevin | McMahon, Kevin | None | M4FT-15SN0811002 SNL International FY15 FINAL.docx | FCRD-UFD-2015-000713
M4FT-15IN0817012 | M4 | 1.02.08.17.01 | INL | FT-15IN081701 | DR Deep Borehole Disposal - INL | Russell, Glenn | Mackinnon, Robert | An interactive web-based mapping tool for visualizing regional geology and siting guidelines | An interactive web-based mapping tool for the Used Fuel Campaign GIS Database | Report on implementation of a web-based interactive mapping tool including user guide | 2015-08-19 04:00 | 2015-09-18 02:00 | 2015-09-01 02:00 | This is a milestone report for the interactive web-based regional geology mapping tool. | 2015 | Completed Late | Regional Geology Interactive Web Based Mapping Application Milestone Report | Russell, Glenn | Russell, Glenn | None | FCRD-Report -Regional Geology Web Map App-Milestone-INL.pdf | FCRD-UFD-2015-000592
M4FT-15PN0817051 | M4 | 1.02.08.17.05 | PNNL | FT-15PN081705 | DR Deep Borehole Disposal - PNNL | Hanson, Brady | Mackinnon, Robert | PNNL Feed to the Borehole Design Report | PNNL Feed to the Borehole Design Report | Summary of PNNL work supporting Borehole to be used in the SNL M2 Design report. | 2015-08-21 06:00 | 2015-09-04 03:00 | 2015-09-11 03:00 | PNNL performed emplacement mode hazard analysis in support of the SNL M2 report. This M4 documents the work performed. | 2015 | Completed Late | Emplacement Mode Hazard Identification and Analysis | Eslinger, Paul | Hanson, Brady | None | PNNL_DeepBore_Hazards_Analysis_PNNL-24616_Final.pdf | FCRD-UFD-2015-000702 | Deep Borehole; emplacement hazards
M2FT-15SN0807071 | M2 | 1.02.08.07.07 | SNL | FT-15SN080707 | DR Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | End of FY update on Crystalline Disposal Research This deliverable will include a section to summarize the applicability of the work to defense waste. | 2015-08-21 10:00 |  | 42230.0833 |  | 2015 | Complete | Used Fuel Disposal in Crystalline Rocks: FY15 Progress Report | Wang, Yifeng | Wang, Yifeng | None | Crystalline yr end report.pdf | FCRD-UFD-2015-000125 | used fuel disposition, crystalline media, radionuclide interaction, bentonite
M4FT-15SN0807082 | M4 | 1.02.08.07.08 | SNL | FT-15SN080708 | DR Crystalline International Collaborations - SNL | Wang, Yifeng | McMahon, Kevin | Report on international collaboration on fluid flow in fracutred crystlline rocks | Report on international collaboration on fluif flows in fractured crystalline rocks | This milestone report will describe the international work to be performed through collaborations with DECOVALEX and KAERI. | 2015-08-25 06:00 |  | 2015-08-25 02:00 |  | 2015 | Complete | International Collaborations on Fluid Flows in Fractured Crystalline Rocks: FY15 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M4FT-15SN0807082.pdf | FCRD-UFD-2015-000711 | Flow in fractured media, spontaneous streaming potential, fracture opening and closure
M4FT-15PN0804011 | M4 | 1.02.08.04.01 | PNNL | FT-15PN080401 | DR Engineered Material Performance - PNNL | Buck, Edgar | McMahon, Kevin | Report on Radiolysis Modeling and Current Status of Used Fuel Disposal Research: Emphasis on the role of Bromine | Radiolysis Modeling and Current Status of Used Fuel Disposal Research: Role of Bromine | Report on modeling activities and integration. | 2015-08-28 12:00 |  | 2015-08-25 03:00 |  | 2015 | Complete | Chloride/Bromide System Radiolysis Model for Integration with the Mixed Potential Model | Buck, Edgar | Buck, Edgar | None | FCRD-UFD-2015-000699.pdf | FCRD-UFD-2015-000699 | radiolysis, radiolysis model, RM-MPM, PFLOTRAN, modeling, bromine
M4FT-15LA0819013 | M4 | 1.02.08.19.01 | LANL | FT-15LA081901 | DR Salt Field Testing - LANL | Stauffer, Philip | MacKinnon, Robert | Brine Transport Experiments in Run-of-Mine Salt | Brine Transport Experiments in Run-of-Mine Salt | Report on experimental studies of evaporation and heat pipe effects in run-of-min salt | 2015-08-31 04:00 |  | 2015-08-31 02:00 |  | 2015 | Complete | Brine Transport Experiments in Granular Salt | Stauffer, Philip | Stauffer, Philip | None | L4_Experiment_milestone_8-31-15.pdf | FCRD-UFD-2015-000604 | Salt Field Testing Preparation
M2FT-15SN0806071 | M2 | 1.02.08.06.07 | SNL | FT-15SN080607 | DR Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | End of FY15 update on progress in argillite disposal research. This deliverable will include a section to summarize the applicability of the work to defense waste. | 2015-09-04 14:00 |  | 42251.0833 | Evaluation of Used Fuel Disposition in Clay-Bearing Rock (Vols. I & II). Report describing FY15 R&D efforts in the evaluation of deep-geological disposal of nuclear waste in clay/shale/argillite rock. | 2015 | Complete | Evaluation of Used Fuel Disposition in Clay-Bearing Rock (Vol. I) (FCRD-UFD-2015-000124) | Jove Colon, Carlos | Jove Colon, Carlos | None | M2FT-15SN0806071_Milestone_UFDC_ARG_FY15_Rev1a.pdf | FCRD-UFD-2015-000124
M2FT-15SN0817091 | M2 | 1.02.08.17.09 | SNL | FT-15SN081709 | Borehole Test Design - SNL | Hardin, Ernest | Mackinnon, Robert | Deep Borehole Field Test Specifications | Deep Borehole Field Test Specifications | SNL will produce a M2 level deliverable that gives a systems overview of the deep borehole field test including a conceptual design of the borehole, conceptual design of the test canisters, description of surface equipment, steps required for demonstration of surface handling and borehole emplacement of canisters, and data that will be acquired from the borehole and related investigations. | 2015-09-15 08:00 |  | 42261.0833 | DBFT Specifications M2 deliverable, having received programmatic and technical reviews at Sandia, is submitted for acceptance review. | 2015 | Complete | Deep Borehole Field Test Specifications | Hardin, Ernest | Hardin, Ernest | None | DBFT Specs M2 Final Rev 1.pdf | FCRD-UFD-2015-000132 | borehole disposal, waste packaging, emplacement, retrieval
M3FT-15LA0817023 | M3 | 1.02.08.17.02 | LANL | FT-15LA081702 | DR Deep Borehole Disposal - LANL | Perry, Frank | Mackinnon, Robert | Interactive web-based mapping application for the UFD GIS Database | Interactive web-based mapping application for the UFD GIS Database | Report on INL and LANL activities to develop and web-based interface for the UFD GIS database | 2015-09-18 02:00 |  | 2015-09-17 02:00 | Milestone report for the interactive web-based regional geology mapping tool. | 2015 | Complete | Regional Geology Interactive Web Based Mapping Application | Russell, Glenn | Russell, Glenn | None | FCRD-Report -Deep Borehole Web Map App-Milestone_INL_R2.pdf | FCRD-UFD-2015-000357 | Regional Geology, Web Application, GIS
M3FT-15LB0818012 | M3 | 1.02.08.18.01 | LBNL | FT-15LB081801 | DR Salt R&D - LBNL | Birkholzer, Jens | MacKinnon, Robert | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures, Level 3, Due Date: September 18, 2015 | 2015-09-18 06:00 |  | 2015-09-18 03:00 | Milestone report delivered on due date. | 2015 | Complete | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | Rutqvist, Jonny | Birkholzer, Jens | None | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures.pdf | FCRD-UFD-2015-000366 | salt, nuclear waste, modeling, coupled processes
M3FT-15LB0819022 input for M3FT-15LB0818012 | M3 | 1.02.08.19.02 | LBNL | FT-15LB081902 | DR Salt Field Testing - LBNL | Birkholzer, Jens | MacKinnon, Robert | Input for "Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures" | Input for "Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures" | Input for "Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures", Level 3, Due Date: September 18, 2015 (milestone listed under the DR Salt R&D workpackage). | 2015-09-18 09:00 |  | 2015-09-18 06:00 | This deliverable is included as part of Milestone M3FT-15LB0818012. | 2015 | Complete | This milestone is input for "Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures" | n/a | n/a | None |  | FCRD-UFD-2015-000367
M2FT-15SN0808011 | M2 | 1.02.08.08.01 | SNL | FT-15SN080801 | DR Generic Disposal System Analysis - SNL | Mariner, Paul | McMahon, Kevin | Application of Generic Disposal System Models | Application of Generic Disposal System Models | Report documenting the application of generic disposal system models to reference cases This deliverable will include a section to summarize the applicability of the work to defense waste. | 2015-09-22 16:00 |  | 42268.1667 | Level 2 deliverable uploaded for DOE policy review. | 2015 | Complete | Application of Generic Disposal System Models |  |  | None | GDSA_2015_draft_r3a.pdf | FCRD-UFD-2015-000126
M4FT-15SN0819032 | M4 | 1.02.08.19.03 | SNL | FT-15SN081903 | DR Salt Field Testing - SNL | Kuhlman, Kris | MacKinnon, Robert | Laboratory Determination of Salt Flow and Transport Properties | Laboratory Testing and Modeling of Salt Flow and Transport Properties | Finishing laboratory testing started in late FY14 on flow and transport properties of both reconsolidated run-of-mine crushed salt and damaged intact salt. Modeling will be conducted in support of laboratory testing and to aid interpretation of results. | 2015-09-24 14:00 |  | 2015-09-22 02:00 | Laboratory test report of two-phase flow properties of salt with summary and analysis of data completed before deadline. | 2015 | Complete | Experimental Inverstigation of Two-Phase Flow in Consolidating and Intact Salt: Analysis of Capillary Pressure Measurements from Core Labs | Malama, Bwalya | Kuhlman, Kris | None | final_core_labs_report.pdf | FCRD-UFD-2015-000716 | salt;
M2FT-15LB0811012 | M2 | 1.02.08.11.01 | LBNL | FT-15LB081101 | DR International Disposal R&D - LBNL | Birkholzer, Jens | McMahon, Kevin | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | M2FT-15LB081101, International Collaboration Activities in Different Geologic Disposal Environments, Level 2, Due Date: September 25, 2015 This activity provides support for the Used Fuel Disposition Campaign Technical Lead for International Activities. The role of the Technical Lead is to: - Integrate and coordinate UFD - supported activities among participating national laboratories and comparable programs outside the US - Serve as the primary point of contact with the Campaign for the DOE/NE-53 Federal Program Manager for International Activities - Work with NE-53 to ensure a consistent and coherent focus to UFD’s international activities. - Primary responsibility for funding of specific international collaborations will remain within the relevant technical work packages. - Advise both the UFD management team and work package managers on international opportunities that complement ongoing R&D within the campaign - Help identify those activities that provide the greatest potential for substantive technical advances - Interact with international organizations and programs to help advance specific collaborations. | 2015-09-25 10:00 |  | 2015-09-25 03:00 | Milestone report submitted on its due date. | 2015 | Complete | International Collaboration Activities in Different Geologic Disposal Environments | Birkholzer, Jens | Birkholzer, Jens | None | M2FT-15LB0811012_Sep 2015 - pp 1 - 100.pdf M2FT-15LB0811012_Sep 2015 - pp 101-195.pdf | FCRD-UFD-2015-000079 | underground research laboratory, disposal research, international
M2FT-15SN0817081 | M2 | 1.02.08.17.08 | SNL | FT-15SN081708 | Site Characterization - SNL | Kuhlman, Kris | Mackinnon, Robert | Conceptual Design and Requirements for Characterization and Field Test Boreholes | Conceptual Design and Requirements for Characterization and Field Test Boreholes | Describes the conceptual design and requirements for the characterization and test boreholes. | 2015-09-29 08:00 |  | 2015-09-24 04:00 | Level-2 milestone report prepared ahead of schedule. | 2015 | Complete | Conceptual Design and Requirements for Characterization and Field Test Boreholes: Deep Borehole Field Test | Kuhlman, Kris | Kuhlman, Kris | None | deep-borehole-conceptual-design-requirements-M2-FINAL.pdf | FCRD-UFD-2015-000131
M3FT-15SN0824011 | M3 | 1.02.08.24.01 | SNL | FT-15SN082401 | DR DOE Managed HLW and SNF Research: Organize information needed for repository design assessments - SNL | Sassani, David | McMahon, Kevin | Status of Defense Waste Repository Safety Assessment Information Needs | Status of Defense Waste Repository Safety Assessment Information Needs | Status update on progress made toward organizing and updating D-waste inventories, progress toward implementation of OWL. | 2015-09-30 02:00 |  | 2015-09-30 02:00 | The FCT QA Cover page with technical review documentation is attached. | 2015 | Complete | Status of DOE-Managed Waste Repository Safety Assessment Information Needs | Sassani, David | Sassani, David | None | signed FCT QA cover sheet M3FT-15SN0824011.pdf | FCRD-UFD-2015-000804 | Repository DOE-mananged waste high level waste
M3FT-15SN08180211 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | FY:15 Transport Properties of Run-of-Mine Salt Backfill – Unconsolidated to Consolidated | FY:15 Transport Properties of Run-of-Mine Salt Backfill – Unconsolidated to Consolidated | Laboratory experiments will be performed to determine the capillary pressures and permeabilities of reconsolidated salt samples. Summary of FY15 work on Transport Properties of Run-of-Mine Salt Backfill – Unconsolidated to Consolidated | 2015-09-30 08:00 |  | 2015-10-06 02:00 | This is complete and loaded into the deliverable section | 2015 | 90 Day | FY:15 Transport Properties of Run-of-Mine Salt Backfill – Unconsolidated to Consolidated | Dewars, Thomas | Dewars, Thomas | None | M3FT-15SN08180211 Dewers FY15 Transport Properties of Run-of-Mine Salt Backfill.docx | FCRD-UFD-2015-000515
M3FT-15SN0818029 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | SNL Benchmarking Results Using Sierra Mechanics | SNL Benchmarking Results Using Sierra Mechanics | Presentations at: This is a continuation of the bench mark modeling initiative. Several laboratories are participating. Sandia is participating using the Sierra Mechanics code •Mechanical Behavior of Salt VIII •ARMA 49th U.S. Rock Mechanics /Geomechanics Symposium | 2015-09-30 10:00 |  | 2015-08-04 02:00 |  | 2015 | Complete | Summary of FY15 Results of Benchmark Modeling Activities | Arguello, Guadalupe | Arguello, Guadalupe | None | SAND2015-6273 R ARGUELLO 2015_FCRD-Report..pdf | FCRD-UFD-2015-000520
M3FT-15SN0818027 | M3 | 1.02.08.18.02 | SNL | FT-15SN081802 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY15 Results | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY15 Results | In FY2015 experiments will be conducted to determine the thermodynamics of basic elements (Na, Ca, K, Mg) in brines. In addition, larger scale testing equipment will come on-line. Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY14 Results | 2015-09-30 10:00 |  | 2015-09-25 02:00 | This work is conducted under Task 2.5, Development of a Chemical Model/database up to 200 oC with High Internal Consistency, in the TP Test Plan for Determining Thermodynamic Properties of Brines, Minerals and Corrosion Products for High Level Radioactive Waste Disposal in Salt (FCRD-UFD-2012- 00033). Sodalite is a candidate waste form for 129I, for contaminated electrolytes from electrorefinery of used nuclear fuel, and for the waste generated by the LiCl-Li2O oxide reduction electrochemical process. Salt formations are the ideal medium for disposal of the sodalite waste form. Therefore, the accurate prediction of its solubility in high ionic strength solutions at elevated temperatures is important to evaluate its performance in geological repositories. In this work, solubility constants of hydroxyl sodalite from 25oC to 100oC are obtained by applying the high temperature Al-Si Pitzer model to evaluate solubility data on hydroxyl sodalite in high ionic strength solutions at elevated temperatures. The validation test with the model-independent experimental data demonstrates that the solubility values produced by the model are in excellent agreement with the experimental data. | 2015 | Complete | Thermodynamics of Brines, Minerals and Corrosion Products at High Temperatures: FY 15 Results | Xiong, Yongliang | Xiong, Yongliang | None | M3FT-15SN0818027.pdf | FCRD-UFD-2015-000518
M4FT-15SN0826021 DRAFT. ULR - SAND2015-8961R | M4 | 1.02.08.26.02 | SNL | FT-15SN082602 | DR DOE Managed HLW and SNF Research: Generic operating procedures; e.g., quality assurance - SNL | Appel, Gordon | McMahon, Kevin | Draft Summary of operating procedures needed generic repository licensing | Draft Summary of operating procedures needed generic repository licensing effort | Draft document identifying and summarizing the principle operating procedures for a generic repository licensing effort. | 2015-10-16 14:00 |  | 2015-10-14 02:00 | Funding Delayed | 2015 | 90 Day | DRAFT Operating Procedures for a Generic Repository Licensing Organization | Appel, Gordon | Appel, Gordon | None | FCRD-UFD-2015-000812_M4FT-15SN0826021_DRAFT generic repository licensing operating procedures.pdf | FCRD-UFD-2015-000812
M4FT-15SN0826011 DRAFT. ULR - SAND2015-8962R | M4 | 1.02.08.26.01 | SNL | FT-15SN082601 | DR DOE Managed HLW and SNF Research: Establish a generic organization framework for records management, IT infrastructure, quality assurance, and systems engineering - SNL | Appel, Gordon | McMahon, Kevin | Draft Summary of generic repository licensing infrastructure | Draft Summary of generic repository licensing infrastructure | Draft document identifying and summarizing the principle elements of a generic repository licensing infrastructure organizational framework. | 2015-10-16 16:00 |  | 2015-10-14 02:00 | Funding Delayed | 2015 | 90 Day | Draft Infrastructure Framework for a Generic Repository Licensing Organization | Appel, Gordon | Appel, Gordon | None | FCRD-UFD-2015-000811_M4FT-15SN0826011_DRAFT generic repository licensing infrastructure.pdf | FCRD-UFD-2015-000811
M4FT-16SN080503031 DRAFT. ULR - SAND2016-7053R | M4 | 1.02.08.05.03.03 | SNL | FT-16SN08050303 | Develop and implement operating procedures - SNL | Appel, Gordon | McMahon, Kevin | Draft Summary of operating procedures needed generic repository licensing | Draft Summary of operating procedures needed generic repository licensing effort | Draft document identifying and summarizing the principle operating procedures for a generic repository licensing effort. | 2015-10-16 22:00 |  | 42291.0833 |  | 2016 | Complete | DRAFT Operating Procedures for a Generic Repository Licensing Organization | Appel, Gordon | Appel, Gordon | None | FCRD-UFD-2015-000812_M4FT-15SN0826021_M4FT-16SN080503031_SAND2015-8961 R.pdf | FCRD-UFD-2016-000632
M4FT-16SN080503022 SAND2016-9090R | M4 | 1.02.08.05.03.02 | SNL | FT-16SN08050302 | Establish organizational framework to meet regulator expectations - SNL | Appel, Gordon | McMahon, Kevin | Draft Summary of generic repository licensing infrastructure | Draft Summary of generic repository licensing infrastructure | Draft document identifying and summarizing the principle elements of a generic repository licensing infrastructure organizational framework. | 2015-10-17 02:00 |  | 42291.0833 |  | 2016 | Complete | DRAFT Infrastructure Framework for a Generic Repository Licensing Organization | Appel, Gordon | Appel, Gordon | None | FCRD-UFD-2015-000811_M4FT-15SN0826011_M4FT-16SN080503022_SAND2015-8962 R.pdf | FCRD-UFD-2016-000633
M3FT-15SN0825012 | M3 | 1.02.08.25.01 | SNL | FT-15SN082501 | DR DOE Managed HLW and SNF Research: EBS concepts and thermal analysis - SNL | Matteo, Edward | Mackinnon, Robert | EBS Concepts and Thermal Analysis Status | DR D-Repository: EBS concepts and thermal analysis - SNL | Update and Status of EBS Concepts and Thermal progress | 2015-10-23 08:00 |  | 2015-10-23 02:00 | on schedule | 2015 | 90 Day | DOE-Managed HLW and SNF Research: FY15 EBS and Thermal Analysis Work Package Status | Matteo, Edward | Matteo, Edward | None | FY15 DOE-Managed HLW and SNF -- EBS and Thermal Analysis v2.pdf | FCRD-UFD-2015-000803
M3FT-16SN080309039 Conference Paper | M3 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Conference paper:Experimental Determination of Cerianite (CeO2) in High Ionic Strength Solutions at High Temperatures: An Analog to An(IV) | Conference paper:Experimental Determination of Cerianite (CeO2) in High Ionic Strength Solutions at High Temperatures: An Analog to An(IV) | x | 2015-11-30 08:00 |  | 42307.0833 |  | 2016 | Complete | Experimental Determination of Solubility of Cerianite (CeO2) in High Ionic Strength Solutions at Elevated Temperatures: An Analog to Tetravalent Actinides | Xiong, Yongliang | Xiong, Yongliang | None | Xiong_Cerianite_EAFORM_Rev.ppt | FCRD-UFD-2016-000435 | High Inoic Strength, Cerianite
M2FT-16SN080309031 | M2 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Proceedings from the 6th US/German Workshop on Salt Repository Research, Design and Operations | Proceedings from the 6th US/German Workshop on Salt Repository Research, Design and Operations | This report will present the collaborative efforts between technical peers in the US and Germany on topics in Salt Mechanics and Repository Design that were the focus of the 6th US/German Workshop. | 2016-01-31 04:00 |  | 42387.0833 |  | 2016 | Complete | Proceedings of the 6th US/German Workshop on Salt Repository Research, Design, and Operation |  |  | None |  | FCRD-UFD-2016-000069
M4FT-16OR080308043 single report covers M4FT-16OR080308043 and M4FT-16OR080308044 | M4 | 1.02.08.03.08.04 | ORNL | FT-16OR08030804 | Deep Borehole Field Test - ORNL | Howard, Rob | Mackinnon, Robert | Draft SoW for DBFT Engineering Demonstration Design | DBFT Design SOW | ORNL will develop a draft SoW for use in procuring engineering services for final design of the DBFT Engineering Demonstration. ORNL will use conceptual design information provided by SNL, and design reviews provided by DOE’s current engineering services contractor, to develop a design process, identify design inputs, and specify deliverables that will achieve the goals of final design. | 2016-03-15 02:00 |  | 2016-03-15 |  | 2016 | Complete | Deep Borehole Field Test Engineering Demonstration Plan | Peretz, Fred | Peretz, Fred | None | UFD - Engineering Demonstration report March 15.pdf | FCRD-UFD-2016-000608 | Deep Borehole Field Test
M4FT-16OR080308044 single report covers M4FT-16OR080308043 and M4FT-16OR080308044 | M4 | 1.02.08.03.08.04 | ORNL | FT-16OR08030804 | Deep Borehole Field Test - ORNL | Howard, Rob | Mackinnon, Robert | DBFT Design Cost Planning | DBFT Cost Planning | Working with SNL, develop rough-order-of-magnitude cost estimates for: 1) the final design activity for which the SoW is described above; 2) fabrication and testing of hardware for the DBFT demonstration; and 3) deployment in the DBFT Engineering Demonstration. These cost estimates are intended for use by the DOE in planning the DBFT project. The costing information will be delivered to SNL informally, as Official Use Only information, separately from the design SoW . | 2016-03-15 02:00 |  | 2016-03-15 |  | 2016 | Complete | Deep Borehole Field Test Engineering Demonstration Plan | Peretz, Fred | Peretz, Fred | None | UFD - Engineering Demonstration report March 15.pdf | FCRD-UFD-2016-000609 | Deep Borehole Field Test
M4FT-16IN080308011 | M4 | 1.02.08.03.08.01 | INL | FT-16IN08030801 | Deep Borehole Field Test - INL | Russell, Glenn | Mackinnon, Robert | Interactive web-based tool for displaying geologic data | Interactive web-based tool for displaying geologic data | Continued support of Deep Borehole Field Test through development, maintenance and enhancement of interactive web based tool for displaying geologic data. | 2016-05-13 12:00 |  | 2016-05-13 02:00 |  | 2016 | Complete | Regional Geology Interactive Web Based Mapping Application Mid-FY2016 Milestone Report | Russell, Glenn | Russell, Glenn | None | FCRD-UFD-2016-000610.pdf | FCRD-UFD-2016-000610
M3FT-16SN0803090316 M3FT-16SN0803090313, same SAND number. | M3 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Consideration of Differences between Bedded and Domal Salt Pertaining to Disposal of Heat-Generating Nuclear Waste | WM2016 Summary of Key Differences of Bedded and Domal Salt Pertaining to the Safety Case | Consideration of Differences between Bedded and Domal Salt Pertaining to Disposal of Heat-Generating Nuclear Waste | 2016-05-31 02:00 | 42559.1667 | 42559.0833 |  | 2016 | Completed Late | Consideration of Differences between Bedded and Domal Salt Pertaining to Disposal of Heat-Generating Nuclear Waste | Hansen, Francis | Leigh, Christi | None | M3FT-16SN0803090313 Comparison of Bedded and Domal Salt 070816 SAND2016-6522R.pdf | FCRD-UFD-2016-000436
M4FT-16LA080308025 | M4 | 1.02.08.03.08.02 | LANL | FT-16LA08030802 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Characterization of Borehole Wallrock using Non-Linear Acoustics | Development of downhole acoustic tool for material characterization | Developent of a downhole tool to characterize material characteristics using acoustics | 2016-06-24 02:00 | 2016-08-05 04:00 | 2016-08-10 02:00 |  | 2016 | Completed Late | In Situ Acoustic Measurements: A Wave Focusing and Fracture Characterization Feasibility Study | Ulrich, Timothy | Ulrich, Timothy | None | UFD-InSituElasticWaveMeasurement-Ulrich.pdf | FCRD-UFD-2016-000611 | deep borehole, fractures, acoustic, measurement
M2FT-16SN080308081 | M2 | 1.02.08.03.08.08 | SNL | FT-16SN08030808 | Field Test Design - SNL | Hardin, Ernest | Mackinnon, Robert | Deep Borehole Field Test Conceptual Design Report | Deep Borehole Field Test Conceptual Design Report | This report will describe the conceptual design and specifications for the surface handling and emplacement system and waste packages and their testing. The current conceptual design of the field test borehole will also be included. | 2016-06-30 10:00 |  | 42550.0833 |  | 2016 | Complete | Deep Borehole Field Test Conceptual Design Report | Hardin, Ernest | Hardin, Ernest | None | DBFT CDR M2 Rev 0 (UFD review).pdf | FCRD-UFD-2016-000070
M4FT-16AN080302011 | M4 | 1.02.08.03.02.01 | ANL | FT-16AN08030201 | DR Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Documents development of the fuel matrix degradation model to account for interactions between the dissolution of used fuel and corroding waste package materials within a breached waste package. | 2016-07-21 07:00 |  | 2016-07-21 01:00 |  | 2016 | Complete | Fuel Matrix Degradation Model: Canister Corrosion and the Effect of Hydrogen on Used Fuel Degradation Rates | Jerden, James | Jerden, James | None | ANL_FMDM_FY2016_M4FT_16AN080302011_M4FT_16AN0803030011.pdf | FCRD-UFD-2016-000613 | source term, used fuel degradation, waste package, canister corrosion.
M4FT-16AN080303011 | M4 | 1.02.08.03.03.01 | ANL | FT-16AN08030301 | DR Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Documents development of the fuel matrix degradation model to account for interactions between the dissolution of used fuel and corroding waste package materials within a breached waste package. | 2016-07-21 09:00 |  | 2016-07-21 01:00 |  | 2016 | Complete | Fuel Matrix Degradation Model: Canister Corrosion and the Effect of Hydrogen on Used Fuel Degradation Rates | Jerden, James | Jerden, James | None | ANL_FMDM_FY2016_M4FT_16AN080302011_M4FT_16AN0803030011.pdf | FCRD-UFD-2016-000614 | source term, used fuel degradation, waste package, canister corrosion
M2FT-16SN080503011 ULR. PREDECISIONAL DRAFT. DOE revised and finalized as Draft Plan for a Defense Waste Repository (Draft - Release for Public Comment;) and finalized as Federal Register Vol. 81, No. 243 Monday, December 19, 2016 Notices. (Copies in Milestones Library.) SAND2016-7053R | M2 | 1.02.08.05.03.01 | SNL | FT-16SN08050301 | Program Planning - SNL | McMahon, Kevin | McMahon, Kevin | Draft Program Plan for the Permanent Disposal of High-Level Radioactive Waste and Spent Nuclear Fuel from Defense and Department of Energy Research and Development Activities | Draft Program Plan for the Permanent Disposal of High-Level Radioactive Waste and Spent Nuclear Fuel from Defense and Department of Energy Research and Development Activities | Develop a Draft Generic Program Plan identifying and summarizing the principle elements necessary for a generic repository program for disposal of DOE managed HLW and Spent Fuel. | 2016-07-29 02:00 |  | 42580.0833 |  | 2016 | Complete | Tittle Page - Draft Program Plan for the Permanent Disposal of High-Level Radioactive Waste and Spent Nuclear Fuel from Defense and Department of Energy Research and Development Activities | Swift, Peter | Swift, Peter | OUO | 20160729_FCRD-UFD-2016-00078 SAND2016-7053 RDocumentation.pdf | FCRD-UFD-2016-000078
M4FT-16SR080502021 | M4 | 1.02.08.05.02.02 | SRNL | FT-16SR08050202 | EBS concepts and thermal analysis - SRNL | Carter, Joe | MacKinnon, Robert | Decay heat of selected Defense Waste Materials | Decay heat of selected DOE managed wastes | Submittal of report to work package manager responsible for milestones that the deliverable supports, Control Account Manager and Laboratory QA POC. Transmittal of document/records via upload in PICSNE in accordance with the FCT QAPD and records management requirements. | 2016-07-29 08:00 |  | 2016-06-21 |  | 2016 | Complete | Decay Heat of Selected DOE-Managed Waste Materials | Wilson, Jason | Wilson, Jason | None | FCRD-UFD-2016-000636 Decay Heat of selected Defense Waste Materials.pdf QA Cover Sheet - Decay Heat of Selected DOE-Managed Waste Materials.pdf | FCRD-UFD-2016-000636 | Decay Heat
M4FT-16LA080308023 | M4 | 1.02.08.03.08.02 | LANL | FT-16LA08030802 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Hydrothermal Experiments on Deep Borehole Seal Materials | Experimental Studies of Seal Materials for the Deep Borehole Field Test | Report will describe experiments in the system wallrock-clay-steel-groundwater to evaluate interactions among seal components, including: mineral phase stability, metal corrosion rates and thermal limits. | 2016-07-29 08:00 |  | 2016-07-28 02:00 |  | 2016 | Complete | Deep Boreholes Seals Subjected to High P, T conditions – Preliminary Experimental Studies | Caporuscio, Florie | Caporuscio, Florie | None | Deep Borehole 2016 deliverable -Caporuscio-LANL.pdf | FCRD-UFD-2016-000615 | pollucite, borehole seals
M4FT-16SR080501021 | M4 | 1.02.08.05.01.02 | SRNL | FT-16SR08050102 | Organize repository design assessment information - SRNL | Carter, Joe | McMahon, Kevin | Inventory input report | DOE Managed Waste Inventory input report | Provide SRNL input to the DOE managed waste inventory. | 2016-07-29 10:00 |  | 2016-06-21 |  | 2016 | Complete | Decay Heat of Selected DOE-Managed Waste Materials | Carter, Joe | Carter, Joe | None | FCRD-UFD-2016-000635 Decay Heat of selected Defense Waste Materials.pdf QA Cover Sheet - M4FT-16SR080501021-Decay Heat of Selected DOE-Managed Waste Materials.pdf | FCRD-UFD-2016-000635 | Decay Heat
M4FT-16PN080302062 | M4 | 1.02.08.03.02.06 | PNNL | FT-16PN08030206 | DR Argillite Disposal R&D - PNNL | Buck, Edgar | McMahon, Kevin | Final Report on FY16 Activities | Status Report on FY16 Activities - Radiolysis Model & Experimental Validation | Peer review paper documenting the FY16 progress on argillite disposal R&D activities. | 2016-08-05 04:00 |  | 2016-08-05 03:00 |  | 2016 | Complete | Addition of Bromide to Radiolysis Model Formulation for Integration with the Mixed Potential Model | Buck, Edgar | Buck, Edgar | None | PNNL RM-Bromide-2016.pdf | FCRD-UFD-2016-000617 | Bromide, radiolysis, argillite disposal, mixed potential model
M4FT-16PN080303072 | M4 | 1.02.08.03.03.07 | PNNL | FT-16PN08030307 | DR Crystalline Disposal R&D - PNNL | Buck, Edgar | McMahon, Kevin | Final Report on FY16 Activities | Final Report on FY16 Activities | Technical report documenting the FY16 progress on developing DR crystalline disposal R&D technical activities. | 2016-08-05 06:00 |  | 2016-08-05 03:00 |  | 2016 | Complete | Effect of Iron on Radiolytic Hydrogen Peroxide Generation | Buck, Edgar | Buck, Edgar | None | RM-Iron_Effects_2016-Crystalline.pdf | FCRD-UFD-2016-000618 | Iron, radiolytic hydrogen peroxide, crystalline disposal, model integration
M4FT-16SN080305022 | M4 | 1.02.08.03.05.02 | SNL | FT-16SN08030502 | DR International Disposal R&D - SNL | McMahon, Kevin | McMahon, Kevin | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL | This is a report that provides input from SNL to a L2 milestone at LBNL entitled "Status of UFD Campaign International Activities in Disposal Research." | 2016-08-12 02:00 |  | 2016-08-22 02:00 |  | 2016 | Completed Late | Report on the Status of the UFD Campaign International Activities in Disposal Research at SNL |  |  | None | M4FT-16SN080305022 SNL International FY16 FINAL.docx | FCRD-UFD-2016-000619
M4FT-16LA080302021 | M4 | 1.02.08.03.02.02 | LANL | FT-16LA08030202 | DR Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite EBS experimental report LANL | Argillite EBS experimental report LANL | This is the deliverable date (8/12/16) for the milestone | 2016-08-12 04:00 |  | 2016-08-02 02:00 |  | 2016 | Complete | Experimental studies of Engineered Barrier Systems conducted at Los Alamos National Laboratory (FY16) | Caporuscio, Florie | Caporuscio, Florie | None | 2016 EBS-LANL -Report-FINAL.pdf | FCRD-UFD-2016-000620
M4FT-16LL080302052 | M4 | 1.02.08.03.02.05 | LLNL | FT-16LL08030205 | DR Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Update to Thermodynamic Database Development and Sorption Database Integration | Update to Thermodynamic Database Development and Sorption Database Integration | A summary of surface complexation database development approaches will be prepared, along with the thermodynamic database development manuscript, as a level 4 milestone. | 2016-08-12 08:00 |  | 2016-09-08 03:00 | This deliverable summarizes LLNL's efforts on thermodynamic database improvements, surface complexation database developments, and international engagement with the NEA. Some of this effort was supported by the International work package funding. Each of these three efforts will continue into FY17; there are multiple manuscripts that are in various stages of preparation, submittal, and revision that pave the way for maintaining NE's capability in thermodynamic modeling of repository systems. | 2016 | Completed Late | M4FT-16LL080302052-Update to Thermodynamic Database Development and Sorption Database Integration | Zavarin, Mavrik | Zavarin, Mavrik | None | M4FT-16LL080302052_final.pdf | FCRD-UFD-2016-000622
M4FT-16LA080308027 | M4 | 1.02.08.03.08.02 | LANL | FT-16LA08030802 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Instrumentation Requirements for Stress Characterization using Geophysical Measurements | Instrumentation Requirements for Stress Characterization | Report documenting the data requirements to perform a joint inversion to create a self-consistent density and velocity model to calculate the stress field due to body forces within the volume of the DBFT | 2016-08-12 08:00 |  | 2016-08-11 02:00 |  | 2016 | Complete | Monitoring Stress Conditions in a Deep Borehole Repository | Delorey, Andrew | Delorey, Andrew | None | LANL_Delorey_M4_Stress_DBH_August.2106.pdf | FCRD-UFD-2016-000621 | Deep borehole, stress modeling
M4FT-16LA080308021 | M4 | 1.02.08.03.08.02 | LANL | FT-16LA08030802 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Geologic Site Model for Deep Borehole Field Test | Geologic Site Model for the Deep Borehole Field Test | Documentation of 3D geologic site model for the DBFT site | 2016-08-12 12:00 |  | 2016-08-04 02:00 |  | 2016 | Complete | Geologic Site Model for the Deep Borehole Field Test-Capability Development | Perry, Frank | Perry, Frank | None | DBH_M4_LANL_Geologic_Framework_Model_Perry_August_2016.pdf | FCRD-UFD-2016-000623 | deep borehole, geologic framework model
M3FT-16LB080302032 | M3 | 1.02.08.03.02.03 | LBNL | FT-16LB08030203 | DR Argillite Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | This milestone will feed into SNL milestone due 9/4/2016. Title: Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks Site: SNL, Level: M2, QA Rigor: QRL3, Estimated Completion Date: 9/15/2016 Title: Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | 2016-08-12 15:00 |  | 2016-08-12 03:00 |  | 2016 | Complete | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock | LBNL | Zheng, Liange | None | M3FT-16LB080302032_LBNL.pdf | FCRD-UFD-2016-000437 | Argillite, bentonite, clay, THMC modeling, THM modeling, fracture damage modeling, heater test modeling, coupled processes
M4FT-16PN080308051 ULR. never finished the R&A and publication of this PNNL report | M4 | 1.02.08.03.08.05 | PNNL | FT-16PN08030805 | Deep Borehole Field Test - PNNL | Hanson, Brady | Mackinnon, Robert | Detailed Test Planning, DBFT Characterization Borehole | Detailed Test Planning, DBFT Characterization Borehole | Provide detailed technical information for implementing assigned downhole investigations. | 2016-08-15 08:00 | 2016-09-02 03:00 | 2016-09-02 03:00 | FY16 summary of Deep Borehole Field Test Support activities. | 2016 | Completed Late | DBH Support to Sandia National Laboratories - Deep Borehole Field Test Support Summary of Support Activities for FY16. | Spane, Frank | Hanson, Brady | None | Milestone M4FT-16PN080308051.pdf | FCRD-UFD-2016-000624 | Deep borehole field test
M3FT-16LB080308032 | M3 | 1.02.08.03.08.03 | LBNL | FT-16LB08030803 | Deep Borehole Field Test - LBNL | Birkholzer, Jens | Mackinnon, Robert | Deep Borehole Field Test Research Activities at LBNL | Deep Borehole Field Test Research Activities at LBNL | This milestone is due 09/26/2016 | 2016-08-19 03:00 |  | 2016-08-19 03:00 |  | 2016 | Complete | Deep Borehole Field Test Research Activities at LBNL | Dobson, Patrick | Lawrence Berkeley National Laboratory | None | M3FT-16LB080308032_FINAL.pdf | FCRD-UFD-2016-000438 | deep borehole, characterization, monitoring,field experiments, modeling
M4FT-16LL080303052 | M4 | 1.02.08.03.03.05 | LLNL | FT-16LL08030305 | DR Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | State of Knowledge for Colloid Facilitated Radionuclide Transport and Update on Actinide Diffusion in Bentonite Backfill | State of Knowledge for Colloid Facilitated Radionuclide Transport and Update on Actinide Diffusion in Bentonite Backfill | Two manuscripts, along with a summary of Np(IV) diffusion in bentonite backfill will be summarized in a level 4 milestone. | 2016-08-19 13:00 |  | 2016-09-08 03:00 | This milestone summarizes LLNL's efforts in radionuclide diffusion and colloid facilitated transport experimental and modeling efforts. Much of the colloid facilitated transport is captured in greater detail in the M3 report that LLNL and LANL authored and LANL submitted earlier. Our Np(IV) diffusion experiments will be completed in the first half of FY17. These data will be provided to GDSA model. These data, along with our other U(VI) diffusion effort (and those available in the literature) can be used to account for radionuclide diffusion into bentonite backfill. | 2016 | Completed Late | M4FT-16LL080303052-State of Knowledge for Colloid Facilitated Radionuclide Transport and Update on Actinide Diffusion in Bentonite Backfill | Zavarin, Mavrik | Zavarin, Mavrik | None | M4FT-16LL080303052_final.pdf | FCRD-UFD-2016-000625
M4FT-16LA080303021 | M4 | 1.02.08.03.03.02 | LANL | FT-16LA08030302 | DR Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | M4FT-16LA030302-Modeling and experimental activities for crystalline rock disposal | Crystalline and Crystalline International Disposal Activities | Level 4 milestone to support Sandia's Level 2 for Crystalline Rock activities. This will include simulation, experiment and support of performance assessment and international activities | 2016-08-22 04:00 |  | 2016-08-18 02:00 |  | 2016 | Complete | Crystalline and Crystalline International Disposal Activities | Viswanathan, Hari | Viswanathan, Hari | None | Viswanathan_Crystaline_M4FT_16LA080303.pdf | FCRD-UFD-2016-000626 | discrete fracture network, colloids
M4FT-16LB080303042 | M4 | 1.02.08.03.03.04 | LBNL | FT-16LB08030304 | DR Crystalline Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | Laboratory Experiments on Bentonite Samples: FY16 Progress | Laboratory Experiments on Bentonite Samples: FY15 Progress | Laboratory Experiments on Bentonite Samples: FY14 Progress, Level 3, Due Date: August 22, 2016 | 2016-08-22 17:00 |  | 2016-08-22 03:00 |  | 2016 | Complete | Milestone Report | Tinnacher, Ruth | Zheng, Liange | None | M4FT-16LB080303042_FINAL.pdf | FCRD-UFD-2016-000627 | uranium, diffusion, adsorption, sorption, surface complexation model, transport, modeling, experiments, radionuclide
M4FT-16SN080302081 feed to LBNL MS: M2FT-16LB0305013 | M4 | 1.02.08.03.02.08 | SNL | FT-16SN08030208 | DR Argillite International Collaborations - SNL | Jove-Colon, Carlos | McMahon, Kevin | International Collaboration Activities on Engineered Barrier Systems | International Collaboration Activities on Engineered Barrier Systems | Level 4 milestone describing R&D activities related to international collaborations on Engineered Barrier Systems. This report is planned as a feed to LBNL MS: M2FT-16LB0305013-International Collaboration Activities in Different Geologic Disposal Environments (due 9-23-2016). | 2016-08-23 10:00 |  | 42613.0833 |  | 2016 | Completed Late | International Collaboration Activities on Engineered Barrier Systems | Jove Colon, Carlos | Jove Colon, Carlos | None | M4FT-16SN080302081 M4 FINAL DRAFT CFJC.pdf | FCRD-UFD-2016-000628
M4FT-16SN080303091 | M4 | 1.02.08.03.03.09 | SNL | FT-16SN08030309 | DR Crystalline International Collaborations - SNL | Wang, Yifeng | McMahon, Kevin | International collaboration on the development of site and material characterization techniques | International collaboration on the development of site characterization and material characterization techniques | This milestone report will document the work done under international collaborations with KAERI and through DECOVALEX project on the development of site and material characterization techniques. | 2016-08-26 12:00 |  | 2016-08-26 06:00 |  | 2016 | Complete | International Collaboration on Used Fuel Disposition in Crystalline Rocks: FY16 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M4FT-16SN080303091.pdf | FCRD-UFD-2016-000629
M3FT-16LA080504031 | M3 | 1.02.08.05.04.03 | LANL | FT-16LA08050403 | FEPS analysis - LANL | Reimus, Paul | Mackinnon, Robert | Colloid Formation and Colloid-Facilitated Radionuclide Transport Synthesis Report | Colloid Formation and Colloid-Facilitated Radionuclide Transport Synthesis Report | Level 3 milestone report on colloid formation and colloid-facilitated radionuclide transport as it relates to geologic disposal of spent fuel and high-level nuclear waste. | 2016-08-31 12:00 |  | 2016-08-30 02:00 |  | 2016 | Complete | Colloid-Facilitated Radionuclide Transport: Current State of Knowledge from a Nuclear Waste Repository Risk Assessment Perspective | Reimus, Paul | Reimus, Paul | None | M3FT_16LA080504031.pdf | FCRD-UFD-2016-000446 | Radionuclide Transport, Colloid Transport
M2FT-16SN080308071 | M2 | 1.02.08.03.08.07 | SNL | FT-16SN08030807 | Site Characterization - SNL | Kuhlman, Kris | Mackinnon, Robert | Deep Borehole Field Test Laboratory and Borehole Testing Strategy | Deep Borehole Field Test Laboratory and Borehole Testing Strategy | This report will describe the test plans for the characterization borehole and laboratory tests, and the analyses, models, and processes used to support development of the test plans. | 2016-08-31 12:00 |  | 2016-08-25 02:00 |  | 2016 | Complete | Deep Borehole Field Test Laboratory and Borehole Testing Strategy | Kuhlman, Kris | Kuhlman, Kris | None | deep-borehole-field-test-laboratory-testing-strategy-M2-FINAL.pdf | FCRD-UFD-2016-000072 | deep borehole; deep borehole field test; characterization; geophysics; in situ testing
M2FT-16SN080302071 | M2 | 1.02.08.03.02.07 | SNL | FT-16SN08030207 | DR Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Clay-Bearing Rocks | Evaluation of Used Nuclear Fuel Disposition in Clay-Bearing Rocks | EOFY 16 update. | 2016-09-15 08:00 |  | 42628.0833 | Milestone deliverable describes R&D work for the disposal in argillite work package. | 2016 | Complete | Evaluation of Used Fuel Disposition in Clay-Bearing Rock | Jove Colon, Carlos | Jove Colon, Carlos | None |  | FCRD-UFD-2016-000074 | Argillite, Nuclear Waste, THMC, Reactive Transport, Bentonite
M4FT-16LA080504081 | M4 | 1.02.08.05.04.08 | LANL | FT-16LA08050408 | Preliminary regional geology evaluation - LANL | Perry, Frank | MacKinnon, Robert | Preliminary regional site evalutions for disposal of DOE-managed HLW and SNF | Preliminary regional site evalutions for disposal of DOE-managed HLW and SNF | Report that documents regional geologic evaluations for technical site selection options for disposal of DOE-managed HLW and SNF | 2016-09-16 02:00 | 2016-10-12 04:00 | 2016-10-12 02:00 | Expected finish on 10/12/16 or several days after 10/12/16. | 2016 | Expected Late | Preliminary Regional Geologic Evaluations for Disposal of DOE-Managed HLW and SNF: Archean Crystalline Rocks of the North-Central United States | Perry, Frank | Perry, Frank | None | Regional Evalution DWR Perry LANL M4FT-16LA080504081 OCT 2106 R2.pdf | FCRD-UFD-2016-000634 | regional geologic evaluation crystalline rocks
M2FT-16SN080308093 | M2 | 1.02.08.03.08.09 | SNL | FT-16SN08030809 | Project Integration and Concept Evaluation - SNL | Freeze, Geoff | Mackinnon, Robert | Deep Borehole Disposal Safety Analysis | Deep Borehole Disposal Safety Analysis | This report will describe safety analyses performed to assess potential pre-closure emplacement hazards and post-closure performance of a deep borehole disposal system using field test design information and generic and site-specific characterization data. | 2016-09-16 12:00 |  | 2016-09-16 02:00 | Report completed and submitted to DOE | 2016 | Complete | Deep Borehole Disposal Safety Analysis | Freeze, Geoff | Freeze, Geoff | None |  | FCRD-UFD-2016-000075 | deep borehole disposal
M4FT-16SN080503032 Same as MFT-15SN0826011 | M4 | 1.02.08.05.03.03 | SNL | FT-16SN08050303 | Develop and implement operating procedures - SNL | Appel, Gordon | McMahon, Kevin | Identify and summarize operating procedures | DOE Managed HLW and SNF Research: Generic operating procedures | Develop Generic List of and Description of operating procedures for DOE Managed HLW and SNF disposal | 2016-09-16 18:00 |  | 42628.3333 | Report completed as scheduled | 2016 | Complete | DRAFT Operating Procedures for a Generic Repository Licensing Organization | Appel, Gordon | Appel, Gordon | None | 20160914_First Page of Procedures Report FY16_Final_with Appendix E.pdf | FCRD-UFD-2016-000638
M2FT-16SN080503021 | M2 | 1.02.08.05.03.02 | SNL | FT-16SN08050302 | Establish organizational framework to meet regulator expectations - SNL | Appel, Gordon | McMahon, Kevin | Generic Organizational and Procedural Framework for DOE Managed HLW and SNF Licensing | Generic Organizational and Procedural Framework for DOE Managed HLW and SNF Licensing | Generic Organizational and Procedural Framework for DOE Managed HLW and SNF Licensing | 2016-09-16 20:00 |  | 2016-09-15 06:00 | Report completed on schedule | 2016 | Complete | Draft Infrastructure Framework for a Generic Repository Development Organization | Appel, Gordon | Appel, Gordon | None | 20160914_Title Page Infrastructure UFD FY16_Final_with Appendix E.pdf | FCRD-UFD-2016-000079 | Infrastructure
M3FT-16LB080309022 | M3 | 1.02.08.03.09.02 | LBNL | FT-16LB08030902 | DR Salt R&D - LBNL | Birkholzer, Jens | MacKinnon, Robert | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | LBNL will continue to test and apply computational models and tools to simulate coupled THM processes and brine migration in salt. LBNL’s modeling work will be based on the extended TOUGH-FLAC model, which incorporated new constitutive models for the damage evolution of salt and also new capabilities for simulating large deformations. LBNL will also explore the possibility of extending the TOUGH-FLAC model to THMC. Specifically, to further test and apply TOUGH-FLAC for modeling salt coupled processes, LBNL may model a heater test conducted in rooms A&B at WIPP in the 1980s, to evaluate the capabilities of TOUGH-EWASG (and TOUGH-FLAC) to model brine migration in natural salt in field conditions; Revisit the Generic Salt Repository in 2D and perform THM modeling using crushed salt and natural salt parameters derived from the modeling of the TSDE test, including halite dissolution/precipitation effects; Compare simulation results using sequential and fully coupled approaches (TOUGH-FLAC and CODE_BRIGHT) to investigate the differences in terms of physical processes modeled as well as in terms of numerical efficiency; Continue fruitful collaboration with TU Clausthal and Prof. Lux's team, and perform further benchmark exercises regarding the disposal of heat-generating nuclear waste in saliferous formations (natural salt host rock and crushed salt backfill). Improved constitutive models for brine migration will be implemented into coupled flow and geomechanical simulators. To inform the derivation of these constitutive relationships, which are applicable at the Darcy (or continuum scale), LBNL will continue development and application of pore scale (or micro-) modeling of heat-drvien transport of brine inclusions. These model applications will allow quantifying rates of migration of individual brine inclusions in salt grains subject to temperature gradients, and will explore the effect of physical and mineralogical heterogeneity in salt grains on the rates of migration. | 2016-09-19 09:00 |  | 2016-09-19 03:00 | Milestone report delivered on due date | 2016 | Complete | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures | Rutqvist, Jonny | Birkholzer, Jens | None | Modeling Coupled THM Processes and Brine Migration in Salt at High Temperatures_v4 MASTER.pdf | FCRD-UFD-2016-000439 | salt, nuclear waste, modeling, coupled processes
M2FT-16SN080303082 | M2 | 1.02.08.03.03.08 | SNL | FT-16SN08030308 | DR Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | This activity will focus on two key technical areas: (1) better characterization and understanding of fractured media and fluid flow and transport in such media, and (2) designing effective engineered barrier systems (EBS) for waste isolation. | 2016-09-21 10:00 |  | 42634.0833 | Annual progress report on used fuel disposition in crystalline rocks R&D | 2016 | Complete | Used Fuel Disposition in Crystalline Rocks: FY16 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M2FT-16SN080303082.pdf | FCRD-UFD-2016-000076
M3FT-16SN080304011 | M3 | 1.02.08.03.04.01 | SNL | FT-16SN08030401 | DR Generic Disposal System Analysis - SNL | Mariner, Paul | Mackinnon, Robert | Advances in Geologic Disposal System Modeling and Application to Crystalline Rock | Generic Disposal System Model Development and Reference Case Applications | This report will describe the development of the disposal system modeling and analysis capability that supports the prioritization of Disposal Research (DR) R&D and the evaluation of disposal system performance, including uncertainty, for a range of disposal option reference cases (e.g., salt, argillite, crystalline, deep borehole). The report will also describe implementation of updated conceptual models of subsystem processes and couplings developed under this and other DR work packages and the approach used to evaluate and integrate DR R&D priorities. | 2016-09-22 16:00 |  | 42635.1667 | M3 technical review complete. | 2016 | Complete | Advances in Geologic Disposal System Modeling and Application to Crystalline Rock |  |  | None | FCRD-UFD-2016-000440_GDSA_Final_r00.pdf | FCRD-UFD-2016-000440 | GDSA; PFLOTRAN; crystalline; performance assessment
M3FT-16SN080302072 | M3 | 1.02.08.03.02.07 | SNL | FT-16SN08030207 | DR Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Argillite and Crystalline Disposal Research Accomplishments Summary and Path Forward | Argillite and Crystalline Disposal Research Accomplishments Summary and Path Forward | Provide a path-forward for two host-rock media-specific disposal research work packages within the Used Fuel Disposition Campaign, argillite and crystalline disposal R&D. These two work packages cover fundamental technical issues that have multiple implications to other disposal research work packages. | 2016-09-23 02:00 |  | 42636.0833 | Milestone deliverable report summary of accomplishments on Argillite and Crystalline Disposal R&D activities. | 2016 | Complete | ARGILLITE AND CRYSTALLINE DISPOSAL RESEARCH: ACCOMPLISHMENTS AND PATH-FORWARD | Jove Colon, Carlos | Jove Colon, Carlos | None | Argillite-Crystalline RD FY16 M3 DRAFT FINAL.pdf | FCRD-UFD-2016-000720 | Argillite, Crystalline, Nuclear Waste, Host Rock, Disposal Research
M2FT-16SN080501042 | M2 | 1.02.08.05.01.04 | SNL | FT-16SN08050104 | Complete and populate online waste library (OWL) - SNL | Sassani, David | McMahon, Kevin | The On-line Waste Library (OWL): Usage and Status Report | The On-line Waste Library (OWL): Usage and Status Report | This Usage and Status Report will describe the content and utility of On-line Waste Library (OWL), as well as how to access the system and the status on full implementation. | 2016-09-23 12:00 |  | 42636.0833 | Completed deliverable M2FT-16SN080501042. This report provides a status of the work to assess the information needs for evaluating the safety of defense waste repository considering both the waste forms to be disposed and the repository concepts being considered, This includes the FY16 progress toward: (1) developing a preliminary DRep inventory for engineering/design analyses; (2) assessing the major differences of this inventory relative to that in other analyzed repository systems and the potential impacts to disposal concepts considered; (3) designing and developing an on-line waste library (OWL) to manage the information of the superset of wastes and their waste forms (i.e., SNL, 2014, including CSNF if desired eventually); and (4) constraining post-closure waste form degradation performance for safety assessments. | 2016 | Complete | The On-line Waste Library (OWL): Usage and Inventory Status Report | Sassani, David | Sassani, David | None | M2FT-16SN080501042 DRep OWL M2 UFD Report final.pdf | FCRD-UFD-2016-000080 | defense repository OWL waste form inventory performance
M4FT-16LB080305014 | M4 | 1.02.08.03.05.01 | LBNL | FT-16LB08030501 | DR International Disposal R&D - LBNL | Birkholzer, Jens | McMahon, Kevin | Update on Fifth Worldwide Review | Continue activities to publish a fifth edition of the “Worldwide Review” series | Update on Fifth Worldwide Review, Level 4, Due Date: September 23, 2016 | 2016-09-23 18:00 |  | 2016-08-30 03:00 |  | 2016 | Complete | International Approaches for Nuclear Waste Disposal in Geological Formations: Report on Fifth Worldwide Review | Faybishenko, Boris | Birkholzer, Jens | None | M4FT-16LB080305014_FINAL.pdf | FCRD-UFD-2016-000630 | nuclear waste, geological disposal, worldwide review
M2FT-16LB080305013 | M2 | 1.02.08.03.05.01 | LBNL | FT-16LB08030501 | DR International Disposal R&D - LBNL | Birkholzer, Jens | McMahon, Kevin | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments, Level 2, Due Date: September 23, 2016 This activity provides support for the Used Fuel Disposition Campaign Technical Lead for International Activities. The role of the Technical Lead is to: - Integrate and coordinate UFD - supported activities among participating national laboratories and comparable programs outside the US - Serve as the primary point of contact with the Campaign for the DOE/NE-53 Federal Program Manager for International Activities - Work with NE-53 to ensure a consistent and coherent focus to UFD’s international activities. - Primary responsibility for funding of specific international collaborations will remain within the relevant technical work packages. - Advise both the UFD management team and work package managers on international opportunities that complement ongoing R&D within the campaign - Help identify those activities that provide the greatest potential for substantive technical advances - Interact with international organizations and programs to help advance specific collaborations. | 2016-09-23 22:00 |  | 2016-09-23 03:00 | Milestone report delivered on due date | 2016 | Complete | International Collaboration Activities in Different Geologic Disposal Environments | Birkholzer, Jens | Birkholzer, Jens | None | M2FT-16LB080305013_corrected.pdf | FCRD-UFD-2016-000077 | underground research laboratory, disposal research, international
M4FT-16SN0803090321 | M4 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Intermediate Scale Testing Recommendation Report | Intermediate Scale Testing Recommendation Report | Intermediate Scale Testing Recommendation Report | 2016-09-30 04:00 |  | 2016-09-15 02:00 | A summary of recommendations for near-term intermediate-scale testing pertaining to a salt repository is provided in this report. Each proposal was asked to implement a phased progression, initiating with test plan production in fiscal year 2017 and early-stage testing, if possible. Beyond 2017, testing is anticipated to progress to an underground setting and involve intermediate-scale field activities. Each test concept was presented at the June 6th 2016 meeting in Las Vegas NV and a team of DOE-NE, DOE-EM, and National Laboratory staff discussed the merits of each proposal. Discussions among managers and researchers in the weeks following the meeting led to selection of a path forward for phased testing that includes a series of small diameter borehole tests designed to illuminate thermomechanical processes and potential vapor and brine transport. These tests are intended to be implemented at the WIPP facility and involve collaboration between SNL, LANL, and LBNL. This document summarizes the test concepts generated by the teams of researchers and decisions made subsequent to the June 6th meeting. | 2016 | Complete | Intermediate Scale Testing Recommendation Report | Hansen, Francis | Hansen, Francis | None | M4FT-16SN0803090321 Intermediate Scale Testing Recommendation Report SAND2016-9041 R lac.docx | FCRD-UFD-2016-000030 | Intermediate Scale Testing
M3FT-16SN0803090319 | M3 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | FY16 Summary Report: Participation in the Kosina Project | FY16 Summary Report: Participation in the Kosina Project | x | 2016-09-30 10:00 |  | 42636.0833 | Completed by Ed Matteo and Frank Hansen | 2016 | Complete | FY16 Summary Report: Participation in the KOSINA Project |  |  | None | M3FT-16SN0803090317 FY16 Summary Report Participation in the KOSINA Project 092316 lac.docx | FCRD-UFD-2016-000442
M3FT-16SN0803090313 | M3 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | FY 16 Summary Report: Participation in Joint Project III | 16 Summary Report: Participation in Joint Project III | x | 2016-09-30 10:00 |  | 42646.0833 | This document is complete and loaded up on PICS NE, but I think there is a system issue because it is not showing it complete here. | 2016 | 90 Day | Reinvestigation into Closure Predictions of Room D at the Waste Isolation Pilot Plant | Reedlunn, Benjamin | Reedlunn, Benjamin | None |  | FCRD-UFD-2016-000441
M3FT-16SN080309037 Conference Paper Abstract and Presentation | M3 | 1.02.08.03.09.03 | SNL | FT-16SN08030903 | DR Salt R&D - SNL | Leigh, Christi | MacKinnon, Robert | Conference paper: Partitioning of fission products between fluids and minerals in salt systems | Conference paper: Partitioning of fission products between fluids and minerals in salt systems | x | 2016-09-30 12:00 |  | 42614.1667 | Motivations for this Investigation: A number of countries are considering reposing nuclear waste in bedded salt formations. Current geochemical models cannot completely account for element behavior in the event of a repository intrusion by brine solutions. Lack of data for sequestration of common radionuclide elements in salt phases. Wastes commonly contain fission products (e.g., 137Cs, 90Sr and 129I). Should brine solution intrude the repository and mobilize the fission products (FP’s), will the FP’s partition into salt phases? | 2016 | Complete | Partitioning of Fission Products (Cs, Sr and I) into Salt Phases | Icenhower, Jonathan | Icenhower, Jonathan | None | Icenhower_Goldschmidt_2016 (Cs Sr and I).pptx | FCRD-UFD-2016-000443 | 137Cs, 90Sr, 129I
M3FT-16LA080309011 | M3 | 1.02.08.03.09.01 | LANL | FT-16LA08030901 | DR Salt R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Experiments and Modeling in Support of Generic Salt Repository Science | Experiments and Modeling in Support of Generic Salt Repository Science | This milestone will include results from both LANL tasks under Salt R&D. Experiments and Modeling will be closely linked and iterative. A single L3 milestone was suggested by Bob MacKinnon. | 2016-09-30 16:00 |  | 2016-09-28 02:00 | FY16 salt experiments and simulations are described in this milestone. | 2016 | Complete | Experiments and Modeling in Support of Generic Salt Repository Science | LANL | Stauffer, Philip | None | LANL_DOE_milestone_M3FT16LA080309011_FCRD_UFD_2016_000445.pdf | FCRD-UFD-2016-000445
M2FT-16SN080502012 | M2 | 1.02.08.05.02.01 | SNL | FT-16SN08050201 | EBS concepts and thermal analysis - SNL | Matteo, Edward | MacKinnon, Robert | Status of Progress Made Toward Preliminary Design Concepts for the Inventory in Select Media for DOE Managed HLW/SNF | Status of Progress Made Toward Preliminary Design Concepts for the Inventory in Select Media for DOE Managed HLW/SNF | Activity to Support EBS and Thermal Analysis | 2016-09-30 18:00 |  | 2016-09-30 02:00 | M2 Milestone completed. | 2016 | Complete | Status of Progress Made Toward Preliminary Design Concepts for the Inventory in Select Media for DOE Managed HLW/SNF | Matteo, Edward | Matteo, Edward | None | Matteo et al. M2FT-16SN08050201 FCRD-UFD-2016-000081 SAND2016-9823 R.pdf | FCRD-UFD-2016-000081 | engineered barrier system, repository design, thermal analysis
M2FT-16SN080504062 | M2 | 1.02.08.05.04.06 | SNL | FT-16SN08050406 | Total system performance assessment - SNL | Sevougian, David | MacKinnon, Robert | Status of Progress Made Toward Safety Analysis and Technical Site Evaluations for DOE Managed HLW and SNF | Status of Progress Made Toward Safety Analysis and Technical Site Evaluations for DOE Managed HLW and SNF | Level 2 Milestone to report the "Status of Progress Made Toward Safety Analysis and Technical Site Evaluations for DOE Managed HLW and SNF" | 2016-11-03 14:00 |  | 42677.25 | Expect to finish on time. | 2016 | 90 Day | Status of Progress Made Toward Safety Analysis and Technical Site Evaluations for DOE Managed HLW and SNF | Sevougian, S. David | Sevougian, S. David | None | FY16 DWR Safety Analysis - SAND2016-11232R rev1.0.pdf | FCRD-UFD-2016-000082 | defense waste repository; post-closure performance assessment; safety analysis; safety case
M4SF-17SN010303015 | M4 | 1.08.01.03.03.01 | SNL | SF-17SN01030301 | Salt R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Report on Confirmatory Geomechanical Testing of Bedded Salt | Test Results and Comparison of Triaxial Strength Testing of Waste Isolation Pilot Plant Clean Salt | Report on confirmatory geomechanical testing of salt samples from WIPP, for comparison with results provided through US/German collaboration. | 2017-01-16 |  | 2016-12-06 02:00 |  | 2017 | Complete | Test Results and Comparison of Triaxial Strength Testing of Waste Isolation Pilot Plant Clean Salt | Buchholz, Stuart | Frank Hansen | None | SAND2016-12363R_RESPEC_report_TLM-189.pdf | SFWD-SFWST-2017-000101
M2SF-17SN010303011 | M2 | 1.08.01.03.03.01 | SNL | SF-17SN01030301 | Salt R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Proceedings from the 7th US/German Workshop on Salt | Proceedings from the 7th US/German Workshop on Salt | This report will present the collaborative efforts between technical peers in the US, Germany and the Netherlands on topics in salt repository research that were the focus of the 7th US/German Workshop in Washington DC. | 2017-02-14 04:00 |  | 2017-01-17 04:00 |  | 2017 | Complete | Proceedings of the 7th US/German Workshop on Salt Repository Research, Design, and Operation | Hansen, Francis | Kuhlman, Kris | None | Proceedings_of_USGerman_Workshop_PREDICISIONAL_part1.pdf | SFWD-SFWST-2017-000008
M3SF-17AN010301031 | M3 | 1.08.01.03.01.03 | ANL | SF-17AN01030103 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Spent fuel matrix degradation and canister corrosion: quantifying the effect of hydrogen on radionuclide source term. | Spent fuel matrix degradation and canister corrosion: quantifying the effect of hydrogen on radionuclide source term | This report will focus on the quantitative relationship between the fuel degradation rate and steel corrosion. It will present results from a comparison of existing experimental data with steel corrosion rates predicted by the FMDM using an electrochemical approach to calculate the actual corrosion current and passivation potential. The purpose of this report is to prompt and facilitate FY2017 progress on canister corrosion modeling. | 2017-02-28 06:00 |  | 42794.0417 |  | 2017 | Complete | Spent Fuel Matrix Degradation and Canister Corrosion: Quantifying the Effect of Hydrogen | Jerden, James | Jerden, James | None | ANL 2017 February Milestone Report M3SF_17AN010301031 and M3SF_17AN010302031.pdf | SFWD-SFWST-2017-000039
M3SF-17AN010302031 | M3 | 1.08.01.03.02.03 | ANL | SF-17AN01030203 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Spent fuel matrix degradation and canister corrosion: quantifying the effect of hydrogen on radionuclide source term | Spent fuel matrix degradation and canister corrosion: quantifying the effect of hydrogen on radionuclide source term | This report will focus on the quantitative relationship between the fuel degradation rate and steel corrosion. It will present results from a comparison of existing experimental data with steel corrosion rates predicted by the FMDM using an electrochemical approach to calculate the actual corrosion current and passivation potential. The purpose of this report is to prompt and facilitate FY2017 progress on canister corrosion modeling. | 2017-02-28 08:00 |  | 42794.0417 |  | 2017 | Complete | Spent Fuel Matrix Degradation and Canister Corrosion: Quantifying the Effect of Hydrogen | Jerden, James | Jerden, James | None | ANL 2017 February Milestone Report M3SF_17AN010301031 and M3SF_17AN010302031.pdf | SFWD-SFWST-2017-000042
M4SF-17SN010306023 | M4 | 1.08.01.03.06.02 | SNL | SF-17SN01030602 | Field Test Design - SNL | Hardin, Ernest | Mackinnon, Robert | Methodology for radiological risk assessment of deep borehole disposal operations | Methodology for radiological risk assessment of deep borehole disposal operations | • Develop a probabilistic risk assessment methodology, drawing on 10CFR63.112, for integrating information such as event probabilities, and conditional radiological consequences, to produce overall risk metrics and insights that describe system capability. | 2017-03-30 06:00 |  | 42824.0833 |  | 2017 | Complete | Methodology for radiological risk assessment of deep borehole disposal operations | Hardin, Ernest | Ernest Hardin | None | Method report Final 30Mar17.pdf | SFWD-SFWST-2017-000105 | deep borehole disposal; nuclear waste handling; operational safety
M4SF-17SN010303012 | M4 | 1.08.01.03.03.01 | SNL | SF-17SN01030301 | Salt R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Intermediate Scale Salt Field Testing Design | Consensus on Intermediate Scale Salt Field Test Design | Development of a test plan for executing in follow-on years. This milestone will be associated with a mid-year consensus on the design of the field test to be written up by the end of the year. | 2017-03-31 04:00 |  | 2017-03-28 02:00 |  | 2017 | Complete | Consensus on Intermediate Scale Salt Field Test Design | Kuhlman, Kris | Kuhlman, Kris | None | SAND2017-3179R_Consensus_on_Salt_Field_Test_V66_final.pdf | SFWD-SFWST-2017-000099 | Salt R&D; radioactive waste; disposal research; in situ testing; heater test; brine migration; brine chemistry; deuterated water; ERT; acoustic emission
M4SF-17OR010306081 | M4 | 1.08.01.03.06.08 | ORNL | SF-17OR01030608 | Deep Borehole Field Test - ORNL | Howard, Rob | Mackinnon, Robert | Hazard analysis for radiological risk assessment of deep borehole disposal operations | Hazard analysis for radiological risk assessment of deep borehole disposal operations | Develop and document a hazard analysis to identify initiating events, factoring in mechanical failure and human error, consistent with precedents adopted for other nuclear facilities. Define the initiating events or sequences using an accepted approach such as fault tree analysis. (26May17). | 2017-05-26 |  | 2017-05-26 |  | 2017 | Complete | Hazard Analysis for Radiological Risk from Deep Borehole Disposal Operations | Peretz, Fred | Peretz, Fred | None | SFWD-SFWST-2017-000109 Hazard Analysis.pdf | SFWD-SFWST-2017-000109 | Deep Borehole Field Test
M4SF-17OR010305022 OUO John Scaglione has password for password-protected file. | M4 | 1.08.01.03.05.02 | ORNL | SF-17OR01030502 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Initial development of a misload analysis methodology | Status report on development of As-loaded canister misload analysis methodology | Initial development of a misload analysis methodology to support as-loaded criticality analysis | 2017-05-31 |  | 42886 |  | 2017 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Liljenfeldt, Henrik | Scaglione, John | OUO |  | SFWD-SFWST-2017-000104
M4SF-17IN010306061 | M4 | 1.08.01.03.06.06 | INL | SF-17IN01030606 | Regional Geology Web Map Application Development - INL | Russell, Glenn | MacKinnon, Robert | Interactive web-based tool for displaying geologic data Version 2 | DBFT-Regional Geology Web Map | Develop and publish updated version 2.0 of web-based tool for geologic data. | 2017-05-31 08:00 | 2017-06-30 02:00 | 2017-06-27 02:00 |  | 2017 | Completed Late | Regional Geology Web Map Application Development: Javascript v2.0 Mid-FY2017 M4 Milestone Report | Russell, Glenn | Russell, Glenn | None | FCRD-UFD-20170619.pdf | SFWD-SFWST-2017-000106 | Regional Geology, Web Map Application, SFWST, UFD, INL, LANL
M3SF-17LB010301051 M3SF-17LB010301061 file name shows as M3SF-17LB010301051. | M3 | 1.08.01.03.01.05 | LBNL | SF-17LB01030105 | Argillite Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | High temperature studies on bentonites and clays | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock:FY17 progress | this activity includes using coupled THMC model to study the alteration of bentonite and clay rock under high temperature and several experiments in the underground laboratories and modeling studies in the argillite international package | 2017-06-23 18:00 |  | 42909.125 |  | 2017 | Complete | Investigation of Coupled Processes and Impact of High Temperature Limits in Argillite Rock: FY17 Progress | LBNL | Zheng, Liange | None | M3SF-17LB010301051.pdf | SFWD-SFWST-2017-000040 | Argillite, bentonite, clay, THMC modeling, THM modeling, fracture damage modeling, heater test modeling, coupled processes
M4SF-17PN010501041 | M4 | 1.08.01.05.01.04 | PNNL | SF-17PN01050104 | Characterize Alternative Wasteforms Long-Term Performance - PNNL | Buck, Edgar | McMahon, Kevin | Report on Radiolysis Modeling for the Defense Repository | Report on Radiolysis Modeling for the Defense Repository | Report on modeling activities to feed into other reports | 2017-07-07 12:00 | 2017-07-28 03:00 | 2017-07-28 03:00 |  | 2017 | Completed Late | Effect of Iodide on Radiolytic Hydrogen Peroxide Generation | Buck, Edgar | Buck, Edgar | None | FY2017-UFD-Report_Buck.docx | SFWD-SFWST-2017-000115 | Radiolysis Model, hydrogen peroxide, radiolytic effects on metallic & ceramic waste forms
M4SF-17LB010303031 | M4 | 1.08.01.03.03.03 | LBNL | SF-17LB01030303 | Salt R&D - LBNL | Rutqvist, Jonny | MacKinnon, Robert | Coupled THM modeling in support phased salt field test plan | Coupled THM modeling in support of phased field test plan | To provide pretest modeling support for the design of a planned intermediated field test | 2017-07-07 15:00 |  | 2017-07-07 06:00 |  | 2017 | Complete | Coupled THM Modeling In Support of a Phased Salt Field Test Plan | Rutqvist, Jonny | LBNL | None | M4SF-17LB010303031.pdf | SFWD-SFWST-2017-000103 | Salt, Coupled Processes, Modeling, thermal, brine, migration, field test, WIPP, TOUGH-FLAC, Creep, Permeability, THM
M4SF-17AN010301032 | M4 | 1.08.01.03.01.03 | ANL | SF-17AN01030103 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Progress report on development of the spent fuel degradation and waste package degradation models and integration with PA | Progress report on development of the spent fuel degradation and waste package degradation models and integration with PA | Progress report on development of the spent fuel degradation and waste package degradation models and integration with PA. | 2017-07-24 05:00 |  | 2017-08-14 01:00 |  | 2017 | Completed Late | Progress Report on Development of the Spent Fuel Degradation and Waste Package Degradation Models and Model Integration | Jerden, James | Jerden, James | None |  | SFWD-SFWST-2017-000091 | spent fuel, radionuclide source term
M4SF-17AN010302032 | M4 | 1.08.01.03.02.03 | ANL | SF-17AN01030203 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | Progress report on development of the used fuel degradation and waste package degradation models and integration with PA | 2017-07-24 05:00 |  | 2017-08-14 01:00 |  | 2017 | Completed Late | Progress Report on Development of the Spent Fuel Degradation and Waste Package Degradation Models and Model Integration | Jerden, James | Jerden, James | None |  | SFWD-SFWST-2017-000095 | spent fuel, radionuclide source term
M4SF-17LA010306071 | M4 | 1.08.01.03.06.07 | LANL | SF-17LA01030607 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Geologic Framework Model for the Deep Borehole Field Test | Geologic Frameowrk Model for the Deep Borehole Field Teste | Report documenting progress on creating a geologic framework model for the deep borehole field test | 2017-07-28 04:00 |  | 2017-07-20 02:00 |  | 2017 | Complete | Data to Support Development of Geologic Framework Models for the Deep Borehole Field Test | Perry, Frank | Perry, Frank | None | LANL_Deep_Borehole_M4SF-17LA010306071.pdf | SFWD-SFWST-2017-000107 | Deep Borehole Geologic Framework Model Data
M4SF-17LA010301041 | M4 | 1.08.01.03.01.04 | LANL | SF-17LA01030104 | Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite Disposal R&D - LANL | Argillite Disposal R&D - LANL | perform hydrothermal experiments with focus on corrosion processes | 2017-08-09 12:00 |  | 2017-08-07 02:00 |  | 2017 | Complete | Argillite Disposal R&D at Los Alamos National Laboratory (FY17) | Caporuscio, Florie | Caporuscio, Florie | None |  | SFWD-SFWST-2017-000092
M3SF-17SN010501022 Draft document of M2 | M3 | 1.08.01.05.01.02 | SNL | SF-17SN01050102 | Characterize Alternative Wasteforms Long-Term Performance - SNL | Sassani, David | McMahon, Kevin | Update to Waste Form Performance Constraints | Update to Waste Form Performance Constraints | Report covering constraints on expected degradation behavior for the suite of waste forms identified for deep geologic disposal and discussion of conditions (including radiolysis processes) that are major variables for waste forms performance variation. | 2017-08-11 06:00 |  | 42957.0833 |  | 2017 | Complete | Update to Waste Form Performance Constraints and OWL Status and Inventory Content | Sassani, David | Sassani, David | None | SFWD-SFWST-2017-000047 M3 final SAND_8621 R.pdf | SFWD-SFWST-2017-000047 | update status OWL inventory waste form characteristics
M4SF-17SR010501031 | M4 | 1.08.01.05.01.03 | SRNL | SF-17SR01050103 | Complete and Populate Online Waste Library (OWL) - SRNL | Carter, Joe | McMahon, Kevin | DOE Managed Waste Inventory Report | DOE Managed Waste Inventory Report Rev 1 | SRNL will support SNL development of the OWL, continue to track potential changes and update to the DOE managed waste inventory and linking with the DOE-SNF revised database when available. | 2017-08-15 |  | 2017-08-15 |  | 2017 | Complete | DOE Managed Waste Inventory Report | Carter, Joe | Carter, Joe | None | DOE Managed Waste Inventory Report - Calculation Overview.pdf | SFWD-SFWST-2017-000114 | Managed Waste Inventory
M4SF-17LL010301071 | M4 | 1.08.01.03.01.07 | LLNL | SF-17LL01030107 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Thermodynamic Database Development | Thermodynamic Database Development | Milestone summarizing efforts to develop thernodynamic databases in support of repository modeling efforts | 2017-08-15 | 2017-10-09 03:00 | 2017-10-10 03:00 | task completed | 2017 | Late | M4SF-17LL010301071: Thermodynamic Database Development | Zavarin, Mavrik | Zavarin, Mavrik | None | M4SF-17LL010301071 rev1 final.pdf | SFWD-SFWST-2017-000093 | thermodynamics, database
M4SF-17LB010302061 | M4 | 1.08.01.03.02.06 | LBNL | SF-17LB01030206 | Crystalline Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | Laboratory Experiments on Bentonite Samples: FY17 Progress | Laboratory Experiments on Bentonite Samples: FY17 Progress | In Crystalline package, we will continue the laboratory experiment to study the diffusion and adsorption in bentonite | 2017-08-18 15:00 |  | 2017-08-18 03:00 |  | 2017 | Complete | Laboratory Experiments on Bentonite Samples: FY17 Progress | Fox, Patricia | Zheng, Liange | None | M4SF-17LB010302061.pdf | SFWD-SFWST-2017-000097 | uranium, adsorption, sorption, experiments, radionuclide, bentonite, heating, FEBE
M4SF-17LA010302041 | M4 | 1.08.01.03.02.04 | LANL | SF-17LA01030204 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Modeling and experimental activities for crystalline rock disposal | Crystalline and Crystalline International Disposal Activities | Level 4 milestone to support Sandia' level 2 for crystalline rock activities. This will include simulation, experiment and support of performance assessment and international activities. | 2017-08-22 06:00 |  | 2017-08-17 02:00 |  | 2017 | Complete | Crystalline and Crystalline International Disposal Activities | Viswanathan, Hari | Viswanathan, Hari | None | FY17_draft_SFWD_final.pdf | SFWD-SFWST-2017-000096 | discrete fracture network, colloids, crystalline rock
M4SF-17LA010306073 | M4 | 1.08.01.03.06.07 | LANL | SF-17LA01030607 | Deep Borehole Field Test - LANL | Perry, Frank | Mackinnon, Robert | Hydrothermal Experiments on DBFT Seal Materials | Hydrothermal Experiments on DBFT Seal Materials | Report of results of hydrothermal experiments on DBFT seal materials | 2017-08-25 02:00 |  | 2017-08-22 02:00 |  | 2017 | Complete | Deep Boreholes Seals Subjected to High P, T conditions – Preliminary Experimental Studies | Caporuscio, Florie | Caporuscio, Florie | None | Deep Borehole Experiments 2017-Caporuscio.pdf | SFWD-SFWST-2017-000108 | borehole, clays seals, experiments
M4SF-17SN010307022 | M4 | 1.08.01.03.07.02 | SNL | SF-17SN01030702 | International Disposal Research Coordination - SNL | McMahon, Kevin | McMahon, Kevin | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | SFWST Campaign International Activities in Disposal Research at SNL | 2017-08-25 04:00 |  | 42969.0833 |  | 2017 | Complete | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | McMahon, Kevin | McMahon, Kevin | None | M4SF-17SN010307022 SNL International FY17 SAND2017-9048 R.docx | SFWD-SFWST-2017-000111
M3SF-17LB010306053 | M3 | 1.08.01.03.06.05 | LBNL | SF-17LB01030605 | Deep Borehole Field Test - LBNL | Dobson, Patrick | Mackinnon, Robert | Deep borehole field test research activities at LBNL | Deep borehole field test research activities at LBNL | Summary report of FY17 deep borehole field test activities at LBNL | 2017-08-26 15:00 |  | 42972.125 |  | 2017 | Complete | Deep Borehole Field Test Research Activities at LBNL 2017 | Dobson, Patrick | LBNL | None | M3SF-17LB010306053.pdf | SFWD-SFWST-2017-000046 | deep borehole, characterization, monitoring, laboratory experiments, modeling, Swedish borehole analog study, seal
M4SF-17SN010302021 | M4 | 1.08.01.03.02.02 | SNL | SF-17SN01030202 | Crystalline International Collaborations - SNL | Wang, Yifeng | McMahon, Kevin | International collaboration on spent fuel disposition in crystalline rocks: FY17 progress report | International collaboration on spent fuel disposition in crystalline rocks: FY17 progress report | The report will document the work on international collaboration through DECOVALEX and with KAERI. | 2017-08-28 12:00 |  | 2017-08-28 02:00 |  | 2017 | Complete | International Collaboration on Spent Fuel Disposition in Crystalline Media: FY17 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M4SF-17SN010302021 reportA.pdf | SFWD-SFWST-2017-000094 | DECOVALEX, gas migration, fluid inclusion, fractured medium
M4SF-17LA010504031 | M4 | 1.08.01.05.04.03 | LANL | SF-17LA01050403 | FEPS Analysis - LANL | Reimus, Paul | Mackinnon, Robert | Mathematical Basis and Test Cases for Colloid-Facilitated Radionuclide Transport Modeling in GDSA-PFLOTRAN | Mathematical Basis and Test Cases for Colloid-Facilitated Radionuclide Transport Modeling in GDSA-PFLOTRAN | M4 Milestone Report | 2017-08-31 06:00 |  | 2017-08-03 02:00 |  | 2017 | Complete | Mathematical Basis and Test Cases for Colloid-Facilitated Radionuclide Transport Modeling in GDSA-PFLOTRAN |  |  | None | M4SF-17LA010504031_Final.docx | SFWD-SFWST-2017-000117
M4SF-17LA010303022 | M4 | 1.08.01.03.03.02 | LANL | SF-17LA01030302 | Salt R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Experiments and Modeling to Support Field Test Design | Experiments and Modeling to Support Field Test Design | This activity includes testing of instruments and equipment expected to be used in FY18 small diameter borehole experiments (Task 1.0). Testing will show expected lifetimes of instruments and equipment and reveal limitations of instruments exposed to the harsh heated salt environment. Testing will be primarily in the laboratory with some in-situ placement to confirm behavior in WIPP. Additionally, existing computational models of THC processes will be used to support the design of in-situ thermal testing and reduction of uncertainties for longer term performance assessment. The modeling will be in accordance with the goals described in the Spent Fuel and Waste Disposition (Formerly UFD) test proposal document (FCRD-UFD-2015-000077, Test Proposal Document for Phased Field Thermal Testing in Salt). In FY17, models will be validated against results obtained from all relevant experimental studies performed in FY12-FY16. Data will be used in an iterative model/data validation strategy with a goal of reducing uncertainty in parameters related to the long term safety basis for spent fuel and waste disposition. | 2017-08-31 08:00 |  | 2017-08-31 02:00 |  | 2017 | Complete | Experiments and Modeling to Support Field Test Design | Stauffer, Philip | Stauffer, Philip | None | 2017_Aug_31_LANL_Salt_Exp_Modeling_Milestone-M4SF-17LA010303022.pdf | SFWD-SFWST-2017-000102 | Simulation, salt repository, HLW, SNF, capillary function
M4SF-17LA010504061 | M4 | 1.08.01.05.04.06 | LANL | SF-17LA01050406 | Preliminary Regional Geology Evaluation - LANL | Perry, Frank | MacKinnon, Robert | Preliminary Regional Geologic Evaluations for Disposal of DOE-Managed HLW and SNF | Preliminary Regional Geologic Evaluations for Disposal of DOE-Managed HLW and SNF | Report documenting a preliminary regional evaluation of the geologic and hydrologic environment in a granite, shale or salt host rock | 2017-09-01 02:00 |  | 2017-08-31 02:00 |  | 2017 | Complete | Regional Geologic Evaluations for Disposal of HLW and SNF: The Pierre Shale of the Northern Great Plains | Perry, Frank | Perry, Frank | None | Pierre Shale Perry LANL M4SF-17LA010504061 Aug 2017.pdf | SFWD-SFWST-2017-000119 | geology, shale, GIS, regional evaluation, Pierre
M4SF-17LL010302072 | M4 | 1.08.01.03.02.07 | LLNL | SF-17LL01030207 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | The Roles of Diffusion and Corrosion in Radionuclide Retardation | The Roles of Diffusion and Corrosion in Radionuclide Retardation | Report summarizing experimental and modeling activities quantifying radionuclide diffusion rates through bentonite and sequestration in corrosion products | 2017-09-01 06:00 |  | 2017-10-10 03:00 | task completed | 2017 | 90 Day | M4SF-17LL010302072: The Roles of Diffusion and Corrosion in Radionuclide Retardation | Zavarin, Mavrik | Zavarin, Mavrik | None | M4SF-17LL010302072 rev1 final.pdf | SFWD-SFWST-2017-000098 | thermodynamics, corrosion, diffusion
M2SF-17SN010306022 unfinished report submitted in FY17 per mgmt direction. The completed report was issued as SAND2019-1827. | M2 | 1.08.01.03.06.02 | SNL | SF-17SN01030602 | Field Test Design - SNL | Hardin, Ernest | Mackinnon, Robert | Preclosure Risk Assessment for Waste Disposal in Crystalline Basement Rock | Preclosure Risk Assessment for Waste Disposal in Crystalline Basement Rock | This report summarizes the preliminary pre-closure Preclosure Risk Assessment for Waste Disposal in Crystalline Basement Rock. | 2017-09-08 06:00 |  | 42978.0833 |  | 2017 | Complete | Preclosure Risk Assessment for Waste Disposal in Crystalline Basement Rock | Hardin, Ernest | Hardin, Ernest | None |  | SFWD-SFWST-2017-000010
M3SF-17OR010305023 | M3 | 1.08.01.03.05.02 | ORNL | SF-17OR01030502 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Update the FY15 summary deliverable on feasibility of direct disposal of commercial SNF in existing DPCs (FCRD-UFD-2015-000129 Rev. 1) to reflect new information | FY17 Summary update on the feasibility of direct disposal of commercial SNF in existing DPCs | Update of the FY15 summary deliverable on feasibility of direct disposal of commercial SNF in existing DPCs (FCRD-UFD-2015-000129 Rev. 1) to reflect new information. | 2017-09-15 |  | 42993 | This report is a revision of the Fiscal Year (FY)-15 summary report on the investigations on technical feasibility of direct disposal of dual-purpose canisters (DPCs) in a geological repository. | 2017 | Complete | Summary of Investigations on Technical Feasibility of Direct Disposal of Dual-Purpose Canisters | Liljenfeldt, Henrik | Scaglione, John | None | direct_disposal_rev2_v8_alb1.pdf | SFWD-SFWST-2017-000045
M2SF-17SN010301011 | M2 | 1.08.01.03.01.01 | SNL | SF-17SN01030101 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | Evaluation of Used Nuclear Fuel Disposition in Clay-bearing Rocks | End of FY17 status update on argillite disposal R&D | 2017-09-15 08:00 |  | 2017-09-15 02:00 | Milestone deliverable M2SF-17SN010301011 (SFWD-SFWST-2017-000006), Evaluation of Used Fuel Disposition in Clay-Bearing Rock. This milestones reports describes key advances in experimental and modeling aspects of chemical and physical phenomena towards the long-term safety assessment of nuclear waste disposition in deep clay/shale/argillaceous rock. | 2017 | Complete | Evaluation of Used Fuel Disposition in Clay-Bearing Rock | Jove Colon, Carlos | Jove Colon, Carlos | None |  | SFWD-SFWST-2017-000006
M4SF-17LA010502041 | M4 | 1.08.01.05.02.04 | LANL | SF-17LA01050204 | Disposal Overpack and Waste Package Options - LANL | Caporuscio, Florie | Mackinnon, Robert | Disposal Overpack and Waste Package Options - LANL | Disposal Overpack and Waste Package Options - LANL | Petrographic and chemical characterization of FEBEX samples | 2017-09-22 04:00 |  | 2017-09-21 02:00 | Document delivered ahead of schedule | 2017 | Complete | Disposal Overpack and Waste Package Options - LANL Petrographic descriptions of FEBEX Section 49 - Dismantlement Phase operation | Caporuscio, Florie | Caporuscio, Florie | None | Disposal Overpack and Waste Package Options- FEBEX Report.pdf | SFWD-SFWST-2017-000116
M2SF-17SN010502011 ULR. FY17 report was for a work package that was terminated early by direction of DOE. Programmatic review and was sent to DOE – but it is an unfinished document that probably shouldn’t leave SNL. | M2 | 1.08.01.05.02.01 | SNL | SF-17SN01050201 | EBS Concepts and Thermal Analysis - SNL | Matteo, Edward | Mackinnon, Robert | Preliminary Design Concepts Status Report | Preliminary Design Concepts Status Report | This report will summarize the progress made on preliminary EBS design concepts for defense waste disposal. | 2017-09-22 04:00 |  | 42978.0833 |  | 2017 | Complete | Preliminary Design Concepts Status Report (DRAFT) | Matteo, Edward | Matteo, Edward | None |  | SFWD-SFWST-2017-000015
M2SF-17SN010302011 | M2 | 1.08.01.03.02.01 | SNL | SF-17SN01030201 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | Evaluation of Used Nuclear Fuel Disposition in Crystalline Rocks | EOFY17 status update for crystalline disposal R&D | 2017-09-22 06:00 |  | 42999.0833 | FY17 progress report on the evaluation of spent fuel disposition in crystalline rocks. | 2017 | Complete | Evaluation of spent fuel disposition incrystalline rocks: FY17 progress report | Wang, Yifeng | Wang, Yifeng | None | M2FT-17SN010302011-9-21-17.pdf | SFWD-SFWST-2017-000007 | crystalline rocks, spent fueld disposition, fractured media
M2SF-17SN010501014 | M2 | 1.08.01.05.01.01 | SNL | SF-17SN01050101 | Complete and Populate Online Waste Library (OWL) - SNL | Sassani, David | McMahon, Kevin | Inventory and Waste Characterization Status Report | Inventory and Waste Characterization Status Report | EOFY17 status update on the DOE Managed HLW & SNF Characterization and Inventory work activities. | 2017-09-22 06:00 |  | 42999.0833 | Report finalized Sept 20 and submitted for milestone completion Sept 21. | 2017 | Complete | Inventory and Waste Characterization Status Report | Sassani, David | Sassani, David | None | M2SF-17SN010501014 SAND-2017-10260 R OWL Inv WF Char.pdf | SFWD-SFWST-2017-000014 | Online waste library inventory waste form characteristics
M3SF-17SN010304011 | M3 | 1.08.01.03.04.01 | SNL | SF-17SN01030401 | Generic Disposal System Analysis - SNL | Mariner, Paul | MacKinnon, Robert | Advances in Geologic Disposal System Modeling and Shale Reference Cases | Advances in Geologic Disposal System Modeling and Shale Reference Cases | This report will describe the development of the disposal system modeling and analysis capability that supports the prioritization of Disposal Research (DR) R&D and the evaluation of disposal system performance, including uncertainty, for two types of shale repository reference cases. The report will also describe implementation of updated conceptual models of subsystem processes and couplings developed under this and other DR work packages and the approach used to evaluate and integrate DR R&D priorities. | 2017-09-22 10:00 |  | 42992.1667 | Technical review completed 9/13/2017. | 2017 | Complete | Advances in Geologic Disposal System Modeling and Shale Reference Cases |  |  | None | SFWD-SFWST-2017-000044.pdf | SFWD-SFWST-2017-000044
M2SF-17SN010503011 DRAFT. Programmatic Review Tracking No: 670971 | M2 | 1.08.01.05.03.01 | SNL | SF-17SN01050301 | Plan Development - SNL (CLOSED) | Appel, Gordon | McMahon, Kevin | Organizational and Procedural Frameworks Status Report | Organizational and Procedural Frameworks Status Report | EOFY 17 status update on Organizational and Procedural Frameworks Development | 2017-09-22 10:00 |  | 42978.0833 |  | 2017 | Complete | FY17 Organizational and Procedural Frameworks Status Report | Appel, Gordon | Appel, Gordon | None |  | SFWD-SFWST-2017-000016
M2SF-17LB010307011 | M2 | 1.08.01.03.07.01 | LBNL | SF-17LB01030701 | International Disposal Research Coordination - LBNL | Birkholzer, Jens | McMahon, Kevin | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | EOFY 17 status update on international collaborations in disposal research. | 2017-09-28 |  | 2017-09-28 03:00 | Milestone report delivered on its due date | 2017 | Complete | International Collaboration Activities in Different Geologic Disposal Environments | Birkholzer, Jens | LBNL | None | M2SF-17LB010307011 V2.pdf | SFWD-SFWST-2017-000013 | underground research laboratory, disposal research, international
M4SF-17SN010303014 | M4 | 1.08.01.03.03.01 | SNL | SF-17SN01030301 | Salt R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Laboratory Testing and Modeling and International Collaboration in Support of a Intermdiate Scale Salt Field Test | Status Report on Laboratory Testing and Benchmark Modeling in Salt | Laboratory tests and numerical modeling in support of developing a test plan and interpreting results from an intermediate scale field test in salt in follow-on years. WEIMOS and KOSINA collaboration projects with German colleagues from the US-German workshop (i.e., geomechanical benchmark modeling and bedded/domal salt comparison) will continue under this. This activity will also contribute to the GDSA model development. A basic 'minimal' process model will be provided to GDSA to support a 2020 repository performance assessment schedule. | 2017-09-30 04:00 |  | 2017-09-25 02:00 | Level-4 milestone report completed ahead of deadline. | 2017 | Complete | Status Report on Laboratory Testing and International Collaborations in Salt | Kuhlman, Kris | Kuhlman, Kris | None | SAND2017-10355R_Salt_2017_status_report_FINAL.pdf | SFWD-SFWST-2017-000100
M4SF-17PN010306093 | M4 | 1.08.01.03.06.09 | PNNL | SF-17PN01030609 | Deep Borehole Field Test - PNNL | Hanson, Brady | Mackinnon, Robert | Pre-test flow analysis | Pre-test flow analysis | Pre-test analysis for flow profile surveys in the deep basement | 2017-09-30 15:00 |  | 2017-09-29 03:00 | An email transmitting this milestone and confirming it was completed on time (9/29/17) was sent to the Control Account Manager on September 29, 2017. | 2017 | Complete | Assessing the Characterization Potential of Flowing Fluid Electrical Conductivity (FFEC) Surveys within Deep Boreholes for Crystalline Basement Disposal | Spane, Frank | Hanson, Brady | None | SFWD SFST 2017 000110.pdf | SFWD-SFWST-2017-000110 | logging surveys, flowing fluid electrical conductivity, open borehole basement sections
M2SF-17SN010504081 ULR. DRAFT Document, August 31, 2017. NOT FOR PUBLIC RELEASE​ | M2 | 1.08.01.05.04.08 | SNL | SF-17SN01050408 | Total System Performance Assessment - SNL | Sevougian, David | MacKinnon, Robert | Safety Analysis for a Generic Deep Geologic Repository in Shale | Safety Analysis for a Generic Deep Geologic Repository in Shale | This report will summarize the progress made on the development of safety analysis methods for a Generic Deep Geologic Repository in Shale. | 2017-11-03 06:00 |  | 42977.75 |  | 2017 | Complete | Safety Analysis for a Generic Deep Geologic Repository in Shale | Sevougian, S. David | Sevougian, S. David | OUO |  | SFWD-SFWST-2017-000017 | Generic Safety Assessment
M3SF-18LA010303013 carried over from FY17: M3SF-17LA010303021 | M3 | 1.08.01.03.03.01 | LANL | SF-18LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Test Plan Document for Thermal Testing in Salt (Carryover Milestone) | Test Plan Document for Thermal Testing in Salt | LANL will work closely with SNL and LBNL to create a test plan to implement recommended thermal experiments in the underground at WIPP. This task will build on a March 2017 SNL deliverable that will outline a set of experiments and scientific goals. LANL will adapt the March 2017 deliverable to refine the initial set of experiments to include details of implementation in the underground (CAD, logistics, etc.). Details of the final experimental plan will be compiled in a test plan in accordance with Quality Assurance (QA) requirements. | 2017-11-30 |  | 43069.0833 |  | 2018 | Complete | Test Plan Document for Thermal Testing in Salt | Johnson, Peter | Stauffer, Philip | None | 2017_Nov_30_Test_Plan_Thermal_M3SF-18LA010303013.pdf |  | Salt Thermal Field-Test
M4SF-18SN010305022 | M4 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Joint Workplan on Filler Investigations for DPCs | Joint Workplan on Filler Investigations for DPCs | Workplan with ORNL to produce a demonstration of filler emplacement (with post-test examination) in scaled models representing DPCs. | 2017-12-20 |  | 43089.0833 |  | 2018 | Complete | Joint Workplan on Filler Investigations for DPCs | Hardin, Ernest | Hardin, Ernest | None | Fillers R&D plan M4 Final 20Dec17.pdf |  | spent fuel; dual-purpose canister; criticality; filler; geologic disposal
M4SF-18SN010303061 | M4 | 1.08.01.03.03.06 | SNL | SF-18SN01030306 | Salt International Collaborations - SNL | Kuhlman, Kris | MacKinnon, Robert | Procedings of 8th US/German Workshop on Salt Repository Research, Design, and Operation | Procedings of 8th US/German Workshop on Salt Repository Research, Design, and Operation | Procedings of 8th US/German Workshop on Salt Repository Research, Design, and Operation | 2018-02-28 |  | 2018-02-09 02:00 |  | 2018 | Complete | Proceedings of the 8th US/German Workshop on Salt Repository Research, Design, and Operation | Hansen, Francis | Kuhlman, Kris | None | M4SF-18SN010303061 8th us german 020918 lac REDUCED SAND2018-1339R.PDF | SFWD-SFWST-2018-000485 | salt, radioactive waste
M4SF-18OR010305016 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Evaluate temperature distribution impacts on a loaded DPC with filler material | Impact of filler materials on DPC temperature distribution in disposal environments | Analysis of operating temperature ranges and distributions expected when the insulating effects of a filler are incorporated into a loaded DPC. | 2018-03-23 |  | 43182 |  | 2018 | Complete | Thermal Analysis of DPC Fillers - Phase I | Robb, Kevin | Scaglione, John | None | SFWD-robb_r6[1].pdf |  | Filler material, thermal
M4SF-18SN010305024 | M4 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | Mackinnon, Robert | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Describe a complete laboratory testing program for filler composition, delivery, emplacement in surrogate canisters, and post-test examination. To the extent possible specify filler material and equipment sources. | 2018-03-30 |  | 43188.0833 |  | 2018 | Complete | Recommendations for Filler Material Composition and Delivery Method for Bench-Scale Testing | Hardin, Ernest | Hardin, Ernest | None | SFWD-SFWST-2018-000490 R0 DPC filler cement recommendations FINAL.pdf | SFWD-SFWST-2018-000490 | spent nuclear fuel; geologic disposal; dual-purpose canister
M5SF-18SN010305027 | M5 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | None | Independent review of DPC direct disposal strategies | Independent Review of DPC Direct Disposal Strategies | Perform a technical review of DPC criticality analyses to evaluate progress and resources needed to support successful licensing, and modifications to future DPCs that could expedite disposal. | 2018-04-27 |  | 43213.75 |  | 2018 | Complete | Independent Review of DPC Direct Disposal Strategies | Alsaed, Abdelhalim | Hardin, Ernest | None | Review of Criticality Evaluations for DPC Disposal - Final.docx | SFWD-SFWST-2018-000491 | spent fuel; geologic disposal; dual-purpose canisters
M4SF-18IN010304011 | M4 | 1.08.01.03.04.01 | INL | SF-18IN01030401 | GDSA - Geologic Modeling - INL | Russell, Glenn | MacKinnon, Robert | Activity to support Geologic Modeling | Geologic Modeling Applications | Develop, publish, support, and maintain updated versions (2.0) of web-based tool for geologic modeling, data, and global survey information. | 2018-05-31 | 2018-06-15 02:00 | 2018-06-12 02:00 |  | 2018 | Completed Late | Regional Geology Interactive Web Based Mapping Application: Javascript v2.0 Mid-FY2018 Milestone Report | Russell, Glenn | Russell, Glenn | None | M4-GDSA-SFWST-RegionalGeologyWebMap2018.pdf |  | GDSA, Web Map, Regional Geologic Framework
M3SF-18LB010301031 | M3 | 1.08.01.03.01.03 | LBNL | SF-18LB01030103 | Argillite Disposal R&D - LBNL | Rutqvist, Jonny | McMahon, Kevin | Investigation of Coupled Processes in Argillite Rock | Investigation of Coupled Processes in Argillite Rock: FY18 progress | This activity include modeling THMC processes in argillite under high temperature, developing robust THMC code | 2018-06-22 |  | 43272.25 |  | 2018 | Complete | Investigation of Coupled Processes in Argillite Rock: FY18 progress | Rutqvist, Jonny | Rutqvist, Jonny | None | M3SF-18LB010301031 V2 Final.pdf |  | Argillite, bentonite, clay, THMC modeling, THM modeling, fracture damage modeling, heater test modeling, coupled processes
M3SF-18SN010303033 | M3 | 1.08.01.03.03.03 | SNL | SF-18SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Salt Heater Test Project Plan | Project Plan: Salt Borehole Heater Test | Project Plan for heater test in salt. | 2018-06-29 |  | 43252.0833 |  | 2018 | Complete | Project Plan: Salt in Situ Heater Test | Kuhlman, Kris | Kuhlman, Kris | None | SAND2018-4673R_salt-heater-test-project-plan-fy18.pdf
M4SF-18LB010303021 | M4 | 1.08.01.03.03.02 | LBNL | SF-18LB01030302 | Salt Disposal R&D - LBNL | Rutqvist, Jonny | MacKinnon, Robert | Salt Coupled THMC Processes Research Activities at LBNL: FY18 Progress Report | Modeling Coupled THMC Processes and Brine Migration at High Temperature | Report on LBNL's FY18 activities related to modeling support for the development of a test plan for a small diameter borehole field test, continued international collaboration for further development, testing and validation of coupled thermal, hydraulic, mechanical and chemical processes models. | 2018-07-31 |  | 2018-07-31 03:00 |  | 2018 | Complete | Salt Coupled THMC Processes Research Activities at LBNL: FY18 Progress | Rutqvist, Jonny | Rutqvist, Jonny | None | M4SF-18LB010303021 V2.pdf |  | Salt, Brine, Coupled processes, Modeling, Migration, Field tests, WIPP, TOUGH-FLAC, Temperature, Permeability, THM, THMC, Cross-borehole Electrical Resistivity Tomography.
M5SF-18SN010305028 | M5 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | None | Review of Requirements for DPC Fillers to Control Postclosure Criticality | Review of Requirements for DPC Fillers to Control Postclosure Criticality | Perform and document a review to identify pertinent requirements that would need to be addressed for adding a filler material to existing loaded DPCs. The assessment will include: a) effectiveness of filler introduction into different types of DPCs; b) the functions of filler materials and their longevity in disposal environments; c) quality control and how representations of quality could be made to a regulator; and d) impact of fillers on potential storage/aging, transportation, and waste retrieval from filled canisters. The scope includes applicability of regulations, orders, consensus standards, guidance documents, DPC operating procedures, and other literature. | 2018-07-31 |  | 2018-07-27 02:00 |  | 2018 | Complete | Technical and Regulatory Considerations for Use of Fillers in DPCs | Alsaed, Abdelhalim | Rigali, Mark | None | SFWD-SFWST-2018-000495 - Fillers Requirements Review Final.pdf | SFWD-SFWST-2018-000495 | spent nuclear fuel; geologic disposal; dual-purpose canister
M4SF-18LL010302082 | M4 | 1.08.01.03.02.08 | LLNL | SF-18LL01030208 | Crystalline International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | Thermodynamic Database Development and Identification of Actinide Sequestration in Corrosion Products | Thermodynamic Database Development and Identification of Actinide Sequestration in Corrosion Products | This milestone deliverable will summarize LLNL activities related to the SFWST program and feed into higher level milestones summarizing international cooperation activities. | 2018-08-01 | 2018-10-15 06:00 | 2018-10-12 03:00 | milestone delivered | 2018 | Late | M4SF-18LL010302082-Thermodynamic Database Development and Identification of Actinide Sequestration in Corrosion Products | Zavarin, Mavrik | Zavarin, Mavrik | None | IM-944007-6-1.pdf |  | thermodynamics, corrosion
M4SF-18LA010301021 ULR. DRAFT. | M4 | 1.08.01.03.01.02 | LANL | SF-18LA01030102 | Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite Disposal R&D - LANL | Argillite Disposal R&D – LANL | begin experimental studies to support disposal in Argillite rock | 2018-08-03 |  | 2018-08-02 02:00 |  | 2018 | Complete | Argillite R&D and International Collaborations – Los Alamos National Laboratory (FY18) | Caporuscio, Florie | Caporuscio, Florie | None | FY18_Argillite_Final.pdf |  | argillite, EBS, analcime, Opalinus Clay, zeolite, steel corrosion
M3SF-18LB010308022 Cindy Tilton confirmed UUR. Problems saving file as PDF. | M3 | 1.08.01.03.08.02 | LBNL | SF-18LB01030802 | Engineered Barrier System R&D - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL: FY18 Progress Report | Engineered Barrier System Research Activities at LBNL: FY18 Progress Report | Engineered Barrier System Research Activities at LBNL | 2018-08-03 |  | 43315.125 |  | 2018 | Complete | Engineered Barrier System Research Activities at LBNL: FY18 Progress Report | Zheng, Liange | Zheng, Liange | None | M3SF-18LB010308022 V3.pdf |  | Engineered Barrier System Research Activities at LBNL: FY18 Progress Report
M4SF-18AN010301017 | M4 | 1.08.01.03.01.01 | ANL | SF-18AN01030101 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Update on Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model | Update on Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model | Progress report | 2018-08-06 |  | 2018-08-06 01:00 |  | 2018 | Complete | Update on Validation and Incorporation of a New Steel Corrosion Module into Fuel Matrix Degradation Model | Jerden, James | Jerden, James | None | ANL 2018 August Milestone Report M4SF-18AN010302016_REV2.pdf |  | spent fuel degradation, steel corrosion
M4SF-18AN010302016 | M4 | 1.08.01.03.02.01 | ANL | SF-18AN01030201 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Update on Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model | Update on Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model | Progress report | 2018-08-06 |  | 2018-08-06 01:00 |  | 2018 | Complete | Update on Validation and Incorporation of a New Steel Corrosion Module into Fuel Matrix Degradation Model | Jerden, James | Jerden, James | None | ANL 2018 August Milestone Report M4SF-18AN010302016_REV2.pdf |  | spent fuel degradation, steel corrosion
M4SF-18OR010305017 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Unit test plan for filler demonstration | Filler demonstration exercise | The deliverable includes (1) computational fluid dynamics simulation of filler flow inside a scaled DPC through the drain pipe and (2) a unit test plan that will be used to benchmark filler material flow simulation through the drain pipe. | 2018-08-10 |  | 2018-08-10 |  | 2018 | Complete | Dual-Purpose Canister Filling Demonstration Project Progress Report | Banerjee, Kaushik | Scaglione, John | None | PB1800785_Banerjee_DPC-FillingDemo-Final.pdf
M4SF-18LA010308051 ULR. DRAFT | M4 | 1.08.01.03.08.05 | LANL | SF-18LA01030805 | Engineered Barrier System International Collaborations - LANL | Caporuscio, Florie | McMahon, Kevin | EBS International Collaborations - LANL | Engineered Barrier System International Collaborations – LANL | To expand existing R&D partnerships with international programs (Swiss, Japanese, NEA ) in nuclear waste disposal underground research laboratory (URL) activities. Participate in data sharing of present and previous experimental results, including bentonite mineral phase transformations and steel corrosion/interface mineralogy characterization. | 2018-08-10 |  | 2018-08-09 02:00 |  | 2018 | Complete | Engineered Barrier System R&D and International Collaborations – LANL (FY18) | Caporuscio, Florie | Caporuscio, Florie | None | EBS_FY18_Final.pdf |  | Grimsel Granodiorite, C(A)SH, experimental results
M4SF-18SN010307022 | M4 | 1.08.01.03.07.02 | SNL | SF-18SN01030702 | Disposal Research International Coordination - SNL | McMahon, Kevin | Birkholzer, Jens | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | SFWST Campaign International Activities in Disposal Research at SNL | 2018-08-17 |  | 2018-08-15 02:00 |  | 2018 | Complete | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | McMahon, Kevin | McMahon, Kevin | None | M4SF-18SN010307022 SNL International FY18 SAND2018-9025 R.docx
M4SF-18LA010302023 | M4 | 1.08.01.03.02.02 | LANL | SF-18LA01030202 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Modeling and experimental activities for crystalline rock disposal | Crystalline and Crystalline International Disposal Activities | Level 4 milestone to support Sandia's Level 2 for Crystalline Rock activities. This will include simulation, experiment and support of performance assessment and international activities | 2018-08-22 |  | 2018-08-21 02:00 |  | 2018 | Complete | Crystalline and Crystalline International Disposal Activities | Viswanathan, Hari | Viswanathan, Hari | None | FY18_draft_SFWD_final.pdf |  | crystalline rock, discrete fracture network, colloids
M4SF-18SN010302092 | M4 | 1.08.01.03.02.09 | SNL | SF-18SN01030209 | Crystalline International Collaborations - SNL | Wang, Yifeng | McMahon, Kevin | International collaboration on spent fuel disposition in crystalline rocks: FY18 progress report | Deliverable Title International collaboration on spent fuel disposition in crystalline rocks: FY18 progress report | The report will document the work on international collaboration through DECOVALEX. | 2018-08-22 |  | 2018-08-22 02:00 |  | 2018 | Complete | International collaboration on spent fuel disposition in crystalline rocks: FY18 progress report | Wang, Yifeng | Wang, Yifeng | None | International collaboration.pdf |  | crystalline rocks, fractured media, waste disposal, fluid flow and transport
M3SF-18OR0103050111 | M3 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Repository criticality consequence analysis roadmap | Repository criticality consequence analysis roadmap | This deliverable will present a criticality consequence analysis roadmap for DPCs that will be followed and updated as needed based on various findings. The deliverable will survey existing literatures, identify analysis codes (e.g., neutroic code, thermal hydraulic code), and identify any gap in the currently available methodology/analysis codes. If any gap is identified, this roadmap will provide recommendation to bridge the gap. The roadmap will also identify validation approach and uncertainty quantification for the consequence analysis methodology. | 2018-08-24 |  | 43336 |  | 2018 | Complete | Criticality Consequence Analysis Roadmap for a Spent Nuclear Fuel Canister in a Repository | Banerjee, Kaushik | Scaglione, John | None | PB1800849_Banerjee_CritRoadmap-Final.pdf
M4SF-18LB010302031 | M4 | 1.08.01.03.02.03 | LBNL | SF-18LB01030203 | Crystalline Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | Crystalline Disposal R&D at LBNL | Crystalline Disposal R&D: FY18 LBNL Progress Report | this is a continuation of the FY 17 experimental work | 2018-08-24 |  | 2018-08-23 03:00 |  | 2018 | Complete | Crystalline Disposal R&D at LBNL | Zheng, Liange | Zheng, Liange | None | M4SF-18LB010302031 V2.pdf |  | Crystalline rock, Nuclear waste disposal, Pore-scale gas bubble migration, Rock deformation, Geophysical measurements, Excavation damage zone, Fractures, Hydraulic properties, Deep borehole.
M4SF-18SN010301092 | M4 | 1.08.01.03.01.09 | SNL | SF-18SN01030109 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | McMahon, Kevin | International Collaboration Activities on Engineered Barrier Systems: Progress Report | Progress Report on International Collaboration Activities on Engineered Barrier Systems | This input will represent an SNL “feeder” report to the Level 2 Milestone for DR International activities at the end of FY18. | 2018-08-24 |  | 43343.0833 |  | 2018 | Completed Late | International Collaboration Activities on Disposal in Argillite R&D: Progress Report | Jove Colon, Carlos | Jove Colon, Carlos | None | M4SF18SN010301092.pdf
M3SF-18LA010303015 | M3 | 1.08.01.03.03.01 | LANL | SF-18LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Experiments and modeling to support field test design | Experiments and modeling to support field test design | This deliverable will present all modeling and related experimental data used to better simulate thermal driven flow in salt. Any new simulations related to the small diameter horizontal borehole experiments in WIPP will be included. Additionally, existing computational models of THC processes will be used to support the design of in-situ thermal testing and reduction of uncertainties for longer term performance assessment. The modeling will be in accordance with the goals described in the Spent Fuel and Waste Disposition (Formerly UFD) test proposal document (FCRD-UFD-2015-000077, Test Proposal Document for Phased Field Thermal Testing in Salt). In FY18, models will be validated against results obtained from all relevant experimental studies performed in FY12-FY18. Data will be used in an iterative model/data validation strategy with a goal of reducing uncertainty in parameters related to the long term safety basis for spent fuel and waste disposition. | 2018-08-31 |  | 43342.0833 |  | 2018 | Complete | Experiments and Modeling to Support Field Test Design | Johnson, Peter | Stauffer, Philip | None | 2018_Aug_31_LANL_Model_Milestone_LA-UR-18-28189.pdf |  | salt repository simulation
M4SF-18LA010304022 | M4 | 1.08.01.03.04.02 | LANL | SF-18LA01030402 | GDSA - Geologic Modeling - LANL | Perry, Frank | Mackinnon, Robert | Geologic and hydrologic conceptual model of basin-fill alluvium in arid regions | Geologic and hydrologic conceptual model of basin-fill alluvium in arid regions | Documentation of activities and progress to support GDSA through development of geologic framework modeling | 2018-08-31 | 2018-09-28 08:00 | 2018-09-27 02:00 | Report documenting the geologic and hydrologic environment of alluvial basins in the Basin and Range province to provide information fees to the generic GDSA reference case for unsaturated media. | 2018 | Completed Late | Regional Geologic Evaluations for Disposal of HLW and SNF: Alluvial Basins of the Basin and Range Province | Perry, Frank | Perry, Frank | None | Alluvial Basins GDSA Perry LANL M4 September 2018 R2.pdf | SFWD-SFWST-2018-000512 | Alluvium, geology, hydrology, siting
M5SF-18SN010305054 | M5 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | None | Engineering Cost Analysis Support - Scoping | Scoping Memo for Engineering and Cost Support - Analysis of DPC Disposal Solutions | Scoping memo describing approach to costing disposal options and modifications to DPCs. | 2018-09-06 |  | 43349 | Milestone completed on time. | 2018 | Complete | Technical & Programmatic Solutions for DPC Direct Disposal: Engineering Cost Analysis Support – Scoping (SFWD) | Hardin, Ernest | SNL | None | Engineering Support Scoping M5 Final.pdf
M4SF-18OR010305015 supercedes M4SF-17OR010305028 | M4 | 1.08.01.03.05.01 | ORNL | SF-18OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Summary status report of DPC filler demonstration project | Status update of DPC filler demonstration | Status update of DPC filler capabilities and results to date | 2018-09-10 |  | 2018-09-10 | This report presents the ORNL DPC filler project status report as of September, 2018. | 2018 | Complete | Dual-Purpose Canister Filling Demonstration Project Progress Report | Banerjee, Kaushik | Scaglione, John | None | DPCFillerStatusReportSept2018.pdf
M2SF-18SN010304062 | M2 | 1.08.01.03.04.06 | SNL | SF-18SN01030406 | GDSA - Framework Development - SNL | Mariner, Paul | Mackinnon, Robert | Advances in Geologic Disposal Safety Assessment and an Unsaturated Alluvium Reference Case | FY18 Status Report - Advances in Geologic Disposal Safety Assessment and an Unsaturated Alluvium Reference Case | This report will document FY18 advances in GDSA modeling capabilities, integration with other work packages, and plans for future development. | 2018-09-17 |  | 2018-09-12 04:00 | 9/12/2018 Milestone complete | 2018 | Complete | Advances in Geologic Disposal Safety Assessment and an Unsaturated Alluvium Reference Case | Mariner, Paul | Mariner, Paul | None | GDSA FW wUZ M2SF-18SN010304062.pdf | SFWD-SFWST-2018-000509 | GDSA Framework, performance assessment, PFLOTRAN, repository, nuclear, unsaturated, alluvium
M5SF-18SN010305051 | M5 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | None | Prepare Draft Outline and Staffing Plan | Analysis of DPC Disposal Solutions - Outline and Staffing Plan | Issue an outline for the final draft analysis of solutions report, and how the effort will be staffed (SNL staff, consultants, other labs). | 2018-09-18 |  | 2018-09-19 02:00 | Completed technical review and Sandia R&A. | 2018 | Completed Late | Technical & Programmatic Solutions for Direct Disposal of DPCs – Draft Outline and Staffing Plan | Hardin, Ernest | Hardin, Ernest | None | C:\Users\ehardin\Documents\DPC Crit Files\DPC disposal T&PS plan final 19Sept18.pdf |  | spent nuclear fuel;geologic disposal;dual-purpose canisters
M5SF-18SN010305071 | M5 | 1.08.01.03.05.07 | SNL | SF-18SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | None | Scoping calculations and coupling strategy | Technical Memo on DPC Criticality Model Coupling Strategy and Scoping Calculations | Perform scoping calculations at limited dimensionality for proof of concept. Develop a strategy for coupling codes (e.g., MCNP, RELAP, FLAC3D) and prepare a technical memo describing the approach. | 2018-09-19 |  | 2018-09-18 02:00 | Completed with Sandia R&A and technical review. | 2018 | Complete | Multiphysics Simulation of DPC Criticality: Scoping Calculations and Coupling Strategy | Hardin, Ernest | Hardin, Ernest | None | C:\Users\ehardin\Documents\DPC Crit Files\Multi-physics workplan Final 18Sep18.pdf |  | spent nuclear fuel; geologic disposal; dual-purpose canisters
M2SF-18SN010308042 | M2 | 1.08.01.03.08.04 | SNL | SF-18SN01030804 | Engineered Barrier System R&D - SNL | Matteo, Edward | McMahon, Kevin | Evaluation of Engineered Barrier Systems in the Disposition of Spent Nuclear Fuel | Evaluation of Engineered Barrier Systems in the Dispositon of Spent Nuclear Fuel | End of FY status report on accomplishments. | 2018-09-24 |  | 2018-09-24 02:00 | M2 Milestone Completed! | 2018 | Complete | Evaluation of Engineered Barrier Systems in the Disposition of Spent Nuclear Fuel | Matteo, Edward | Matteo, Edward | None | EBS R&D_M2SF-18SN010308042 FY18_SAND2018-12124 R.pdf |  | Engineered Barrier System; Geotechnical barriers; Repository design
M2SF-18SN010302051 | M2 | 1.08.01.03.02.05 | SNL | SF-18SN01030205 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Evaluation of Spent Nuclear Fuel Disposition in Crystalline Rocks | Evaluation of Spent Nuclear Fuel Disposition in Crystalline Rocks | End of FY18 status report on accomplishments. | 2018-09-24 |  | 43367.0833 | This milestone summarizes the work performed in FY18 on spent fuel disposal in crystalline rocks. | 2018 | Complete | Evaluation of Spent Fuel Disposition in Crystalline Rocks: FY18 Progress Report | Wang, Yifeng | Wang, Yifeng | None | M2SF-18SN010302051a.pdf |  | Spent fuel, crystalline rocks
M2SF-18SN010303031 | M2 | 1.08.01.03.03.03 | SNL | SF-18SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Evaluation of Spent Nuclear Fuel Disposition in Salt Rocks | Evaluation of Spent Nuclear Fuel Disposition in Salt Rocks | Planning, modeling, laboratory, and field work related to evaluation of salt for disposal of radioactive waste. | 2018-09-24 |  | 2018-09-24 02:00 | Level-2 milestone report for salt R&D completed on schedule | 2018 | Complete | Evaluation of Spent Nuclear Fuel Disposition in Salt (FY18) | Kuhlman, Kris | Kuhlman, Kris | None | SAND2018-11355R_Salt_2018_M2_59sm.pdf
M2SF-18SN010301051 | M2 | 1.08.01.03.01.05 | SNL | SF-18SN01030105 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Spent Nuclear Fuel Dispositon in Clay-Bearing Rocks | Evaluation of Spent Nuclear Fuel Dispositon in Clay-Bearing Rocks | End of FY18 status report of accomplishments. | 2018-09-24 |  | 2018-09-24 02:00 | This milestone deliverable summarizes R&D activities conducted under the disposal in argillite work package for FY18. | 2018 | Complete | Evaluation of Used Fuel Disposition in Clay-Bearing Rock | Jove Colon, Carlos | Jove Colon, Carlos | None | M2SF-18SN010301051.pdf |  | Argillite, disposal, nuclear waste , clay, barrier, spent fuel, R&D
M2SF-18SN010309013 | M2 | 1.08.01.03.09.01 | SNL | SF-18SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, David | MacKinnon, Robert | Inventory and Waste Characterization Status Report and OWL Update | Inventory and Waste Characterization Status Report and OWL Update | End of FY status report on accomplishments | 2018-09-24 |  | 43367.0833 | Completed milestone deliverable M2SF-18SN010309013 “Inventory and Waste Characterization Status Report and OWL Update” that reports on FY2018 activities for the work package SF-18SN01030901. This report has been through Programmatic Review (R&A) here at Sandia, so it is still internal use only so I would not be loading the file into PICSNE (this waits for the DOE acceptance review and then gets Formally R&A’d as a public release UNCLASSIFIED UNLIMITED RELEASE, and then the document can be loaded). | 2018 | Complete | Inventory and Waste Characterization Status Report and OWL Update | Sassani, David | Sassani, David | None | M2SF-18SN010309013 SAND2018_12352 R.pdf |  | Online waste library OWL waste form characteristics
M2SF-18SN010305026 | M2 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | Mackinnon, Robert | FY18 Summary Update on the Feasibility of Direct Disposal of SNF in Existing DPC's | Summary Update on the Feasibility of Direct Disposal of SNF in Existing DPC's |  | 2018-09-24 |  | 2018-09-21 02:00 | Complete technical review, and Sandia programmatic R&A. Submitted here for acceptance review (limited release, internal use only). | 2018 | Complete | Summary Update on the Feasibility of Direct Disposal of SNF in Existing DPCs (Pre-Decisional Draft) | Hardin, Ernest | Rigali, Mark | None | DPC disposal M2 21Sept2018 Final for DOE review.pdf | SFWD-SFWST-2018-000511 | spent nuclear fuel;geologic disposal;dual-purpose canisters
M2SF-18LB010307012 | M2 | 1.08.01.03.07.01 | LBNL | SF-18LB01030701 | Disposal Research International Coordination - LBNL | Birkholzer, Jens | Birkholzer, Jens | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geological Disposal Environments | This report gives a comprehensive overview of these initiatives and describes the various opportunities arising from DOE’s membership in international initiatives as well DOE's partnership with individual international disposal program. The report also provides an overview of the various R&D activities conducted in FY18 as related to international collaboration. | 2018-09-28 |  | 2018-09-28 03:00 | This report describes the status of international collaboration regarding geologic disposal research in the Spent Fuel and Waste Disposition (SFWD) Campaign. Since 2012, SFWD has advanced active collaboration with several international geologic disposal programs in Europe and Asia. Such collaboration allows the SFWD Campaign to benefit from a deep knowledge base in regards to alternative repository environments developed over decades, and to utilize international investments in research facilities (such as underground research laboratory testing and modeling), saving millions of R&D dollars that have been and are being provided by other countries. To date, SFWD’s International Disposal R&D Program has established formal collaboration agreements with several international initiatives and various international partners, and national lab scientists associated with SFWD have conducted specific collaborative R&D activities that align well with its R&D priorities. These now form a considerable portion of SFWD disposal research, and significant advances have been made over the past few years. | 2018 | Complete | International Collaboration Activities in Different Geologic Disposal Environments | Birkholzer, Jens | Birkholzer, Jens | None | M2SF-18LB010307012 V2.pdf |  | International collaboration, underground research laboratories, in situ testing, nuclear waste disposal, host rock, argillite, crystalline rock, salt, engineering barriers, radionuclide transport, international collaboration, DECOVALEX Project.
M3SF-18LA010303014 | M3 | 1.08.01.03.03.01 | LANL | SF-18LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | MacKinnon, Robert | Implementation of small diameter borehole thermal experiments in WIPP | Implementation of small diameter borehole thermal experiments in WIPP | Summary of work done on small diameter borehole testing in WIPP for FY18. | 2018-09-30 |  | 43371.0833 | Summary of thermal testing at WIPP completed a bit early. Contributions and edits from all authors appreciated and included. | 2018 | Complete | Implementation of Small Diameter Borehole Thermal Experiments at WIPP | Boukhalfa, Hakim | Stauffer, Philip | None | Shakedown_test_update_M3-Sept_28_2018_M3SF-18LA010303014.pdf |  | thermal test, salt, vapor, WIPP
M4SF-18LA010303041 | M4 | 1.08.01.03.03.04 | LANL | SF-18LA01030304 | Salt International Collaborations - LANL | Stauffer, Philip | MacKinnon, Robert | LANL Salt international update | LANL Salt international update | We will summarize the efforts of our international outreach and collaboration a level 4 milestone. | 2018-09-30 |  | 2018-09-25 02:00 | LANL International milestone completed and submitted 5 days early. | 2018 | Complete | LANL Salt International Update | Johnson, Peter | Stauffer, Philip | None | 2018_Sept_25_LANL_international_milestone-M4SF-18LA010303041.pdf
M4SF-19OR0103050110 supercedes M4SF-18OR0103050117 Predecisional Draft. | M4 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Status report summarizing GDSA/PFLOWTRAN simulation status on HPC environment | Summary status report of GDSA/PFLOWTRAN simulation on HPC environment | Develop a M4 Status report summarizing the above activities suitable for incorporation or reference by either M2SF-18SN010304065 “GDSA Framework Development and Process Model Integration” or M3SF-18SN010305072 “DPC Criticality Simulation Preliminary Phase” | 2018-11-16 |  | 43420 |  | 2019 | Complete | Status Report Summarizing GDSA/PFLOWTRAN Simulation on HPC Environment | Howard, Rob | Scaglione, John | None | PFLOTRAN Status Report 16Nov2018.pdf
M5SF-19OR0103050114 | M5 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | None | Draft multi year plan for Direct Disposal WBS | Draft multiyear plan for Direct Dispsoal R&D | Draft long-range plan for R&D activities leading to a regulatory case for direct disposal of commercial SNF in DPCs, including decision points for fillers investigations, multi-physics modeling, and consequence screening activities | 2018-12-14 |  | 43448 |  | 2019 | Complete | Draft GDSA plan accounting for Direct disposal of DPCs (12/14/2018) | Scaglione, John | Scaglione, John | None
M4SF-19OR0103050113 Per Matt Brainard 12/9/2019: Document not available in PICS:NE. Notes: Document is currently a draft awaiting peer review evaluation for inclusion as official BWR data benchmark data (as of 11/10/2020). Once peer review is complete document will be available. Contact John Scaglione for a copy. supercedes M4SF-18OR0103050120 and M4SF-18OR0103050121 | M4 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Mackinnon, Robert | Prepare BWR data evaluation report | SFCOMPO BWR data evaluation report | • Draft evaluation reports for a boiling water reactor (BWR) dataset will be prepared by ORNL for independent peer review by the Technical Review Group for the SFCOMPO database. The report will include a detailed uncertainty analysis of the data. | 2018-12-28 |  | 2018-12-28 |  | 2019 | Complete | Draft BWR Data Evaluation for SFCOMPO | ORNL | Scaglione, John | None
M3SF-19SN010305061 same as M3SF-18SN010305061 | M3 | 1.08.01.03.05.06 | SNL | SF-19SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | MacKinnon, Robert | Probabilistic Postclosure DPC Criticality Consequence Analysis - Scoping | Criticality Consequence Analysis for Geologic Disposal, Scoping | Develop technical and regulatory strategy for low consequence analyses, founded in regulations and existing generic PA models. Identify an appropriate set of criticality FEPs. Identify appropriate uses for simulation and enumeration approaches for repository performance assessment. Define key parameters and metrics. | 2019-01-22 |  | 43487.0833 |  | 2019 | Complete | Postclosure Criticality Consequence Analysis - Scoping Phase | SNL | Price, Laura | None | M3SF-19SN010305061_DPC Crit Cons-Scoping_01-22-2019.pdf
M3SF-19OR0103050115 | M3 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Initial validation of CFD filling simulation | Initial validation of CFD filling simulation | This milestone report will document the initial validation of the CFD filling simulation of a scaled-DPC model using experimental data for various surrogate filling materials. | 2019-02-15 |  | 43511 | This report discusses the initial progress made at the Oak Ridge National Laboratory to support direct disposal of dual-purpose canisters (DPCs) using filler materials to demonstrate that the probability of criticality in DPCs during disposal to be below the probability for inclusion in a repository performance assessment. | 2019 | Complete | Dual-Purpose Canister Filling Demonstration Project Progress Report | Cetiner, Nesrin | Scaglione, John | None | PB1900211_CetinerN_DPC_final.pdf
M5SF-19OR0103050120 ULR - waiting for feedback from DOE before publishing. | M5 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | None | Multiyear plan for direct disposal R&D | Long-Range R&D Plan for DPC Direct Disposal Investigations | Coauthored internal planning report identifying long-range plan for R&D activities leading to a regulatory case for direct disposal of commercial SNF in DPCs, including decision points for fillers investigations, multi-physics modeling, and consequence screening activities. | 2019-02-15 |  | 43511 | Long-range R&D plan for Dual-purpose canister direct disposal investigations. Prepared for technical and programmatic integration between national laboratories, particularly ORNL and SNL, and presentation to the DOE Program Manager. | 2019 | Complete | Long-Range R&D Plan for DPC Direct Disposal Investigations | SNL | Scaglione, John | None | DPC Long-Range RD Plan SNL Final 15Feb.pdf
M5SF-19SN010305055 ULR -- Waiting for feedback from DOE before publishing. | M5 | 1.08.01.03.05.05 | SNL | SF-19SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | None | Long-Range R&D Plan for DPC Direct Disposal Investigations | Long-Range R&D Plan for DPC Direct Disposal Investigations | Prepare a long-range plan for R&D activities leading to a regulatory case for direct disposal of commercial SNF in DPCs, including decision points for fillers investigations, multi-physics modeling, and consequence screening activities. | 2019-02-15 |  | 43511.0833 | Complete through programmatic review at SNL; for limited internal use only (pending discussions with the DOE Program Mgr). This version is intended to satisfy both the SNL M5 and ORNL M5 deliverables (numbers on cover sheet). | 2019 | Complete | Long-Range R&D Plan for DPC Direct Disposal Investigations | Hardin, Ernest | Hardin, Ernest | None | DPC Long-Range RD Plan SNL Final 15Feb.pdf |  | spent nuclear fuel; dual-purpose canisters; geologic disposal
M3SF-19AN010301012 | M3 | 1.08.01.03.01.01 | ANL | SF-19AN01030101 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Validation Results For the Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Deliverable | 2019-03-19 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M3SF-19AN010302012 | M3 | 1.08.01.03.02.01 | ANL | SF-19AN01030201 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Validation Results For the Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA | Validation and Implementation of Steel Corrosion Module into Fuel Matrix Degradation Model: Electrochemical Experimental Results and Integration with GDSA PA | Deliverable | 2019-03-19 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M4SF-18LA010301023 | M4 | 1.08.01.03.01.02 | LANL | SF-18LA01030102 | Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | argillite disposal (with cement) R&D interim report | argillite disposal (with cement) R&D interim report | argillite disposal (with cement) R&D | 2019-03-29 |  | 2018-09-27 02:00 | The L4 document was incorporated into the Sandia L2 Argillite Disposal R&D document | 2018 | Complete | Argillite R&D and International Collaborations – Los Alamos National Laboratory (FY18) |  |  | None
M3SF-18PN010308032 | M3 | 1.08.01.03.08.03 | PNNL | SF-18PN01030803 | Engineered Barrier System R&D - PNNL | Buck, Edgar | McMahon, Kevin | Progress Report EBS R&D PNNL | In-situ Corrosion Studies on Nuclear Waste Forms | Report on research work at PNNL on EBS and waste form related work. | 2019-03-29 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M4SF-18LA010308053 | M4 | 1.08.01.03.08.05 | LANL | SF-18LA01030805 | Engineered Barrier System International Collaborations - LANL | Caporuscio, Florie | McMahon, Kevin | EBS international FEBEX interactions | EBS International interim report | EBS international FEBEX interactions | 2019-03-29 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M4SF-19OR010304071 Per Matt Brainard this deliverable satisfies both milestones M4SF-19OR010304071 and M4SF-19OR010304072 in PICS:NE | M4 | 1.08.01.03.04.07 | ORNL | SF-19OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | ORNL Input GDSA Modeling in Unsaturated Rock | ORNL Input to GDSA Repository Model in Unsaturated Rock | This deliverable will report progress on developing and simulating generic reference case repositories with GDSA Framework, especially in a UZ host rock, and including DPC inventory and waste packages. | 2019-03-29 | 43616 |  | Work on this milestone was delayed based on incremental funding. | 2019 | Expected Late |  |  |  | None
M3SF-19PN010308032 | M3 | 1.08.01.03.08.03 | PNNL | SF-19PN01030803 | Engineered Barrier System R&D - PNNL | Buck, Edgar | McMahon, Kevin | Engineered Barrier System R&D - Progress Report PNNL | In-situ Corrosion Studies on Nuclear Waste Forms | Report on research work at PNNL on EBS and waste form related work. | 2019-03-29 |  |  | On schedule. | 2019 | 90 Day |  |  |  | None
M4SF-19OR0103050116 | M4 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Initial full-scale/Scaled-drain pipe filling experiment and data collection | Full-scale/Scaled-drain pipe filling experiment and data collection | The milestone report will document the data collected from a full-scale/scaled pipe experiment. This experiment will simulate the filling through the DPC drain pipe and help uncover any issue of filling a DPC using drain pipe. | 2019-03-31 |  | 2019-04-02 | This report documents experiments that are being used to determine the feasibility of filling dual-purpose canisters (DPCs) using the existing drain pipe. | 2019 | 90 Day | Demonstration and Feasibility Analyses of Using the Dual-Purpose Canister Drain Pipe to Support the Filling Process | Elvis Dominguez-Ontiveros | John Scaglione | None | PB1900363_Dominguez-Ontiveros_DPC-final_alb.pdf
M4SF-18SN010308082 Input for Level 2 - Is this ULR/Draft? | M4 | 1.08.01.03.08.08 | SNL | SF-18SN01030808 | Engineered Barrier System International Collaborations - SNL | Matteo, Edward | McMahon, Kevin | FY18 Progress of EBS International Collaborations | FY18 Progress Report of EBS International Collaborations | This input will represent an SNL “feeder” report to the Level 2 Milestone for DR International activities at the end of FY18. | 2019-03-31 |  |  |  | 2018 | On Schedule |  | Matteo, Edward | Matteo, Edward | None
M3SF-19LA010303011 supercedes M3SF-18LA010303016 | M3 | 1.08.01.03.03.01 | LANL | SF-19LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | Stein, Emily | Salt Thermal Testing in Heated Boreholes: Experiments and Simulations | Salt Thermal Testing in Heated Boreholes: Experiments and Simulations | Report summarizing progress in data and modeling for the WIPP experiments in heated boreholes. | 2019-03-31 |  |  | We are working on our deliverable, simulations of the borehole heater test. | 2019 | 90 Day |  |  |  | None
M4SF-19LA010301062 supercedes M4SF-18LA010301061 | M4 | 1.08.01.03.01.06 | LANL | SF-19LA01030106 | Argillite International Collaborations - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite International Collaborations - LANL | Argillite International collaborations | Argillite International Collaborations - LANL | 2019-04-19 |  |  | on schedule | 2019 | 90 Day |  |  |  | None
M3SF-19SN010309012 No report in PICS. Internal use only | M3 | 1.08.01.03.09 | SNL | SF-19SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, Dave | McMahon, Kevin | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | Status Report on OWL Capabilities Expansion for Tailored Outputs Usable for Direct Input to Generic Transportation, Storage, and Disposal Analyses | This draft report is internal use only and represents completion of milestone deliverable M3SF-19SN010309012 “Status Report on OWL Capabilities Expansion” that reports interim status on FY2019 activities for the work package (WP) SF-19SN01030901. This report provides the draft status information for in process FY2019 work activities for WP SF-19SN01030901, and serves as a draft template for the milestone deliverable M2SF-19SN010309013 “Online Waste Library (OWL) and Waste Forms Characteristics Annual Report” due on August 2, 2019 for WP SF-19SN01030901. | 2019-04-30 |  | 2019-04-30 | This draft report represents completion of milestone deliverable M3SF-19SN010309012 “Status Report on OWL Capabilities Expansion” that reports interim status on FY2019 activities for the work package (WP) SF-19SN01030901 and is internal use only. This report provides the draft status information for in process FY2019 work activities for WP SF-19SN01030901, and serves as a draft template for the milestone deliverable M2SF-19SN010309013 “Online Waste Library (OWL) and Waste Forms Characteristics Annual Report” due on August 2, 2019 for WP SF-19SN01030901. | 2019 | Complete | Status Report on OWL Capabilities Expansion | Dave Sassani | Dave Sassani | Other- Internal use only draft report |  |  | online waste library waste form characteristics
M2SF-19SN010304051 supercedes M2SF-18SN010304076 | M2 | 1.08.01.03.04.05 | SNL | SF-19SN01030405 | GDSA - Repository Systems Analysis - SNL | Sevougian, David | Stein, Emily | GDSA Repository Systems Analysis Progress Report - Generic Repository in Unsaturated-Zone Host Rock | GDSA Repository Systems Analysis Progress Report | This deliverable will report progress on developing and simulating generic reference case repositories with GDSA Framework, especially in a UZ host rock, and including DPC inventory and waste packages. | 2019-04-30 |  |  | Still plan to finish on schedule | 2019 | 90 Day |  |  |  | None
M2SF-18SN010303032 Found M3SF-185N010303033 Project Plan Salt in Situ Heater Test​ doe SAND2018-4673R​ | M2 | 1.08.01.03.03.03 | SNL | SF-18SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | MacKinnon, Robert | Salt Heater Test | Salt Heater Test Progress Report | Progress report on laboratory, modeling, and field studied supporting the borehole heater tests in salt at WIPP. | 2019-04-30 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M2SF-19SN010303031 | M2 | 1.08.01.03.03.03 | SNL | SF-19SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Salt Heater Test | Salt Heater Test Progress Report | Progress report on laboratory, modeling, and field studied supporting the borehole heater tests in salt at WIPP. | 2019-04-30 |  |  | work is on schedule. M2 deliverable is already in draft form. | 2019 | 90 Day |  |  |  | None
M2SF-19SN010304042 supersedes M2SF-18SN010304065 | M2 | 1.08.01.03.04.04 | SNL | SF-19SN01030404 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | GDSA Model Integration and R&D Roadmap | Geologic Disposal Safety Assessment Status Report | Progress on integration of process models with GDSA Framework. Update of 2012 UFD R&D Roadmap document and associated generic repository R&D priorities. Results of R&D roadmap workshops with Crystalline, Argillite, and Salt work packages. | 2019-04-30 |  |  | on schedule | 2019 | 90 Day |  |  |  | None
M3SF-19LA010303012 | M3 | 1.08.01.03.03.01 | LANL | SF-19LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | Stein, Emily | 2019 LANL contribution to Salt-GDSA Integration | 2019 LANL contribution to Salt-GDSA Integration | 2019 LANL contribution to Salt-GDSA Integration | 2019-04-30 |  |  | We are working with SNL to summarize our notes on the GSDA workshop that took place Jan 2019. | 2019 | 90 Day |  |  |  | None
M3SF-19OR010305016 | M3 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Initial neutronic and thermal hydraulic coupling for waste package | Neutronic and thermal hydraulic coupling for waste package | This deliverable includes an initial implementation of neutronics and thermal hydraulic coupling to simulate DPC criticality and quantify various important parameters such as change in isotopic inventory, increase in temperature, and increase in pressure. | 2019-04-30 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M4SF-19SN010305053 | M4 | 1.08.01.03.05.05 | SNL | SF-19SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | Engineering and Cost Analysis for DPC Disposal Solutions | Preliminary Cost Analysis for DPC Disposal Solutions | Produce ROM cost estimates for identified options and DPC modifications. | 2019-05-02 |  |  | Subcontractor deliverable (analysis activity) received. | 2019 | 90 Day |  |  |  | None
M3SF-18LB010301072 | M3 | 1.08.01.03.01.07 | LBNL | SF-18LB01030107 | Argillite International Collaborations - LBNL | Rutqvist, Jonny | McMahon, Kevin | LBNL Expanded Argillite International Collaboration | LBNL Argillite International Collaboration | Report on LBNL Expanded Argillite International Collaboration | 2019-05-03 |  |  | On schedule | 2018 | On Schedule |  |  |  | None
M3SF-19LB010301031 supercedes M3SF-18LB010301033 | M3 | 1.08.01.03.01.03 | LBNL | SF-19LB01030103 | Argillite Disposal R&D - LBNL | Rutqvist, Jonny | McMahon, Kevin | Argillite Disposal R&D at LBNL | Argillite Disposal R&D at LBNL | Report on Argillite Disposal R&D at LBNL | 2019-05-17 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M4SF-19LA010308012 supercedes M4SF-18LA010308012 | M4 | 1.08.01.03.08.01 | LANL | SF-19LA01030801 | Engineered Barrier System R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Engineered Barrier R&D - LANL | Engineered Barrier R&D - LANL | Engineered Barrier R&D - LANL | 2019-05-20 |  |  | on schedule | 2019 | 90 Day |  |  |  | None
M4SF-19LA010308052 | M4 | 1.08.01.03.08.05 | LANL | SF-19LA01030805 | Engineered Barrier System International Collaborations - LANL | Caporuscio, Florie | McMahon, Kevin | Engineered Barrier International Collaborations - LANL | Engineered Barrier Inernational Collaborations - LANL | Engineered Barrier International Collaborations - LANL | 2019-05-20 |  |  | on schedule | 2019 | 90 Day |  |  |  | None
M4SF-19SN010301091 supercedes M3SF-18SN010301093 | M4 | 1.08.01.03.01.09 | SNL | SF-19SN01030109 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | McMahon, Kevin | International Collaborations Activities on Disposal in Argillite R&D: Interim Report - 2019 | Argillite Disposal R&D International Collaborations interim report - 2019 | Interim progress report provides description of R&D efforts related to FY19 international collaborations activities. This include studies of bentonite interactions from heater tests experiments (FEBEX-DP, Switzerland)and interactions of cementitious material with groundwater in a flooded drift (GREET experiment, Mizunami site, Japan) | 2019-05-24 |  |  | Work progressing as expected | 2019 | 90 Day |  |  |  | None
M4SF-19LA010302023 supercedes M4SF-18LA010302026 | M4 | 1.08.01.03.02.02 | LANL | SF-19LA01030202 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Modeling and experimental activities for crystalline rock disposal to support GDSA | Modeling and experimental activities for crystalline rock disposal to support GDSA | Describe DFN, reduced order models, colloid experiments supporting GDSA | 2019-05-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19LA010301021 | M4 | 1.08.01.03.01.02 | LANL | SF-19LA01030102 | Argillite Disposal R&D - LANL | Caporuscio, Florie | McMahon, Kevin | Argillite Disposal with cement Report | argillite disposal (with cement) R&D interim report | LANL Argillite disposal R&D Report | 2019-05-30 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M4SF-19LL010301042 supercedes M4SF-18LL010301042 | M4 | 1.08.01.03.01.04 | LLNL | SF-19LL01030104 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Code development in support of the SFWST Thermodynamic database | Code development in support of the SFWST Thermodynamic database | Report on water code development | 2019-05-31 |  | 2018-12-12 |  | 2019 | Complete | A Stand-Alone Fortran Code for Evaluating the IAPWS-95 Equation-of-State Model for Water | Wolery, Tom | LLNL | None | H2OI95_v1_Report.pdf
M3SF-19LB010308022 supercedes M3SF-18LB010308023 | M3 | 1.08.01.03.08.02 | LBNL | SF-19LB01030802 | Engineered Barrier System R&D - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL: FY19 Progress Report | Engineered Barrier System Research Activities at LBNL: FY19 Progress Report | Engineered Barrier System Research Activities at LBNL: FY19 Progress Report | 2019-05-31 |  | 2019-05-31 | This report summarizes LBNL’s work Engineered Barrier System R&D package. The research activities have focused on understanding and modeling the evolution of the EBS bentonite and the associated coupled processes and impacts of high temperature on parameters and processes relevant to performance of a crystalline and argillite repository. The objective of the research work is developing modeling capability for reliable assessment of these processes and ultimately supporting GDSA model with detailed coupled THMC process models. | 2019 | Complete | Engineered Barrier System Research Activities at LBNL: FY19 Progress Report | Liange Zheng Hao Xu, Benjamin Gilbert,Nithya Subramanian, Laura Lammers, Francis Claret, Stephane Gaboreau, Marco Voltolini, Alastair MacDowell, Harrison Lisabeth, Jonathan Ajo-Franklin | Liange Zheng | None | M3SF-19LB010308022 Final.pdf |  | Bentonite alteration, THMC, EBS, microscopic study, fundamental understanding
M4SF-19LA010303042 | M4 | 1.08.01.03.03.04 | LANL | SF-19LA01030304 | Salt International Collaborations - LANL | Stauffer, Philip | Stein, Emily | LANL Presentations to WM2019 | LANL Presentations to WM2019 | We will summarize our presentations and papers that will be presented at the Waste Management meeting WM2019 (International meeting). | 2019-05-31 |  |  | We prepared our presentations for WM2019 during Feb. | 2019 | On Schedule |  |  |  | None
M4SF-19LL010301082 supercedes M4SF-18LL010301082 | M4 | 1.08.01.03.01.08 | LLNL | SF-19LL01030108 | Argillite International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | Surface complexation and ion exchange database development phase 1: Clay minerals | Surface complexation and ion exchange database development phase 1: Clay minerals | Report on surface complexation/ion exchange database development with an initial focus on clay minerals | 2019-05-31 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19LL010302042 supercedes M4SF-18LL010302042 | M4 | 1.08.01.03.02.04 | LLNL | SF-19LL01030204 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Pu incorporation into reduced iron oxide phases | Pu incorporation into reduced iron oxide phases | report on Pu incorporation into reduced iron oxide phases | 2019-05-31 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19LL010302082 | M4 | 1.08.01.03.02.08 | LLNL | SF-19LL01030208 | Crystalline International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | International thermodynamics and surface complexation modeling activities | international thermodynamics and surface complexation modeling activities |  | 2019-05-31 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19SN010303035 | M4 | 1.08.01.03.03.03 | SNL | SF-19SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Salt-GDSA Integration | Salt-GDSA Integration | Salt-GDSA Integration | 2019-05-31 |  |  | on schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19LB010308061 | M3 | 1.08.01.03.08.06 | LBNL | SF-19LB01030806 | Engineered Barrier System International Collaborations - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19 progress report | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19 progress report | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19 progress report | 2019-06-14 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M2SF-19SN010305051 ULR. Predecisional Draft. | M2 | 1.08.01.03.05.05 | SNL | SF-19SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | Analysis of Solutions for DPC Disposal | Analysis of Solutions for Disposal of Spent Fuel in DPCs - Draft | Report describing goals, technical options, uncertainties, and management cases for DPC disposal. | 2019-06-19 |  |  | This effort is staffed and report prep. has begun. | 2019 | On Schedule |  |  |  | None
M4SF-19LB010302031 supercedes M4SF-18LB010302033 and M4SF-18LB010302073 | M4 | 1.08.01.03.02.03 | LBNL | SF-19LB01030203 | Crystalline Disposal R&D - LBNL | Zheng, Liange | McMahon, Kevin | LBNL Crystalline Disposal R&D in FY19 | LBNL Crystalline R&D progress: FY19 | This activity includes - Expanding pore scale modeling of gas bubble migration to better account for the long-term mass transfer between the clay matrix and fracture(s) - Laboratory and modeling studies on EDZ behavior in granitic rocks and shale. Induced damage in core samples will be examined for its geophysical (seismic velocities), AE signatures, and hydrological properties (permeability) Numerical modeling of the laboratory experiments will be conducted via discrete modeling of fracture growth. | 2019-06-21 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M4SF-19LB010305041 supercedes M4SF-18LB010305041 | M4 | 1.08.01.03.05.04 | LBNL | SF-19LB01030504 | Direct Disposal of Dual Purpose Canisters - LBNL | Rutqvist, Jonny | Freeze, Geoff | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | Geotechnical and performance assessment impacts of DPC disposal in various host rock environments | 2019-06-21 |  |  | On Schedule | 2019 | On Schedule |  |  |  | None
M4SF-18LA010305032 Not complete yet- Florie Caporuscio to send deliverable when published | M4 | 1.08.01.03.05.03 | LANL | SF-18LA01030503 | Direct Disposal of Dual Purpose Canisters - LANL | Caporuscio, Florie | Mackinnon, Robert | Experimental Determination of Solubility of Aluminum Boron Carbide | Final Report on Experimental Determination of Solubility of Aluminum Boron Carbide | Experimental Determination of Solubility of Aluminum Boron Carbide | 2019-06-28 |  |  |  | 2018 | Expected Late |  |  |  | None
M2SF-19SN010301051 | M2 | 1.08.01.03.01.05 | SNL | SF-19SN01030105 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Interim report 2019 | Evaluation of Spent Nuclear Fuel Dispositon in Clay-Bearing Rocks - 2019 Interim Report | Interim progress report provides description of R&D efforts on disposal in argillaceous rock for FY19. This include experimental and process model development efforts on the disposal of heat-generating spent fuel in clay-bearing rock. | 2019-06-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-19SN010302051 | M2 | 1.08.01.03.02.05 | SNL | SF-19SN01030205 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | FY19 Mid-Report on Spent Fuel Disposal in Crystalline Media | FY19 mid-year report on spent disposal in | The report will document all the work to be performed under the additional funding from the March 23rd Omnibus Bill for the crystalline work packages. | 2019-06-30 |  |  | On schedule | 2019 | On Schedule |  |  |  | None
M2SF-19SN010308042 supercedes M2SF-18SN010308044 | M2 | 1.08.01.03.08.04 | SNL | SF-19SN01030804 | Engineered Barrier System R&D - SNL | Matteo, Edward | McMahon, Kevin | Evaluation of Engineered Barrier Systems Mid-year Status Report | Evaluation of Engineered Barrier Systems Mid-year Status Report | Report on status of activities associated with FY18 funding. | 2019-06-30 |  |  | OK | 2019 | On Schedule |  |  |  | None
M4SF-19LA010304021 supercedes M3SF-18LA010304023 | M4 | 1.08.01.03.04.02 | LANL | SF-19LA01030402 | GDSA - Geologic Modeling - LANL | Perry, Frank | Stein, Emily | Prorgress report on development of geologic framework model capability to support GDSA | Prorgress report on development of geologic framework model capability to support GDSA | Report on progress in developing a geologic framework modeling capability for alternative geologic media. Information feeds to GDSA reference case. | 2019-07-26 |  | 2019-08-08 | on schedule | 2019 | Complete |  |  |  | None
M2SF-19SN010309013 | M2 | 1.08.01.03.09.01 | SNL | SF-19SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, David | McMahon, Kevin | Online Waste Library (OWL) and Waste Forms Characteristics Annual Report | Online Waste Library (OWL) and Waste Forms Characteristics Annual Report | new and updated GDSA simulations and analyses, with a focus on a generic bedded salt repository, including DPC disposal. | 2019-08-02 |  | 2019-08-02 |  | 2019 | Complete |  |  |  | None
M4SF-19SN010303064 | M4 | 1.08.01.03.03.06 | SNL | SF-19SN01030306 | Salt International Collaborations - SNL | Kuhlman, Kris | Stein, Emily | International Collaborations on Radioactive Waste Disposal Salt | FY19 International Collaborations on Radioactive Waste Disposal Salt | International Collaborations on Radioactive Waste Disposal Salt | 2019-08-02 |  | 2019-08-02 | on schedule | 2019 | Complete |  |  |  | None
M3SF-19LB010303023 supercedes M3SF-18LB010303023 | M3 | 1.08.01.03.03.02 | LBNL | SF-19LB01030302 | Salt Disposal R&D - LBNL | Rutqvist, Jonny | Stein, Emily | LBNL Salt Coupled THMC R&D Realted to Small Borehole Test | Salt Coupled THMC Processes Research Activities at LBNL: FY2019 Progress | Report on LBNL Salt Coupled THMC R&D Related to Small Borehole Test | 2019-08-16 |  | 2019-08-16 | On Schedule | 2019 | Complete |  |  |  | None
M4SF-19SN010307022 | M4 | 1.08.01.03.07.02 | SNL | SF-19SN01030702 | Disposal Research International Coordination - SNL | McMahon, Kevin | Birkholzer, Jens | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | Report on the Status of the SFWST Campaign International Activities in Disposal Research at SNL | This is input for the M2. It includes only the activities associated with SNL international coordination. International activities associated with the host-rock specific and EBS work packages will be forthcoming from those work packages. | 2019-08-16 |  | 2019-07-29 |  | 2019 | Complete |  |  |  | None
M4SF-19SN010308082 | M4 | 1.08.01.03.08.08 | SNL | SF-19SN01030808 | Engineered Barrier System International Collaborations - SNL | Matteo, Edward | McMahon, Kevin | FY19 Report on Activities for EBS International | Milestone to Report on Additional FY18 Activities for EBS Int'l | This report provides a description of key technical activities related to international collaborations associated with the EBS Work Package. | 2019-08-30 |  | 2019-08-30 | The M4 has been completed | 2019 | Complete | FY19 Report on Activities for EBS International | Edward N. Matteo | Edward N. Matteo | None
M3SF-19OR010305013 supercedes M3SF-18OR010305018 | M3 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results including misload analysis results into the existing living document. | 2019-08-30 |  | 2019-08-30 |  | 2019 | Complete |  |  |  | None
M4SF-19OR010304072 | M4 | 1.08.01.03.04.07 | ORNL | SF-19OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | ORNL Input to GDSA Repository Systems Analysis FY19 Update | ORNL Input to GDSA Repository Systems Analysis FY19 Update | ORNL input on New and updated GDSA simulations and analyses, with a focus on repository DPC disposal. | 2019-08-30 |  | 2019-09-30 |  | 2019 | Complete |  |  |  | None
M4SF-19LA010310012 | M4 | 1.08.01.03.10.01 | LANL | SF-19LA01031001 | Planning for URL - LANL | Stauffer, Philip | Stein, Emily | LANL Contributions to Technical Support for Underground Research Laboratory Activities | LANL Contributions to Technical Support for Underground Research Laboratory Activities | Review of international URLs from the perspective of considering operational impacts that a URL may have on long-term performance. | 2019-08-31 |  | 2019-09-30 | Due to funding being held back, this task was not yet created at LANL. We have been in contact with SNL and LBNL on aspects of this work. | 2019 | Complete |  |  |  | None
M3SF-19SN010303033 | M3 | 1.08.01.03.03.03 | SNL | SF-19SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Salt Heater Test: FY19 Progress | Salt Heater Test: Update | Status update on salt heater test implementation | 2019-09-02 |  | 2019-08-30 | on schedule | 2019 | Complete |  |  |  | None
M2SF-19SN010304041 supercedes M3SF-18SN010304063 Notes: Per Matt Brainard- Marked complete in PICS:NE as of 9/16/2019. Milestone will be uploaded after Sandia formal review. | M2 | 1.08.01.03.04.04 | SNL | SF-19SN01030404 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | GDSA Framework Development and Process Model Integration | Status of Disposal Research | Development of GDSA Framework and integration of process models in PA and the safety case | 2019-09-16 |  | 2019-09-16 | on schedule | 2019 | Complete |  |  |  | None
M3SF-19SN010305071 | M3 | 1.08.01.03.05.07 | SNL | SF-19SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | Freeze, Geoff | DPC Criticality Simulation Preliminary Phase | Preliminary Multiphysics Simulations for Disposal Criticality Scenarios | This report documents progress in modeling the degradation of commercial spent nuclear fuel and dual-purpose canister baskets, in response to corrosion once waste packages in a repository are breached and admit ground water, and to ground motion once the fuel assemblies and baskets are degraded. It is intended that degraded fuel/basket configurations will be evaluated for nuclear reactivity, as the configurations evolve with time over many thousands of years. The capabilities demonstrated may also be used in the future to simulate the behavior of disposal criticality control features added to DPC baskets or fuel assemblies. | 2019-09-18 |  | 2019-09-18 | Reviewed by Mike Nole/SNL; programmatic R&A for DOE review prior to publication. | 2019 | Complete | DPC Criticality Simulation Preliminary Phase: Fuel/Basket Degradation Models | Hardin,Ernest | Hardin,Ernest | None | Fuel & Basket Modeling M3 18Sept19 Final.pdf
M3SF-19OR0103050117 | M3 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | DPC filler simulation and demonstration progress report | DPC filler simulation and demonstration progress report | This report will document the filler simulation and experimental validation progress made at ORNL by end of FY19. The report will also document the planned pipe experiment and data analysis. | 2019-09-20 |  | 2019-09-20 |  | 2019 | Complete |  |  |  | None
M3SF-19OR010305015 supercedes MSF-18OR0103050110 | M3 | 1.08.01.03.05.01 | ORNL | SF-19OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Scaglione, John | Freeze, Geoff | Initial Neutronics and Thermal-Hydraulic Coupling for Spent Nuclear Fuel Canister | Initial Neutronics and Thermal-Hydraulic Coupling for Spent Nuclear Fuel Canister | This deliverable captures the Multiphysics criticality excursion consequence analysis methodology status and reports path forward. | 2019-09-20 |  | 2019-09-20 |  | 2019 | Complete |  |  |  | None
M2SF-19LB010307012 | M2 | 1.08.01.03.07.01 | LBNL | SF-19LB01030701 | Disposal Research International Coordination - LBNL | Birkholzer, Jens | Birkholzer, Jens | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | This report gives a comprehensive overview of these initiatives and describes the various opportunities arising from DOE’s membership in international initiatives as well DOE's partnership with individual international disposal program. The report also provides an overview of the various R&D activities conducted in FY19 as related to international collaboration. | 2019-09-27 |  |  | ON SCHEDULE | 2019 | On Schedule |  |  |  | None
M3SF-19PN010308033 | M3 | 1.08.01.03.08.03 | PNNL | SF-19PN01030803 | Engineered Barrier System R&D - PNNL | Buck, Edgar | McMahon, Kevin | Annual Report on EBS Activities at PNNL | Annual report on EBS Activities at PNNL | Summary of work conduced on the EBS effort at PNNL. Study will include work on in-situ methods for monitoring corrosion and comparison to models. | 2019-09-27 |  | 9/?/2019 | On schedule. | 2019 | Complete |  |  |  | None
M3SF-19SN010304052 | M3 | 1.08.01.03.04.05 | SNL | SF-19SN01030405 | GDSA - Repository Systems Analysis - SNL | Sevougian, David | Stein, Emily | GDSA Repository Systems Analysis FY19 Update | GDSA Repository Systems Analysis Update | New and updated GDSA simulations and analyses, with a focus on a generic bedded salt repository, including DPC disposal. | 2019-09-27 |  | 2019-09-27 | Plan to complete on time. | 2019 | Complete |  |  |  | None
M4SF-19LB010310021 | M4 | 1.08.01.03.10.02 | LBNL | SF-19LB01031002 | Planning for URL - LBNL | Dobson, Patrick | Stein, Emily | 1.08.01.03.10 - Technical Support for Underground Research Laboratory Activities | Review of Impacts of Underground Research Laboratory Activities on Long-Term Performance | A level 4 milestone report on this activity will be generated in August 2019 - this will feed into a level 3 milestone report written by SNL in September | 2019-09-30 |  | 2019-09-30 | Underground research laboratories (URLs) are commonly used to help characterize and assess the suitability of a site for geologic radioactive waste disposal. One concern is whether the presence of a URL could affect the long-term performance of a co-located repository. This report (together with a companion study conducted by LANL) provides insights obtained from a literature review of existing evaluations of the potential impacts that URLs might pose to repository waste isolation capabilities. This report summarizes the results of these impact studies, and provides some general observations that could be implemented for current and future site-specific URLs. | 2019 | On Schedule | 1.08.01.03.10 - Technical Support for Underground Research Laboratory Activities | Patrick Dobson | Patrick Dobson | None | M4SF-19LB010310021 FINAL V2.pdf |  | Underground research laboratories (URLs), site characterization, performance assessment
M4SF-19PN010308072- - Reached out to Brady Hanson for report supersedes M4SF-18PN010308074 and M4SF-18PN010308073 | M4 | 1.08.01.03.08.07 | PNNL | SF-19PN01030807 | Engineered Barrier System International Collaborations - PNNL | Hanson, Brady | McMahon, Kevin | PNNL R&D Input to International Collaboration | PNNL R&D Input to International Collaborations | Results of R&D and other interactions with international collaborators. | 2019-09-30 | 2019-11-01 |  |  | 2019 | Delayed |  |  |  | None
M2SF-19SN010305021 supercedes M3SF-18SN010305029 | M2 | 1.08.01.03.05.02 | SNL | SF-19SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | Freeze, Geoff | Accelerated Testing of Selected Filler Compositions | Results from Accelerated Testing of Selected DPC Fillers | Select one or more cement compositions for accelerated testing, optimizing the slurry recipe, and emphasizing evaluation of injectability, slurry pH, thermal setting, dewatering, and shrinkage. | 2019-09-30 |  | 2019-09-26 |  | 2019 | Complete |  |  |  | None
M2SF-19SN010304031 | M2 | 1.08.01.03.04.03 | SNL | SF-19SN01030403 | GDSA - Uncertainty and Sensitivity Analysis Methods - SNL | MacKinnon, Robert | Stein, Emily | Status Report on UQ/SA Tools in GDSA Framework | Status Report on UQ/SA Tools in GDSA Framework | M3 report documenting and demonstrating newly developed UQ/SA tools and the progress of UQ/SA tools during the UFD and SFWST campaigns | 2019-09-30 |  | 2019-09-30 | Status report is on schedule | 2019 | Complete |  |  |  | None
M3SF-19LA010303014 | M3 | 1.08.01.03.03.01 | LANL | SF-19LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | Stein, Emily | 2019 LANL Experiments and Simulations in Support of Salt R&D | 2019 LANL Experiments and Simulations in Support of Salt R&D | 2019 LANL Experiments and Simulations in Support of Salt R&D | 2019-09-30 |  | 2019-09-30 | We continue to build components of the borehole heater test. | 2019 | Complete |  |  |  | None
M3SF-19SN010303066 | M3 | 1.08.01.03.03.06 | SNL | SF-19SN01030306 | Salt International Collaborations - SNL | Kuhlman, Kris | Stein, Emily | Proceedings for US/German Workshop | Proceedings of Tenth US/German Workshop on Salt Repository Research, Design and Operations | Organize May 2019 workshop and prepare proceedings. | 2019-09-30 |  | 2019-08-19 | work will begin soon. | 2019 | Complete |  |  |  | None
M3SF-19SN010310032 | M3 | 1.08.01.03.10.03 | SNL | SF-19SN01031003 | Planning for URL - SNL | Kuhlman, Kris | Stein, Emily | Assessment of possible impacts of URL operation on repository long-term performance | Assessment of possible impacts of URL operation on repository long-term performance | Assessment of possible impacts of URL operation on repository long-term performance | 2019-09-30 |  | 2019-09-30 | now that FY19 funding has arrived, this work has begun and will be on schedule | 2019 | Complete |  |  |  | None
M4SF-19AN010301013 | M4 | 1.08.01.03.01.01 | ANL | SF-19AN01030101 | Argillite Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Fuel Matrix Degradation Model Development Update | Fuel Matrix Degradation Model Experimental Validation Update |  | 2019-09-30 |  | 2019-09-30 |  | 2019 | Complete |  |  |  | None
M4SF-19AN010302013 | M4 | 1.08.01.03.02.01 | ANL | SF-19AN01030201 | Crystalline Disposal R&D - ANL | Jerden, James | McMahon, Kevin | Fuel Matrix Degradation Model Development Update | Fuel Matrix Degradation Model Experimental Validation Update | Fuel Matrix Degradation Model Development Update | 2019-09-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M3SF-19LB010308025 | M3 | 1.08.01.03.08.02 | LBNL | SF-19LB01030802 | Engineered Barrier System R&D - LBNL | Zheng, Liange | McMahon, Kevin | Engineered Barrier System Research Activities at LBNL: FY19-FY20 Progress Report | Engineered Barrier System Research Activities at LBNL: FY19-FY20 Progress Report | Engineered Barrier System Research Activities at LBNL: FY19-FY20 Progress Report | 2019-10-11 |  | 2019-10-11 |  | 2019 | Complete |  |  |  | None
M4SF-20SN010305063 | M4 | 1.08.01.03.05.06 | SNL | SF-20SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Preliminary Investigation of Criticality Termination Processes in Disposed-of DPCs | Preliminary Investigation of Criticality Termination Processes in Disposed-of DPCs | Perform a preliminary investigation of the processes that could terminate a critical event in a disposed-of DPC. Identify areas for further research. | 2019-11-22 |  | 2019-11-22 02:00 | This report documents a study that examines the processes that could permanently terminate a critical event in a disposed of DPC. | 2020 | Complete | Permanent Criticality Termination Processes in Disposed DPCs | Halim Alsaed | Halim Alsaed | None | Criticality Termination Report NE Format 061220_SAND.pdf |  | DPC direct disposal, postclosure criticality
M4SF-20SN010101021 | M4 | 1.08.01.01.01.02 | SNL | SF-20SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | Conduct KM Focus Group | Focus Group Report | Conduct Knowledge Management Focus Group with Staff | 2019-12-20 |  | 2019-12-20 02:00 | Focus Group documentation completed on 12/20/2019 with attached report. | 2020 | Complete | Managing and Preserving Tacit Knowledge within the Nuclear Energy Fuel Cycle Program: Lessons Learned from Focus Group Discussions | Janette Meacham | Evaristo J. Bonano | None | 2019-12-01_KM_Focus Group Report_1091491.docx
M4SF-19IN010304012 | M4 | 1.08.01.03.04.01 | INL | SF-19IN01030401 | GDSA - Geologic Modeling - INL | Russell, Glenn | Stein, Emily | Support for Geologic Modeling | GDSA – Geologic Modeling – INL – Web Visualization and Innovations in Interactive Subsurface Profiling Tools | Support web visualization and user interaction with geologic data and modeling for the Regional Geologic Framework GIS Database and Global Survey web map applications. | 2019-12-20 |  | 2019-07-12 | On schedule | 2019 | Complete |  |  |  | None
M2SF-20SN010305061 Supercedes: M2SF-19SN010305062 same as M2SF-18SN010305062 | M2 | 1.08.01.03.05.06 | SNL | SF-19SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Preliminary Probabilistic/Regulatory Analysis of Postclosure DPC Criticality Consequences | Preliminary Probabilistic Criticality Consequence Assessment for Geologic Disposal of Spent Fuel in DPCs | Probabilistic PA-style analysis of criticality consequences focusing on risk, including consequences from individual events (e.g., thermal and fission product inventory), and factors controlling event incidence (e.g., frequency and recurrence). | 2019-12-31 |  | 2019-12-21 | This report documents a preliminary study of the consequences on repository performance of a postclosure critical event in a DPC. | 2020 | Complete | Preliminary Analysis of Postclosure DPC Criticaltiy Consequences | Laura Price, Halim Alsaed, Amanda Barela, Pat Brady, Fred Gelbard, Mike Gross, Michael NOle, Jeralyn Prouty, Kaushik Banerjee, S. Bhatt, Greg Davidson, Zufeng Fang, Rob Howard, S. Johnson, Scott Painter, Matthew Swinney, and E. Gonzalez | Laura Price | None | Prelim Analysis Postclosure DPC Crit Cons.pdf |  | postclosure criticality, DPC disposal
M2SF-20SN010308043 Supercedes: M2SF-19SN010308043 | M2 | 1.08.01.03.08.04 | SNL | SF-19SN01030804 | Engineered Barrier System R&D - SNL | Matteo, Edward | McMahon, Kevin | Evaluation of Engineered Barrier Systems FY19 Report | Evaluation of Engineered Barrier Systems FY19 Report | Evaluation of Engineered Barrier Systems FY19 Report | 2020-01-31 |  | 2020-01-30 | This report describes research and development (R&D) activities conducted during fiscal year 2019 (FY19) specifically related to the Engineered Barrier System (EBS) R&D Work Package in the Spent Fuel and Waste Science and Technology (SFWST) Campaign supported by the United States (U.S.) Department of Eneregy (DOE). The R&D activities focus on understanding EBS component evolution and interactions within the EBS, as well as interactions between the host media and the EBS. A primary goal is to advance the development of process models that can be implemented directly within the Genreric Disposal System Analysis (GDSA) platform or that can contribute to the safety case in some manner such as building confidence, providing further insight into the processes being modeled, establishing better constraints on barrier performance, etc. The FY19 EBS activities involved not only modeling and analysis work, but experimental work as well. | 2020 | Complete | Evaluation of Engineered Barrier Systems FY19 Report | Edward N. Matteo | Edward N. Matteo | None | M2SF-20SN010308043.pdf
M3SF-20SN010303034 | M3 | 1.08.01.03.03.03 | SNL | SF-20SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Update Project Plan | Salt Heater Test Project Plan | Update project plan document at beginning of BATS test to reflect as-built status. | 2020-01-31 |  | 2020-01-30 02:00 | milestone completed 1 day early | 2020 | Complete | Project Plan: Salt in situ Heater Test | Kris Kuhlman (SNL) | Kris Kuhlman (SNL) | None | SAND2020-1251R_salt-heater-test-project-plan-fy20_08.pdf | salt; BATS; WIPP; heater test | salt; BATS; WIPP; heater test
M4SF-19SN010101022- Superseded by M4SF-20SN010101022 | M4 | 1.08.01.01.01.02 | SNL | SF-20SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | KM Workshop | Briefing on KM Workshop | Plan and deliver KM Workshop | 2020-01-31 |  | 2020-01-10 02:00 | Workshops were conducted at Sandia on schedule. | 2020 | Complete |  | Janette Meacham | Janette Meacham | None | NEFC KM Workshop Agenda Final.pdf
M3SF-20PN010101041- Document will not be uploaded to PICS. Contact Mark Nutt. | M3 | 1.08.01.01.01.04 | PNNL | SF-20PN01010104 | Electromagnetic Technologies Report - PNNL | Nutt, Mark | Swift, Peter | Draft Report on Electromagnetic Technologies for the Neutralization of Radioactive Wastes | Draft Report on Electromagnetic Technologies for the Neutralization of Radioactive Wastes | The deliverable will be a draft report to DOE that evaluates the scientific basis for the technology, potential effects on U.S. nuclear waste and storage, potential benefits to the nuclear power industry, and any implications for nuclear security. | 2020-02-28 |  | 2020-02-27 03:00 | This draft report was developed in response to the direction provided in the Appropriations Committees’ Conference Report accompanying Public Law 116-94, (Further Consolidated Appropriations Act, 2020) which stipulated: | 2020 | Complete | Electromagnetic Technologies for the Neutralization of Radioactive Wastes |  |  | None | Document not up-loaded to PICS-NE and is being maintained limited distribution. Please contact Mark Nutt.
M4SF-19SN010101023- Superseded by M4SF-20SN010101023 | M4 | 1.08.01.01.01.02 | SNL | SF-20SN01010102 | Knowledge Management - SNL | Meacham, Janette | Swift, Peter | Conduct Deep Dives | Deep Dive Conducted | Conduct Deep Dive information sessions as a follow-on to the knowledge collection from Workshops | 2020-02-28 |  | 2020-02-07 02:00 | Deep Dives were conducted on January 28 and 29 with documentation complete on 2/7/20 | 2020 | Complete |  | Janette Meacham |  | None | NEFC KM Deep Dives Agenda.pdf
M3SF-20SN010101031- Draft. Will not be uploaded to PICS. | M3 | 1.08.01.01.01.03 | SNL | SF-20SN01010103 | Innovative Options Report - SNL | Swift, Peter | Swift, Peter | Report on Innovative Options for Permanent Disposal of High-Level Radioactive Waste and Spent Nuclear Fuel | Report on Innovative Options for Permanent Disposal of High-Level Radioactive Waste adn Spent Nuclear Fuel | The deliverable will be a draft report to DOE summarizing past work on alternative options for permanent disposal of spent nuclear fuel and high-level radioactive waste. | 2020-03-13 |  | 2020-03-04 02:00 | "The Department is directed to provide to the Committees on Appropriations of both Houses of Congress not later than 180 days after enactment of this Act a report on new electromagnetic technologies for the neutralization of radioactive wastes, including an evaluation of the scientific basis for the technology, potential effects on U.S. nuclear waste and storage, potential benefits to the nuclear power industry, and any implications for nuclear security.” | 2020 | Complete | Innovative Options for the Disposition of High-Level Waste and Spent Nuclear Fuel Review Draft | Peter Swift | Peter Swift | None | Draft text delivered to NE-81 for federal review and revision. Because of draft nature of the work product, a copy has not been uploaded to PICS.
M3SF-20OR010304072 | M3 | 1.08.01.03.04.07 | ORNL | SF-20OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | GDSA Waste Package Reference Physical and Thermal Characteristics | GDSA waste package reference physical and thermal characteristics | Develop a reference documenting waste package physical and thermal characteristics for a range of waste package sizes to include small packages 4 PWR/9 BWR through 37 PWR/89 BWR. | 2020-03-31 | 2020-07-31 | 2020-07-13 | The DOE Spent Fuel and Waste Sciences and Technologies (SFWST) Campaign R&D Roadmap Update, M2SF-19SN010304042, Rev. 1, SAND2019-9033, identifies “development of new waste package concepts and models for evaluation of waste package performance for long-term disposal” and “source term development with and without criticality” as high-priority R&D activities. This document provides information supporting both of these activities. | 2020 | Completed Late | GDSA Waste Package Reference Physical and Thermal Characteristics | Abi Adeniyi | Abi Aneniyi | None | GDSA Waste Package Report_13Jul2020.pdf M3SF-20OR010304072_GDSA Waste Package Report_Rev01.pdf |  | waste package
M3SF-19SN010301092- Reached out to Carlos Jove-Colon for document | M3 | 1.08.01.03.01.09 | SNL | SF-19SN01030109 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | McMahon, Kevin | International Collaborations Activities on Disposal in Argillite R&D: Bentonite Barrier Characterization Studies and Modeling Investigations | International Collaborations Activities on Disposal in Argillite R&D: Bentonite Barrier Characterization Studies and Modeling Investigations |  | 2020-03-31 |  |  |  | 2019 | On Schedule |  |  |  | None
M3SF-20SN010301091 | M3 | 1.08.01.03.01.09 | SNL | SF-20SN01030109 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | Camphouse, Chris | International Collaborations Activities on Disposal in Argillite R&D: Bentonite Barrier Characterization Studies and Modeling Investigations | International Collaborations Activities on Disposal in Argillite R&D: Bentonite Barrier Characterization Studies and Modeling Investigations | Interim report of international collaborations in the disposal in argillite work package related to characterization, modeling, studies experimental on bentonite barrier material. Also, coupled process modeling of URL experiments (GREET) at the Mizunami site, Japan. | 2020-04-22 |  | 2020-05-01 02:00 | Deliverable on International Collaborations R&D Activities related to Disposal in Argillite work package (interim report) | 2020 | Completed Late | International Collaborations Activities on Disposal in Argillite R&D: Bentonite Barrier Characterization Studies and Modeling Investigations | Carlos F. Jove Colon | Carlos F. Jove Colon | None | M3SF-20SN010301091_SNL_Arg_Int_DRAFT_RA_rev6.pdf |  | Argillite, International Collaborations, Bentonite, Engineered Barrier
M4SF-20PN010802092 | M4 | 1.08.01.08.02.09 | PNNL | SF-20PN01080209 | Quality Assurance - PNNL | Wilson, Emily | Brainard, Matt | PNNL SFWD Quality Audit | PNNL SFWD Quality Audit | Completion of PNNL SFWD Quality Audit with a final report to be provided to the Federal Manager. | 2020-04-30 | 2020-07-31 06:00 | 2020-07-29 03:00 | An email transmitting the milestone report titled, 2020 PNNL SFWD QA Assessment 7-28-2020 and confirming its completion was sent to the FM on July 29, 2020. | 2020 | Completed Late | 2020 PNNL SFWD QA Assessment 7-29-20 | Emily Wilson | Emily Wilson | None | 2020 PNNL SFWD QA Assessment 7-29-20.pdf |  | Assessment, Quality Audit
M4SF-20SN010305051 | M4 | 1.08.01.03.05.05 | SNL | SF-20SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | DPC Modification Evaluation | Draft Options for Modification of Future DPC Fuel and Baskets | Evaluate possible modifications to future DPCs or fuel prior to loading, for postclosure criticality control, particularly for BWR fuel. | 2020-04-30 |  | 2020-04-30 02:00 | Approved for unclassified release (not for public distribution) | 2020 | Complete | Draft Options for Future Fuel/Basket Modifications for DPC Disposition | Hardin,Ernest | Hardin,Ernest | None | DPC F&B mod eval April 2020 Final.pdf |  | postclosure criticality;dual-purpose canisters;geologic disposal
M4SF-20OR010305092 | M4 | 1.08.01.03.05.09 | ORNL | SF-20OR01030509 | Neutron Absorber Evaluation - ORNL | Chatzidakis, Stylianos | Freeze, Geoff | Draft Advanced Manufacturing Neutron Absorber Specification | Draft Advanced Manufacturing Neutron Absorber Specification | Draft Advanced Manufacturing Neutron Absorber Specification suitable as an initial reference for further development and testing. | 2020-06-01 |  | 2020-06-01 | This report describes the development and selection of Additive Manufacturing (AM) – 3D printing procedures for Borated Stainless Steel (BSS), a potential Neutron Absorber Material that could be introduced in future canisters to provide long-term performance in a range of disposal environments. The report summarizes the main BSS properties, currently available AM capabilities at ORNL, and proposed procedures for manufacturing BSS using AM at the Manufacturing Demonstration Facility at Oak Ridge National Laboratory. Powder bed fusion was selected as optimal 3D printing process and 304B4 Grade A BSS (1.0-1.24% boron content) powder has been ordered (lead time 6-8 weeks). 3D printing of coupons is expected to start once powder is received early August. In addition to 304B4 BSS, conventional 304 stainless-steel coupons will be produced as a benchmark for comparison. The coupons will be delivered to Idaho National Laboratory (INL) for subsequent corrosion testing. | 2020 | Complete | Advanced Manufacturing Neutron Absorber Specification | Stylianos Chatzidakis | Stylianos Chatzidakis | None | M4SF-20OR010305092_Advanced Manufacturing Neutron Absorber Specification_06012020_1700.pdf
M4SF-20IN010305081 | M4 | 1.08.01.03.05.08 | INL | SF-20IN01030508 | Neutron Absorber Evaluation - INL | Jarrell, Josh | Freeze, Geoff | Develop test plan for neutron absorber corrosion characterization | Develop Test Plan for Neutron Absorber Corrosion Characterization | Develop test plan for neutron absorber corrosion characterization at INL based on input from DOE sponsors, ORNL, and SNL. | 2020-06-01 |  | 2020-06-01 02:00 | Milestone completed on schedule and submitted via email. | 2020 | Complete | Neutron Absorber Material Test Plan | Tedd Lister | Tedd Lister | None | 2020-06_FY20-NAM-test-plan_PLN-6095_Lister_final.pdf
M3SF-20LB010308062 Supercedes: M3SF-19LB010308064 | M3 | 1.08.01.03.08 | LBNL | SF-20LB01030806 | Engineered Barrier System International Collaborations - LBNL | Zheng, Liange | Camphouse, Chris | Engineered Barrier System Research Activities at LBNL: FY2020 progress report | Engineered Barrier System Research Activities at LBNL via international collaboration: FY19-FY20 progress report | The report provides a summary of LBNL’s research in understanding and modeling the evolution of the EBS bentonite. Specifically, the report documents the following research activities: – Progress in upgrading THMC simulator and application of THMC for generic argillite repository – Sorption and diffusion experiments on bentonite samples – Progress on an integrated set of experiments, molecular simulations, and thermodynamic modeling to develop a predictive understanding of ion exchange-driven swelling and collapse of montmorillonite clay. – A research plan for a newly added research activity on the development and validation of a microscopic model of coupled transport processes in bentonite and using this model to determine cost effective augmentation strategies to increase the bulk thermal conductivity of hydrated bentonite. – Progress in using coupled THMC modeling for understanding the THMC evolution of bentonite in FEBEX-DP. – Numerical modeling in support of the HotBENT field test – A high tempereature benchtop-scale laboratory experiment, HotBENT-Lab, which provides a laboratory analog of the HotBENT experiment, to obtain a more comprehensive set of characterization and monitoring measurements. | 2020-06-04 |  | 2020-06-04 | This report summarizes LBNL’s work in packages “SF-20LB01030802 Engineered Barrier System R&D – LBNL” and “SF-20LB01030806 Engineered Barrier System International Collaborations – LBNL”. The research activities have focused on understanding and modeling the evolution of the EBS bentonite and the associated coupled processes and impacts of high temperature on parameters and processes relevant to performance of a crystalline and argillite repository. The objective of the research work is developing modeling capability for reliable assessment of these processes and ultimately supporting GDSA model with detailed coupled THMC process models. | 2020 | Complete | Engineered Barrier System Research Activities at LBNL: FY2020 progress report | Liange Zheng¬, Hao Xu, Benjamin Gilbert, Nithya Subramanian, Laura Lammers, Peter Nico, Patricia Fox, Christophe Tournassat, Michael Whittaker, Sharon Borglin, Yuxin Wu, Chun Chang, Chunwei Chou, Tim Kneafsey | LianGe Zheng | None | MS3F-20LB010308062 FINAL.pdf |  | Bentonite alteration, THMC, EBS, numerical modeling, fundamental understanding
M4SF-20AN010301013 | M4 | 1.08.01.03.01.01 | ANL | SF-20AN01030101 | Argillite Disposal R&D - ANL | Jerden, James | Camphouse, Chris | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activities | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activitie | This report presents results from electrochemical experiments conducted to quantify the corrosion rates of the four most abundant alloys that make up the internal components of a typical spent fuel waste package (316 stainless steel, carbon steel, and aluminum alloy and Zircaloy-4) at several pH values and chloride concentrations. These rates are used to determine the amount of hydrogen gas generated during anoxic corrosion and to parameterize a prototype in-package chemistry (IPC) model that has been integrated with the fuel matrix degradation (FMD) model. The combined model provides spent fuel degradation rates over a range of Eh, pH and chemical conditions relevant for argillite and crystalline rock repository environments. | 2020-06-08 |  | 2020-06-08 01:00 | Completed level 4 milestone report. The report discusses our electrochemical corrosion data sets for 316SS, C-steel, Zircaloy and Boral and presents new model results that quantify the implications of our data on in package chemistry and spent fuel degradation. | 2020 | Complete | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activities | James Jerden | James Jerden | None | Argonne_2020_M4SF-20AN010301013.pdf |  | Spent Fuel Degradation, Alloy Corrosion, In Package Chemistry, Source Term
M4SF-20AN010302013- Same deliverable report as M4SF-20AN010301013 | M4 | 1.08.01.03.02.01 | ANL | SF-20AN01030201 | Crystalline Disposal R&D - ANL | Jerden, James | Camphouse, Chris | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activities | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activities | This report presents results from electrochemical experiments conducted to quantify the corrosion rates of the four most abundant alloys that make up the internal components of a typical spent fuel waste package (316 stainless steel, carbon steel, and aluminum alloy and Zircaloy-4) at several pH values and chloride concentrations. These rates are used to determine the amount of hydrogen gas generated during anoxic corrosion and to parameterize a prototype in-package chemistry (IPC) model that has been integrated with the fuel matrix degradation (FMD) model. The combined model provides spent fuel degradation rates over a range of Eh, pH and chemical conditions relevant for argillite and crystalline rock repository environments. | 2020-06-08 |  | 2020-06-08 01:00 | Completed level 4 milestone report. The report discusses our electrochemical corrosion data sets for 316SS, C-steel, Zircaloy and Boral and presents new model results that quantify the implications of our data on in package chemistry and spent fuel degradation. | 2020 | Complete | Results from Fuel Matrix Degradation Model Parameterization Experiments and Model Development Activities | James Jerden | James Jerden | None | Argonne_2020_M4SF-20AN010301013.pdf | Spent Fuel Degradation, Alloy Corrosion, In Package Chemistry, Source Term | Spent Fuel Degradation, Alloy Corrosion, In Package Chemistry, Source Term
M3SF-20IN010304011 | M3 | 1.08.01.03.04.01 | INL | SF-20IN01030401 | GDSA - Geologic Modeling - INL | Russell, Glenn | Stein, Emily | Support for Geologic Modeling | M3 - Mid-Year Summary Report | M3 Mid-Year Milestone Report on application development. | 2020-06-12 |  | 2020-06-29 02:00 | Milestone complete 6/29/20. | 2020 | Completed Late | GDSA – Geologic Modeling – INL – Web Visualization in Interactive Subsurface Profiling Tools | Glenn Russell | Glenn Russell | None | M3SF-20IN010304011-SFWD-GDSA-GeologicModeling-INL.pdf
M4SF-20LL010301042 | M4 | 1.08.01.03.01.04 | LLNL | SF-20LL01030104 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | Camphouse, Chris | Deliver updated thermodynamic database for use in GDSA | Updated thermodynamic database for use in GDSA | This progress report (Level 4 Milestone Number M4SF-20LL010301042) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Argillite Activity Number SF-20LL010301041. | 2020-06-15 |  | 2020-07-09 03:00 | This progress report (Level 4 Milestone Number M4SF-20LL010301042) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Argillite Activity Number SF-20LL010301041. LLNL is leading efforts in the development of thermodynamic databases in support of the Spent Fuel and Waste Science Technology (SFWST) program. Thermodynamic models provide the basis for understanding the stability of solid phases and speciation of aqueous species and modeling the evolution of repository conditions. The LLNL effort is being performed in coordination with other US database development efforts. The effort includes a review of available thermochemical databases and a path forward for database integration. International coordination with the NEA-TDB is supported through crystalline international work package. | 2020 | Completed Late | M4SF-20LL010301042: Updated Thermodynamic Database for Use in Generic Disposal System Assessment | T. Wolery | M. Zavarin | None | M4SF-20LL010301042.pdf |  | Thermodynamics, database
M4SF-20LL010301082 | M4 | 1.08.01.03.01.08 | LLNL | SF-20LL01030108 | Argillite International Collaborations - LLNL | Zavarin, Mavrik | Camphouse, Chris | Deliver Sorption Database and Model for GDSA | Sorption Database and Model for GDSA | This progress report (Level 4 Milestone Number M4SF-20LL010301082) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Argillite International Collaborations Activity Number Activity SF-20LL010301081. | 2020-06-15 |  | 2020-07-09 03:00 | This progress report (Level 4 Milestone Number M4SF-20LL010301082) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Argillite International Collaborations Activity Number Activity SF-20LL010301081. The activity is focused on our long-term commitment to engaging our partners in international nuclear waste repository research. The focus of this milestone is surface complexation model international collaborations. Specifically, we are developing a database framework for Spent Fuel and Waste and Science Technology (SFWST) that is aligned with the Helmholtz Zentrum Dresden Rossendorf (HZDR) sorption database development group in support of the database needs of the SFWST program. | 2020 | Completed Late | M4SF-20LL010301082-Sorption Database and Model for Generic Disposal System Assessment | M. Zavarin | M. Zavarin | None | M4SF-20LL010301082.pdf |  | Sorption, database
M4SF-20LL010302042 | M4 | 1.08.01.03.02.04 | LLNL | SF-20LL01030204 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | Camphouse, Chris | Deliver process model for radionuclide incorporation into corrosion products | Process model for radionuclide incorporation into corrosion products | This progress report (Level 4 Milestone Number M4SF-20LL010302042) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Crystalline Activity Number SF-20LL010302041. | 2020-06-15 |  | 2020-07-09 03:00 | This progress report (Level 4 Milestone Number M4SF-20LL010302042) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Crystalline Activity Number SF-20LL010302041. The research is focused on actinide and radionuclide sequestration in steel corrosion products. | 2020 | Completed Late | M4SF-20LL010302042: Process Model for Radionuclide Incorporation into Corrosion Products | E. Balboni | M. Zavarin | None | M4SF-20LL010302042.pdf |  | Corrosion, iron oxide
M4SF-20LL010302082 | M4 | 1.08.01.03.02.08 | LLNL | SF-20LL01030208 | Crystalline International Collaborations - LLNL | Zavarin, Mavrik | Camphouse, Chris | Comprehensive NE thermodynamic database for GDSA | NE thermodynamic database and relationship to other international database development efforts | This progress report (Level 4 Milestone Number M4SF-20LL010302082) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Crystalline International Collaborations Activity Number SF-20LL010302081. | 2020-06-15 |  | 2020-07-09 03:00 | This progress report (Level 4 Milestone Number M4SF-20LL010302082) summarizes research conducted at Lawrence Livermore National Laboratory (LLNL) within the Crystalline International Collaborations Activity Number SF-20LL010302081. The activity is focused on our long-term commitment of engaging our partners in international nuclear waste repository research. This includes participation in the Nuclear Energy Agency Thermochemical Database (NEA TDB) Project (Cindy Atkins-Duffin) and development of methodologies for integrating US and international thermodynamic databases for use in SFWST Generic Disposal System Assessment (GDSA) efforts. | 2020 | Completed Late | M4SF-20LL010302082- Thermodynamic Database for Generic Disposal System Assessment | C. Atkins-Duffin | M. Zavarin | None | M4SF-20LL010302082.pdf
M4SF-20LL010302042- No matching records found in PICS Supercedes: M4SF-19LL010302043 | M4 | 1.08.01.03.02.04 | LLNL | SF-19LL01030204 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Deliver process model for radionuclide incorporation into corrosion products | Process model for radionuclide incorporation into corrosion products |  | 2020-06-15 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20LL010302082- No matching records found in PICS Supercedes: M4SF-19LL010302083 | M4 | 1.08.01.03.02.08 | LLNL | SF-19LL01030208 | Crystalline International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | Comprehensive NE thermodynamic database for GDSA | NE thermodynamic database and relationship to other international database development efforts |  | 2020-06-15 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20LL010301042 Supercedes: M4SF-19LL010301043 | M4 | 1.08.01.03.01.04 | LLNL | SF-19LL01030104 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | McMahon, Kevin | Deliver updated thermodynamic database for use in GDSA | Updated thermodynamic database for use in GDSA |  | 2020-06-15 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20LL010301082 Supercedes: M4SF-19LL010301083 | M4 | 1.08.01.03.01.08 | LLNL | SF-19LL01030108 | Argillite International Collaborations - LLNL | Zavarin, Mavrik | McMahon, Kevin | Deliver Sorption Database and Model for GDSA | Sorption Database and Model for GDSA |  | 2020-06-15 |  |  |  | 2020 | On Schedule |  |  |  | None
M3SF-20LA010301021 | M3 | 1.08.01.03.01.02 | LANL | SF-20LA01030102 | Argillite Disposal R&D - LANL | Caporuscio, Florie | Camphouse, Chris | Argillite Disposal R&D - LANL | Argillite Disposal R&D - LANL | produce Sandia Argillite R&D report | 2020-06-18 |  | 2020-06-17 02:00 | completed ahead of schedule | 2020 | Complete | Argillite Disposal R&D and Argillite International Collaborations - LANL | F. Caporuscio | F. Caporuscio | None | AgilliteRD_International_2020_1 w Sauer reference.pdf
M3SF-20LA010301061- This is a combined document with "Argillite R&D- LANL (SF-19LA01030102) | M3 | 1.08.01.03.01.06 | LANL | SF-20LA01030106 | Argillite International Collaborations - LANL | Caporuscio, Florie | Camphouse, Chris | Argillite international collaborations LANL | Argillite International Collaborations - LANL | provide Sandia Argillite international report as part of Argillite R&D report | 2020-06-18 |  | 2020-06-17 02:00 | completed ahead of schedule | 2020 | Complete | Argillite Disposal R&D and Argillite International Collaborations - LANL | F. Caporuscio | F. Caporuscio | None | AgilliteRD_International_2020_1 w Sauer reference.pdf
M4SF-20LB010302031 | M4 | 1.08.01.03.02.03 | LBNL | SF-20LB01030203 | Crystalline Disposal R&D - LBNL | Zheng, Liange | Camphouse, Chris | LBNL Crystalline R&D FY20 Research | LBNL Crystalline Disposal R&D in FY2020 | The report includes the following deliverables: - Results of developing a new laboratory test apparatus to evaluate the impact of THMC process on excavation damage zone (EDZ) and permeability measurement of granite samples obtained from the Grimsel URL. - Results of LBNL’s research in collaboration with the Collisional Orogeny in the Scandinavian Caledonides (COSC) scientific team, to use the COSC-1 borehole as a testbed to evaluate the hydrology of a crystalline basement environment to provide insights for the crystalline basement disposal option. We also present updated laboratory and modeling results on characterizing the hydraulic properties. We of crystalline rock cores from the COSC-1 well determined using a unique laboratory-scale apparatus developed at LBNL. | 2020-06-18 |  | 2020-06-18 03:00 | The objective of LBNL's work is to support the overall objective of Crystalline Disposal R&D which focuses on advancing our understanding of long-term disposal of spent fuel in crystalline rocks and to develop necessary experimental and computational capabilities to evaluate various disposal concepts in such media. LBNL’s FY20 work specifically focuses on the reducing the uncertainties of key flow parameters in the EDZ, which will support GDSA and PA model directly or through better parameterization of a process model that feeds either GDSA/PA. The research work include laboratory experiments to evaluate how THMC processes affect the evolution of excavation disturbed zone and the use of a crystalline basement analog site in Sweden to evaluate fracture transmissivity using unique borehole monitoring tool, called Step-rate Injection Method for Fracture In-situ Properties (SIMFIP) and compare identified flow zones with different fracture sets observed in the field with core studies in the laboratory. The results of these studies are presented in this report. | 2020 | Complete | Crystalline Disposal R&D at LBNL: FY20 Progress Report | Yves Guglielmi, Chun Chang, Paul Cook, Patrick Dobson, Florian Soom, Seiji Nakagawa, Auli Niemi, Chris Juhlin, Henning Lorenz, Jan-Eri, Alexandru Tatomir, Farzad Basirat, Emil Lundberg, Bjarne Almqvist, Sharon Borglin, Christine Doughty, LianGe Zheng | LianGe Zheng | None | M4SF-20LB010302031 Final.pdf |  | Crystalline rock, Nuclear waste disposal, Rock deformation, Geophysical measurements, Excavation damage zone, Fractures, Hydraulic properties
M4SF-20LB010305042 | M4 | 1.08.01.03.05.04 | LBNL | SF-20LB01030504 | Direct Disposal of Dual Purpose Canisters - LBNL | Rutqvist, Jonny | Freeze, Geoff | Geomechanical and performance assessment impact of direct disposal of DPCs in various host rock environments | Geomechanical and performance assessment impact of direct disposal of DPCs in various host rock environments | Report on FY20 activities addressing geomechanical and performance assessment impacts of direct disposal of DPCs in various host rock environments through coupled processes modeling of the waste package, engineered barrier system, and near field rock. | 2020-06-26 |  | 2020-06-25 03:00 | This report presents preliminary modeling related to geomechanical and performance assessment of impacts of direct disposal of commercial spent nuclear fuel (SNF) in dual-purpose canisters (DPCs) in various host rock environments. Three-dimensional simulations are used for prediction of the detailed temperature evolution near the waste package, while two-dimensional simulations are employed for faster scoping simulations of various thermally induced coupled THM processes and geotechnical issues. Overall, the study presented in this report highlights the importance of coupled THM processes for high-temperature systems, where damage could be caused around the waste emplacement tunnels and the host rock if the systems are not properly designed. | 2020 | Complete | Geomechanical and performance assessment impacts of DPC disposal in various host rock environments | Jonny Rutqvist | Jonny Rutqvist | None | M4SF-20LB010305042 FINAL.pdf |  | Dual Purpose Canister, bentonite, thermal conductivity, high temperature, geomechanics, ductile shale, brittle shale, THM modeling, coupled processes
M4SF-20PN010308071 | M4 | 1.08.01.03.08.07 | PNNL | SF-20PN01030807 | Engineered Barrier System International Collaborations - PNNL | Hanson, Brady | Camphouse, Chris | Collaboration with EU DisCo Project | PNNL Input to International Collaboration Report | Collaborate with the EU DisCo Project on spent fuel dissolution in the presence of degraded canister material | 2020-06-26 |  | 2020-06-26 03:00 | This report discusses the progress made in FY20 at Pacific Northwest National Laboratory in the program focused on the dissolution of UO2 fuel with various dopants. | 2020 | Complete | PNNL Engineered Barrier Systems International Collaborations | Brady Hanson | Brady Hanson | None | M4SF-20PN010308071.pdf
M5SF-20OR0103050123 | M5 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik |  | Reactivity analysis extended to 1E5 or 1E6 years | Reactivity analysis extended to 1E5 or 1E6 years | Extend representative, as-loaded reactivity calcs. to 1E5 or 1E6 years | 2020-06-30 |  | 2020-06-30 | This report documents the extension of the UNF-ST&DARDS postclosure criticality calculations to time frames beyond 1,000,000 years. | 2020 | Complete | Extension of Direct Disposal Criticality Calculations to 1,000,000 Years | Justin Clarity | Kaushik Banerjee | None | PB2000708_Clarity_Extension-to_kaushik.pdf
M4SF-20LL010802032 | M4 | 1.08.01.08.02.03 | LLNL | SF-20LL01080203 | Quality Assurance - LLNL | Pope, Greg | Brainard, Matt | Internal Review | Internal Audit Plan and Report | Internal audit of DOE NE-8 tasks | 2020-06-30 |  | 2020-06-30 03:00 | Reviewed and corrected document uploaded | 2020 | Complete | LLNL SFWD Quality Assurance (QA) Assessment |  |  | None | SFWD QA Assessment Report 2020.pdf
M4SF-20SR010802052 | M4 | 1.08.01.08.02.05 | SRNL | SF-20SR01080205 | Quality Assurance - SRNL | Smith, Pat | Brainard, Matt | SRNL Quality Assurance Surveillance | Complete Level 4 QA Surveillance | Complete QA Surveillance of the SRNL NE program. | 2020-06-30 | 2020-08-31 | 2020-07-29 | This Surveillance is for the scope of NE8 - Spent Fuel and Waste Disposition. | 2020 | Completed Late | Nuclear Fuel Cycle and Supply Chain (NFCSC) Quality Assurance (QA) Assessment Report NE-8 Spent Fuel and Waste Disposition | Pat Smith | Pat Smith | None | NE8 Report 2020-SUR-11-000011 signed.pdf |  | Annual QA Surveillance/Assessment
M3SF-20PN010308033 | M3 | 1.08.01.03.08.03 | PNNL | SF-20PN01030803 | Engineered Barrier System R&D - PNNL | Buck, Edgar | Camphouse, Chris | Report on In-situ and Electrochemical Work for Model Validation | Report on In-situ and Electrochemical Work for Model Validation |  | 2020-06-30 | 2020-07-30 03:00 | 2020-07-28 03:00 | An email transmitting this milestone and confirming it was completed was sent to NTD/CAM on July 28, 2020. | 2020 | Completed Late | Report on In-situ and Electrochemical Work for Model Validation | Edgar Buck, Xiao-Ying Yu, Jennifer Yao, Jiyoung Son, Shawn Reichers | Edgar Buck | None | EBS-Report-Milestone_2020-Final (1).pdf |  | spent uranium oxide, fuel, corrosion
M4SF-20AN010802062 | M4 | 1.08.01.08.02.06 | ANL | SF-20AN01080206 | Quality Assurance - ANL | Riel, Roberta | Brainard, Matt | QA Surveillance | QA Surveillance Report | QA Surveillance | 2020-06-30 | 2020-07-31 01:00 | 2020-07-17 01:00 | Assessment completed; report attached. | 2020 | Completed Late | SFWD QA Assessment Report NSE-FY20-MA-004 | riel, roberta | riel, roberta | None | Appendix_E-NSE-FY-MA-004 signed.pdf SFWD QA Assessment Report NSE-FY20-MA-004-fixed final.pdf
M4SF-20LA010802012 | M4 | 1.08.01.08.02.01 | LANL | SF-20LA01080201 | Quality Assurance - LANL | Dunwoody, John | Brainard, Matt | Summary report of QA Assessment conducted on LANL SFWD work package(s) | LANL SFWD QA Assessment Report | Conduct an assessment of LANL SFWD work package(s) and provide report for summary roll-up report | 2020-06-30 |  | 2020-06-24 02:00 | assessment was completed 6/11, report was finalized 6/24 | 2020 | Complete | Summary report of QA assessment conducted on LANL SFWD work packages | John Dunwoody | John Dunwoody | None | SFWD LA-UR-20-24565.pdf
M4SF-20LA010302021 | M4 | 1.08.01.03.02.02 | LANL | SF-20LA01030202 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | Camphouse, Chris | Experimental and Modeling Activities to Support Crystalline Disposal Activities | Experimental and Modeling Activities to Support Crystalline Disposal Activities | This report presents the results of work conducted between August 2019 and July 2020 at the Los Alamos National Laboratory in the crystalline disposal and crystalline international disposal work packages of the Spent Fuel and Waste Systems Technology Campaign for the DOE-NE’s Fuel Cycle Research and Development program. Los Alamos focused on two main activities during this period: Discrete fracture network (DFN) modeling to describe flow and radionuclide transport in complex fracture networks that are typical of crystalline rock environments, and a comprehensive interpretation of three different colloid-facilitated radionuclide transport experiments. | 2020-07-15 |  | 2020-07-08 02:00 | This is the LANL Level 4 milestone for the crystalline work package. It contains 1) discrete fracture network modeling to support GDSA 2) discrete fracture network modeling to support Task 9 of the SKB task force for international work 3) experiments that quantify bentonite swelling. | 2020 | Complete | Crystalline and Crystalline International Disposal Activities | Hari Viswanathan | Hari Viswanathan | None | M4SF-20LA01032021.pdf |  | fracture modeling, bentonite swelling, crystalline rock
M2SF-20SN010301051 Supersedes M2SF-19SN010301052 supersedes M2SF-18SN010301052 | M2 | 1.08.01.03.01.05 | SNL | SF-19SN01030105 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | McMahon, Kevin | Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Process Model Development And Experimental Studies | Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Process Model Development And Experimental Studies | End of FY19 status report of accomplishments for R&D activities on disposal in argillaceous / clay-bearing rock | 2020-07-15 |  | 2020-07-15 | Submittal of the report "Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Process Model Development And Experimental Studies (M2SF-20SN010301051)" describes various R&D activities within the disposal in argillite work package. | 2020 | Complete | Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Process Model Development And Experimental Studies | Carlos F. Jove Colon | Carlos F. Jove Colon | None | M2SF-20SN010301051_finalRev.pdf |  | Spent Nuclear Fuel Disposal Argillite Engineered Natural Modeling Coupled Processes
M2SF-20SN010302051 Supersedes M2SF-19SN010302052 | M2 | 1.08.01.03.02.05 | SNL | SF-19SN01030205 | Crystalline Disposal R&D - SNL | Wang, Yifeng | McMahon, Kevin | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks | This milestone will document the minimal set of process models that need to be incorporated into a GDSA model as well as the experimental work that will support the process models. | 2020-07-15 |  | 2019-07-15 | FY20 year-end report on process model development and experimental investigation for spent fuel disposal in crystalline rocks | 2020 | Complete | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks: FY20 Report | Yifeng Wang | Yifeng Wang | None | M2SF-20SN010302051 final.pdf |  | Crystalline rock, spent fuel, process model
M4SF-19LA010302026- Reached out to Hari Viswanathan for document | M4 | 1.08.01.03.02.02 | LANL | SF-19LA01030202 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | McMahon, Kevin | Experimental and Modeling Activities to Support Crystalline Disposal Activities | Experimental and Modeling Activities to Support Crystalline Disposal Activities |  | 2020-07-15 |  |  |  | 2020 | On Schedule |  |  |  | None
M3SF-20SN010309012- The draft report will be sent via email to the Control Account Manager, NTD, and the DOE NE-81 lead. This draft provides the kernel of the milestone due at the end of November. | M3 | 1.08.01.03.09.01 | SNL | SF-20SN01030901 | OWL - Inventory and Waste Characterization - SNL | Sassani, Dave | Camphouse, Chris | Status of OWL Updates and WF Characteristics Projects | Status Report on OWL and Waste Form Characteristics | Draft document of OWL updates and WF Char progress | 2020-07-17 |  | 2020-07-17 02:00 | Completed M3 milestone deliverable. This is a Draft Report -- for internal use only that focuses primarily on the detailed management control processes for the OWL development and release process/version control (and archiving) of OWL versions. Two detailed processes are fully drafted (1) for tracking/control of changes to the OWL (Appendix C) and (2) for the version release process and archiving of OWL versions (Appendix D). | 2020 | Complete | Status of OWL Updates and WF Characteristics Projects | Dave Sassani | Dave Sassani | Draft Report - internal use only
M4SF-20LA010308051- Same report as M4SF-20LA010308011 | M4 | 1.08.01.03.08.05 | LANL | SF-20LA01030805 | Engineered Barrier System International Collaborations - LANL | Caporuscio, Florie | Camphouse, Chris | Engineered Barrier System International Collaborations - LANL | Engineered Barrier System International Collaborations - LANL | Engineered Barrier System International Collaborations - LANL | 2020-07-24 |  | 2020-07-23 02:00 | Combined with Engineered Barrier System R&D | 2020 | Complete | Engineered Barrier System R&D and International Collaborations - LANL - FY20 | Florie Caporuscio | Florie Caporuscio | None | EBS_RD_IntColl_FY20_Final.pdf
M4SF-20LA010308011 | M4 | 1.08.01.03.08.01 | LANL | SF-20LA01030801 | Engineered Barrier System R&D - LANL | Caporuscio, Florie | Camphouse, Chris | Engineered Barrier System R&D - LANL | Engineered Barrier System R&D - LANL | provide Engineered Barrier report | 2020-07-24 |  | 2020-07-23 02:00 | submitted one day ahead of schedule | 2020 | Complete | Engineered Barrier System R&D and International Collaborations – LANL – FY20 | Florie Caporuscio | Florie Caporuscio | None | EBS_RD_IntColl_FY20_Final.pdf
M3SF-20LA010304022 | M3 | 1.08.01.03.04.02 | LANL | SF-20LA01030402 | GDSA - Geologic Modeling - LANL | Gross, Michael | Stein, Emily | Geologic Framework Models for the Alluvial Basin Reference Case | Geologic Framework Models for the Alluvial Basin Reference Case | A workflow and case study for constructing a geologic framework model in a generic alluvial basin that account for variability in lithofacies and hydrologic properties. | 2020-07-31 |  | 2020-07-31 01:00 | This report summarizes research conducted in FY20 on the geologic characterization of alluvial basins as potential repositories for nuclear waste. The team was tasked with developing techniques and workflows that can be applied to a generic alluvial basin using publicly-available data, e.g., published maps, reports and journal articles. | 2020 | Complete | Geologic Framework Models for the Alluvial Basin Reference Case | Michael Gross | Los Alamos National Laboratory | None | 2020_LANL_GDSA_Alluvial_Fans_LA-UR-20-25594_08_2020.pdf |  | Alluvial basin, geologic framework model, meshing
M4SF-20OR010305018 Supercedes: M4SF-19OR010305017 | M4 | 1.08.01.03.05 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | Initial structural performance analysis of waste package for various criticality scenarios | Structural performance analysis of waste package for various criticality scenarios | In this report, a lifting and structural analysis was conducted on an MPC-37 (DPC) loaded with spent nuclear fuel and its internal void space conservatively filled with a high-density filler material. An additional study was performed by flooding the MPC-37 with water (in case of a criticality event) to determine the effect of changing the internal temperature and pressure on the canister structural integrity. | 2020-07-31 | 2020-08-21 | 2020-08-31 | In this report, a lifting and structural analysis was conducted on an MPC-37 (DPC) loaded with spent nuclear fuel and its internal void space conservatively filled with a high-density filler material. An additional study was performed by flooding the MPC-37 with water (in case of a criticality event) to determine the effect of changing the internal temperature and pressure on the canister structural integrity. | 2020 | Complete | Initial Lifting and Structural Analysis of a Void-Filled Loaded MPC 37 PWR Canister | Abiodun Adeniyi | Kaushik Banerjee | None | MPC-37 Lifting and Structural Analysis_Final-0914.pdf
M4SF-20OR010305018 | M4 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | Initial structural performance analysis of waste package for various criticality scenarios | Structural performance analysis of waste package for various criticality scenarios | This deliverable includes structural changes of fuel assemblies and DPC due to criticality excursion. A structural analysis code will be used to calculate structural performance of a DPC after a criticality event. | 2020-07-31 | 2020-08-21 | 2020-08-31 | In this report, a lifting and structural analysis was conducted on an MPC-37 (DPC) loaded with spent nuclear fuel and its internal void space conservatively filled with a high-density filler material. An additional study was performed by flooding the MPC-37 with water (in case of a criticality event) to determine the effect of changing the internal temperature and pressure on the canister structural integrity. | 2020 | Completed Late | Initial Lifting and Structural Analysis of a Void-Filled Loaded MPC 37 PWR Canister | Abiodun Adeniyi | Kaushik Banerjee | None | MPC-37 Lifting and Structural Analysis_Final-0914.pdf
M3SF-20OR010310071 | M3 | 1.08.01.03.10.07 | ORNL | SF-20OR01031007 | Planning for URL - ORNL | Chatzidakis, Stylianos | Stein, Emily | Initial Test Plan for URL Muon Scoping Experiment | Safety protocols and process requirements for entry to URL | M4 milestone report documenting test plan including equipment, equipment requirements, selection of proposed test location, proposed schedule/timing of test, etc., suitable for coordination and planning with URL management and operations staff. | 2020-07-31 |  | 2020-07-30 | Characterization of cosmic ray background at URL could provide a better understanding of how muons can be integrated into future URL characterization activities, including geological mapping (e.g., voids, fractures) and nonproliferation. This report describes a test plan for cosmic ray muon characterization activities along with access and safety considerations for safe entry to URL suitable for coordination and planning with URL management and operations staff. Further, it includes a preliminary evaluation of activities to determine if there are any potential impacts that could result in test interference, test to test interference or activities that may impact the URL or surrounding area for future uses. No adverse effects or other hazards that may limit the long-term performance of the URL have been identified. | 2020 | Complete | Initial Test Plan for URL Muon Scoping Experiment. | Stylianos Chatzidakis and Rob Howard | Stylianos Chatzidakis | None | M3SF-20OR010310071_Initial Test Plan for Muon Scoping Experiment_07302020_1300.pdf M3SF-20OR010310071_Initial Test Plan for Muon Scoping Experiment_08122020_1400.pdf
M3SF-20SN010303062 | M3 | 1.08.01.03.03.06 | SNL | SF-20SN01030306 | Salt International Collaborations - SNL | Kuhlman, Kris | Stein, Emily | Salt International Collaborations (FY20) | Salt International Collaborations Update (FY20) | Summary of international collaborative efforts | 2020-07-31 |  | 2020-07-22 02:00 | M3 report finished one week ahead of schedule | 2020 | Complete | International Collaborations on Radioactive Waste Disposal in Salt (FY20) | Kris Kuhlman | Kris Kuhlman | None | SAND2020-7440R_Salt_2020_international_status_report_04.pdf | salt; KOMPASS; RANGERS; WEIMOS; FEPs; DECOVALEX | salt; KOMPASS; RANGERS; WEIMOS; FEPs; DECOVALEX
M4SF-19SN010101024- Superseded by M4SF-20SN010101024 | M4 | 1.08.01.01.01.02 | SNL | SF-20SN01010102 | Knowledge Management - SNL | Meacham, Janette | Sassani, Dave | Develop Pilot KM Repository | Repository Deployed | Develop SharePoint repository for storage and retrieval of NWM tacit knowledge collected during pilot project | 2020-07-31 |  | 2020-07-23 02:00 | The repository for the Pilot KM project is complete and has been deployed to the Sandia NEFC Program staff. The repository was demonstrated to the NE-8 customer and accepted. | 2020 | Complete | NEFC KM Pilot Database PICS Deliverable 07-20 | Janette Meacham | Janette Meacham | None | NEFC KM Pilot Database PICS Deliverable 07-20.pdf
M4SF-20LB010802022 | M4 | 1.08.01.08.02.02 | LBNL | SF-20LB01080202 | Quality Assurance - LBNL | Faybishenko, Boris | Brainard, Matt | LBNL QA Surveillance | LBNL QA surveillance report | LBNL QA Surveillance | 2020-07-31 |  | 2020-07-31 03:00 | Lawrence Berkeley National Laboratory (LBNL) has conducted a self- assessment of Quality Assurance (QA) for work conducted for DOE’s Spent Fuel and Waste Disposition (SFWD) Program. This report presents a summary of the QA requirements, methods used for the self-assessment, and results of the self- assessment, along with a required assessment checklist. | 2020 | Complete | Spent Fuel and Waste Disposition (SFWD) Quality Assurance (QA) Assessment Report Format | Boris Faybishenko | Boris Faybishenko | None | M4SF-20LB010802022 LBNL QA Assessment FY20 Report.doc |  | Quality Assurance, SFWD program, Self-assessment report,
M5SF-20OR0103050124- No report for this milestone | M5 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik |  | DPC Reactivity analysis with porous cementitious filler | DPC Reactivity analysis with porous cementitious filler | DPC reactivity analysis with porous fillers, permeated with fresh water, with solid phase composition representing phosphate cement, and including particulate B4C in various amounts. | 2020-07-31 |  | 2020-07-31 | This effort includes calculations performed to assess the impact of the addition of cementitious filler materials on post closure criticality safety for a single canister from the Zion site. | 2020 | Complete |  | Justin Clarity | Kaushik Banerjee | None
M3SF-20OR010304073- no notes as to why this report is not in PICS | M3 | 1.08.01.03.04.07 | ORNL | SF-20OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | ORNL Input to GDSA Repository Systems Analysis FY20 | ORNL Input to GDSA Repository Systems Analysis FY19 | Report documenting FY2020 GDSA modeling activities that may include sensitivity analyses on waste package breach area, sensitivity analyses on infiltration rates, modeling options for including the potential for flux impinging on the package to be diverted by the overpack, and concentrated at localized corrosion, | 2020-07-31 | 2020-11-30 |  | Deliverable is late because of resource availability | 2020 | Late |  |  |  | None
M2SF-20SN010305073 | M2 | 1.08.01.03.05 | SNL | SF-20SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | Freeze, Geoff | Enhanced Multi-physics Modeling of Fuel/Basket Degradation | Progress Report on Fuel/Basket Degradation and Waste Package Pressure Effects Modeling | This report summarizes progress in FY19-20 on modeling of fuel assembly and DPC basket degradation in the disposal environment, and waste package breach behavior in response to internal heat generation (from a criticality event). | 2020-08-14 |  | 2020-08-13 | Completed SNL technical review and programmatic R&A. | 2020 | Complete | Progress Report on Fuel/Basket Degradation and Waste Package Pressure Effects Modeling | Hardin, Ernest | Hardin, Ernest | None | DPC Multiphysics M2 13Aug20 final R0.pdf |  | spent nuclear fuel;dual-purpose canisters;geologic disposal
M4SF-20OR010802082 | M4 | 1.08.01.08.02.08 | ORNL | SF-20OR01080208 | Quality Assurance - ORNL | Vance, Mark | Brainard, Matt | ORNL SFWD QA POC Surveillance | FY 2020 Suveillance of the ORNL SFWD QA Program | Plan, conduct, document, and submit report to PICS:NE concerning ORNL's FY2020 QA surveillance of ORNL SFWD QA program. | 2020-08-15 |  | 2020-08-11 | Completion of ORNL's QA Assessment of SFWD/IWM work package deliverables. | 2020 | Complete | Assessment of the Quality Rigor Levels Assigned to Work Package Deliverables Sponsored by the Department of Energy’s NE-8/Office of Spent Fuel and Waste Disposition and Conducted at the Oak Ridge National Laboratory | Mark C. Vance | Mark C. Vance | None | ORNLSFWDFY2020AssessmentReporttFinal.pdf |  | SFWD, QA, assessment, deliverables
M3SF-20LB010303022 | M3 | 1.08.01.03.03.02 | LBNL | SF-20LB01030302 | Salt Disposal R&D - LBNL | Rutqvist, Jonny | Stein, Emily | Salt Coupled THMC Processes Research Activities at LBNL: FY20 Progress | Salt Coupled THMC Processes Research Activities at LBNL: FY20 Progress | Report on LBNL's activities related to salt coupled processes | 2020-08-21 |  | 2020-08-20 03:00 | This report documents the status of LBNL’s research activities on coupled THMC processes in salt formations. In particular, the status of the TOUGH-FLAC simulator for modeling salt coupled processes, new long-term repository simulations for large sized disposal canisters, the development and testing of a dual continuum model for brine-migration, including brine inclusions in salt grains, new micro-mechanical modeling of crushed salt reconsolidation, LBNL’s modeling support of the new borehole experiments at WIPP, focusing on THM mechanisms of brine-release and brine-inflow and borehole mechanical closure rate, status of geophysical monitoring of the WIPP experiments, in particular, related to Cross-borehole Electrical Resistivity Tomography (ERT) and fiber optical sensing. The description of international research collaborations, including BenVaSim code comparison project and the newly launched DECOVALEX-2023. | 2020 | Complete | Salt Coupled THMC Processes Research Activities at LBNL: FY20 Progress | Jonny Rutqvist, Yuxin Wu, Mengsu Hu, Sebastian Uhlemann, Jiannan Wang, and Jens Birkholzer | Jonny Rutqvist | None | M3SF-20LB010303022 FINAL.pdf |  | Salt, Brine, Coupled processes, Modeling, Migration, Field tests, WIPP, TOUGH-FLAC, Temperature, Permeability, THM, Micromechanical modeling, Cross-borehole Electrical Resistivity Tomography.
M4SF-20LB010304081 | M4 | 1.08.01.03.04.08 | LBNL | SF-20LB01030408 | GDSA Modeling and Integration - LBNL | Zheng, Liange | Stein, Emily | LBNL FY20 research in GDSA Modeling and Integration | Integrating THC and THM models into GDSA | Progress in this activity will be documented in milestone report | 2020-08-21 |  | 2020-08-20 03:00 | The objective of this activity is to develop a methodology and toolsets for integrating complex, coupled models (such as THMC or THC) into the GDSA model for evaluating disposal system performance for nuclear waste. Because the GDSA model is designed for the entire repository with a thousand emplacement tunnels, a systematic methodology is needed on how to simplify some coupled processes/parameters. In this report, we specifically target the derivation of a reduced-order model (ROM) for the distribution coefficient (Kd) of Uranium in bentonite buffer and application of the ROM in the GDSA model. | 2020 | Complete | LBNL FY20 research in GDSA Modeling and Integration | Haruko Wainwright1, Dinara Ermakova1, Hannah Lu2, Daniel Tartakovsky2, LianGe Zheng1, 1LBNL, 2Stanford University. | LianGe Zheng | None | M4SF-20LB010304081 FINAL.pdf |  | reduced-order model, distribution coefficient (Kd), THC model; Uranium
M4SF-20LA010305032 | M4 | 1.08.01.03.05.03 | LANL | SF-20LA01030503 | Direct Disposal of Dual Purpose Canisters - LANL | Caporuscio, Florie | Freeze, Geoff | Direct Disposal of Dual Purpose Canisters - LANL | Direct Disposal of Dual Purpose Canisters - LANL | produce document for Sandia M2 on direct disposal | 2020-08-28 |  | 2020-08-27 04:00 | The document was delivered ahead of schedule | 2020 | Complete | Direct Disposal of Dual Purpose Canisters - LANL | Florie Caporuscio | Florie Caporuscio | None | FY20_DirectDisposal_Boral_Aug20 - FINAL REVISED 090220.pdf
M2SF-20SN010303032 | M2 | 1.08.01.03.03 | SNL | SF-20SN01030303 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Update on Brine Availability Test in Salt | Brine Availability Test in Salt (FY20) | The test is funded by the DOE Office of Nuclear Energy (DOE-NE) and is located underground at the Waste Isolation Pilot Plant (WIPP), a DOE Office of Environmental Management (DOE-EM) site managed by the Carlsbad Field Office (CBFO). | 2020-08-28 |  | 2020-08-22 | M2 report submitted one week early for DOE review to satisfy milestone. | 2020 | Complete | FY20 Update on Brine Availabiltiy Test in Salt | Kris Kuhlman | Kris Kuhlman | None | SAND2020-9034R-FY20-Update-on-BATS-80a-sm.pdf |  | BATS, brine availability test in salt, WIPP, Waste Isolation Pilot Plant, field test, heater test, salt
M3SF-20LA010303012 | M3 | 1.08.01.03.03.01 | LANL | SF-20LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | Stein, Emily | 2020 LANL Contributions to the BATS Test in WIPP | 2020 LANL Contributions to the BATS Test in WIPP | This activity includes field work and modeling associated with the BATS testing at WIPP. | 2020-08-30 |  | 2020-08-29 02:00 | Annual report for LANL on Salt R&D related to the BATS experiment. | 2020 | Complete | 2020 LANL Contributions to the BATS Test in WIPP | Eric Guiltinan | Philip Stauffer | None | 2020_Augut_30_M3SF-20LA010303012.pdf
M2SF-20SN010308042 | M2 | 1.08.01.03.08 | SNL | SF-20SN01030804 | Engineered Barrier System R&D - SNL | Matteo, Ed | Camphouse, Chris | Evaluation of Engineered Barrier Systems FY20 Report | Evaluation of Engineered Barrier Systems FY20 Report | This report describes research and development (R&D) activities conducted during fiscal year 2020 (FY20) specifically related to the Engineered Barrier System (EBS) R&D Work Package in the Spent Fuel and Waste Science and Technology (SFWST) Campaign supported by the United States (U.S.) Department of Energy (DOE). The R&D activities focus on understanding EBS component evolution and interactions within the EBS, as well as interactions between the host media and the EBS. A primary goal is to advance the development of process models that can be implemented directly within the Generic Disposal System Analysis (GDSA) platform or that can contribute to the safety case in some manner such as building confidence, providing further insight into the processes being modeled, establishing better constraints on barrier performance, etc. The FY20 EBS activities involved not only modeling and analysis work, but experimental work as well. Despite delays to some planned activities due to COVID-19 precautions, progress was made during FY20 in multiple research areas and documented in this report as follows: (1) EBS Task Force: Task 9/FEBEX Modeling Final Report: Thermo-Hydrological Modeling with PFLOTRAN, (2) preliminary sensitivity analysis for the FEBEX in-situ heater test, (3) cement-carbonate rock interaction under saturated conditions: from laboratory to modeling, (4) hydrothermal experiments, (5) progress on investigating the high temperature behavior of the uranyl-carbonate complexes, (6) in-situ and electrochemical work for model validation, (7) investigation of the impact of high temperature on EBS bentonite with THMC modeling, (8) sorption and diffusion experiments on bentonite, (9) chemical controls on montmorillonite structure and swelling pressure, (10) microscopic origins of coupled transport processes in bentonite, (11) understanding the THMC evolution of bentonite in FEBEX-DP—coupled THMC modeling, (12) modeling in support of HotBENT, an experiment studying the effects of high temperatures on clay buffers/near-field, and (13) high temperature heating and hydration column test on bentonite. The R&D team represented in this report consists of individuals from Sandia National Laboratories, Lawrence Berkeley National Laboratory (LBNL), Los Alamos National Laboratory (LANL), Pacific Northwest National Laboratory (PNNL), the Nuclear Research Center of the Negev in Israel, the Nuclear Research and Consultancy Group (NRG) in the Netherlands, and Vanderbilt University. In addition, the EBS R&D work leverages international collaborations to ensure that the DOE program is active and abreast of the latest advances in nuclear waste disposal. For example, the FY20 work on modeling coupled THMC processes at high temperatures relied on the bentonite properties from the Full-scale Engineered Barrier EXperiment (FEBEX) Field Test conducted at the Grimsel Test Site in Switzerland. Overall, significant progress has been made in FY20 towards developing the modeling tools and experimental capabilities needed to investigate the performance of EBS materials and the associated interactions in the drift and the surrounding near-field environment under a variety of conditions including high temperature regimes. | 2020-08-31 |  | 2020-08-31 | The FY20 EBS activities involved not only modeling and analysis work, but experimental work as well. Despite delays to some planned activities due to COVID-19 precautions, progress was made during FY20 in multiple research areas and documented in this report as follows: (1) EBS Task Force: Task 9/FEBEX Modeling Final Report: Thermo-Hydrological Modeling with PFLOTRAN, (2) preliminary sensitivity analysis for the FEBEX in-situ heater test, (3) cement-carbonate rock interaction under saturated conditions: from laboratory to modeling, (4) hydrothermal experiments, (5) progress on investigating the high temperature behavior of the uranyl-carbonate complexes, (6) in-situ and electrochemical work for model validation, (7) investigation of the impact of high temperature on EBS bentonite with THMC modeling, (8) sorption and diffusion experiments on bentonite, (9) chemical controls on montmorillonite structure and swelling pressure, (10) microscopic origins of coupled transport processes in bentonite, (11) understanding the THMC evolution of bentonite in FEBEX-DP—coupled THMC modeling, (12) modeling in support of HotBENT, an experiment studying the effects of high temperatures on clay buffers/near-field, and (13) high temperature heating and hydration column test on bentonite. | 2020 | Complete | Evaluation of Engineered Barrier Systems FY20 Report | Edward Matteo | Edward Matteo | None | M2SF-20SN010308042_SAND2020-11452 R.pdf
M4SF-20SN010308082- Reached out to Ed Matteo for document | M4 | 1.08.01.03.08.08 | SNL | SF-20SN01030808 | Engineered Barrier System International Collaborations - SNL | Matteo, Ed | Camphouse, Chris | FY20 Report on Activities for EBS International | Milestone to Report on Additional FY20 Activities for EBS Int'l | FY20 Report on Activities for EBS International | 2020-08-31 |  | 2020-08-31 02:00 |  | 2020 | Complete | FY20 Report on Activities for EBS International | Edward N Matteo | Edward N Matteo | None
M3SF-20PN010304091 | M3 | 1.08.01.03.04.09 | PNNL | SF-20PN01030409 | GDSA - Modeling and Integration - PNNL | Nutt, Mark | Stein, Emily | GDSA Biosphere Model Implementation Plan | GDSA Biosphere Model Implementation Plan | Develop a requirements document and implementation plan for the development of an open-source biosphere component model within the GDSA framework. | 2020-08-31 |  | 2020-08-31 03:00 | This software requirements document was developed to outline the purpose, scope, and requirements of the proposed GDSA Biosphere model. This document is meant to introduce the planned capabilities, limitations, and user interactions with the GDSA Biosphere model. This software requirements document will serve as a framework and requirements document throughout development of the GDSA Biosphere model. | 2020 | Complete | GDSA Biosphere Model Software Requirements Document | Caitlin Condon | Caitlin Condon | None | M3SF-20PN010304091 Biosphere Model Software Requirements Document.pdf |  | GDSA, Biosphere
M4SF-20SN010802042 | M4 | 1.08.01.08.02.04 | SNL | SF-20SN01080204 | Quality Assurance - SNL | Camphouse, Chris | Brainard, Matt | Summary of Assessments Performed in FY20 by SNL QA POC for SFWD Work Activities | Summary of Assessments Performed FY20 by SNL QA POC for SFWD Work Activities at Sandia National Laboratories | Summary of Assessments Performed FY20 by SNL QA POC for SFWD Work Activities at Sandia National Laboratories | 2020-08-31 | 2020-07-31 08:00 | 2020-08-04 02:00 | M4 report for SNL FY20 QA activities in support of SFWD completed. | 2020 | Complete | Summary of Assessments Performed in FY 20 by SNL QA POC for FY 19 SNL SFWD Milestone Deliverables | Chris Camphouse | Chris Camphouse | None | 20200804_SNL_SFWD_FY19 Milestone Deliverables QA Assessment Report_SAND2020-8064 R.pdf
M3SF-20ID010310061- no notes as to why this report is not in PICS | M3 | 1.08.01.03.10.06 | DOE-ID | SF-20ID01031006 | Medium Voltage Unit Substations to Support Underground Research Facility (URF) - DOE-ID | Ford, Brayton | Stein, Emily | Purchase of Medium Voltage Unit Substations | Delivery of Medium voltage Substations |  | 2020-08-31 | 2021-06-30 02:00 |  | ENAD completed the fabrication and delivered the medium voltage substations. However, due to COVID we can't install and test the units. | 2020 | Late |  |  |  | None
M5SF-20OR010305093- No report for this milestone | M5 | 1.08.01.03.05.09 | ORNL | SF-20OR01030509 | Neutron Absorber Evaluation - ORNL | Chatzidakis, Stylianos |  | Deliver Advanced Manufacturing NAM Samples to INL for testing | Advanced Manufactured NAM Samples | Deliver Advanced Manufacturing NAM Samples to INL for testing | 2020-09-01 | 2020-10-30 |  | Delay due to unavailability of technician and long queue at the fab shop. | 2020 | Expected Late |  |  |  | None
M3SF-20OR010304074- no notes as to why this report is not in PICS | M3 | 1.08.01.03.04.07 | ORNL | SF-20OR01030407 | GDSA - Modeling and Integration - ORNL | Howard, Rob | Stein, Emily | Draft Experimental Plan for Commercial SNF Degradation in Repository Environments | Updated Experimental Plan for Commercial SNF Degradation in Repository Environments | Collaborate with SNL, PNNL, and ANL to develop a draft experimental test plan for commercial SNF degradation in select repository environments. | 2020-09-11 | 2020-11-30 |  | deliverable is late due to resource availability | 2020 | Expected Late |  |  |  | None
M3SF-20SN010305052 | M3 | 1.08.01.03.05.05 | SNL | SF-20SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | DPC Disposal Concepts of Operation | DPC Direct Disposal Concepts of Operation | Describe DPC disposal concepts of operation, for four disposal environments, and the available approaches for dealing with postclosure criticality. | 2020-09-18 |  | 2020-09-16 02:00 | Completed SNL technical review and R&A (limited distribution). | 2020 | Complete | DPC Disposal Concepts of Operations | Hardin,Ernest | Hardin,Ernest | None | DPC disposal concepts of operation FY20 M3 Final Draft 3.pdf |  | spent nuclear fuel;geologic disposal;dual-purpose canisters
M3SF-20OR010305015 No report in PICS. OUO. | M3 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | Update of DPC direct disposal criticality analysis report | DPC direct disposal criticality analysis report | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results including misload analysis results into the existing living document. | 2020-09-18 |  | 2020-09-18 | This report presents the dual-purpose canister (DPC) criticality evaluations performed in FY 2020 to support the feasibility determination of direct disposal of DPCs. | 2020 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | Justin Clarity | Kaushik Banerjee | OUO
M4SF-20IN010305082 | M4 | 1.08.01.03.05.08 | INL | SF-20IN01030508 | Neutron Absorber Evaluation - INL | Jarrell, Josh | Freeze, Geoff | Provide initial analysis of corrosion experiments | Provide initial analysis of corrosion experiments | Provide initial analysis of corrosion experiments in a short (<10 page) report including a brief overview of results to-date and suggest FY21 experiments including variations in parameters and chemistries. | 2020-09-18 |  | 2020-09-18 02:00 | Completed on-time and submitted via email. | 2020 | Complete | Neutron Absorber Material Corrosion Testing Preliminary Report | Tedd Lister | Tedd Lister | None | FY20 NAM prelim report final.pdf
M3SF-20OR010305017 | M3 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | DPC filler simulation and demonstration progress report | Update on filler demonstration project | This report will document the filler simulation and experimental validation progress made at ORNL by end of FY19. The report will also document the planned pipe experiment and data analysis. | 2020-09-23 | 2020-10-12 | 2020-10-12 | The report was slightly late due to extremely slow ORNL’s internal review process because of current global scenario. | 2020 | Expected Late | Dual-Purpose Canister Filling Demonstration Project Progress Report | Nesrin O. Cetiner | Kaushik Banerjee | None | FillerStatusReport_FY20.pdf |  | DPC, filler, casting
M3SF-20SN010304032 | M3 | 1.08.01.03.04.03 | SNL | SF-20SN01030403 | GDSA - Uncertainty and Sensitivity Analysis Methods - SNL | Swiler, Laura | Stein, Emily | Advances in Uncertainty and Sensitivity Analysis Methods and Applications in GDSA Framework | Advances in Uncertainty and Sensitivity Analysis Methods and Applications in GDSA Framework | A report documenting development and application of UQ/SA tools for GDSA Framework. | 2020-09-25 |  | 2020-09-25 04:00 | The technically-reviewed document has been transmitted to the DOE program managers. | 2020 | Complete | Advances in Uncertainty and Sensitivity Analysis Methods and Applications in GDSA Framework | Laura P. Swiler | Laura P. Swiler | None | GDSA_SAUQ_2020_Final_SAND2020-10802R.pdf |  | uncertainty quantification; sensitivity analysis
M2SF-20ID010801086 | M2 | 1.08.01.08.01 | DOE-ID | SF-20ID01080108 | Program Controls - Management of PICS:NE and Analytic Support - DOE-ID | Brainard, Matt | Brainard, Matt | Conduct Monthly Program Performance Analysis and Submit Performance Review Presentations to DOE (FY 2020) | FY20 SFWD Program Performance Reviews |  | 2020-09-30 |  | 2020-09-30 | Distributed the final FY 2020 August Monthly Performance Review on 9/30/2020 to claim completion of this M2 milestone. Previous Monthly/Quarterly Performance Review distributions include FY19 September Year End through FY20 July reviews (twelve in total). | 2020 | Complete | FY 2020 SFWD Monthly Program Performance Reviews (FY19 September thru FY20 August) | Matt Brainard | Allegheny Science and Technology | None | SFWD_Monthly Performance Review_FY20_August_Final.pdf
M2SF-20SN010304052 | M2 | 1.08.01.03.04 | SNL | SF-20SN01030405 | GDSA - Repository Systems Analysis - SNL | LaForce, Tara | Stein, Emily | GDSA Repository Systems Analysis Investigations in FY2020 | GDSA Repository Systems Analysis Investigations in FY2020 |  | 2020-09-30 |  | 2020-09-30 | Technical review complete via email from Paul Mariner. | 2020 | Complete | GDSA Repository Systems Analysis Investigations in FY2020 |  |  | None
M3SF-20OR010305016 | M3 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | Multiphysics criticality consequence analysis capability development status report | Multiphysics criticality consequence analysis capability development status report | This deliverable captures the Multiphysics criticality excursion consequence analysis methodology status and reports path forward. | 2020-09-30 |  | 2020-09-30 | This report details initial calculations of the sustainable power level of a critical dual-purpose canister (DPC) in a saturated repository. | 2020 | Complete | Initial Coupled Simulations of a Critical Dual-Purpose Canister in a Saturated Repository | Gregory G. Davidson | Kaushik Banerjee | None | M3SF-20OR010305016.pdf |  | criticality, dual-purpose canister, multiphysics
M2SF-20LB010307012 | M2 | 1.08.01.03.07 | LBNL | SF-20LB01030701 | Disposal Research International Coordination - LBNL | Birkholzer, Jens | Birkholzer, Jens | International Collaboration Activities in Different Geologic Disposal Environments | International Collaboration Activities in Different Geologic Disposal Environments | This annual report describes the FY20 status of international collaboration regarding geologic disposal research in the SFWD. The focus of the report is on opportunities that provide access to field data (and respective interpretation and modeling), and/or allow participation in ongoing and planned field experiments. The first major segment of the report describes various multinational and bilateral collaboration opportunities available to SFWD researchers. The second major segment summarizes the individual international R&D activities conducted by SFWD scientists, addressing relevant R&D challenges in fields like near-field perturbation, engineered barrier integrity, RN transport, and integrated system behavior. These now form a considerable portion of SFWD disposal research, and significant advances have been made over the past few years. | 2020-09-30 |  | 2020-09-30 | This report describes the status of international collaboration regarding geologic disposal research in the Spent Fuel and Waste Disposition (SFWD) Campaign. Since 2012, SFWD has advanced active collaboration with several international geologic disposal programs in Europe and Asia. Such collaboration allows the SFWD Campaign to benefit from a deep knowledge base in regards to alternative repository environments developed over decades, and to utilize international investments in research facilities (such as underground research laboratory testing and modeling), saving millions of R&D dollars that have been and are being provided by other countries. To date, SFWD’s International Disposal R&D Program has established formal collaboration agreements with several international initiatives and various international partners, and national lab scientists associated with SFWD have conducted specific collaborative R&D activities that align well with its R&D priorities. These now form a considerable portion of SFWD disposal research, and significant advances have been made over the past few years. | 2020 | Complete | International Collaboration Activities in Geologic Disposal Research: FY20 Progress | Jens Birkholzer, Boris Faybishenko | Jens Birkholzer | None | M2SF-20LB010307012 FINAL.pdf |  | International collaboration, underground research laboratories, in situ testing, nuclear waste disposal, host rock, argillite, crystalline rock, salt, engineering barriers, radionuclide transport, international collaboration, DECOVALEX Project.
M3SF-20SN010310033 | M3 | 1.08.01.03.10.03 | SNL | SF-20SN01031003 | Planning for URL - SNL | Kuhlman, Kris | Stein, Emily | Draft test plan for passive monitoring of an underound research laboratory | Draft Test Plan for Passive Monitoring of an Underground Research Laboratory | Draft test plan for passive atmospheric monitoring at a vadose zone underground research lab. | 2020-09-30 |  | 2020-09-28 02:00 | Draft Test Plan finished 2 days ahead of schedule. | 2020 | Complete | Passive Atmospheric Monitoring in a Vadose Zone Underground Research Laboratory | Kris Kuhlman | Kris Kuhlman | None | URL-TestPlan-15-Sept28-final.pdf
M5SF-20OR010310073 | M5 | 1.08.01.03.10.07 | ORNL | SF-20OR01031007 | Planning for URL - ORNL | Chatzidakis, Stylianos |  | Muon flux experimental apparatus and calibration results | Experimental apparatus and calibration results | M5 milestone report documenting lab-scale experimental data, analysis, and results on developing a muon detector system, including calibration and efficiency measurements. | 2020-09-30 |  | 2020-09-30 | M5 Milestone report describing preliminary modeling and simulation results of muon apparatus. | 2020 | Complete | Progress Report – Development of URL Muon Scoping Experimental Apparatus and Simulation Results | Stylianos Chatzidakis | Stylianos Chatzidakis | None | M5SF-20OR010310073_Progress Report_Development of URL Muon Scoping Apparatus _09302020_1600.pdf |  | URL planning, muon flux
M2SF-20SN010305022- Reached out to Mark Rigali for document | M2 | 1.08.01.03.05 | SNL | SF-20SN01030502 | DPC Fillers R&D - SNL | Rigali, Mark | Freeze, Geoff | Progress Report on Cement Slurry Filler Development | Progress Report on Cement Slurry Filler Development |  | 2020-09-30 |  | 2020-09-30 | Milestone completed on 9/30/2020. It is currently in draft form and has been sent out for policy review. | 2020 | Complete | Progress Report on Cement Slurry Filler Development | M. Rigali | SNL | None
M4SF-20SN010305064 | M4 | 1.08.01.03.05.06 | SNL | SF-20SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Status Report - Progress in Developing Repository-Scale Performance Assessment Model | Status Report - Progress in Developing Repository-Scale Performance Assessment Model | Develop the computer code that will be used to perform the PA. Perform sensitivity analyses to understand the oscillatory nature of a "steady-state" postclosure critical event in a DPC. Investigate potential criticality termination mechanisms including cladding/grid spacer degradation. Investigate effects of critical event on in-package chemistry. Perform sensitivity analysis of the effects of transient critical events on engineered barriers. | 2020-09-30 | 2020-10-12 06:00 | 2020-10-12 03:00 | We anticipate completing this milestone by 10/12/20. | 2020 | Expected Late | Status Report - Progress in Developing a Repository-Scale Performance Assessment Model | SNL, ORNL, University of Michigan | Laura Price | None | ULR_DPC Crit_Sept 2020 M4_v3_clean.pdf |  | postclosure criticality, dual-purpose canister, performance assessment, nuclear criticality
M4SF-20OR010308091 | M4 | 1.08.01.03.08.09 | ORNL | SF-20OR01030809 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Perform detailed isotopic analyses on PWR samples | Isotopic Data on North Anna PWR Spent Nuclear Fuel | Perform detailed IC-PMS isotopic analysis on Sister rod samples and document results. | 2020-09-30 |  | 2020-09-30 | Report provides the status of work to dissolve and perform high performance isotopic analyses on 8 North Anna high burnup fuel segments. The report identifies the isotopes to be measured and the status of preparing spikes, standards, procedures etc. required to achieve the high level precision of these measurements. | 2020 | Complete | Status Update on the High Precision Isotopic Measurements on High Burnup LWR Fuel in 2020 | Bruce Bevard | Bruce Bevard | None | PB2001174_FY20_Iso-HBU-LWR_093020.pdf
M4SF-20PN010305121- Reached out to Brady Hanson for document | M4 | 1.08.01.03.05.12 | PNNL | SF-20PN01030512 | Cladding Degradation Conceptual Model - PNNL | Hanson, Brady | Freeze, Geoff | Develop Input to SNL Cladding Degradation Model | Input to SNL Cladding Degradation Conceptual Model Report | Cladding degradation processes and their details will be surveyed from the literature, and the processes most important to criticality analysis will be identified and scoped. Processes to be considered will include creep rupture, localized corrosion, Zr-oxidation, hydride reorientation, and unzipping. Some of these processes have been determined to be inconsequential for normal repository conditions without criticality, but they are temperature sensitive and may be exposed to elevated temperatures for extended duration in a criticality scenario. The range of chemical, thermal, and radiolytic conditions likely during criticality events (steady state) will be described. The temperature dependence of rate processes will be identified and estimated where reasonable to do so. Input to the SNL conceptual model report will be generated to serve as the basis for future quantitative modeling of cladding performance. | 2020-10-02 | 2020-10-23 06:00 |  | Input will be provided directly into the SNL M3 report. | 2020 | Expected Late |  |  |  | None
M4SF-21PN010309101 | M4 | 1.08.01.03.09.10 | PNNL | SF-21PN01030910 | Cladding Degradation Conceptual Model - PNNL | Hanson, Brady | Camphouse, Chris | Develop Input to SNL Cladding Degradation Model | Input to SNL Cladding Degradation Conceptual Model Report | Cladding degradation processes and their details will be surveyed from the literature, and the processes most important to criticality analysis will be identified and scoped. Processes to be considered will include creep rupture, localized corrosion, Zr-oxidation, hydride reorientation, and unzipping. Some of these processes have been determined to be inconsequential for normal repository conditions without criticality, but they are temperature sensitive and may be exposed to elevated temperatures for extended duration in a criticality scenario. The range of chemical, thermal, and radiolytic conditions likely during criticality events (steady state) will be described. The temperature dependence of rate processes will be identified and estimated where reasonable to do so. Input to the SNL conceptual model report will be generated to serve as the basis for future quantitative modeling of cladding performance. | 2020-10-23 |  | 2020-10-18 | Completed 10/18/20. PNNL provided this input as direct comments and additions to the draft SNL model report via attachment to an email to Pat Brady on 10/18/20. This milestone was previously M4SF-20PN010305121. | 2021 | Complete | Input to SNL Cladding Degradation Conceptual Model Report | Patrick V. Brady and Brady Hanson | Brady Hanson | None | RE_ clad report in sfwst format.pdf |  | degradation pathways, cladding, stress corrosion cracking
M3SF-20SN010305111 | M3 | 1.08.01.03.05.11 | SNL | SF-20SN01030511 | Cladding Degradation Conceptual Model - SNL | Price, Laura | Freeze, Geoff | Develop Cladding Degradation Conceptual Model | Cladding Degradation Conceptual Model | Cladding degradation processes and their details will be surveyed from the literature, and the processes most important to criticality analysis will be identified and scoped. Processes to be considered will include creep rupture, localized corrosion, Zr-oxidation, hydride reorientation, and unzipping. Some of these processes have been determined to be inconsequential for normal repository conditions without criticality, but they are temperature sensitive and may be exposed to elevated temperatures for extended duration in a criticality scenario. The range of chemical, thermal, and radiolytic conditions likely during criticality events (steady state) will be described. The temperature dependence of rate processes will be identified and estimated where reasonable to do so. A conceptual model report will be generated to serve as the basis for future quantitative modeling of cladding performance. | 2020-10-30 |  | 2020-10-30 | We anticipate completing this milestone on time. | 2020 | Complete | An Updated Analysis of Clad Degradation | Patrick V. Brady | Patrick V. Brady | None | Cladding_Degradation_Final.pdf |  | cladding degradation, corrosion, fluoride
M3SF-21SN010309111 | M3 | 1.08.01.03.09.11 | SNL | SF-21SN01030911 | Cladding Degradation Conceptual Model - SNL | Price, Laura | Camphouse, Chris | Develop Cladding Degradation Conceptual Model | Cladding Degradation Conceptual Model | Cladding degradation processes and their details will be surveyed from the literature, and the processes most important to criticality analysis will be identified and scoped. Processes to be considered will include creep rupture, localized corrosion, Zr-oxidation, hydride reorientation, and unzipping. Some of these processes have been determined to be inconsequential for normal repository conditions without criticality, but they are temperature sensitive and may be exposed to elevated temperatures for extended duration in a criticality scenario. The range of chemical, thermal, and radiolytic conditions likely during criticality events (steady state) will be described. The temperature dependence of rate processes will be identified and estimated where reasonable to do so. A conceptual model report will be generated to serve as the basis for future quantitative modeling of cladding performance. | 2020-10-30 |  | 2020-10-30 03:00 |  | 2021 | Complete | An Updated Analysis of Clad Degradation | Patrick V. Brady | Patrick V. Brady | None | clad_sfwst_report_final_SAND-13018 R.pdf Cladding_Degradation_Final.pdf |  | clad, spent nuclear fuel, corrosion, degradation
M4SF-20OR010305131- Reached out to Rob Howard for document | M4 | 1.08.01.03.05.13 | ORNL | SF-20OR01030513 | Disposal Control Rod Placement Demo - ORNL | Howard, Rob | Freeze, Geoff | ORNL Input to SNL fuel/basket modification demo test plan | ORNL Input to SNL fuel/basket modification demo test plan | SNL and ORNL investigators collaborate on test plan for fuel modification demonstration, and prepare a M3 milestone deliverable. | 2020-11-02 | 2020-11-30 |  | This document is expected to be done coincident with the SNL workshop | 2020 | Expected Late |  |  |  | None
M3SF-20SN010305024- Reached out to Mark Rigali for document | M3 | 1.08.01.03.05.02 | SNL | SF-20SN01030502 | DPC Fillers R&D - SNL | Rigali, Mark | Freeze, Geoff | Joint Work Plan for DPC Filler Testing | Joint Work Plan for DPC Filler Testing |  | 2020-11-13 |  |  | Test plan development underway. | 2020 | 90 Day |  |  |  | None
M3SF-21SN010304064 | M3 | 1.08.01.03.04.06 | SNL | SF-21SN01030406 | GDSA - Repository Systems Analysis - SNL | LaForce, Tara | Stein, Emily | Disposal Concepts for a High- Temperature Repository in Shale | Disposal Concepts for a High- Temperature Repository in Shale |  | 2020-11-16 |  | 2020-11-10 02:00 | Technical review received via email from Laura Price | 2021 | Complete | Disposal Concepts for a High-Temperature Repository in Shale |  |  | None | M3SF-21SN010304064_High-T-Shale-Concepts_SAND2020-12471R.docx
M3SF-20LA010303042 | M3 | 1.08.01.03.03.04 | LANL | SF-20LA01030304 | Salt International Collaborations - LANL | Stauffer, Philip | Stein, Emily | LANL Contributions to Salt International Activities: 2020 | LANL Contributions to Salt International Activities : 2020 | This report will include outcomes from our Nov 2019 DECOVALEX presentation and our March 2020 Waste Management presenatations/papers. We will also include updates on benchmarking collaborations with GRS | 2020-11-30 |  | 2020-11-30 | We continue to make progress on our intentional activities and will summarize in our Nov 30 milestone. | 2020 | Complete | LANL Contributions to Salt International Activities: 2020 | Eric Guiltinan | Philip Stauffer | None | 2020_LANL_International_Milestone_M3SF-20LA010303042-LA-UR-20-29681.pdf
M3SF-21LA010303021 | M3 | 1.08.01.03.03.02 | LANL | SF-21LA01030302 | Salt International Collaborations - LANL | Stauffer, Philip | Stein, Emily | LANL Contributions to Salt International Activities: 2020 | LANL Contributions to Salt International Activities : 2020 | This report will include outcomes from our Nov 2019 DECOVALEX presentation and our March 2020 Waste Management presenatations/papers. We will also include updates on benchmarking collaborations with GRS | 2020-11-30 |  | 2020-11-30 | Description of LANL's international efforts during FY20. | 2021 | Complete | LANL Contributions to Salt International Activities: 2020 | Eric Guiltinan | Philip Stauffer | None | 2020_LANL_International_Milestone_M3SF-20LA010303042-LA-UR-20-29681.pdf
M4SF-21OR010305111 | M4 | 1.08.01.03.05.11 | ORNL | SF-21OR01030511 | Disposal Criticality Control Features - ORNL | Connolly, Kevin | Freeze, Geoff | ORNL Input to SNL fuel/basket modification demo test plan | ORNL Input to SNL fuel/basket modification demo test plan | SNL and ORNL investigators collaborate on test plan for fuel modification demonstration, and prepare a M3 milestone deliverable. | 2020-11-30 |  | 2020-11-30 |  | 2021 | Complete | ORNL Input to SNL Fuel/Basket Modification Demonstration Test Plan | Kevin Connolly | Kevin Connolly | None | M4SF-21OR010305111.pdf |  | disposal hardware, PWR, BWR, criticality, workshop
M4SF-20SN010305065- no notes as to why this report is not in PICS | M4 | 1.08.01.03.05.06 | SNL | SF-20SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Develop and Implement 1-D Model to Simulate Postclosure Criticality | 1-D Model of Postclosure Criticality | Develop and implement a 1-D conceptual model to simulate transient criticality events in a DPC due to a rapid reactivity insertion during geologic disposal. The model is a simplified 1-D neutronic and thermal-hydraulic representation of a DPC that can be used to estimate duration of criticality excursions, power and total energy release, as well as fuel, cladding, basket and DPC shell temperatures. The conceptual model shall simulate various geologies or DPC failure modes that could result in a increased pressure in the DPC during the excursion. | 2020-12-11 |  |  | We anticipate completing this milestone on time. | 2020 | 90 Day |  |  |  | None
M4SF-21SN010305062 | M4 | 1.08.01.03.05.06 | SNL | SF-21SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Develop and Implement 1-D Model to Simulate Postclosure Criticality | 1-D Model of Postclosure Criticality | Develop and implement a 1-D conceptual model to simulate transient criticality events in a DPC due to a rapid reactivity insertion during geologic disposal. The model is a simplified 1-D neutronic and thermal-hydraulic representation of a DPC that can be used to estimate duration of criticality excursions, power and total energy release, as well as fuel, cladding, basket and DPC shell temperatures. The conceptual model shall simulate various geologies or DPC failure modes that could result in a increased pressure in the DPC during the excursion. | 2020-12-11 | 2021-08-31 |  | New estimated completion date is March 31, 2021. | 2021 | Late |  |  |  | None
M3SF-21SN010305052 | M3 | 1.08.01.03.05.05 | SNL | SF-21SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | Develop fuel/basket modification demo test plan | Fuel/Basket Modification Demo Test Plan | SNL and ORNL investigators collaborate on test plan for fuel modification demonstration, and prepare a M3 milestone deliverable. | 2020-12-15 | 2020-12-23 02:00 | 2020-12-21 02:00 | Late completion approved in advance. | 2021 | Completed Late | Workshop to Plan R&D Support of Fuel/Basket Modification for Direct Disposal of Future DPCs | Hardin,Ernest | Hardin,Ernest | None | F&B mod test plan Final Dec 2020.pdf
M3SF-20SN010305054- no notes as to why this report is not in PICS | M3 | 1.08.01.03.05.05 | SNL | SF-20SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | Develop fuel/basket modification demo test plan | Fuel/Basket Modification Demo Test Plan | SNL and ORNL investigators collaborate on test plan for fuel modification demonstration, and prepare a M3 milestone deliverable. | 2020-12-15 |  |  | Workshop has been scheduled and planned in detail. | 2020 | 90 Day |  |  |  | None
M3SF-21SN010305022- The completed document was delivered to DOE for review on 12/18/2020. We will upload the completed document to PICS-NE after we have addressed DOE comments, if any, and you have approved the final document for public release. | M3 | 1.08.01.03.05.02 | SNL | SF-21SN01030502 | DPC Fillers R&D - SNL | Rigali, Mark | Freeze, Geoff | Joint Work Plan for DPC Filler Testing | Joint Work Plan for DPC Filler Testing | This document is an update of the Joint Workplan on Filler Investigations for DPCs (M4SF-18SN010305022) which: (1) documented a literature review and market research to identify specific filler material sources and equipment options; (2) reviewed and established filler performance requirements from previous work in the U.S. and internationally and provided a workplan with input from, and agreement with ORNL to demonstrate filler emplacement in scale-models representing DPCs. | 2020-12-18 |  | 2020-12-18 02:00 | M3SF-21SN010305022 "Joint Work Plan for DPC Filler Testing" was completed on schedule and delivered to DOE for review on 12/18/2020. | 2021 | Complete | Joint Work Plan for DPC Filler Testing | Sandia National Laboratories and Oak ridge National Laboratories | Sandia National Laboratories (Mark J. Rigali) | None |  |  | Dual Purpose Canister, Cement Fillers, Metal Fillers, Research and Development Plan
M4SF-21IN010305081 | M4 | 1.08.01.03.05.08 | INL | SF-21IN01030508 | Neutron Absorber Evaluation - INL | Jarrell, Josh | Freeze, Geoff | Complete comprehensive report on FY20 testing campaign results | Complete comprehensive report on FY20 testing campaign results | This publicly-releasable report satisfies the level 4 deliverable, M4SF-21IN010305081, to develop a comprehensive report on the FY20 testing campaign results. It covers the restart of corrosion testing activities performed at INL for neutron absorbing alloys performed in three environments. Testing examined materials based on nickel and stainless alloys using B and Gd as neutron absorber additions as well as employing benchmark alloys with established corrosion properties. These activities initiate what will soon include a broader set of materials including coatings other advanced manufactured materials. | 2020-12-18 |  | 2020-12-16 02:00 | Completed on-time via email sent to Control Account Manager. | 2021 | Complete | Neutron Absorber Material Corrosion Testing Final Report | Tedd Lister | Tedd Lister | None | FY20 NAM comp report final.pdf
M3SF-20OR010308092- no notes as to why this report is not in PICS | M3 | 1.08.01.03.08.09 | ORNL | SF-20OR01030809 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Isotopic and ORIGEN Analyses of Eight North Anna PWR SNF Fuel Samples | Isotopic and ORIGEN Analyses of Eight North Anna PWR SNF Fuel Samples | Perform detailed IC-PMS isotopic analysis on all 8 Sister rod samples and document results. Perform corresponding ORIGEN calculations for all 8 analyzed samples. | 2020-12-31 | 2021-02-26 |  | progress on the first several samples is being made and all samples should be complete by the revised date | 2020 | Expected Late |  |  |  | None
M4SF-20OR010308093- no notes as to why this report is not in PICS | M4 | 1.08.01.03.08.09 | ORNL | SF-20OR01030809 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Isotopic and ORIGEN Analyses of Eight Limerick BWR SNF Fuel Samples | Isotopic and ORIGEN Analyses of Eight Limerick BWR SNF Fuel Samples | Perform isotopic measurements on 8 BWR Limerick SNF samples; perform corresponding ORIGEN calculations for the 8 BWR samples | 2020-12-31 | 2021-04-30 |  | samples have been identified; work continues on attempting to get sufficient operating history to allow calculations to be compared to experimental results | 2020 | Expected Late |  |  |  | None
M3SF-20OR0103050127- no notes as to why this report is not in PICS | M3 | 1.08.01.03.05.01 | ORNL | SF-20OR01030501 | Direct Disposal of Dual Purpose Canisters - ORNL | Banerjee, Kaushik | Freeze, Geoff | Develop DPC loading optimization tool from post-closure criticality perspective | Develop DPC loading optimization tool from post-closure criticality perspective | Develop a tool that will generate DPC loading maps taking into account all the assemblies in the pool including any future discharges (stretch goal) that would minimize criticality potential in a geological repository. | 2021-01-22 |  |  | On Schedule | 2020 | On Schedule |  |  |  | None
M2SF-20SN010309013 Superseded by- M2SF-21SN010309012 | M2 | 1.08.01.03.09 | SNL | SF-21SN01030901 | OWL - Inventory - SNL | Weck, Philippe | Camphouse, Chris | Annual Status Update for OWL and Waste Form Characteristics | Annual status update for OWL and Waste Form Characteristics | This report represents completion of milestone deliverable M2SF-21SN010309012 "Annual Status Update for Online Waste Library (OWL) and Waste Form Characteristics" that provides an annual update on status of fiscal year 2020 activities for the work package SF-21SN01030901. | 2021-01-29 |  | 2021-01-20 | This draft report for internal use only represents completion of milestone deliverable M2SF-21SN010309012 "Annual Status Update for OWL and Waste Form Characteristics". The final UUR report will be uploaded after the policy review is addressed and the report is finalized as UUR from Sandia R&A. | 2021 | Complete | Annual Status Update for OWL and Waste Form Characteristics | Philippe F. Weck | Philippe F. Weck | None | Annual Status Update for OWL and WF Characteristics_M2SF-21SN010309012_REV00.pdf
M3SF-21OR010305125 | M3 | 1.08.01.03.05.12 | ORNL | SF-21OR01030512 | DPC Reactivity and Criticality Modeling - ORNL | Banerjee, Kaushik | Freeze, Geoff | DPC criticality analysis with fuel/basket modification | DPC criticality analysis with fuel/basket modification | Analyze various fuel loading and basket modification options geared towards criticality control in a repository including loading assemblies with disposal control elements, loading DPCs with additional neutron absorber inserts, and rechanneling BWR assemblies with neutron absorber materials. | 2021-01-29 |  | 2021-01-29 | This report uses three of the most reactive canisters that have been analyzed to-date using UNF-ST&DARDS to examine the performance of three potential reactivity suppression technologies under disposal conditions. | 2021 | Complete | Basket Modification Concepts for Disposal Reactivity Control of Dual Purpose Canisters | Justin Clarity | Kaushik Banerjee | None | basket_modification_final.pdf
M3SF-21OR010309072 | M3 | 1.08.01.03.09.07 | ORNL | SF-21OR01030907 | SNF Degredation Testing - ORNL | Montgomery, Rose | Camphouse, Chris | Draft Experimental Plan for Commercial SNF Degradation in Repository Environments | Draft Experimental Plan for Commercial SNF Degradation in Repository Environments | Collaborate with SNL, PNNL, and ANL to develop a draft experimental test plan for commercial SNF degradation in select repository environments. | 2021-01-29 | 2021-05-31 | 2021-05-27 | This document was delayed to accommodate full collaboration among the laboratories. It represents input from ORNL, ANL, PNNL, SNL and LANL. | 2021 | Complete | Draft Experimental Plan for Commercial SNF Degradation in Repository Environments with a Focus on Fuel Matrix Degradation | Jennifer Meszaros | Jennifer Meszaros | None | ORNLSPR-20212007_DraftExpPlan_SNFDegradation.pdf |  | waste form characterization
M3SF-20SN010304102- Superseded by M3SF-21SN010304112 Note: Because this preliminary report represents a status update, there is no plan to make it publicly available. The plan is for the final report, which will most likely be due in early FY22, to be made publicly available. | M3 | 1.08.01.03.04 | SNL | SF-21SN01030411 | GDSA - FEPs Reevaluation for ABD Glass - SNL | Price, Laura | Stein, Emily | Preliminary Results of FEP and preclosure safety reassessment for SRS ABD Glass Waste Form | Summary Report for Reassesment of ABD Glass WF | Report documenting preliminary results of the FEP and preclosure safety reassessment for SRS ABD glass waste. | 2021-01-29 |  | 2021-01-29 | This report documents preliminary results of the FEP and preclosure safety reassessment for SRS ABD glass waste. The evaluation is continuing, and final results will be report in late 2021. | 2021 | Complete | Report documenting preliminary results of the FEP and preclosure safety reassessment for SRS ABD glass waste. | Sandia National Laboratories | Laura Price | None | Note: Because this preliminary report represents a status update, there is no plan to make it publicly available. The plan is for the final report, which will most likely be due in early FY22, to be made publicly available.
M3SF-20OR010308094- no notes as to why this report is not in PICS | M3 | 1.08.01.03.08.09 | ORNL | SF-20OR01030809 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Report on Isotopic Analysis of 8 PWR and 8 BWR SNF samples | Report on Isotopic Analysis of 8 PWR and 8 BWR SNF samples | Report on both the PWR and BWR SNF fuel isotopic analysis along with the corresponding ORIGEN calculations | 2021-01-29 | 2021-05-28 |  | progress is being made on the analyis of PWR samples; BWR samples have been identified and will be processed upon the completion of the PWR samples | 2020 | Expected Late |  |  |  | None
M3SF-21OR010304082 | M3 | 1.08.01.03.04.08 | ORNL | SF-21OR01030408 | GDSA - Modeling and Integration - ORNL | Montgomery, Rose | Stein, Emily | ORNL Input to GDSA Repository Systems Analysis | ORNL Input to GDSA Repository Systems Analysis FY19 | Report documenting GDSA modeling activities that may include sensitivity analyses on waste package breach area, sensitivity analyses on infiltration rates, modeling options for including the potential for flux impinging on the package to be diverted by the overpack, and concentrated at localized corrosion, | 2021-02-26 | 2021-03-19 | 2021-03-19 | Document submitted to program for review on 2/26; comments are being incorporated. | 2021 | Expected Late | ORNL Input to GDSA Repository Systems Analysis FY21 | Scott Painter | Rose Montgomery | None | M3SF-21OR010304082 ORNL Input to GDSA Repository Systems Analysis FY21 Rev3.pdf | GDSA
M4SF-21PN010309062 | M4 | 1.08.01.03.09.06 | PNNL | SF-21PN01030906 | SNF Modeling and Testing International Collaborations - PNNL | Hanson, Brady | Camphouse, Chris | FY21 SPFT Results | FY21 SPFT Results |  | 2021-02-26 | 2021-08-31 | 2021-08-03 | This report will be delayed to 4/30/21 after the decision was made to continue running the test as a scoping study on effects of hydrogen in the sparge gas. The delay allows all the data, including SEM, for FY21 to be included in this report. | 2021 | Complete | Scoping Studies on the Effects of Dopants and Hydrogen on UO2 Dissolution Rates | Brady Hanson, SE Asmussen, AP Goulet | Brady Hanson | None | M4SF-21PN010309062 - PNNL-31733 - Final.pdf |  | dissolution of UO2 fuel
M3SF-21SN010303055 | M3 | 1.08.01.03.03.05 | SNL | SF-21SN01030305 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Brine Availability Test in Salt (BATS) Extended Plan | Brine Availability Test in Salt (BATS) Extended Plan | Test Plan for the Brine Availability Test in Salt (BATS) at the Waste Isolation Pilot Plant | 2021-03-31 |  | 2021-03-25 | 5-year test plan (M3) finished 1 week ahead of scheduled due date. | 2021 | Complete | Brine Availability Test in Salt (BATS) Extended Plan for Experiments at the Waste Isolation Pilot Plant (WIPP) | Kris Kuhlman | Kris Kuhlman | None | SAND2021-3497R_BATS-5-yr-test-plan-20.pdf
M4SF-21SN010101051-This completed report, submitted on schedule, will not be available for public release until DOE review and approval. | M4 | 1.08.01.01.01.05 | SNL | SF-21SN01010105 | Management Alternatives Cost Duration - SNL | Freeze, Geoff | Sassani, Dave | Evaluation of Assumptions for Comparative Cost Analysis | Evaluation of Assumptions for Comparative Cost Analysis of SNF Management Alternatives | Evaluation of assumptions about duration of judgment funds costs and potential effects on costs of alternative scenarios | 2021-04-30 |  | 2021-04-30 | Report completed on schedule | 2021 | 90 Day | Comparative Cost Analysis of Spent Nuclear Fuel Management Alternatives – Evaluation of Assumptions for Judgment Fund Costs | Laura Price | Geoff Freeze | None |  |  | waste management
M3SF-21OR010309091 | M3 | 1.08.01.03.09.09 | ORNL | SF-21OR01030909 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Isotopic and ORIGEN Analyses of Eight North Anna PWR SNF Fuel Samples | Isotopic and ORIGEN Analyses of Eight North Anna PWR SNF Fuel Samples | Perform detailed IC-PMS isotopic analysis on all 8 Sister rod samples and document results. Perform corresponding ORIGEN calculations for all 8 analyzed samples. | 2021-04-30 | 2021-08-31 |  | The hot cells have been shut down for a safety stand down for some of February and most of March with restart expected soon but still TBD so the isotopic work will be further delayed | 2021 | Expected Late |  |  |  | None
M4SF-21SN010301082 | M4 | 1.08.01.03.01.08 | SNL | SF-21SN01030108 | Argillite International Collaborations - SNL | Jove-Colon, Carlos | Camphouse, Chris | International Collaborations Activities on Disposal in Argillite R&D: Characterization Studies and Modeling Investigations | International Collaborations Activities on Disposal in Argillite R&D: Characterization Studies and Modeling Investigations | FY21 status report of accomplishments for international collaboration activities on disposal in argillaceous / clay-bearing rock | 2021-05-07 |  | 2021-05-07 | The report summarizes details of International R&D activities conducted in the Argillite R&D work package. | 2021 | Complete | International Collaborations Activities on Disposal in Argillite R&D: Characterization Studies and Modeling Investigations | Carlos F. Jove Colon | Carlos F. Jove Colon | None | M4SF-21SN010301082_SNL_Arg_Int_final-DRAFT3_RA_SAND2021-6358R_rev0.pdf |  | International Collaborations; Experimental; Modeling; R&D
M4SF-21LB010301031 | M4 | 1.08.01.03.01.03 | LBNL | SF-21LB01030103 | Argillite Disposal R&D - LBNL | Rutqvist, Jonny | Camphouse, Chris | Investigation of Coupled Processes in Argillite Rock: FY21 Progress | Investigation of Coupled Processes in Argillite Rock: FY20 Progress | Argillite Disposal R&D activities at LBNL including coupled processes model development and fundamental studies | 2021-05-28 |  | 2021-05-27 | The report introduces the relevance of coupled processes related to deep geological disposal of nuclear waste in argillite host rocks and gives a brief overview of the current state in coupled processes model developments. New model development and testing associated with shale creep are then presented. This is followed by numerical modeling results of three different modeling tasks related to the international DECOVALEX-2023 project. This includes results related to the Mont Terri FE (Full-scale Emplacement) Experiment conducted at the Mont Terri Laboratory, Switzerland, modeling tasks related thermal and gas fracturing at the Meuse/Haute-Marne (MHM) URL in Bure, France, as well as modeling gas migration in bentonite. The report present new work relate to dicrete fracture modeling, including applications of machine learning of fracture morphology and mesh optimization and new development and applications related modeling of fractured argillite around a heated tunnel. The report further presents new field test results and modeling related controlled fault activation experiments at the Mont Terri Laboratory. Related to geochemistry, the report presents development of a model using Phase-Field Lattice Boltzmann Method (PF-LBM) for application to interfaces (such as cement-bentonite interfaces) as well as new modeling of the Cement–Opalinus Clay Interaction (CI) Experiment at the Mont Terri Laboratory. The report end with a section on the current status on the integration of coupled THM processes models into the Geologic Disposal Safety Assessment (GDSA) and Performance Assessment (PA. The report is concluded with a summary of progress and plans for future work. | 2021 | Complete | Investigation of Coupled Processes in Argillite Rock: FY21 Progress | Jonny Rutqvist, Yves Guglielmi, Mengsu Hu, Tsubasa Sasaki, Hang Deng, Pei Li, Carl Steefel, Christophe Tournassat, Hao Xu, Shaswat Babhulgaonkar, Jens Birkholzer | Jonny Rutqvist | None | M4SF-21LB010301031_Argillite _FINAL.pdf |  | gas migration; Argillite; shale creep; clay; THM modeling; heater test modeling; coupled processes; discrete fracture modeling; cement-clay interface.
M4SF-21LA010802012 | M4 | 1.08.01.08.02.01 | LANL | SF-21LA01080201 | Quality Assurance - LANL | Dunwoody, John | Brainard, Matt | Summary report of QA Assessment conducted on LANL SFWD work package(s) | LANL SFWD QA Assessment Report | Conduct an assessment of LANL SFWD work package(s) and provide report for summary roll-up report | 2021-05-28 |  | 2021-04-19 | Report completed 4/19, approved, released 5/4 | 2021 | Complete | Los Alamos National Laboratory Spent Fuel Waste Disposition (SFWD) Quality Assurance (QA) Assessment Reporty Rev.0 | John Dunwoody | John Dunwoody | None | LA-UR-21-24303.pdf
M4SF-21OR010802082 | M4 | 1.08.01.08.02.08 | ORNL | SF-21OR01080208 | Quality Assurance - ORNL | Vance, Mark | Brainard, Matt | ORNL SFWD QA POC Surveillance | FY 2020 Suveillance of the ORNL SFWD QA Program | Plan, conduct, document, and submit report to PICS:NE concerning ORNL's FY2020 QA surveillance of ORNL SFWD QA program. | 2021-05-31 |  | 2021-05-27 | Submission of ORNL QA level 4 milestone - SFWD QA POC Surveillance completed. | 2021 | Complete | Assessment of the Quality Program for Work Packages and Deliverables Sponsored by the Department of Energy’s NE-8/Office of Spent Fuel and Waste Disposition and Conducted at the Oak Ridge National Laboratory | Mark C. Vance | Mark C. Vance | None | ORNLFY21SFWDAssessmentFinalReport_5-27-21.pdf |  | SFWD; QA; deliverables
M4SF-21AN010802062 | M4 | 1.08.01.08.02.06 | ANL | SF-21AN01080206 | Quality Assurance - ANL | Riel, Roberta | Brainard, Matt | QA Surveillance | QA Surveillance Report | QA Surveillance | 2021-05-31 |  | 2021-05-28 | Approved assessment report attached. | 2021 | Complete | SFWD QA Assessment Report NSE-FY21-MA-002 | Roberta Riel | Roberta Riel | None | SFWD QA Assessment Report NSE-FY21-MA-002-signed.pdf
M3SF-21LB010308031 | M3 | 1.08.01.03.08.03 | LBNL | SF-21LB01030803 | Engineered Barrier System R&D - LBNL | Zheng, Liange | Camphouse, Chris | LBNL Engineered Barrier System R&D Activities in FY21 | Engineered Barrier System Research Activities at LBNL: FY2021 progress report | Progress in this activity will be documented in milestone report "Engineered Barrier System Research Activities at LBNL: FY2021 progress report" that is scheduled on June 4, 2021 | 2021-06-04 |  | 2021-06-04 | This report documents LBNL’s work in packages “SF-21LB01030803 Engineered Barrier System R&D - LBNL” and “SF-21LB01030804 Engineered Barrier System International Collaborations - LBNL”. The research activities have focused on the coupled thermal-hydrological-mechanical-chemical (THMC) process in EBS. The objective of the research work is developing modeling capability for reliable assessment of these processes and ultimately supporting GDSA model with detailed coupled THMC process models. | 2021 | Complete | The report provides a summary of LBNL’s research in understanding and modeling the evolution of the EBS bentonite. Specifically, the report documents the following research activities: – Progress of a research activity of combining novel microscopic | Liange Zheng, Sharon Borglin, Laura Lammers, Michael Whittaker, Piotr Zarzycki, Patricia Fox, Chun Chang, Nithya Subramanian, Peter Nico, Christophe Tournassat, Chunwei Chou, Hao Xu, Esther Singer, Carl Steefel, Luca Peruzzo, Yuxin Wu | Liange Zheng | None | MS3F-21LB010308062 DRAFT - Internal only.pdf |  | Bentonite alteration; THMC; EBS; numerical modeling; fundamental understanding
M4SF-21LB010305041 | M4 | 1.08.01.03.05.04 | LBNL | SF-21LB01030504 | Direct Disposal of Dual Purpose Canisters - LBNL | Rutqvist, Jonny | Freeze, Geoff | Geomechanical and performance assessment impact of direct disposal of DPCs in various host rock environments: FY21 Progress | Geomechanical and performance assessment impact of direct disposal of DPCs in various host rock environments: FY21 Progress | Continuation of activities on geomechanical and performance assessment impact of direct disposal of DPCs in various host rock environments through coupled processes modeling of the waste package, engineered barrier system and near field rock. | 2021-06-18 |  | 2021-06-11 | This report presents modeling related to geomechanical and performance assessment of impacts of direct disposal of commercial spent nuclear fuel (SNF) in dual-purpose canisters (DPCs) in various host rock environments. The report presents results on disposal in salt host rock, including coupled THM behavior as a result of high decay heat, and the potential for long term sinking of heavy DPCs as a result of creep deformation. The report also presents a first study related to the impact of post-closure in-package criticality on the coupled THM evolution for disposal in argillite and crystalline host rocks. | 2021 | Complete | Geomechanical and performance assessment impacts of DPC disposal in various host rock environments | Jonny Rutqvist, Hafssa Tounsi | Jonny Rutqvist | None | M4SF-21LB010305042_DRAFT - Internal only.pdf |  | Dual Purpose Canister; high temperature; THM modeling; coupled processes; salt, argillite; crystalline; criticality
M4SF-21LB010302031 | M4 | 1.08.01.03.02.03 | LBNL | SF-21LB01030203 | Crystalline Disposal R&D - LBNL | Zheng, Liange | Camphouse, Chris | LBNL FY21 Crystalline R&D Research | Crystalline Disposal R&D at LBNL: FY21 Progress Report | The report includes the following deliverables: – Results of laboratory rock core studies of the permeability evolution of EDZ impacted by the swelling stress of bentonite and the temperature increase. – Results of LBNL’s research in collaboration with the Collisional Orogeny in the Scandinavian Caledonides (COSC) scientific team. The Step-rate Injection Method for Fracture In-situ Properties (SIMFIP) tests conducted in the COSC-1 deep borehole provided field data on the complex interplay between the stress and fracture hydromechanical properties in a foliated “hard” rock crust. We developed a workflow to integrate the results of the SIMFIP analysis into a larger discrete fracture network. We also made tensile strength measurements of core samples, which revealed that the tensile strength of the rock in the direction parallel to the foliation plane was approximately 50% of that in the direction perpendicular to the foliation plane. We also updated numerical simulations of previously conducted laboratory fracture flow-through experiments to better capture the effect of fracture heterogeneity. – Results of investigations of multi-scale modeling capabilities to simulate coupled hydrological-mechanical processes in fractured-porous rock. | 2021-06-25 |  | 2021-06-24 | The objective of LBNL's work is to support the SFWD’s Crystalline Disposal R&D which focuses on advancing our understanding of long-term disposal of spent fuel in crystalline rock, and to develop necessary experimental and computational capabilities to evaluate various disposal concepts in such host rock. LBNL’s FY21 work has specifically focused on the evaluation of uncertainties of key THMC parameters used for modeling of the Excavation Damaged Zone (EDZ) in support the GDSA and PA models. The LBNL researchers have conducted laboratory experiments to evaluate how THMC processes affect the evolution of EDZ; analyzed the results of the Step-rate Injection Method for Fracture In-situ Properties (SIMFIP) field experiments, which were conducted in a crystalline basement analog site in Sweden to evaluate fracture transmissivity, and compared identified the features of borehole fracture flow zones with the results laboratory core studies; investigations of multi-scale modeling capabilities to simulate coupled hydrological-mechanical processes in fractured-porous rock. | 2021 | Complete | Crystalline Disposal R&D at LBNL: FY21 Progress Report | Liange Zheng | Liange Zheng | None | M4SF-21LB010302031 Final Draft-Internal Use.pdf |  | Crystalline rock; Nuclear waste disposal; Rock deformation; Geophysical measurements; Excavation Damaged Zone; Fractures; Hydraulic properties; Multi-scale modeling
M3SF-21OR010305126 | M3 | 1.08.01.03.05.12 | ORNL | SF-21OR01030512 | DPC Reactivity and Criticality Modeling - ORNL | Banerjee, Kaushik | Freeze, Geoff | Develop DPC loading optimization tool from post-closure criticality perspective | Develop DPC loading optimization tool from post-closure criticality perspective | Develop a tool that will generate DPC loading maps taking into account all the assemblies in the pool including any future discharges (stretch goal) that would minimize criticality potential in a geological repository. | 2021-06-25 |  | 2021-06-25 | This report details work on the optimization of loading a DPC from a criticality perspective. | 2021 | Complete | Optimization of Canister Loading Patterns in Dual Purpose Canisters for Criticality Suppression | Justin Clarity | Gregory Davidson | None | M3SF-21OR010305126_Final_Report.pdf |  | loading optimization; machine learning
M3SF-21SN010309113- The report is not uploaded here because, although not classified, it is not approved for public release. A copy of the report was sent to the Control Account Manager and the National Technical Director via email. | M3 | 1.08.01.03.09.11 | SNL | SF-21SN01030911 | Cladding Degradation Conceptual Model - SNL | Price, Laura | Camphouse, Chris | Cladding degradation under anticipated repository conditions | Cladding Degradation Under Anticipated Repository Conditions | Models of cladding degradation under anticipated repository conditions. | 2021-06-30 | 2021-08-31 | 2021-08-30 | This report on a conceptual model for cladding degradation was completed on August 30, 2021. It is not classified but is not authorized for public or widespread release. | 2021 | Complete | Cladding Degradation Under Anticipated Repository Conditions | Pat Brady | Pat Brady | None | The report is not uploaded here because, although not classified, it is not approved for public release. A copy of the report was sent to the Control Account Manager and the National Technical Director via email. |  | SNF, spent nuclear fuel, cladding
M4SF-21SN010305055 | M4 | 1.08.01.03.05.05 | SNL | SF-21SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | Freeze, Geoff | DPC Disposal Thermal Scoping Analysis | DPC Disposal Thermal Scoping Analysis | Collaborate with GDSA to develop DPC thermal analysis cases. Perform semi-analytical scoping calculations, and a couple thermal-mechanical simulation for a salt repository. | 2021-06-30 |  | 2021-06-24 | Completed 6 days early so that resources can be focused on other deliverable(s). | 2021 | Complete | DPC Disposal Thermal Scoping Analysis | Hardin,Ernest | Hardin,Ernest | None | M4 2020 DPC thermal FINAL.pdf |  | spent nuclear fuel; dual-purpose canisters; geologic disposal
M3SF-21IN010304011 | M3 | 1.08.01.03.04.01 | INL | SF-21IN01030401 | GDSA - Geologic Modeling - INL | Russell, Glenn | Stein, Emily | Follow on Support for Geologic Modeling | GDSA – Geologic Modeling – INL – Web Visualization in Interactive Subsurface Profiling Tools | Continued support, maintenance and R&D for 2D and 3D web map applications for geologic modeling. | 2021-06-30 | 2021-07-23 | 2021-07-23 | INL M3 Milestone submission for Geologic Modeling in Web Visualization Applications | 2021 | Complete | GDSA – Geologic Modeling – INL – Web Visualization Applications and Assessment Tools | Glenn Rusell/ Tessica Oldemeyer | Glenn Russell | None | INL_2021SFWD_SFWST_GFMWebVisM3Milestone.pdf
M4SF-21LL010802032 | M4 | 1.08.01.08.02.03 | LLNL | SF-21LL01080203 | Quality Assurance - LLNL | Pope, Greg | Brainard, Matt | Internal Review | Internal Audit Plan and Report | Internal audit of DOE NE-8 tasks | 2021-06-30 |  | 2021-06-30 | Completed and reviewed, revised, rereviewed. | 2021 | Complete | LLNL SFWD Quality Assurance (QA) Assessment |  |  | None | SFWD QA Assessment Report 2021 sig.pdf
M4SF-21SN010309021 | M4 | 1.08.01.03.09.02 | SNL | SF-21SN01030902 | Waste Form Testing, Modeling, and Performance - SNL | Jove-Colon, Carlos | Camphouse, Chris | Modeling Activities Related to Waste Form Degradation: Progress Report | Modeling Activities Related to Waste Form Degradation: Progress Report | Description of modeling approaches related to waste form degradation as part of the Waste Form Testing, Modeling, and Performance work package | 2021-06-30 |  | 2021-06-30 | The report summarizes modeling activities on waste glass degradation with emphasis on Stage III accelerated degradation rate, DFT study on the sodium uranate clarkeite to evaluate thermodynamic and mechanical properties, and development of a zero-D thermodynamically-based electrochemical model of SNF (UO2) corrosion. | 2021 | Complete | Modeling Activities Related to Waste Form Degradation: Progress Report | Carlos F. Jove Colon | Carlos F. Jove Colon | None | M4SF-21SN010309021_ Modeling_Act_WF_Degrad_Prog_Report_CFJC_rev3.pdf |  | waste form degradation; modeling; waste glass dissolution; clarkeite; thermodynamics; SNF; UO2 corrosion; electrochemicstry
M4SF-21SR010802052 | M4 | 1.08.01.08.02.05 | SRNL | SF-21SR01080205 | Quality Assurance - SRNL | Smith, Pat | Brainard, Matt | SRNL Level 4 Quality Assurance Surveillance | Complete Level 4 QA Surveillance | Complete QA Surveillance of the SRNL NE program. | 2021-06-30 |  | 2021-06-28 | An assessment was conducted of Savannah River National Laboratory (SRNL) work activities as required to complete the Fiscal Year (FY) 2021 Work Package (WP) SF-21SR01080205, Milestone #M4SF-21SR010802052 assigned Quality Rigor Level 4 (QRL4). | 2021 | Complete | SRNL Quality Assurance (QA) Assessment Report for the NE8, Spent Fuel and Waste Disposition (SFWD) Program | P. Smith | P. Smith | None | 2021-SUR-11-0006.pdf |  | Surveillance; Spent Fuel and Waste Disposition
M4SF-21SN010802042 | M4 | 1.08.01.08.02.04 | SNL | SF-21SN01080204 | Quality Assurance - SNL | Camphouse, Chris | Brainard, Matt | Summary of Assessments Performed in FY21 by SNL QA POC for SFWD Work Activities | Summary of Assessments Performed FY20 by SNL QA POC for SFWD Work Activities at Sandia National Laboratories | Summary of Assessments Performed in FY20 by SNL QA POC for SFWD Work Activities at Sandia National Laboratories | 2021-06-30 |  | 2021-07-01 | The M4 milestone was completed on 6/30 but wasn't loaded into PICs until 7/1. | 2021 | Complete | Summary of Assessments Performed in FY21 by SNL QA POC for FY20 SNL SFWD Milestone Deliverables | Mike Wallace | Chris Camphouse | None | SNL_SFWD_FY20 Milestone Deliverables QA Assessment Report.pdf
M4SF-21IN010802072 | M4 | 1.08.01.08.02.07 | INL | SF-21IN01080207 | Quality Assurance - INL | Sharp, Michelle | Brainard, Matt | Assessment of INL SFWD Activities | Assessement of INL SFWD activities | Assessment of SFWD Activities based on the requirements detailed in PLN-3708. | 2021-06-30 |  | 2021-06-24 | Assessment of INL SFWD completed on 6/24/21 | 2021 | Complete |  | Michelle Sharp | Michelle Sharp | None | 2021 INL SFWD QA Assessment final.pdf
M2SF-21SN010305073 | M2 | 1.08.01.03.05.07 | SNL | SF-21SN01030507 | Multi-Physics Simulation of DPC Criticality - SNL | Hardin, Ernest | Freeze, Geoff | Accelerated Final Development of Fuel/Basket Degradation Model | Fuel/Basket Degradation Model Summary | Generate a catalog of degraded fuel/basket configurations for reactivity analysis. Organize the model for description in a M3 milestone. Support review activities. Note this activity is exxpected to carry over approximately $100k to FY22. | 2021-07-15 |  | 2021-07-12 | Finished early due to vacation schedules of staff and management. | 2021 | Complete | Fuel/Basket Degradation Modeling Summary | Hardin,Ernest | Hardin,Ernest | None | M2 2021 DPC multiphysics Final.pdf |  | spent nuclear fuel; dual-purpose canisters; geologic disposal
M4SF-21LA010302014 | M4 | 1.08.01.03.02.01 | LANL | SF-21LA01030201 | Crystalline Disposal R&D - LANL | Viswanathan, Hari | Camphouse, Chris | Summary Report on FY21 Crystalline and Crystalline International Disposal Activities | Summary Report on FY21 Crystalline and Crystalline International Disposal Activities | Level 4 milestone that summarize LANL Crystalline and Crystalline International activities. | 2021-07-16 |  | 2021-07-06 | This report describes the discrete fracture network modeling activities and colloid experiments conducted for FY21. | 2021 | Complete | Crystalline and Crystalline International Disposal Activities | Hari Viswanathan | Hari Viswanathan | None | M4SF-21LA010302014.pdf |  | fractures; colloids; performance assessment+X687; crystalline rock
M4SF-21LL010301052 | M4 | 1.08.01.03.01.05 | LLNL | SF-21LL01030105 | Argillite Disposal R&D - LLNL | Zavarin, Mavrik | Camphouse, Chris | Deliver SUPCRTNE Thermodynamic database engine | Deliver SUPCRTNE Thermodynamic database engine | Milestone report | 2021-07-16 | 2021-07-23 | 2021-09-10 | Final milestone report for SF-21LL01030105 | 2021 | Complete | M4SF-21LL010301052- SUPCRTNE Thermodynamic Database Engine | Mavrik Zavarin | T. Wolery | None | M4SF-21LL010301052.pdf
M4SF-21LL010301062 | M4 | 1.08.01.03.01.06 | LLNL | SF-21LL01030106 | Argillite International Collaborations - LLNL | Zavarin, Mavrik | Camphouse, Chris | Deliver Rev0 Non-Electrostatic Surface Complexation Database for GDSA. | Deliver Rev0 Non-Electrostatic Surface Complexation Database for GDSA. | Milestone report | 2021-07-16 | 2021-07-23 | 2021-09-10 | Final Milestone report for SF-21LL01030106. | 2021 | Complete | M4SF-21LL010301062 Rev0 Non-Electrostatic Surface Complexation Database for GDSA | Mavrik Zavarin | Mavrik Zavarin | None | M4SF-21LL010301062.pdf |  | thermodynamics; database
M4SF-21LL010302052 | M4 | 1.08.01.03.02.05 | LLNL | SF-21LL01030205 | Crystalline Disposal R&D - LLNL | Zavarin, Mavrik | Camphouse, Chris | Review of steel corrosion impacts on radionuclide immobilization | Review of steel corrosion impacts on radionuclide immobilization | Draft report to SFWST | 2021-07-16 | 2021-07-23 | 2021-09-10 | Final Milestone report for SF-21LL01030205 | 2021 | Complete | M4SF-21LL010302052-Steel Corrosion Impacts on Radionuclide Immobilization | Mavrik Zavarin | Enrica Balboni | None | M4SF-21LL010302052.pdf |  | corrosion
M4SF-21LL010302062 | M4 | 1.08.01.03.02.06 | LLNL | SF-21LL01030206 | Crystalline International Collaborations - LLNL | Zavarin, Mavrik | Camphouse, Chris | Update on NEA-TDB database development and deliver database formatting tool | Update on NEA-TDB database development and deliver database formatting tool | Milestone report | 2021-07-16 | 2021-07-23 | 2021-09-10 | Final milestone report for SF-21LL01030206 | 2021 | Complete | M4SF-21LL010302062-Update on NEA-TDB Database Development and Database Formatting Tool | Mavrik Zavarin | Mavrik Zavarin | None | M4SF-21LL010302062.pdf |  | Thermodynamics, database
M3SF-21SN010309013 | M3 | 1.08.01.03.09.01 | SNL | SF-21SN01030901 | OWL - Inventory - SNL | Weck, Philippe | Camphouse, Chris | Status of OWL Updates | Status Report on OWL | Draft document of OWL updates | 2021-07-16 |  | 2021-07-15 | Draft Report – Internal Use Only – representing completion of Milestone deliverable M3SF-21SN010309013 “Status of OWL Updates”, which provides an update on status of FY 2021 activities for the work package SF-21SN01030901 | 2021 | Complete | Status of OWL Updates | Philippe Weck | Philippe Weck | None
M3SF-21LA010301011 | M3 | 1.08.01.03.01.01 | LANL | SF-21LA01030101 | Argillite Disposal R&D - LANL | Sauer, Kirsten | Camphouse, Chris | Argillite R&D report - LANL | Argillite R&D Report - LANL | The United States’ Department of Energy Spent Fuel and Waste Disposition program is investigating disposal concepts in a variety of host rock settings and thermal loads. Target geologic formations include crystalline (e.g., granite), argillite (e.g., sedimentary rocks with a high clay mineral content), and salt. Different configurations and loadings of spent nuclear fuel and waste within disposal canisters are also being investigated, some of which have the potential to generate repository temperatures higher than previously considered (i.e., temperatures > 100ºC) by foreign and domestic concepts. This report focuses on understanding geochemical and mineralogical changes in the engineered barrier system (EBS), consisting of waste canister, bentonite buffer, and cementitious materials, in a high temperature argillite-hosted repository. Experiments were designed to develop EBS concepts in a high-temperature argillite environment in 1) bentonite-cement reactions, 2) interaction between waste canister materials and bentonite, and 3) influence of phosphate additives to the bentonite buffer. Experiment results are applied to understanding long-term repository performance. See report for more information. | 2021-07-19 |  | 2021-07-15 | Completed on schedule. | 2021 | Complete | Argillite Disposal R&D and Argillite International Collaborations - LANL | Kirsten Sauer | Kirsten Sauer | None | ArgilliteRD_International_LANL_FY21.pdf |  | argillite, bentonite, EBS, experimental, Opalinus Clay, zeolite, ordinary Portland cement
M3SF-21LA010301021- same report uploaded to pics as M3SF-21LA010301011 | M3 | 1.08.01.03.01.02 | LANL | SF-21LA01030102 | Argillite International Collaborations - LANL | Caporuscio, Florie | Camphouse, Chris | Argillite International Collaboration Report - LANL | Argillite International Collaboration Report - LANL | This is a combined document with Argillite R&D - Los Alamos National Laboratory | 2021-07-19 |  | 2021-07-19 | delivered on time | 2021 | Complete | Argillite Disposal R&D and Argillite International Collaborations - LANL | Kirsten Sauer | Florie Caporuscio | None | ArgilliteRD_International_LANL_FY21.pdf
M3SF-21AN010309032 | M3 | 1.08.01.03.09.03 | ANL | SF-21AN01030903 | SNF Modeling and Testing - ANL | Thomas, Sara | Camphouse, Chris | Report on simfuel studies | Report on simfuel studies | Summary report documenting synthesis and characterization of Simfuel materials, electrochemical tests, and initial development of module for FMDM | 2021-07-19 |  | 2021-07-19 | Completed level 3 milestone report. The report discusses the synthesis and characterization of two simulated spent fuel (SIMFUEL) materials and the initial electrochemical corrosion tests that were performed to determine the effect of noble metal presence on UO2 dissolution rate. | 2021 | Complete | Synthesis, Characterization, and Electrochemical Corrosion of SIMFUEL: Preliminary Results | Sara Thomas | Sara Thomas | None | ANL_M3SF-21AN010309032.pdf |  | Spent fuel degradation, SIMFUEL, electrochemical corrosion
M3SF-21SN010304072 | M3 | 1.08.01.03.04.07 | SNL | SF-21SN01030407 | GDSA PFLOTRAN Development – SNL | Nole, Michael | Stein, Emily | PFLOTRAN Development FY2021 | PFLOTRAN Development FY2021 | This milestone will describe in detail the PFLOTRAN software development that took place over the fiscal year in support of GDSA Framework and GDSA Repository Systems Analysis. | 2021-07-21 |  | 2021-07-19 | This deliverable was completed on time. Tara LaForce performed a technical review. | 2021 | Complete | PFLOTRAN Development FY2021 | Applied Systems Analysis and Research | Michael Nole | None | PFLOTRAN-Dev-FY21.pdf |  | GDSA; disposal research; subsurface simulation; software development
M3SF-21SN010303062 | M3 | 1.08.01.03.03.06 | SNL | SF-21SN01030306 | Salt International Collaborations - SNL | Kuhlman, Kris | Stein, Emily | Salt International Collaborations FY21 Update | Salt International Collaborations FY21 Update |  | 2021-07-30 |  | 2021-07-29 | Salt International M3 completed on schedule. | 2021 | Complete | Salt International Collaborations FY21 Update | Kris Kuhlman | Kris Kuhlman | None | SAND2021-9232R_Salt_2021_international_status_report_09.pdf
M4SF-21PN010802092 | M4 | 1.08.01.08.02.09 | PNNL | SF-21PN01080209 | Quality Assurance - PNNL | Wilson, Emily | Brainard, Matt | PNNL SFWST Quality Audit | PNNL SFWD Quality Audit | Completion of PNNL SFWST Quality Audit with a final report to be provided to the Federal Manager. | 2021-07-30 | 2021-07-16 09:00 | 2021-07-13 | Ram wants everyone to get their deliverables in by end of June to allow time for Michelle Sharp to consolidate a report for Ram. | 2021 | Complete | Spent Fuel Waste Disposition (SFWD) Quality Assurance (QA) Assessment Report Rev. 0 | Emily Wilson | Emily Wilson | None | 2021 PNNL SFWD QA Assessment 07.16.21.pdf |  | Quality Audit
M4SF-21OR010310051 | M4 | 1.08.01.03.10.05 | ORNL | SF-21OR01031005 | Planning for URL - ORNL | Montgomery, Rose | Stein, Emily | Experimental Apparatus and Calibration Results | Experimental Apparatus and Calibration Results | Develop experimental apparatus and perform calibration and testing. | 2021-07-30 |  | 2021-07-30 | Progress report submitted instead of calibration results per email with CAM on 4/26/2021 | 2021 | Complete | Underground Research Laboratory Muon Detector Project Progress Report | Jennifer Meszaros | Jennifer Meszaros | None | M4SF-21OR010310051_ORNL_URL-muon-detector-project.pdf |  | URL; muon detector
M4SF-21LB010802022 | M4 | 1.08.01.08.02.02 | LBNL | SF-21LB01080202 | Quality Assurance - LBNL | Faybishenko, Boris | Brainard, Matt | LBNL QA Surveillance | LBNL QA Surveillance Report FY21 | LBNL QA Surveillance | 2021-07-31 |  | 2021-07-30 | An assessment was conducted to complete the FY21 Milestone report M4SF-21LB01080202 of the Lawrence Berkeley National Laboratory (LBNL), and to verify that the LBNL’s SFWD activities are conducted according to the SFWD Quality Assurance (QA) Program and meet the QAPD Revision 6 requirements. This report presents a summary of the QA requirements, methods used for the self-assessment, and results of the self-assessment, along with a required assessment checklist. | 2021 | Complete | Spent Fuel and Waste Disposition (SFWD) LBNL Quality Assurance (QA) Assessment Report - FY21 | Boris Faybishenko | Boris Faybishenko | None | M4SF-21LB010802022-LBNL QA Assessment FY21 Report-2021-07-30.pdf |  | Quality Assurance; SFWD program; Self-assessment report, Assessment checklist
M2SF-21SN010304054 | M2 | 1.08.01.03.04.05 | SNL | SF-21SN01030405 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | SFWST Disposal Research R&D 5-Year Plan Update | SFWST Disposal Research R&D 5-Year Plan FY2021 | Disposal Research R&D 5-Year plan update | 2021-08-12 |  | 2021-08-10 | Draft internal-use report. Technical review complete. | 2021 | Complete | SFWST Disposal Research R&D 5-Year Plan – FY2021 Update | David Sassani | Paul Mariner | None | SFWST Disposal Research R&D 5-Year Plan FY21 Final M2 SAND2021_12491R.pdf |  | Disposal research plan
M4SF-21LB010304091 | M4 | 1.08.01.03.04.09 | LBNL | SF-21LB01030409 | GDSA Modeling and Integration - LBNL | Zheng, Liange | Stein, Emily | LBNL FY21 research in GDSA Modeling and Integration | LBNL FY21 research in GDSA Modeling and Integration | The report provides a summary of LBNL’s research in development of methodologies to integrate surrogate-model-based Kd into the GDSA models. We extended the surrogate modeling approach implemented in FY21 to represent the spatio-temporal heterogeneity of uranium concentrations within the buffer. This extension allows for more flexible connections between the THC and PA models to simulate radionuclide fluxes from the buffer to the host rock, and to apply the Kd concept to conserve fluxes in addition to the mass conservation within the buffer. | 2021-08-13 |  | 2021-08-13 | This report documents LBNL’s research activities conducted in Work Package “SF-21LB01030409, GDSA Modeling and Integration - LBNL.” The objective of this activity is to develop a methodology and toolsets for integrating complex, coupled models (such as THMC or THC) into the GDSA model of nuclear waste disposal. The research activities have focused on developing a methodology to integrate surrogate-model-based Kd into the GDSA models. | 2021 | Complete | LBNL FY21 Research in GDSA Modeling and Integration | Haruko Wainwright1, Hannah Lu2, Dinara Ermakova3, Daniel Tartakovsky2, LianGe Zheng1, 1LBNL, 2Stanford University, 3University of California, Berkeley | LianGe Zheng | None | FY21 M4SF-21LB010304091 FINAL 08.13.21.pdf |  | Surrogate model; Kd; THC; EBS; GDSA; Reduced Order Modeling
M3SF-21SN010304042 | M3 | 1.08.01.03.04.04 | SNL | SF-21SN01030404 | GDSA - Uncertainty and Sensitivity Analysis Methods - SNL | Swiler, Laura | Stein, Emily | Uncertainty and Sensitivity Analysis Methods and Applications in the GDSA Framework (FY2021) | Uncertainty and Sensitivity Analysis Methods and Applications in the GDSA Framework (FY2021). | Work on UQ and SA methods and demonstrations, culminating in report documenting development and application of UQ/SA tools for GDSA Framework. | 2021-08-13 |  | 2021-08-13 | Final report for M3SF-21SN010304042. | 2021 | Complete | Uncertainty and Sensitivity Analysis Methods and Applications in the GDSA Framework (FY2021). | Laura Swiler | Laura Swiler | None | GDSA_SAUQ_2021_Final_Aug13.pdf |  | uncertainty quantification; sensitivity analysis
M4SF-21LA010304032 | M4 | 1.08.01.03.04.03 | LANL | SF-21LA01030403 | GDSA - Modeling and Integration - LANL | Hyman, Jeffrey | Stein, Emily | dfnWorks development in support of GDSA | Report Document of dfnWorks Development in support of GDSA | Report Document of dfnWorks Development in support of GDSA | 2021-08-15 |  | 2021-08-11 | Complete milestone report and submitted. | 2021 | Complete | dfnWorks development in support of GDSA | Jefrey Hyman | Jefrey Hyman | None | M4SF-21LA010304032.pdf |  | discrete fracture networks
M3SF-21LA010303012 | M3 | 1.08.01.03.03.01 | LANL | SF-21LA01030301 | Salt Disposal R&D - LANL | Stauffer, Philip | Stein, Emily | 2021 LANL Contributions to the BATS Test in WIPP | 2021 LANL Contributions to the BATS Test in WIPP | This document describes the LANL contributions to the BATS experiments performed during fiscal year 2021. | 2021-08-17 |  | 2021-08-17 | Work continues on simulating isotopic fractionation in the BATS 1.0 experiment. Updates to our porous flow simulator to allow more detailed humidity boundary conditions have been implemented and are being tested. New tracer data are being analyzed. We are helping with planning for BATS 2.0 and are working on procurements to ensure that we are ready to install the test soon after drilling. Lab experiments on isotopes are starting to move again after COVID delays. NMR experiments on core are ongoing. | 2021 | Complete | 2021 LANL Contributions to the BATS Test in WIPP | Eric Guiltinan | Philip Stauffer | None | 2021_Augut_17_M3SF-21LA010303012.pdf |  | WIPP; Experiment; Heat; Tracer test
M2SF-21SN010302072 | M2 | 1.08.01.03.02.07 | SNL | SF-21SN01030207 | Crystalline Disposal R&D - SNL | Wang, Yifeng | Camphouse, Chris | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks: FY21 Report | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks: FY21 Report | This report will summarize all the work that will be accomplished in FY21 for crystalline work packages across multiple labs. | 2021-08-17 |  | 2021-08-13 | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks: FY21 Report | 2021 | Complete | Process Model Development and Experimental Investigation for Spent Fuel Disposal in Crystalline Rocks: FY21 Report | Yifeng Wang | Yifeng Wang | None | M2SF-21SN010302072A.pdf
M3SF-21LB010303031 | M3 | 1.08.01.03.03.03 | LBNL | SF-21LB01030303 | Salt Disposal R&D - LBNL | Rutqvist, Jonny | Stein, Emily | Salt Coupled THMC Processes Research Activities at LBNL: FY21 Progress | Salt Coupled THMC Processes Research Activities at LBNL: FY21 Progress | Activities related to coupled THMC processes research at LBNL with inputs from LBNL Salt International Collaboration | 2021-08-17 |  | 2021-08-17 | This report documents the status of LBNL’s research activities on coupled THMC processes in salt formations. In particular, the status of the TOUGH-FLAC simulator for modeling salt coupled processes, description of newly implemented salt constitutive models, LBNL’s modeling THM modeling of a repository tunnel using the new constitutive models, modeling of potential long-term waste canister movements, new coupled mechanical-chemical modeling of salt micro-scale compaction, DECOVALEX-2023 modeling tasks, and status of LBNL’s research activities on monitoring modeling of geophysical processes at the Brine Availability Test in Salt (BATS) at WIPP, ,in particular, related to Cross-borehole Electrical Resistivity Tomography (ERT) and fiber optical sensing of temperature and strain. | 2021 | Complete | Salt Coupled THMC Processes Research Activities at LBNL: FY21 Progress | Jonny Rutqvist, Mengsu Hu, Hafssa Tounsi, Yuxiin Wu, Carl Steefel, Sebatian Uhlemann, Jiannan Wang, Jens Birkholzer | Jonny Rutqvist | None | FY21 M3SF-21LB010303031 Final 08.17.21.pdf |  | Salt, Brine; Coupled processes; Modeling; Micro-scale compaction; Field tests; WIPP; TOUGH-FLAC; Temperature; Permeability; THM; Cross-borehole Electrical Resistivity Tomography
M3SF-21SN010301072- Deliverable not found in PICS for FY 2020, 2021, or 2022. Emailed Carlos Jove Colon. | M3 | 1.08.01.03.01.07 | SNL | SF-21SN01030107 | Argillite Disposal R&D - SNL | Jove-Colon, Carlos | Camphouse, Chris | Evaluation of Nuclear Spent Fuel Disposal in Clay-Bearing Rock - Process Model Development And Experimental Studies | End of FY20 status report of accomplishments for R&D activities on disposal in argillaceous / clay-bearing rock | End of FY21 status report of accomplishments for R&D activities on disposal in argillaceous / clay-bearing rock | 2021-08-20 |  |  |  | 2021 | Complete |  |  |  | None
M4SF-21SN010308062 | M4 | 1.08.01.03.08.06 | SNL | SF-21SN01030806 | Engineered Barrier System International Collaborations - SNL | Matteo, Ed | Camphouse, Chris | FY21 Report on EBS International Activities | FY21 Report on EBS International Activities | Feeder to International M2 | 2021-08-27 |  | 2021-08-27 | This report describes SNL international activities associated with DECOVALEX2023, Task C. | 2021 | Complete | FY21 Report on Activities for EBS International | Edward N. Matteo | Edward N. Matteo | None
M3SF-21PN010309054 | M3 | 1.08.01.03.09.05 | PNNL | SF-21PN01030905 | SNF Modeling and Testing - PNNL | Buck, Edgar | Camphouse, Chris | Report on Electrochemical Cells for SNF Model Validation | Report on In-situ and Electrochemical Work for Model Validation | FY21 Final Report | 2021-08-27 |  | 2021-08-31 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 1, 2021. | 2021 | Complete | Microfluidic Electrochemical Cells for Monitoring Uranium Oxide Corrosion | Xiao-Ying Yu, Jen Yao, Eugene S Ilton, Shalini Tripathi, Shawn Riechers, Nabajit Lahiri, Jaeyoung Heo, Jiyoung Son, Dongsheng Li, Edgar Buck | Edgar Buck | None | SFWST_FY21_Final-Report_Buck.pdf |  | Uranium oxide corrosion, System for Analysis at the Vacuum Liquid Interface (SALVI)
M4SF-21LA010309041 | M4 | 1.08.01.03.09.04 | LANL | SF-21LA01030904 | SNF Modeling and Testing - LANL | Migdissov, Artaches | Camphouse, Chris | SNF Modeling and Testing - LANL | SNF Modeling and Testing Report - LANL | delivered ahead of schedule | 2021-08-27 |  | 2021-07-21 | This contribution consists of two parts, the first of which reports findings from FY21 on the behavior of uranium in carbonate bearing aqueous solutions at elevated temperatures up to 250 °C. This study demonstrates that the aqueous transport of U by carbonate aqueous complexes is significant only at temperatures below 120-140 °C. At higher temperatures, carbonate complexes of U destabilize and, thus, will not predominate in aqueous solutions with carbonate concentrations typically associated with natural surface waters and deep geological fluids. Considering that many models assume carbonate as a main vehicle for U transport in natural fluids, this finding has important consequences, and likely necessitates a re-evaluation of current models that assess the transport of U. The results of this study have been reported in a paper published by Communications Chemistry (Nature Research) (Kalintsev et al., in press). The second part of this report is devoted to re-visiting experimental data on the aqueous speciation of U, reported at previous stages of the project. Since 2018, the behavior of U in hydrothermal solutions has been investigated for a set of aqueous systems, including chloride- and sulfate-bearing fluids. This data has been reported in a set of contributions published in Geochimica et Cosmochimica Acta and J. Phys. Chem. B (Migdisov et al., 2018a; Alcorn et al., 2019; Kalintsev et al., 2019). Incorporation of this data into predictive thermodynamic models requires the representation of experimental data in the form of Equations of State (EoS) suitable for modeling with major thermodynamic codes. Thus, the second part of this contribution documents the efforts aimed at fitting the published experimental data, together with previously reported data available in the literature, to the Modified Ryzhenko-Bryzgalin (MRB) and the Helgeson-Kirkham-Flowers (HKF) models and reports the tables of species-specific parameters for these equations of state. | 2021 | Complete | SNF Modeling and Testing - LANL (FY21) |  |  | None | FY21_SNF Modeling and Testing - LANL - corrected.pdf
M2SF-21SN010303052 | M2 | 1.08.01.03.03.05 | SNL | SF-21SN01030305 | Salt Disposal R&D - SNL | Kuhlman, Kris | Stein, Emily | Brine Availability Test in Salt (BATS) FY21 Update | Brine Availability Test in Salt (BATS) FY21 Update | This level-2 milestone report summarizes data collected as part of the Brine Availability Test in Salt (BATS) at the Waste Isolation Pilot Plant (WIPP). The milestone includes contributions from LANL and LBNL level-3 milestone reports. | 2021-08-31 |  | 2021-08-30 | M2 report finished one day early | 2021 | Complete | Brine Availability Test in Salt (BATS) FY21 Update | Kris Kuhlman | Kris Kuhlman | None | SAND2021-10962R_FY21-Update-on-BATS-41-final.pdf |  | salt; field test; brine availability test in salt; BATS; waste isolation pilot plant; WIPP
M4SF-21SN010302082 | M4 | 1.08.01.03.02.08 | SNL | SF-21SN01030208 | Crystalline International Collaborations - SNL | Wang, Yifeng | Camphouse, Chris | Report on international collaborations | Report on international collaborations | A summary report will be provided to LBNL on international collaborations for crystalline work packages. | 2021-08-31 |  | 2021-08-30 | On schedule | 2021 | Complete | FY21 report on international collaborations | Yifeng Wang | Yifeng Wang | None | Internationa collaboration SNL_Hadgu_and_Wang_2021.docx
M2SF-21SN010304062 | M2 | 1.08.01.03.04.06 | SNL | SF-21SN01030406 | GDSA - Repository Systems Analysis - SNL | LaForce, Tara | Stein, Emily | GDSA Repository Systems Analysis Investigations in FY2021 | GDSA Repository Systems Analysis Investigations in FY20213 | Milestone report | 2021-09-01 |  | 2021-08-31 | Technical review complete via email from Michael Nole, Alex Salazar, and Rick Jayne. | 2021 | Complete | GDSA Repository Systems Analysis Investigations in FY2021 |  |  | None | 2021 GDSA RSA SAND2021-11691R UUR.pdf
M3SF-21LA010308011 | M3 | 1.08.01.03.08.01 | LANL | SF-21LA01030801 | Engineered Barrier System R&D - LANL | Caporuscio, Florie | Camphouse, Chris | EBS R&D report - LANL | EBS R&D report - LANL |  | 2021-09-03 |  | 2021-09-02 | submitted one day ahead of schedule | 2021 | Complete | Engineered Barrier System R&D and International Collaborations – LANL – FY21 | Caporuscio / Sauer / Rock | Florie Caporuscio | None | FY21_EBS_compressed.pdf
M3SF-21LA010308021- Same report as M3SF-21LA010308011 | M3 | 1.08.01.03.08.02 | LANL | SF-21LA01030802 | Engineered Barrier System International Collaborations - LANL | Caporuscio, Florie | Camphouse, Chris | Engineered Barrier System International Collaboration report - LANL | Engineered Barrier System International Collaboration report - LANL | carry over | 2021-09-03 |  | 2021-09-02 | submitted one day ahead of schedule | 2021 | Complete | Engineered Barrier System R&D and International Collaborations – LANL – FY21 | Caporuscio / Sauer / Rock | Florie Caporuscio | None | FY21_EBS_compressed.pdf
M2SF-21SN010304053 | M2 | 1.08.01.03.04.05 | SNL | SF-21SN01030405 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | GDSA Framework Development and Process Model Integration | GDSA Framework Development and Process Model Integration FY2021 | Report on FY21 progress on GDSA Framework development | 2021-09-13 |  | 2021-09-13 | Technical review complete, as acknowledged by email from reviewer David Sassani to Paul Mariner | 2021 | Complete | GDSA Framework Development and Process Model Integration FY2021 |  |  | None | 2021 GDSA Framework Dev SAND2021-12626 R M2SF-21SN010304053.pdf
M3SF-21OR010305127 | M3 | 1.08.01.03.05.12 | ORNL | SF-21OR01030512 | DPC Reactivity and Criticality Modeling - ORNL | Banerjee, Kaushik | camphouse, Chris | Update of DPC direct disposal criticality analysis report | DPC direct disposal criticality analysis report | This report will be an update of the current DPC disposal criticality report to incorporate the newly developed templates and results including misload analysis results into the existing living document. | 2021-09-17 |  | 2021-09-17 | This revision adds to the prior report a summary of direct disposal analyses performed during FY21, including a variety of additional US reactor sites. | 2021 | Complete | Dual Purpose Canister Reactivity and Groundwater Absorption Analyses | ORNL | Justin Clarity | None | M3SF-21OR010305127.pdf
M4SF-21SN010101023 | M4 | 1.08.01.01.01.02 | SNL | SF-21SN01010102 | Knowledge Management - SNL | Meacham, Janette | Sassani, Dave | Analysis and Planning for KM program expansion | Report documenting analysis and planning | Explore potential for expanding KM program to other areas of Sandia and DOE. To include potential international collaborations (NEA, NEI, etc.) | 2021-09-17 |  | 2021-09-17 | Taxonomy workshops, focus groups, and planning sessions were completed in February and will continue into March and April. | 2021 | Complete | Knowledge Management Analysis for Content Migration | Janette Meacham | Janette Meacham | None | 2021-10-01_KM Content Migration Plan SAND2021-12346.pdf |  | knowledge management analysis
M3SF-21IN010305082 | M3 | 1.08.01.03.05.08 | INL | SF-21IN01030508 | Neutron Absorber Evaluation - INL | Jarrell, Josh | Freeze, Geoff | Complete report on FY21 testing | Complete report on FY21 testing | Report will document additional FY21 test results, including corrosion performance of new coated and 3D printed materials, and will provide additional recommendations for follow-on activities. | 2021-09-17 |  | 2021-09-16 | Deliverable completed on time and transmitted via email to CAM and NTD. | 2021 | Complete | Neutron Absorber Material Corrosion Testing Final Report FY2021 | Tedd Lister | Tedd Lister | None | FY21 NAM comp report final.pdf
M4SF-21SN010101022- Only agendas are in PICS not final reports | M4 | 1.08.01.01.01.02 | SNL | SF-21SN01010102 | Knowledge Management - SNL | Meacham, Janette | Sassani, Dave | Conduct Additional Deep Dive Workshops | Final Reports for each Deep Dive Conducted | Conduct additional Deep Dive Workshop - Potentially Storage & Transportation, Requirements for a Repository Project, Regulatory Requirements, Others TBD - building on knowledge capture from FY20. | 2021-09-17 |  | 2021-08-20 | Two Deep Dive Meetings are scheduled to be conducted in March. | 2021 | Complete |  |  |  | None
M4SF-21LA010305031 | M4 | 1.08.01.03.05.03 | LANL | SF-21LA01030503 | Direct Disposal of Dual Purpose Canisters - LANL | Caporuscio, Florie | Freeze, Geoff | Direct Disposal of Dual Purpose Canisters - LANL | Direct Disposal of Dual Purpose Canisters - LANL |  | 2021-09-24 |  | 2021-09-23 | delivered ahead of schedule | 2021 | Complete | Direct Disposal of Dual Purpose Canisters - LANL | Florie Caporuscio | Florie Caporuscio | None | DirectDisposal_FY21_reduced_newdisclaimer.pdf
M3SF-21OR010305019 | M3 | 1.08.01.03.05.01 | ORNL | SF-21OR01030501 | DPC Fillers R&D - ORNL | Banerjee, Kaushik | Freeze, Geoff | DPC filler simulation and demonstration progress report | Update on filler demonstration project | This report will document the filler simulation and experimental validation progress made at ORNL by end of FY21. The report will also document the planned pipe experiment and data analysis. | 2021-09-24 |  | 2021-09-24 | Status report complete and attached here. | 2021 | Complete | Dual-Purpose Canister Filling Demonstration Project Progress Report | Bret Brickner | Bret Brickner | None | M3SF-21OR010305019-Dual-Purpose Canister Filling Demonstration Project Progress Report.pdf.pdf |  | filler; direct disposal; DPC
M3SF-21OR010309093 | M3 | 1.08.01.03.09.09 | ORNL | SF-21OR01030909 | Advanced Isotopic Measurements of HBU SNF - ORNL | Bevard, Bruce | Camphouse, Chris | Report on Isotopic Analysis of 8 PWR and 8 BWR SNF samples | Report on Isotopic Analysis of 8 PWR and 8 BWR SNF samples | Report on both the PWR and BWR SNF fuel isotopic analysis along with the corresponding ORIGEN calculations | 2021-09-24 | 2022-09-30 |  | this work is delayed and will be completed after both PWR and BWR isotopic work is completed | 2021 | Expected Late |  |  |  | None
M3SF-21LA010304022 | M3 | 1.08.01.03.04.02 | LANL | SF-21LA01030402 | GDSA - Geologic Modeling - LANL | Gross, Michael | Stein, Emily | Advances in 3D geologic modeling of alluvial basins with a focus on facies and property modeling | Advances in 3D geologic modeling of alluvial basins with a focus on facies and property modeling | Geologic framework models will be developed at multiple scales in order to evaluate the suitability of alluvial basins for hosting nucleear waste repositories. | 2021-09-30 |  | 2021-09-30 | The project is on schedule for completion of deliverable. | 2021 | Complete | Advances in 3D Geologic Modeling of Alluvial Basins with a Focus on Facies and Property Modeling | Michael Gross, Eric Guiltinan, Damien Milazzo, Terry A. Miller, Erika Swanson, Elizabeth Miller, Anita Lavadie-Bulnes Philip Stauffer, Tara LaForce | Michael Gross | None | FY21 LANL_GDSA_Alluvium_Milestone.pdf |  | Geologic modeling; alluvial basin; lithofacies; permeability
M3SF-21ID010801067 | M3 | 1.08.01.08.01.06 | DOE-ID | SF-21ID01080106 | Program Controls - Management of PICS:NE and Analytic Support - DOE-ID | Brainard, Matt | Brainard, Matt | Conduct Monthly Program Performance Analysis and Submit Performance Review Presentations to DOE (FY 2020) | FY21 SFWD Program Performance Reviews | Monthly Program Review Presentations. Quarterly Program Review Presentations and Telecons. | 2021-09-30 |  | 2021-09-30 | Distributed the final FY 2021 August Monthly Performance Review on 9/30/2021 to claim completion of this M3 milestone. Previous Monthly/Quarterly Performance Review distributions include FY20 September Year End through FY21 July reviews (twelve in total). | 2021 | Complete | FY 2021 SFWD Monthly Program Performance Reviews (FY20 September thru FY21 August) | Matt Brainard | AST | None | SFWD_Quarterly Performance Review_FY20_Q4_Final.pdf
M3SF-21PN010304101 | M3 | 1.08.01.03.04.10 | PNNL | SF-21PN01030410 | GDSA - Modeling and Integration - PNNL | Nutt, Mark | Stein, Emily | Prototype GDSA Biosphere Model | Prototype GDSA Biosphere Model | Report describing prototype GDSA Biosphere Model. | 2021-09-30 |  | 2021-09-30 | GDSA Biosphere Prototype Model Design Document Rev 0 describes the software design and mathematical basis for the transport and exposure of radionuclides in the prototype biosphere model. The proposed biosphere model was designed to be flexible and generic in order to accommodate a variety of different sites and climate states. The source of radionuclides in the biosphere is the radionuclides in the groundwater as determined through PFLOTRAN simulation. The GDSA Biosphere model then assesses the potential movement of radionuclides through the surface biosphere and the subsequent exposure to a human receptor living in the biosphere. The prototype of the biosphere model focused on developing a full exposure pathway for a human receptor (groundwater/surface water to irrigated crops to harvested crops to ingested crops to human receptor dose). | 2021 | Complete | GDSA Biosphere Model Design Document | Saikat Ghosh, Caitlin A Condon, Bruce A Napier, Glenn Hammond | Caitlin Condon | None | M3SF-21PN010304101 GDSA Biosphere SDD.pdf
M2SF-21LB010307012 | M2 | 1.08.01.03.07.01 | LBNL | SF-21LB01030701 | Disposal Research International Coordination - LBNL | Birkholzer, Jens | Birkholzer, Jens | International Collaboration Activities in Geologic Disposal Research: FY21 Progress Report | International Collaboration Activities in Geologic Disposal Research: FY21 Progress Report | This report gives a comprehensive overview of international collaboration initiatives. Opportunities arising from DOE’s membership in international initiatives as well DOE's partnership with individual international disposal program are described. The report then provides a comprehensive overview of the various R&D activities conducted in FY21 as related to international collaboration. | 2021-09-30 |  | 2021-09-30 | The report M2SF-20LB010307012 “International Collaboration Activities in Different Geologic Disposal Environments” describes the status of international collaboration regarding geologic disposal research in the Spent Fuel and Waste Disposition (SFWD) Campaign. Since 2012, SFWD has been conducting active collaboration with several international geologic disposal programs across the world. Such collaboration has allowed the SFWD Campaign to benefit from a deep knowledge base in regards to alternative repository environments developed over decades and has provided a framework for active peer-to-peer research participation in international groups which conduct, analyze, and model performance-relevant processes. Via international collaboration, the SFWD Campaign also benefits from substantial international investments in research facilities (such as underground research laboratory testing and modeling) and achieves significant cost savings via joint funding of expensive field experiments. The SFWD’s International Disposal R&D Program has currently established formal collaboration agreements with several international initiatives and international partners to provide an opportunity for the US National Lab scientists associated with SFWD to conduct specific collaborative R&D activities that align with the SFWD R&D priorities. These activities are now forming a considerable portion of SFWD disposal research, and significant advances have been made over the past years, including participation in the DECOVALEX program. | 2021 | Complete | International Collaboration Activities in Geologic Disposal Research: FY21 Progress Report | Jens Birkholzer, Boris Faybishenko | Jens Birkholzer | None | FY21 M2SF-20LB010307012_09.30.21 PDF.pdf |  | Geological disposal; nuclear waste; international collaboration; host rock; engineering barriers; argillite; crystalline rock; salt; performance assessment; modeling; flow and radionuclide transport.
M3SF-21SN010310012 | M3 | 1.08.01.03.10.01 | SNL | SF-21SN01031001 | Planning for URL - SNL | Kuhlman, Kris | Stein, Emily | Planning for URL Final Test Plan | Final Test Plan for Passive URL Monitoring |  | 2021-09-30 |  | 2021-09-29 | Completed level-3 milestone report 1 day early. | 2021 | Complete | Passive Atmospheric Monitoring in a Vadose Zone Underground Research Laboratory | Kris Kuhlman | Kris Kuhlman | None | SAND2021-12109O_URL_test_plan_Sept2021_04.pdf
M2SF-21SN010305061- Report for DOE review. It will be sent via email to the Control Account Manager, the National Technical Director, and the Federal Manager for review prior to public release. | M2 | 1.08.01.03.05.06 | SNL | SF-21SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Repository-Scale Performance Assessment Incorporating Postclosure Criticality | Analysis of Repository Performance Including Postclosure Criticality | Prepare the technical bases for a repository-scale performance assessment that includes postclosure criticality. | 2021-09-30 |  | 2021-09-30 | This report documents a performance assessment of a geologic repository, comparing the performance of the repository with the occurrence of a criticality event to its performance in the absence of a criticality event. | 2021 | Complete | Repository-Scale Performance Assessment Incorporating Postclosure Criticality | Laura Price, Alex Salazar, Eddie Basurto, Halim Alsaed, Jeff Cardoni, Fred Gelbard, Michael Nole, Jeralyn Prouty, Charlotta Sanders, Greg Davidson, Mathew Swinney, Santosh Bhatt, Evan Gonzalez and Brian Kiedrowski | Laura Price | None |  |  | DPC; geologic disposal; postclosure criticality; criticality consequence
M3SF-21OR010305128 | M3 | 1.08.01.03.05.12 | ORNL | SF-21OR01030512 | DPC Reactivity and Criticality Modeling - ORNL | Banerjee, Kaushik | Freeze, Geoff | Multiphysics criticality consequence analysis capability development status report | Multiphysics criticality consequence analysis capability development status report | This deliverable captures the Multiphysics criticality consequence analysis methodology development status and reports path forward. | 2021-09-30 |  | 2021-09-30 | This report details work led by ORNL to compute the power level maintainable in a critical DPC under 1) steady-state and 2) repository-transient conditions as well as an end-of-year update on fast-transient capabilities. | 2021 | Complete | Steady-State and Time-Dependent Coupled Simulations of a Critical Dual-Purpose Canister in a Saturated Repository | ORNL | Mathew Swinney | None | PICS_Report.pdf
M2SF-20SN010305062- No matching records found in PICS Superseded by- M2SF-21SN010305061 | M2 | 1.08.01.03.05 | SNL | SF-21SN01030506 | Probabilistic Post-Closure DPC Criticality Consequence Analyses - SNL | Price, Laura | Freeze, Geoff | Repository-Scale Performance Assessment Incorporating Postclosure Criticality | Analysis of Repository Performance Including Postclosure Criticality |  | 2021-09-30 |  |  |  | 2021 | In Progress |  |  |  | None
M4SF-21OR010305091-3D printed coupons providing representative surfaces and neutron absorber alternatives were delivered to INL for corrosion testing. The results from INL are not yet available. | M4 | 1.08.01.03.05.09 | ORNL | SF-21OR01030509 | Neutron Absorber Evaluation - ORNL | Montgomery, Rose | Freeze, Geoff | Development of Neutron Absorber Materials | Progress Report on Development of Neutron Absorber Materials | Production of NAM samples suitable for corrosion testing using advanced manufacturing techniques. This work will be based on input received from INL corrosion testing results. | 2021-09-30 |  | 2021-09-01 | 3D printed absorber materials were submitted to INL for corrosion testing. ORNL will continue to interface with the project and support as requested. | 2021 | Complete |  | Rose Montgomery |  | None
M2SF-22SN010309082 | M2 | 1.08.01.03.09 | SNL | SF-22SN01030908 | OWL - Inventory - SNL | Weck, Philippe | Camphouse, Chris | Annual Status Update for OWL | Annual status update for OWL | This report represents completion of deliverable M2SF-22SN010309082 Annual Status Update for OWL, which is due on November 30, 2021 as part of the fiscal year 2022 (FY2022) work package SF-22SN01030908. This report provides an annual update on status of FY2021 activities for the work package “OWL - Inventory – SNL”. This is "Draft -internal use only" and is being policy reviewed with the final public report to be uploaded after addressing policy comments. | 2021-11-30 |  | 2021-11-17 | This report represents completion of milestone deliverable M2SF-22SN010309082 Annual Status Update for OWL, which is due on November 30, 2021 as part of the fiscal year 2022 (FY2022) work package SF-22SN01030908. This report provides an annual update on status of FY2021 activities for the work package “OWL - Inventory – SNL”. This is "Draft -internal use only" and is being policy reviewed with the final public report to be uploaded after addressing policy comments. | 2022 | Complete | Annual Status Update for OWL | Philippe F. Weck | Philippe F. Weck | None | Annual Status Update for OWL_M2SF-22SN010309082_final UUR.pdf
M2SF-20SN010304042 | M2 | 1.08.01.03.04 | SNL | SF-20SN01030404 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | Advances in GDSA Framework Development and Process Model Integration | Advances in GDSA Framework Development and Process Model Integration |  |  |  | 2020-09-14 | Technical review complete, as acknowledged by email from David Sassani to Paul Mariner | 2020 | Complete | Advances in GDSA Framework Development and Process Model Integration | Mariner, Paul |  | None | 2020 GDSA FW Dev- SAND2020-10787 R - M2SF-20SN010304042.pdf
M2SF-20SN010304045 | M2 | 1.08.01.03.04 | SNL | SF-20SN01030404 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | Disposal Research Five-Year Research and Development Plan | SFWST Disposal Research R&D 5-Year Plan - Draft Report | Final deliverable uploaded by Program Controls on 8/31/2020 at NTD's request. CUI Type changed to None. |  |  | 2020-07-30 | Draft internal-use report. Technical review complete. | 2020 | Complete | SFWST Disposal Research R&D 5-Year Plan | David Sassani | Paul Mariner | None | SFWST Disposal Research R&D 5-Year Plan |  | Disposal research plan
M3SF-20SN010304044 | M3 | 1.08.01.03.04 | SNL | SF-20SN01030404 | GDSA - Framework Development - SNL | Mariner, Paul | Stein, Emily | Surrogate Model Development of Spent Fuel Degradation for Repository Performance Assessment | Surrogate Model Development of Spent Fuel Degradation for Repository Performance Assessment |  |  |  | 2020-09-16 | Technical review complete, as acknowledged by email from Laura Swiler to Paul Mariner | 2020 | Complete | Surrogate Model Development of Spent Fuel Degradation for Repository Performance Assessment | Mariner, Paul |  | None | 2020 FMD surrogates - SAND2020-10797 R - M3SF-20SN010304044.pdf
M1508010102 Put in Non-Public NE 81 Milestones library because unsure it's the right report. | M1 | 1.5.08.01 | ANL | AN1015080101 | Campaign Management and Integration |  |  | Update of the UFD campaign implementation plan
M41UF030401 | M4 | 1.02.08.03 | ANL | FTAN11UF0304 | LLW Disposition |  |  | ANL Input to SRNL Level 3 Milestone: LLW Disposal Issues and Alternatives
M41UF035402 ULR. Internal Use Only. | M4 | 1.02.08.03 | SRNL | FTSR11UF0354 | Technical Bases / Lessons Learned |  |  | SRNL Input to SNL L3 MS: System-Wide Integration and Site Selection Concepts for Future Disposition Options for HLW
M21UF010201 | M2 | 1.02.08.01 | SNL | FTSN11UF0102 | Campaign Management and Integration - SNL |  |  | Preliminary UFD Campaign QA Implementation Plan
M21UF033701 | M2 | 1.02.08.03 | SNL | FTSN11UF0337 | Technical Bases / Lessons Learned |  |  | Report on the Basis for Selection of Disposal Options (SNL)
M21UF033901 | M2 | 1.02.08.03 | SNL | FTSN11UF0339 | Generic EBS Evaluation |  |  | Evaluation of THMC Processes at EBS Interfaces (SNL)
M21UF034004 (Author: Wang, Yifeng) | M2 | 1.02.08.03 | SNL | FTSN11UF0340 | Generic Natural System Evaluation |  |  | Evaluation of key physical, chemical and hydrological processes in natural systems (SNL)
M21UF034101 | M2 | 1.02.08.03 | SNL | FTSN11UF0341 | Generic Disposal System-Level Modeling |  |  | Report describing the integrated generic disposal system environment (GDSE) model (SNL)
M2508030901 | M2 | 1.5.08.03 | SNL | SN1015080309 | Technical Bases - Lessons Learned |  |  | End of FY10 Report â€“ Used Fuel Disposition: Technical Bases and Lessons Learned
M2508040501 | M2 | 1.5.08.04 | SNL | SN1015080405 | FEPs Categorization and Cross-Map |  |  | Used Fuel Disposition Campaign Features, Events, And Processes (FEPs); FY10 Progress Report
M31UF010101 | M3 | 1.02.08.01 | ANL | FTAN11UF0101 | Campaign Management and Integration - ANL |  |  | UFD Disposal R&D Roadmap
M31UF020101 | M3 | 1.02.08.02 | ANL | FTAN11UF0201 | External and International Interactions - ANL |  |  | UFD International Collaboration Plan
M31UF032101 | M3 | 1.02.08.03 | LANL | FTLA11UF0321 | Repository Science/salt disposal investigations |  |  | Develop the NQA-1 requirements and QA project plan for the SDI project.
M31UF032102 | M3 | 1.02.08.03 | LANL | FTLA11UF0321 | Repository Science/salt disposal investigations |  |  | Determine and document functional and operational requirements (F&OR) for a field test in salt.
M31UF032801 | M3 | 1.02.08.03 | LLNL | FTLL11UF0328 | Technical Bases / Lessons Learned |  |  | LLNL Input to SNL L2 MS: Report on the Basis for Selection of Disposal Options
M31UF033601 | M3 | 1.02.08.03 | PNNL | FTPN11UF0336 | Repository Science/waste form degradation & RN mobilization |  |  | PNNL Input to SNL L3 MS: Used Fuel Waste Form Degradation FY11 Summary Report
M31UF034702 | M3 | 1.02.08.03 | SNL | FTSN11UF0347 | Repository Science/Thermal load management & design concepts |  |  | FY11 Investigations on Repository Near-Field Thermal Modeling
M31UF035503 | M3 | 1.02.08.03 | SRNL | FTSR11UF0355 | Inventory |  |  | Low Level Waste Inventory Update
M3508020104 Per Mark Nutt: M3508020104 and M3508020502 were met in a single report – attached (External Interactions and International FY10 Summary.doc). | M3 | 1.5.08.02 | ANL | AN1015080201 | External Interactions |  |  | Summary of External Interactions Completed in FY10
M3508020502 Per Mark Nutt: M3508020104 and M3508020502 were met in a single report – attached (External Interactions and International FY10 Summary.doc). | M3 | 1.5.08.02 | ANL | AN1015080205 | International |  |  | Summary of UFC International Collaboration in FY10
M3508040604 | M3 | 1.5.08.04 | ANL | AN1015080406 | R&D Roadmap and Workshop |  |  | Revised UFDC R&D Roadmap
M3508042204 (Author: Yifeng Wang) | M3 | 1.5.08.04 | SNL | SN1015080422 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | End of FY10 status report
M41UF030201 Per Mark Nutt: ANL Input to SNL L2 Milestone: Report describing the integrated generic disposal system environment (GDSE) model – attached (ANL Clay GDSE Model - FY11 Report (Rev 0).doc) | M4 | 1.02.08.03 | ANL | FTAN11UF0302 | Generic Disposal System-Level Modeling |  |  | ANL Input to SNL L2 Milestone: Report describing the integrated generic disposal system environment (GDSE) model
M41UF030301 | M4 | 1.02.08.03 | ANL | FTAN11UF0303 | Perspectives on Nuclear Waste Management |  |  | ANL Input to SNL L3 MS: Evaluation of Possible Future Perspectives on Nuclear Waste Management
M41UF032802 | M4 | 1.02.08.03 | LLNL | FTLL11UF0328 | Technical Bases / Lessons Learned |  |  | LLNL Input to SNL L3 MS: System-Wide Integration and Site Selection Concepts for Future Disposition Options for HLW
M41UF033001 | M4 | 1.02.08.03 | LLNL | FTLL11UF0330 | Generic EBS Evaluation |  |  | LLNL input to SNL L2 milestone: Evaluation of THMC Processes at EBS Interfaces
M41UF035102 | M4 | 1.02.08.03 | SNL | FTSN11UF0351 | Repository Science/System Level analysis |  |  | General GoldSim model architecture report
M4508032302 | M4 | 1.5.08.03 | SRNL | SR1015080323 | LLW Disposition - Quantities and Inventory |  |  | Initial LLW Generation Estimates
M4508032304 | M4 | 1.5.08.03 | SRNL | SR1015080323 | LLW Disposition - Quantities and Inventory |  |  | LLW generation waste estimates for additional fuel cycle alternatives
M4508032602 | M4 | 1.5.08.03 | SRNL | SR1015080326 | LLW Disposition - Disposal Issues and Alternatives |  |  | History and status of existing LLW disposal facilities
M4508032604 | M4 | 1.5.08.03 | SRNL | SR1015080326 | LLW Disposition - Disposal Issues and Alternatives |  |  | Alternative LLW Disposal Methods
M4508032606 | M4 | 1.5.08.03 | SRNL | SR1015080326 | LLW Disposition - Disposal Issues and Alternatives |  |  | year end report
M4508041801 | M4 | 1.5.08.04 | ANL | AN1015080418 | Disposal Systems Evaluations and Tool Development - Generic Disposal System Modeling |  |  | Input to Year End Status Report - Clay Model
M4508042501 | M4 | 1.5.08.04 | LLNL | LL1015080425 | Disposal Systems Evaluations and Tool Development - Engineered Barrier System Evaluation |  |  | Mid FY progress Report on Evaluation of EBS

## NE 81 ST FY10-FY21
Milestone ID Number | Level | WBS | Site | WP Number | WP Title | FCTWPM | CAM | Milestone Title | Deliverable Title | Deliverable Description | Estimated Finish | Revised Finish | Actual Finish | Narrative | FY | Status | Main Document Title | Document Author/Creator | Document Owner | CUI Type | Uploaded Document Name | DMS Tracking Number | Keywords
M3SF-19PN010203028- Reached out to Brady Hanson for document. | M3 | 1.08.01.02.03 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Compare FAST/FRAPCON model with sister rod data | FAST/FRAPCON Model Validation Against Sister Rods |  | 2019-05-31 | 2019-11-22 |  |  | 2019 |  |  |  |  | None
M2SF-19SN010305021 Per Matt Brainard: Milestone marked complete on 9/26/2019, however the submission comment reads “The report is under review by DOE and will be uploaded by program controls manager upon completion of review.” I have yet to receive a copy of this report to upload into PICS:NE. | M2 | 1.08.01.03.05.02 | SNL | SF-19SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | Freeze, Geoff | Accelerated Testing of Selected Filler Compositions | Results from Accelerated Testing of Selected DPC Fillers | Select one or more cement compositions for accelerated testing, optimizing the slurry recipe, and emphasizing evaluation of injectability, slurry pH, thermal setting, dewatering, and shrinkage. | 2019-09-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M3SF-19OR010205034- Reached out to Sylvia Saltzstein for document Per Matt Brainard: The Subject milestone was marked “Complete” on 8/30/2019, however a Deliverable document was never uploaded into PICS:NE. One comment was entered: “Technology development completed. We have a working demo. Waiting on some new radio hardware to arrive which should dramatically improve the bandwidth and video quality between the aircraft and the ground.” | M3 | 1.08.01.02.05.03 | ORNL | SF-19OR01020503 | Security - ORNL | Scaglione, John | Saltzstein, Sylvia | Tethered system integration into MAVNet | Proof of concept demonstration of technology development | A tethered multirotor aircraft that can deploy from a vehicle and stay airborne for a long time using a power source from the ground. Control of this system (camera position, altitude, up/down, etc.) will be integrated into our existing MAVNet system. The concept is that this vehicle would provide local birds-eye view situational awareness, communication system relay and be able to optionally detach and pursue a target should the need arise. | 2019-08-30 |  | 2019-08-30 | M3 deliverable completed on schedule | 2019 | Complete | Proof of concept demonstration of technology development | Stinson | Scaglione | None
M3SF-19PN010201031- Reached out to Brady Hanson for superseding document supercedes M3SF-18PN010201033, which superseded M3SF-17PN010201033 Per Martt Brainard: It appears that this milestone may have been dropped during the FY20 work package planning phase as there are no milestones with the same title in the FY20 follow-on work package. | M3 | 1.08.01.02.01.03 | PNNL | SF-19PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | Hydride Cooling Rate Study | Cooling Rate Studies | Determine effect of cooling rate on hydride formation to inform sister rod testing. Perform material properties testing on prehydrided samples to inform sister rod testing. Supply samples to ANL for RCT. | 2019-08-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M2SF-20SN020801011- Reached out to Cynthia Huber for document Supercedes: M3SF-19SN010401014 Per Matt Brainard: Document not in PICS:NE. Last performance update: “Revised project schedule indicates that the analysis of Legacy systems will be completed in March 2020.” supercedes M3SF-18SN010401014 | M3 | 1.08.01.04.01.01 | SNL | SF-19SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Analyze Priority One Legacy Application Functionality | Complete requirements document of legacy application functionality. | Analyze Priority One Legacy Application Functionality | 2019-05-31 | 2019-06-28 02:00 |  | A revised schedule for P1 Analysis has been developed. | 2019 | Expected Late |  |  |  | None
M3SF-19SR010205022 Per Matt Brainard: Report marked OUO and will not be uploaded into PICS:NE. Contact Joe T. Carter (SRNL) for a copy of the report. | M3 | 1.08.01.02.05.02 | SRNL | SF-19SR01020502 | Security - SRNL | Carter, Joe | Saltzstein, Sylvia | Drone Attack Security Assessment | Drone Attack Security Assessment Report | This report is required by Activity SF-19SR010205021-Security Assessment Support. This report satisfies Milestone M3SF-19SR010205022. | 2019-09-30 |  | 2019-09-30 | This report is required by Activity SF-19SR010205021-Security Assessment Support. This report satisfies Milestone M3SF-19SR010205022. | 2019 | Complete | Security Assessment Support | Joe T. Carter/Robert Jones | Joe T. Carter/Robert Jones | OUO |  |  | Assessment
M3SF-20PN0102010310- covid delays | M3 | 1.08.01.02.01.03 | PNNL | SF-20PN01020103 | Sibling Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | Gap Analysis for ATF | Initial ATF Storage and Transportation Gap Analysis | Document data needs for ATF and higher burnup fuels for storage and transportation. | 2020-05-01 | 2020-12-04 03:00 |  | Delays due to COVID shutdown and getting agreement on gaps. Significant modifications being made after discussions with NE-4. | 2020 | Late |  |  |  | None
M3SF-20SN010207062- Reached out to Sam Durbin for document. | M3 | 1.08.01.02.07.06 | SNL | SF-20SN01020706 | Lead Canister Field Demonstration - SNL | Durbin, Sam | Saltzstein, Sylvia | Preliminary Test Design and Plan for a Lead Canister Field Demonstration | Preliminary Test Design and Plan for a Lead Canister Field Demonstration | Report to document a preliminary design for heaters, ancillary structures, instrumentation, control systems, and other supporting subsystems for a lead canister in a field demonstration. | 2020-11-20 |  |  | On schedule. | 2020 | 90 Day |  |  |  | None
M4SF-20SR010205023- OUO. No report uploaded to PICS. Contact Joe Carter if needed. | M4 | 1.08.01.02.05.02 | SRNL | SF-20SR01020502 | Security - SRNL | Carter, Joe | Saltzstein, Sylvia | Report on Strawman Rules of Engagement for Drone Attacks | Report on Strawman Rules of Engagement for Drone Attacks | The referenced OUO report satisfies M4SF-20SR010205023, Mitigating Unmanned Aerial System Attacks & Rules of Engagement", due August 30, 2020. | 2020-08-30 |  | 2020-08-30 | The purpose of this report is to expand upon the report “Unmanned Aerial Systems Threat Against Dry Fuel Storage Considerations”, dated September 26, 2019 . Unmanned Aerial Systems (UAS) technology continues to evolve and pose significant risks to critical infrastructure and facilities. This report provides additional information to evaluate security related risks from UAS attack(s) and to implement a protective force response strategy that is overdue and needed to protect life and property. | 2020 | Complete | Mitigating Unmanned Aerial System Attack & Rules of Engagement | Steven Whitcomb, Wendell Edwards, Christopher Amos | Joe T. Carter | OUO |  |  | Unmanned Aerial System Attacks
M4SF-20PN010207054- Reached out to Brady Hanson for document | M4 | 1.08.01.02.07.05 | PNNL | SF-20PN01020705 | Lead Canister Field Demonstration - PNNL | Hanson, Brady | Saltzstein, Sylvia | Functions and Requirements for Lead Canister Field Test | Functions and Requirements for Lead Canister Field Test | Develop the Functions and Requirements for the lead canister to inform the test design. Document the results of the thermal and deposition modeling. | 2020-10-30 |  |  | On schedule but could be delayed if the COVID restrictions continue to impact the project. | 2020 | 90 Day |  |  |  | None
M3SF-19PN010201087- Reached out to Brady Hanson for superseding document. Per Matt Brainard: The Subject milestone was marked as Late during the September performance reporting period in PICS:NE with a Revised Finish Date stated in FY20 (2/28/2020). The milestone narrative reads “This report will be canceled and replaced by a FY20 deliverable | M3 | 1.08.01.02.01.08 | PNNL | SF-19PN01020108 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Consequence Analysis for Moisture After Drying | PNNL Input to SRNL for Consequence Analysis for Moisture after Drying | Supply input to SRNL M2 on consequence analysis for moisture after drying | 2020-02-28 |  |  | On schedule. | 2020 | On Schedule |  |  |  | None
M3SF-20PN010203028- no notes as to why this report is not in PICS | M3 | 1.08.01.02.03.02 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Drying Consequence Analysis | Updated Fuel Oxidation Model | Develop an oxidation model to feed to SRNL Consequence Report update | 2020-07-31 | 2021-06-25 06:00 |  | Delayed until 6/25/21; Work delayed due to COVID shutdown. Carryover redirected to other tasks so work will be further delayed until new FY21 funding is received. | 2020 | Late |  |  |  | None
M3SF-20SN010205012- no notes as to why this report is not in PICS | M3 | 1.08.01.02.05.01 | SNL | SF-20SN01020501 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Investigations of unmanned aerial systems (UAS) as part of adversary toolkit for transportation security-based scenarios | Investiagations of unmanned aerial systems (UAS) as part of adversary toolkit for transportation security-based scenarios | M4 classified report on the potential use of UAS on SNF transport | 2020-09-30 | 2020-12-18 10:00 |  | On schedule for revised finish. | 2020 | Expected Late |  |  |  | None
M3SF-20OR010207035- no notes as to why this report is not in PICS | M3 | 1.08.01.02.07.03 | ORNL | SF-20OR01020703 | Stress Corrosion Cracking - ORNL | Chatzidakis, Stylianos | Saltzstein, Sylvia | Update of Development and Validation of Phenomenological Model on Aerosol Transport and Plugging Through Stress Corrosion Cracks | Update of Development and Validation of Phenomenological Model on Aerosol Transport and Plugging Through Stress Corrosion Cracks |  | 2020-09-30 | 2020-12-15 |  | Model and GUI taking longer than anticipated. | 2020 | Expected Late |  |  |  | None
M3SF-20PN0102030211- no notes as to why this report is not in PICS | M3 | 1.08.01.02.03.02 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Thermal Sensitivity to Canister Internal Environment | Thermal Sensitivity to Canister Internal Environment | Report results of thermal modeling looking at component temperature changes as a function of canister internal pressure and composition. | 2020-11-20 | 2021-02-26 06:00 |  | Work and deliverable will be delayed as staff have been asked to accelerate work on the Lead Canister Field Demonstration thermal model. Proposed new due date: 02/26/2021. | 2020 | Expected Late |  |  |  | None
M3SF-20PN010207071- no notes as to why this report is not in PICS | M3 | 1.08.01.02.07.07 | PNNL | SF-20PN01020707 | SONGS Filter Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Filter Analysis | Filter Analysis for Particulate Release | Receive filters from SONGS, perform counting to determine radionuclide content, perform particle size analysis, and document in a report. | 2020-11-30 | 2021-04-02 06:00 |  | This deliverable is significantly delayed due to COVID issues at both SONGS and PNNL which delayed the shipment of the filters. In addition, the filters are a different material than we were originally told and will require much more work to try to remove particles for particle size distribution analysis. Proposed deliverable date is now 4/2/20. | 2020 | Expected Late |  |  |  | None
M3SF-21SN010205022- Report is classified SNSI | M3 | 1.08.01.02.05.02 | SNL | SF-21SN01020502 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Investiagations of unmanned aerial systems (UAS) as part of adversary toolkit for transportation security-based scenarios | Investiagations of unmanned aerial systems (UAS) as part of adversary toolkit for transportation security-based scenarios | Classified or OUO report on UAS attacks against spent fuel transport | 2020-12-18 |  | 2020-12-18 02:00 | SNSI classified report SAND2020-14191 completed. | 2021 | Complete | Unmanned Aerial Systems Spent Fuel Transportation Analysis | Mancel Jordan Parks | Mancel Jordan Parks | Deliverable is classified report SAND2020-14191.. |  |  | spent nuclear fuel; unmanned aerial system; radiological sabotage
M2FT-12AN0803011 | M2 | 1.02.08.03.01 | ANL | FT-12AN080301 | ST R&D Investigations - ANL | Liu, Yung | Sorenson, Ken | Aging Management Plans for Existing Dry Cask Storage Designs Report: | Managing Aging Effects Report | Develop a path forward to address storage system degradation issues at existing ISFSIs through Aging Management Plans | 2012-06-30 08:00 |  | 2012-06-29 01:00 |  | 2012 | Complete |  | Chopra, Omesh | Liu, Yung | None | FCRD-USED-2012-000119.pdf | FCRD-UFD-2012-000119
M2FT-12AN0805082 | M2 | 1.02.08.05.08 | ANL | FT-12AN080508 | ST Engineered Materials Experimental - ANL | Liu, Yung | Sorenson, Ken | Complete Phase I of fuel clad ring compression tests | Letter Report | Complete Phase I Cladding Tests & Letter Report | 2011-12-31 06:00 |  | 2011-12-31 02:00 |  | 2012 | Complete |  |  |  | None | ANL L2 Report_123111_FINAL.pdf | FCRD-USED-2012-000039
M2FT-12IN0802021 | M2 | 1.02.08.02.02 | INL | FT-12IN080202 | ST Field Testing - INL | Birk, Sandy | Sorenson, Ken | Identify and Assess NRC RAI's Against the Technical Data Gap Report | NRC RAI Assessment Document | This report will provide an up-to-date listing of the current NRC Requests for Additional Information for casks and storage relicense applications and will include an assessment of those requests that provides focus for future research | 2011-12-31 12:00 |  | 2011-12-31 02:00 |  | 2012 | Complete |  | Birk, Sandy | Birk, Sandy | None | NRC RAIs on Applications for Renewal of ISFSI Licenses FCRD-USED-2012-000037.pdf |  | RAI Request for Additional Information
M2FT-12OR0805041 | M2 | 1.02.08.05.04 | ORNL | FT-12OR080504 | ST Engineered Materials Experimental - ORNL | Howard, Rob | Sorenson, Ken | Initiate clad testing at HFIR: | Neutron Irradiation of Hydrided Cladding Material in HFIR - Summary of Initial Activities | This activity milestone will indicate the start of un-irradiated clad testing at ORNL | 2012-03-31 04:00 |  | 2012-03-30 |  | 2012 | Complete |  | Howard, Rob | Howard, Rob | None | Transmittal_Package_FCRD-UFD-2012-000080 (2).pdf | FCRD-UFD-2012-000080
M2FT-12OR0813031 | M2 | 1.02.08.13.03 | ORNL | FT-12OR081303 | ST Transportation - ORNL | Scaglione, John | Sorenson, Ken | Criticality analysis and mitigations for degraded UNF in storage canisters report | Criticality safety assessment to miitgate potential materials testing data needs | This report will define potential alternative paths for transportation criticality safety assessments. | 2012-09-01 04:00 |  | 2012-08-31 |  | 2012 | Complete |  | Marshall, William | Wagner, John | None | UFD_Transportation_Consequences_of_Fuel_Failure_Draft.pdf | FCRD-UFD-2012-000262 | Criticality, fuel failure
M2FT-12PN0803042 | M2 | 1.02.08.03.04 | PNNL | FT-12PN080304 | ST R&D Investigations - PNNL | Hanson, Brady | Sorenson, Ken | Review of Technical Data Gaps Relative to Similar External Studies | Review of Technical Data Gaps Relative to Similar External Studies | Compare the NE Data Gap Report with the NRC report and other similar reports once they are published. | 2012-07-31 11:00 |  | 2012-07-31 03:00 |  | 2012 | Complete |  | Hanson, Brady | Hanson, Brady | None | Gap Comparison Rev 0.pdf | FCRD-UFD-2012-000215
M2FT-12SN0813052 | M2 | 1.02.08.13.05 | SNL | FT-12SN081305 | ST Transportation - SNL | McConnell, Paul | Sorenson, Ken | Compilation of Transportation Issues and Resolutions | Transportation Team Compilation Report | This is a muti-lab effort to assemble relevant transportation issues and provide status of resolution of the issues. | 2012-09-30 10:00 |  | 2012-09-28 02:00 |  | 2012 | Complete |  | McConnell, Paul | McConnell, Paul | None | Compilation 2012 FCRD-Report 092812.pdf
M3FT-12AN0802012 | M3 | 1.02.08.02.01 | ANL | FT-12AN080201 | ST Field Testing - ANL | Liu, Yung | Sorenson, Ken | NRC Requests for Additional Informaton identification and assessment | Letter report | ANL will support the development of TVC planning document and other major task activities. ANL will support identification and assess NRC Requests for Additional Information (RAIs) related to renewal of Licenses and Certificates of Compliance for ISFSIs and Dry Cask Storage Systems. | 2012-09-28 12:00 |  | 2012-09-14 01:00 |  | 2012 | Complete |  | Diercks, D | Liu, Y | None | Letter report_FT-12AN080201.pdf | FCRD-UFD-2012-000509
M3FT-12AN0813012 | M3 | 1.02.08.13.01 | ANL | FT-12AN081301 | ST Transportation - ANL | Liu, Yung | Sorenson, Ken | ST Transportation | Letter report | ANL will support (1) gap analysis for transportation for long-term storage and high burnup assessment, (2) development of a test plan on fuel assembly in a cask under normal conditions of transport, (3) ASME NUPACK, and (4) other transportation-related activities, as deemed necessary. | 2012-09-28 05:00 |  | 2012-09-11 01:00 | Letter report submitted 9/10/2012. | 2012 | Complete |  | Han, ZH | Han, ZH | None | Letter report_FT-12AN081301.pdf | FCRD-UFD-2012-000510
M3FT-12IN0802024 | M3 | 1.02.08.02.02 | INL | FT-12IN080202 | ST Field Testing - INL | Birk, Sandy | Sorenson, Ken | Dry Cask Transfer Report | Dry Cask Transfer Report | Deliver final summary report to Control Account Manager | 2012-05-30 10:00 |  | 2012-05-30 02:00 |  | 2012 | Complete |  | Carlsen, Brett | INL | None | Dry Transfer Systems for UNF FCRD UFD 2012 000115.pdf | FCRD-UFD-2012-000115 | "dry transfer system" DTS "DTS Options" fcrd 000115
M3FT-12IN0802026 Per Steve Marschman: Sandy Birk was the peer reviewer on this deliverable, so I think it safe to say the INL work is incorporated. | M3 | 1.02.08.02.02 | INL | FT-12IN080202 | ST Field Testing - INL | Birk, Sandy | Sorenson, Ken | AGING Management PLN SCC | Aging Management Plan SCC to ANL | Submit Aging Management Plan for SCC info to ANL for incorporation into generic AMPs | 2012-08-30 10:00 |  | 2012-06-28 02:00 |  | 2012 | Complete |  | Wahnschaffe, Steve | Wahnschaffe, Steve | None | SCC Aging Management 1.docx | FCRD-UFD-2012-000687
M3FT-12IN0805022 | M3 | 1.02.08.05.02 | INL | FT-12IN080502 | ST Engineered Materials Experimental - INL | Birk, Sandy | Sorenson, Ken | Report on Facility modifications | Report on Facility Modifications | Final report submitted to control account manager including INL contributions to Control Account | 2012-09-30 02:00 | 2012-08-16 02:00 | 2012-08-16 02:00 |  | 2012 | Complete |  | Wahnschaffe, Steve | Wahnschaffe, Steve | None | INL_Dry_Storage_Demo_Options_WhitePaper[1].docx Tev-1187.pdf | FCRD-UFD-2012-000632
M3FT-12IN0813022 repeat of M3FT-12IN0813023, was supposed to be support letter report for Transportation | M3 | 1.02.08.13.02 | INL | FT-12IN081302 | ST Transportation - INL | Birk, Sandy | Sorenson, Ken | INL Support Activities for Transportation Control Account | Support Letter Report | This deliverable is a letter report documenting INL support for the Transportation Control Account Milestone Deliverables | 2012-09-28 12:00 | 2012-08-15 02:00 | 2012-08-15 02:00 |  | 2012 | Complete |  | Morton, Keith | Morton, Keith | None | Document_Cover_Sheet_INL_EXT-12-26798[1].docx FCRD-Transmittal_INL_EXT-12-26798[1].docx INL_EXT-12-26798[1].pdf | FCRD-UFD-2012-000195
M3FT-12IN0813023 same as M3FT-12IN0813022 | M3 | 1.02.08.13.02 | INL | FT-12IN081302 | ST Transportation - INL | Birk, Sandy | Sorenson, Ken | Moderator Exclusin Summary Report | Moderator Exclusion Summary Report | This report will document the scope performed for task 1 and 2 listed under scope section | 2012-09-28 02:00 | 2012-08-15 02:00 | 2012-08-15 02:00 |  | 2012 | Complete |  | Morton, Keith | Morton, Keith | None | Document_Cover_Sheet_INL_EXT-12-26798[1].docx FCRD-Transmittal_INL_EXT-12-26798[1].docx INL_EXT-12-26798[1].pdf | FCRD-UFD-2012-000195
M3FT-12IN0813071 | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Prepare Test Plan | Test Plan document | Test Plan | 2012-08-30 04:00 |  | 2012-08-30 02:00 |  | 2012 | Complete |  | Kunerth, Dennis | Kunerth, D | None | EXT-12-27119_InspDryStgCasks_rbkedit[1][1][1].pdf | FCRD-UFD-2012-000273 | Inspection, Dry Cask, NDE, NDA,
M3FT-12IN08130710 | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Licensing support for inspections | Licensing support for inspections | All licensing evaluations necessary to conduct internal inspections of storage systems | 2012-06-29 02:00 | 2013-01-31 12:00 |  | Milestone to be renamed and redated in FY 13 Field Demonstn WP | 2012 | Late |  |  |  | None
M3FT-12IN0813074 | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Initial Draft Plan submitted to DOE | Draft S&T RD&D Plan | Draft S&T RD&D Plan | 2012-01-15 02:00 |  | 2012-01-15 02:00 |  | 2012 | Complete |  | INL | INL | None | UFS RD&D Plan_DFT 16Jan12 Rev0.pdf | FCRD-FCT-2012-000053
M3FT-12IN0813075 | M3 | 1.02.08.13.07 | INL | FT-12IN081307 | Measurement Development and Testing Program - INL | Birk, Sandy | Sorenson, Ken | Revised Plan submitted to DOE | Revised S&T RD&D Plan | Revised S&T RD&D Plan | 2012-02-15 02:00 | 2012-03-30 08:00 | 2012-03-27 02:00 |  | 2012 | Completed Late |  | Braase, L | Kemal Pasamehmetoglu - INL | None | UNF S&T RD&D Plan Draft Rev0 27Mar12.pdf |  | Gap analysis, RD&D, storage, transportation, used nuclear fuel
M3FT-12OR0810031 | M3 | 1.02.08.10.03 | ORNL | FT-12OR081003 | ST Engineering Analysis - ORNL | Wagner, John | Sorenson, Ken | Report on the Identification of specific applications for early analysis | Report on the Identification of specific applications for early analysis | This report will be the result of the multi-lab team's assessment of early analysis work that can be initiated to support the data gap report. | 2012-07-31 08:00 | 2012-10-31 | 2012-12-07 | Milestone delayed further due to other priorities and its original purpose being overcome by other activities and milestones. | 2012 | Late |  | Scaglione, John | Scaglione, John | None | Early_Analysis_Report_Draft_12_7_12.pdf | FCRD-UFD-2012-000630
M3FT-12OR08160610 | M3 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Howard, Rob | Wagner, John | Final Implementation Plan on the Feasibility of Direct Disposal of DPCs | Final Implementation Plan on the Feasibility of Direct Disposal of DPCs | Final implementation plan on the feasibility of direct disposal of DPCs that incorporates comments from review of the draft implementation plan. | 2012-05-14 02:00 |  | 2012-05-14 |  | 2012 | Complete |  | Howard, Rob | Howard, Rob | None | Combined_STAD_Implementation_DPC_Disposal_Plan_5_14_12.pdf | FCRD-UFD-2012-000106 | Dual Purpose Canister Disposal
M3FT-12OR08160613 | M3 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Howard, Rob | Wagner, John | FY12 Year End Status of Standardized Canister and Feasibility of Direct Disposal of DPCs Activities | FY12 Status Report Development and Licensing of Standardized Transportation, Aging, and Disposal Canisters and the Feasibility of Direct Disposal of Dual Purpose Canisters | This report will cover the status of activities identified in the “Implementation Plan on the Development and Licensing of Standardized Transportation, Aging, and Disposal Canisters and the Feasibility of Direct Disposal of Dual Purpose Canisters” | 2012-09-26 |  | 2012-09-26 | This deliverable was submitted on time. | 2012 | Complete |  | Howard, Rob | Howard, Rob | None | ORNL M3FT-12OR081606_Letter_Report_9_26_2012_Final.pdf | FCRD-UFD-2012-000629
M3FT-12OR08220213 | M3 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | Wagner, John | Complete Prototype UNF Database and Associated Documentation | Prototype UNF Database and Associated Documentation | This will be the first version of the database, that will subsequently be refined and expanded upon. | 2012-09-28 |  | 2012-09-28 |  | 2012 | Complete |  | ORNL | Scaglione, John | None | M3FT-12OR08220213-9-28-2012-FINAL.pdf | FCRD-UFD-2012-000628
M3FT-12PN0802051 | M3 | 1.02.08.02.05 | PNNL | FT-12PN080205 | Field Testing - PNNL | Buelt, James | Sorenson, Ken | Spent Fuel Sample Disposition Pathway | Spent Fuel Sample Disposition Report | Develop and review options for disposition of sample spent fuel waste | 2012-08-31 14:00 |  | 2012-09-01 03:00 | Milestone completed on 8/31/12. System won't take the correct date. | 2012 | Completed Late |  | Raap, Michaele | Doherty, A | None | FCRD-UFD-2012-000279 Sample Disposition Report_31Aug Final.pdf | FCRD-UFD-2012-000279
M3FT-12PN0803044 | M3 | 1.02.08.03.04 | PNNL | FT-12PN080304 | ST R&D Investigations - PNNL | Hanson, Brady | Sorenson, Ken | R&D Investigations Year End Summary Report | R&D Investigations FY12 Year End Summary Report | Report summarizing FY12 R&D activities and results. | 2012-09-28 09:00 |  | 2012-09-28 03:00 | Milestone complete. | 2012 | Complete |  | Hanson, Brady | Hanson, Brady | None | RD Investigations Year End Summary Report.pdf | FCRD-UFD-2012-000382
M3FT-12PN0810041 | M3 | 1.02.08.10.04 | PNNL | FT-12PN081004 | ST Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Report on Realistic Temperature Profiles | Report on Realistic Temperature Profiles | Report on realistic temperature profiles. | 2012-05-04 14:00 |  | 2012-05-04 03:00 |  | 2012 | Complete |  | Adkins, Harold | Adkins, Harold | None | Thermal_Modeling_HSM15.pdf | FCRD-UFD-2012-000114
M3FT-12PN0810043 | M3 | 1.02.08.10.04 | PNNL | FT-12PN081004 | ST Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Report on Realistic Temperature Profiles - Second Canister | Report on Realistic Temperature Profiles - Second Canister | Prepare a report on realistic temperature profiles of the second dry storage canister to be inspected at Calvert Cliffs. | 2012-09-24 06:00 |  | 2012-09-24 03:00 | Milestone complete. | 2012 | Complete |  | Adkins, Harold | Adkins, Harold | None |  | FCRD-UFD-2012-000344
M3FT-12PN0813044 | M3 | 1.02.08.13.04 | PNNL | FT-12PN081304 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Report summarizing FY12 efforts on contribution to the consolidation of FEPs for storage and transportation & Canister Stabilization Feasibility | Report summarizing acccomplishments for FY12 on Tasks 2 - 4 | Report summarizing acccomplishments for FY12 on the identification and evaluation of issues associated with the dry repackaging of bare used nuclear fuel into canisters or transportation containers and the evaluation of issues associated with canister stabilization feasibility. | 2012-08-31 02:00 |  | 2012-08-31 03:00 |  | 2012 | Complete |  | Ross, Steven | Ross, Steven | None | Summary of PNNL Transportation Activities for FY12 to Support the UFD Program.pdf UFD_Container Stabilization_Final Report_PNNL-21664.pdf | FCRD-UFD-2012-000243
M3FT-12SN0805063 | M3 | 1.02.08.05.06 | SNL | FT-12SN080506 | ST Engineered Materials Experimental - SNL | Bryan, Charles | Sorenson, Ken | Final report: Immersion tests to evaluate corrosion of Alloy 22 in heated brine solutions | Final Report: Immersion tests to evaluate corrosion of Alloy 22 in heated brines | This Level 3 milestone will the final report on the ongoing immersion tests with Alloy 22 in brine solutions at elevated temperatures. These experiments were carried out to verify the corrosion behavior of this material, and will provide a set of high quality corrosion data for this extremely corrosion-resistant material. | 2012-06-30 12:00 | 2012-07-13 02:00 | 2012-07-13 02:00 |  | 2012 | Completed Late |  | Enos, David | Bryan, Charles | None | FCRD-UFD-2012-000181-Final Report Alloy 22 Immersion Testing.pdf | FCRD-UFD-2012-000181
M3FT-12SN0805065 | M3 | 1.02.08.05.06 | SNL | FT-12SN080506 | ST Engineered Materials Experimental - SNL | Bryan, Charles | Sorenson, Ken | Status report entitled: Engineered Materials Performance: Gap Analysis and Status of Existing Work | Engineered Materials Performance: Gap Analysis and Status of Existing Work | Completion of FY11 end of year status report. This status report includes a gap analysis identifying future research needs, a status of existing work, and a preliminary work plan for FY12 work. This report was delayed for a few months due to the LANL fire and due to injury of one of the principal authors. | 2011-10-31 08:00 |  | 2011-10-27 02:00 |  | 2012 | Complete |  | Bryan, Charles | Bryan, Charles | None | Final FCRD-USED-2011-000407 Engineered Materials Performance Gap Analysis and Status Report.pdf | FCRD-USED-2011-000407
M3FT-12SN0810054 | M3 | 1.02.08.10.05 | SNL | FT-12SN081005 | ST Engineering Analysis - SNL | Tikare, Veena | Sorenson, Ken | Final report | Final report | A report that outlines the areas assessed with model and analysis with the suggested mitigation strategies. | 2012-09-30 08:00 | 2012-10-31 02:00 |  | This deliverable has been expanded to a full roadmap for hydride formation | 2012 | Expected Late |  |  |  | None
M3FT-12SN0813055 | M3 | 1.02.08.13.05 | SNL | FT-12SN081305 | ST Transportation - SNL | McConnell, Paul | Sorenson, Ken | Normal transport tests report | Normal Transport Test Report | Report describing tests of a fuel assembly within a transport cask under normal transport conditions. Dependent upon access to fuel assembly, cask, and logistical concerns. | 2012-09-30 16:00 |  | 2012-09-28 02:00 |  | 2012 | Complete |  | McConnell, Paul | McConnell, Paul | None | Assemby Shaker Test Plan.pdf | FCRD-UFD-2012-000341
M3FT-12SN0816075 | M3 | 1.02.08.16.07 | SNL | FT-12SN081607 | Standardized Canisters - SNL | Hardin, Ernest | Wagner, John | Report on Dual-Purpose Canister Disposal Mission Assumptions | Report on Assumptions for DPC Concept Evaluation | Document results from Scoping and Assumptions Phase of DPC disposal feasibility work, for the Standard Canister/DPC Disposal project as described in Section 3.1 of workplan FCRD-UFD-2012-000106. | 2012-09-24 04:00 |  | 2012-09-24 02:00 | Completed and distributed on schedule. | 2012 | Complete |  | Hardin, Ernest | Hardin, Ernest | None | Dual-Purpose Canister Disposal Catalog and Analysis Assumptions Final.docx | FCRD-UFD-2012-000352
M3FT-12SR0802073 | M3 | 1.02.08.02.07 | SRNL | FT-12SR080207 | Storage and Transportation Field Testing | Smith, Pat | Sorenson, Ken | Consolidated Storage Cost Estimate | Consolidated Storage Cost Estimate | SRNL will work with the System Architecture Study Team to identify the functional requirements and design concepts for various approaches to consolidated storage. These concepts will be modular to support the various storage methods (Dry Vertical, Dry Horizontal, and Pool) in use by utilities. SRNL will provide a rough order-of-magnitude (ROM) cost estimate for each module specified by the System Architecture Study Team. The ROM estimate work breakdown structure can be combined to result in estimates for various consolidated storage concepts. A ROM estimate will be developed for a Green Field Used Fuel Research and Development Test Facility. Concept definition for this module will be based on updated functional requirements developed for the Test and Validation Complex in FY-11. | 2012-08-30 |  | 2012-08-20 |  | 2012 | Complete |  | Carter, Joe | Carter, Joe | None | UFD-NE Test and Validation Facility Cost Study (Rev 0).pdf | FCRD-UFD-2012-000206 | Test and Validation
M3FT-12SR0813061 | M3 | 1.02.08.13.06 | SRNL | FT-12SR081306 | ST Transportation - SRNL | Carter, Joe | Sorenson, Ken | Complete Dry Storage Database and Transportation Cask Issues and ISFSI Shipment Options Reports | Dry Storage Database, Transportation Cask Issues and ISFSI Shipment Options | SRNL shall produce and maintain a database which extends the StoreFuel database to include details on transportation issues for all light water reactor assemblies in dry storage in the U.S. SRNL will produce a report detailing transportation issues associated with dry stored light water power reactor fuel. SRNL will produce a report to document the logistical challenges of dry transfers at a typical ISFSI site for each of the canister cask systems in use in the U.S | 2012-08-15 02:00 |  | 2012-08-15 |  | 2012 | Complete |  | Leduc, DR | Leduc, DR | None | Dry Storage of Used Fuel_Transition to Transport - FCRD-UFD-2012-000253.pdf | FCRD-UFD-2012-000253
M4FT-12IN0803021 | M4 | 1.02.08.03.02 | INL | FT-12IN080302 | ST R&D Investigations - INL | Birk, Sandy | Sorenson, Ken | Lab Contribution to R&D Investigation | Lab Contribution to R&D Investigation | This summarizes INL's contribution to the Level 2 documents prepared by SNL for the Revision to the Gap analysis report and the Preparation of a Gap Prioritization report | 2012-09-28 04:00 |  | 2012-09-28 02:00 | Lab contribution report complete | 2012 | Complete |  | Birk, Sandy | Birk, Sandy | None | End of Year Lab Contribution to R.docx | FCRD-UFD-2012-000530
M4FT-12IN08100110 | M4 | 1.02.08.10.01 | INL | FT-12IN081001 | ST Engineering Analysis - INL | Birk, Sandy | Sorenson, Ken | Can in Can Letter Report | Can in can Letter Report | Letter report documeting support to ORNL for can in can work | 2012-06-30 02:00 | 2012-08-27 02:00 | 2012-09-01 02:00 | Can in can document completed on 8/27/12 | 2012 | Completed Late |  | Birk, Sandy | Birk, Sandy | None | EOY INL_FY12_End_of_Year_Submittals_for_Can-In-Can[1][2][1].pdf | FCRD-UFD-2012-000327
M4FT-12IN0810013 | M4 | 1.02.08.10.01 | INL | FT-12IN081001 | ST Engineering Analysis - INL | Birk, Sandy | Sorenson, Ken | Operational Assessment of Cask Drying | Operational Assessment of Cask Drying | Provide letter report documenting the assessement of drying for potential modeling and analysis evaluations | 2012-08-30 10:00 |  | 2012-06-28 02:00 |  | 2012 | Complete |  | Smith, Rebecca | Smith, Rebecca | None | CaninCan_Rev_2_Final[1].pdf | FCRD-UFD-2012-000326 | Drying, Can in can
M4FT-12LA0803072 | M4 | 1.02.08.03.07 | LANL | FT-12LA080307 | ST R&D Investigations - LANL | Perry, Frank | Sorenson, Ken | Mid year status report: material integrity measurement and monitoring to meet storage needs | Mid year status report facility needs for material integrity measurement and monitoring | Status of LANL efforts to meet measurement and monitoring needs for long-term storage focusing on non-linear acoustic methods | 2012-03-30 10:00 |  | 2012-03-29 02:00 |  | 2012 | Complete |  | Ulrich, Timothy | Ulrich, Timothy | None | Ulrich-March-2012-LANL-ST_R&D-Milestone.pdf | FCRD-UFD-2012-000090 | Concrete degradation storage
M4FT-12LL0802032 | M4 | 1.02.08.02.03 | LLNL | FT-12LL080203 | S&T Field Testing - LLNL | Halsey, Bill | Sorenson, Ken | Summary of LLNL support to development of storage platform feasibility report | Summary of LLNL Support to ST T&E Capability Development | Summary (via letter report) of LLNL support to Storage and Transportation activities, including support to development of the storage platform feasibility report and other support as determined through the year. | 2012-08-27 09:00 |  | 2012-08-27 03:00 |  | 2012 | Complete |  | Halsey, Bill | Halsey, Bill | None | LLNL_UFD_S&T_M4_8-27-2012.docx | FCRD-UFD-2012-000574
M4FT-12OR0802041 | M4 | 1.02.08.02.04 | ORNL | FT-12OR080204 | ST T&E Capability Development - ORNL | Jubin, Bob | Sorenson, Ken | Mid-Year Status Report | Mid-Year Status Report | Mid-Year report describing the efforts in the first half of FY12 to support the rescoped Field Testing activities. | 2012-03-30 06:00 |  | 2012-03-29 |  | 2012 | Complete |  | Jubin, Bob | Jubin, Bob | None | M4FT-12OR0802041 Mid Year Status Report - Complete package.pdf | FCRD-SWF-2012-000583
M4FT-12OR0802043 | M4 | 1.02.08.02.04 | ORNL | FT-12OR080204 | ST T&E Capability Development - ORNL | Jubin, Bob | Sorenson, Ken | End-Of Year Status Report | End-of-year Status Report | End of year report will focus on regulatory assessments supporting the dry storage platform | 2012-09-28 04:00 |  | 2012-10-01 | Complete. | 2012 | 90 Day |  | Jubin, Bob | Jubin, Bob | None | M4FT-12OR0802043 End-of-Year Status Report - Complete package.pdf | FCRD-SWF-2012-000491
M4FT-12OR0803034 | M4 | 1.02.08.03.03 | ORNL | FT-12OR080303 | ST R&D Investigations - ORNL | Howard, Rob | Sorenson, Ken | Prepare ORNL End of Year Status Report for R&D Investigations | ORNL R&D Investigations Year End Status Report | Prepare End of Year Status Report for R&D Investigations | 2012-09-07 02:00 |  | 2012-09-07 |  | 2012 | Complete |  | Howard, Rob | ORNL | None | ORNL FT-12OR080303_Letter_Report_9_7_12.pdf | FCRD-UFD-2012-000585
M4FT-12OR0810032 | M4 | 1.02.08.10.03 | ORNL | FT-12OR081003 | ST Engineering Analysis - ORNL | Wagner, John | Sorenson, Ken | Engineering Analysis Year End Status Report | Engineering Analysis Year End Status Report | Report summarizing all of the Engineering Analysis lab team efforts for FY12, including analyses of selected applications and plans for Fy13. | 2012-09-28 02:00 |  | 2012-09-28 |  | 2012 | Complete |  | Wagner, John | Wagner, John | None | M4FT-12OR0810032-Eng Analysis Year End Status Report_9_28_12_Rev01.pdf | FCRD-UFD-2012-000587
M4FT-12OR0810038 | M4 | 1.02.08.10.03 | ORNL | FT-12OR081003 | ST Engineering Analysis - ORNL | Wagner, John | Sorenson, Ken | Status Report on Integrated Canister Design and Evaluation | Status Report on Integrated Canister Design and Evaluation | Issue a status report on the FY12 multi-laboratory efforts to design and evaluate the integrated canister concept. | 2012-09-28 02:00 |  | 2012-09-28 |  | 2012 | Complete |  | Scaglione, John | Scaglione, John | None | M4FT-12OR0810038-Status Report on Integrated Canister Design and Evaluation-9-28-2012.pdf | FCRD-UFD-2012-000588
M4FT-12PN0805052 | M4 | 1.02.08.05.05 | PNNL | FT-12PN080505 | ST Engineered Materials Experimental - PNNL | Hanson, Brady | Sorenson, Ken | Support Clad and Neutron Poison Testing | Support Clad and Neutron Poison Testing | Support clad and neutron poison testing. | 2012-09-14 06:00 |  | 2012-09-27 03:00 | Milestone complete. | 2012 | Completed Late |  | Hanson, Brady | Hanson, Brady | None | Clad and Neutron Poison Testing Final.pdf | FCRD-UFD-2012-000597
M4FT-12SN0803055 | M4 | 1.02.08.03.05 | SNL | FT-12SN080305 | ST R&D Investigations - SNL | Stockman, Christine | Sorenson, Ken | ST R&D SNL Year-End Summary | ST R&D SNL Year-End Summary | FY12 SUmmary of SNL contribution to ST R&D | 2012-09-14 08:00 |  | 2012-09-13 02:00 |  | 2012 | Complete |  | Stockman, Christine | Stockman, Christine | None | ST R&D SNL Year-End Summary 2012 with cover.pdf | FCRD-UFD-2012-000534
M4FT-12SN0805064 | M4 | 1.02.08.05.06 | SNL | FT-12SN080506 | ST Engineered Materials Experimental - SNL | Bryan, Charles | Sorenson, Ken | Test plan for experimental work on corrosion of storage container and waste package materials at Sandia National Labs | Test plan: Experimental work evaluating corrosion of storage container and waste package materials at Sandia National Laboratories | This Level 4 milestone will be the finalized test plan for experimental work on corrosion of storage container and waste package materials that will be carried out under this work package. | 2012-01-31 14:00 |  | 2012-01-31 02:00 |  | 2012 | Complete |  |  |  | None | FCRD-UFD-2012-000052 SNL Corrosion Technical Work Plan.pdf | FCRD-UFD-2012-000052
M4FT-12SR0802074 | M4 | 1.02.08.02.07 | SRNL | FT-12SR080207 | Storage and Transportation Field Testing | McConnell, Steven | Sorenson, Ken | Fuel Storage Research and Development Module | UFD TVC Functions and Requirement Document Revision 1 | Revise the functional requirements developed in FY11 for the Test and Validation Facility based on the results of the fuel storage Gap Analysis and the Storage and Transportation Roadmap currently being developed. | 2012-05-31 |  | 2012-05-31 |  | 2012 | Complete |  | Delley, Alexcia | Delley, Alexcia | None | UFD-NE Test and Validation Facility F&Rs (Rev 2).pdf | FCRD-USED-2011-000030 Rev. 2 | Used Fuel, Test and Validation
M4FT-12SR0803061 | M4 | 1.02.08.03.06 | SRNL | FT-12SR080306 | ST R&D Investigations - SRNL | Smith, Pat | Sorenson, Ken | SRNL Support to R&D Investigation | SRNL Support to R&D Investigations | End of FY12 letter report capturing activities performed to support Rev. 1 of the Technical Gap Analysis Report, Gap Prioritization and Closure Plan Report, ASTM Drying Standard Committee, and development of instrumentation and monitoring plan. | 2012-09-30 |  | 2012-09-27 | Closure Document: Email from Dennis Vinson to Patricia Smith, "Completion of SRNL Milestone M4FT-12SR0803061, SRNL Support to R&D Investigation | 2012 | Complete |  | Vinson, Dennis | Vinson, Dennis | None | Completion of SRNL Milestone M4FT-12SR0803061.pdf | FCRD-UFD-2012-000536
M4FT-12SR0805071 | M4 | 1.02.08.05.07 | SRNL | FT-12SR080507 | ST Engineered Materials Experimental - SRNL | Smith, Pat | Sorenson, Ken | Provide SRNL support to Engineered Material Experimental Work Package | SRNL Support to Engineered Material Experimental | End of FY12 letter report capturing activities performed to support workshop and test plan development. | 2012-09-30 |  | 2012-09-27 | Closure Document: See email Dennis Vinson to Patricia Smith, Completion of SRNL Milestone M4FT-12SR0805071, SRNL Support Engineered Material Experimental | 2012 | Complete |  | Vinson, Dennis | Vinson, Dennis | None | Completion of SRNL Milestone M4FT-12SR0805071.pdf | FCRD-UFD-2012-000537
M5FT-12OR08220224 | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Report describing technical and interface requirements for M&S toolset | Report describing technical and interface requirements for M&S toolset | Develop technical requirements for initial integrated M&S toolset, to include UNF characterization, criticality safety and thermal analyses | 2012-08-03 | 2012-08-15 | 2012-08-13 |  | 2012 | Completed Late |  | Radulescu, Georgeta | Scaglione, John | None |  | FCRD-UFD-2012-000543
M5FT-12OR08220225 | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Report documenting prioritized list of UNF assemblies and casks to be modeled | Prioritized list for modeling | Report documenting prioritized list of UNF assemblies and casks to be modeled | 2012-07-13 |  | 2012-07-13 |  | 2012 | Complete |  | Scaglione, John | Scaglione, John | None | FCRD-Report-12OR08220225-draft.pdf | FCRD-UFD-2012-000544
M2FT-13AN0805011 | M2 | 1.02.08.05.01 | ANL | FT-13AN080501 | ST Storage and Transportation Experiments - ANL | Liu, Yung | Sorenson, Ken | Data report on ring compression and DBTT tests for PWR cladding | Data report on ring compression and DBTT tests for PWR cladding | ST Storage and Transportation Experiments - ANL | 2013-09-30 04:00 |  | 2013-09-30 05:00 | Completed on 9/30/13 | 2013 | Complete |  | Billone, Michael | Billone, Michael |  | FCRD-UFD-2013-000401.pdf | FCRD-UFD-2013-000401.pdf
M2FT-13IN0802067 supersedes M2FT-12IN0802081 | M2 | 1.02.08.02.06 | INL | FT-13IN080206 | ST Field Demonstration - INL | Marschman, Steve | Sorenson, Ken | Long Term Used Nuclear Fuel Storage Viability Report | Long Term Used Nuclear Fuel Storage Viability Report | Long Term Used Nuclear Fuel Storage Viability Report | 2012-11-15 02:00 |  | 2012-11-15 02:00 |  | 2013 | Complete |  |  |  | None | HBUF_Viability_Report_Rev_1b.pdf | FCRD-UFD-2013-000027
M2FT-13OR0805041 | M2 | 1.02.08.05.04 | ORNL | FT-13OR080504 | ST Storage and Transportation Experiments - ORNL | Howard, Rob | Sorenson, Ken | Data report on hydrogen doping and irradiation in HFIR | Data report on hydrogen doping and irradiation in HFIR | Data report on hydrogen doping and irradiation in HFIR | 2013-09-30 02:00 |  | 2013-09-30 02:00 | Completed on 9/30/13 | 2013 | Complete |  | Howard, Rob | Howard, Rob | None | FY2013_UFDC_ORNL_Experimental_Summary_FCRD-UFD-2013-000369.pdf | FCRD-UFD-2013-000369
M2FT-13OR0822011 supersedes M2FT-12OR0822031 | M2 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Wagner, John | Used Fuel Performance Modeling, Simulation and Experimental Integration Plan | Used Fuel Performance Modeling, Simulation and Experimental Integration RD&D Plan | This milestone will be the blueprint for how to move forward for the next several years to resolve the numerous technical challenges related to ES of UNF that will require M&S, measured data, and UQ. | 2013-04-01 17:00 |  | 2013-04-01 |  | 2013 | Complete |  | Adkins, Harold | Howard, Rob | None | Modeling Simulation and Experimental Integration RDD Plan_R0.pdf | FCRD-UFD-2013-000135
M2FT-13OR0822015 Supersedes M2FT-12OR08220310 | M2 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Wagner, John | Demonstration of Approach and Results on Used Fuel Performance Characterization | Used Fuel Performance UQ Focused Modeling, Simulation and Experimental Integration | Submission of final Execution RD&D Plan and Demonstration of Approach on Selected Technical Issue | 2013-09-30 02:00 |  | 2013-09-30 02:00 | Completed on 9/30/13 | 2013 | Complete |  | Adkins, Harold | Howard, Rob | None | FCRD-UFD-2013-000325_M2.pdf | FCRD-UFD-2013-000325
M2FT-13PN0805051 | M2 | 1.02.08.05.05 | PNNL | FT-13PN080505 | ST Storage and Transportation Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Data report on hydrogen doping/distribution tests | Data report on hydrogen doping/distribution tests | Data report on hydrogen doping/distribution tests | 2013-04-30 16:00 |  | 2013-04-30 06:00 |  | 2013 | Complete |  | Hanson, Brady | Hanson, Brady | None | Hydride Rim Report Rev 0 - Hanson.pdf | FCRD-UFD-2013-000151
M2FT-13SN0805061 | M2 | 1.02.08.05.06 | SNL | FT-13SN080506 | ST Storage and Transportation Experiments - SNL | Bryan, Charles | Sorenson, Ken | Data report on corrosion testing of stainless steel SNF storage canisters | Data report on corrosion testing of stainless steel storage canisters | Data report on stainless steel canister corrosion testing activities. | 2013-09-30 12:00 |  | 2013-09-30 02:00 | In fulfillment of the Level 2 Milestone # M2FT-13SN0805061, this is a status report describing work at Sandia National Laboratories evaluating the corrosion of stainless steel SNF interim storage containers. The report has two parts. First, the environment on the surface of SNF interim storage canisters is evaluated. Then, a suite of experiments evaluating deliquescence-induced localized corrosion of stainless steel is described. | 2013 | Complete |  | Enos, David | Bryan, Charles | None | FCDR-UFD-2013-000324--Corrosion Testing of Stainless Steel Interim Storage Containers.pdf | FCDR-UFD-2013-000324
M2FT-13SN0810031 | M2 | 1.02.08.10.03 | SNL | FT-13SN081003 | ST Storage and Transportation Engineering Analysis - SNL | Tikare, Veena | Sorenson, Ken | Report on methodology to estimate used fuel cladding hydride re-orientation during thermal excursions simulated during drying | Report on analytical methodology to estimate used fuel cladding hydride re-orientation during thermal excursions simulated during drying | Report on analytical methodology to estimate used fuel cladding hydride re-orientation during thermal excursions simulated during drying | 2013-08-30 04:00 |  | 2013-08-28 02:00 |  | 2013 | Complete |  | Tikare, Veena | Tikare, Veena | None | TikareL2MilestoneReport.pdf | FCRD-UFD·2013-000251
M2FT-13SN0813041 | M2 | 1.02.08.13.04 | SNL | FT-13SN081304 | ST Transportation - SNL | McConnell, Paul | Sorenson, Ken | Conduct assembly shaker table test. Prepare test report. | Data report on assembly shaker table test | Prepare fuel assembly for shaker (vibration/shock) test. Conduct tests. Analyze data. Prepare test report on assembly shaker test. | 2013-06-30 14:00 |  | 2013-06-30 02:00 |  | 2013 | Complete |  | McConnell, Paul | McConnell, Paul | None | M2FT-13SN0813041_AssemblyShakerTest_063013.pdf | FCRD-UFD-2013-000190
M3FT-13AN0802011 | M3 | 1.02.08.02.01 | ANL | FT-13AN080201 | ST Field Demonstration - ANL |  | Sorenson, Ken | ST Field Demonstration | Managing Aging Effects on Dry Cask Storage Systems for Extended Long-Term Storage and Transportation of Used Fuel, Revision 1 |  | 2013-09-30 06:00 |  |  | M3 report submitted to NTD, etc. on 9/30/2013 | 2013 | 90 Day |  |  |  | None |  | FCRD-UFD-2013-000294
M3FT-13IN08020612 | M3 | 1.02.08.02.06 | INL | FT-13IN080206 | ST Field Demonstration - INL | Marschman, Steve | Sorenson, Ken | Data Needs from Full-Scale Demonstration | Data Needs from Full-Scale Demonstration | Define data needed by National Laboratories from the full-scale demonstration | 2013-09-30 04:00 |  | 2013-09-13 02:00 | The purpose of this report is to recommend used fuels that might be acquired to support of the Used Fuel Disposition Campaign, Storage and Transportation research and development (R&D) program. | 2013 | Complete |  | Marschman, Steve | Marschman, Steve | None | Strategy for Used Fuel Acquisition.pdf | FCRD-UFD-2013-000335
M3FT-13LA0805031 | M3 | 1.02.08.05.03 | LANL | FT-13LA080503 | ST Storage and Transportation Experiments - LANL | Ulrich, Timothy | Sorenson, Ken | Experimental Investigations | Mid-year status report | Laboratory-scale: - determine sample preparation necessary to create relevant damage (e.g., thermal damage gradient in concrete, degradation of concrete reinforcement, and SCC in stainless steel). - determine method of testing damaged samples. - prepare concrete, reinforced concrete and stainless steel samples using information obtained in above activies. | 2013-03-29 04:00 | 2013-04-30 04:00 | 2013-04-30 04:00 |  | 2013 | Completed Late |  | Ulrich, Timothy | Ulrich, Timothy | None | Storage_Midyear_Report-LANL.pdf | FCRD-NFST-2013-000156
M3FT-13LA0805032 | M3 | 1.02.08.05.03 | LANL | FT-13LA080503 | ST Storage and Transportation Experiments - LANL | Ulrich, Timothy | Sorenson, Ken | Experimental Investigations II | End of year technical report | Laboratory-scale: - test/monitor samples at various damage conditions. Facility-scale: - Inspect thermal and radiation damaged concrete slab avialable at LANSCE using the TREND technique reported upon in FY12 (FT-12LA080307). | 2013-09-13 02:00 |  | 2013-09-13 02:00 | Report completed Aug. 30th, released by LANL after quality review on Sept. 9th (LA-UR-13-27010). | 2013 | Complete |  | Ulrich, Timothy | Ulrich, Timothy | AT | Storage Experimentation - LANL endyear - Final.pdf | FCRD-UFD-2013-000315 | NDE, nonlinear ultrasonics, stress corrosion cracking, concrete degradation
M3FT-13LA0805033 | M3 | 1.02.08.05.03 | LANL | FT-13LA080503 | ST Storage and Transportation Experiments - LANL | Ulrich, Timothy | Sorenson, Ken | Borated Steel studies | The Effect of Boron on the Thermal Sensitization of Grade ‘A’ Type 304 Stainless Steel | Scope: ASTM G108-94 covers a laboratory procedure for conducting electrochemical potentiokinetic reactivation (EPR) tests on Type 304 and 304L SS. All testing for thermal sensitization shall follow ASTM G108-94. This workscope will consist of (a) performing a ‘demonstration of preparedness’ by EPR testing on 304SS; (b) EPR testing on borated 304B4 stainless steels (BSS) both in the as received and heat treated states; and (c) examining the fate of boron after the 304B4 samples have corroded. Objective: To identify the Effect of Boron on the Thermal Sensitization of Grade ‘A’ Type 304 Stainless Steel Assumptions and Prerequisites: Samples need to be purchased, prepared and supplied by commercial vendor able to prepare SS304 and 304B4 to ASTM specifications. Activities (in support of below milestone): A. Demonstration of Preparedness on 304SS (first 2 months) B. Electrochemical potentiokinetic reactivaion (EPR) tests on 304B4 BSS (second 2 months) C. Determination of the Fate of Boron upon Corrosion of BSS (third 2 months) | 2013-04-30 04:00 |  | 2013-04-15 02:00 |  | 2013 | Complete |  | Tokash, Justin | Tokash, Justin | None | LANL-Borated Stainless Steel Report.pdf | FCRD-NFST-2013-000145
M3FT-13OR0810014 | M3 | 1.02.08.10.01 | ORNL | FT-13OR081001 | ST Storage and Transportation Engineering Analysis - ORNL | Scaglione, John | Sorenson, Ken | Report Quantifying Sensitivities and Uncertainties in UNF Characteristics | Report Quantifying Sensitivities and Uncertainties in UNF Characteristics | Develop libraries based on covariance data, and apply the libraries to quantify uncertainties for applications to UNF decay heat, radiation source terms relevant to geologic disposal considerations, and isotopic compositions relevant to burnup credit criticality analyses as a function of time (out to 300 years, or longer). Uncertainties in keff for a relevant storage/transportation configuration based on the isotopic composition uncertainties should also be quantified. | 2013-09-30 |  | 2013-09-30 | M3 milestone report describing the status of preliminary studies to develop nuclear data uncertainties and covariance files required for UNF uncertainty analysis, and the initial implementation of these data in a methodology for uncertainty quantification for used fuel studies. | 2013 | Complete |  | Gauld, Ian | Scaglione, John | None | A comprehensive Monte Carlo Sampling Uncertainty Quantification Methodology for UNF.pdf | FCRD-UFD-2013-000381
M3FT-13OR0813091 | M3 | 1.02.08.13.09 | ORNL | FT-13OR081309 | ST Transportation - ORNL | Scaglione, John | Sorenson, Ken | Update Transportation fuel failure criticality consequence report | Consequences of Fuel Failure on Criticality Safety of Used Nuclear Fuel | Resolve and incorporate external review comments on draft Consequences of Fuel Failure on Criticality Safety of Used Nuclear Fuel report | 2012-12-21 |  | 2012-12-21 |  | 2013 | Complete |  | Marshall, William | Scaglione, John | None | UFD_Transportation_Consequences_of_Fuel_Failure.pdf | FCRD-UFD-2012-000262
M3FT-13PN0805057 | M3 | 1.02.08.05.05 | PNNL | FT-13PN080505 | ST Storage and Transportation Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Report on clad rewetting and drying effects | Report on clad rewetting and drying effects | Report on clad rewetting and drying effects. | 2013-09-27 09:00 |  | 2013-09-30 12:00 | Milestone complete. | 2013 | Completed Late |  | Hanson, Brady | Hanson, Brady | None | FCRD-UFD-2013-000379 Cover Sheet.pdf | FCRD-UFD-2013-000379
M3FT-13PN0805058 Superseded M3FT-12PN0805051. | M3 | 1.02.08.05.05 | PNNL | FT-13PN080505 | ST Storage and Transportation Experiments - PNNL | Hanson, Brady | Sorenson, Ken | NDE for Weld Examination report | NDE for Weld Examination report | NDE for Weld Examination report | 2012-12-14 06:00 | 2013-01-14 06:00 | 2013-01-14 06:00 |  | 2013 | Completed Late |  | Hanson, Brady | Hanson, Brady | None | FCRD UFD 2013 000085 Cover.pdf FCRD UFD 2013 000085.pdf | FCRD-UFD-2013-000085
M3FT-13PN0810022 | M3 | 1.02.08.10.02 | PNNL | FT-13PN081002 | ST Storage and Transportation Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Report on Inspection 1 | Report on Inspection 1 | Report on Inspection 1 | 2013-08-30 03:00 |  | 2013-08-29 03:00 |  | 2013 | Complete |  | Hanson, Brady | Hanson, Brady | None | FCRD-Document Cover Sheet_M3FT 13PN0810022.pdf Pre-Inspection_HopeCreek_Thermal Analysis.pdf | FCRD-UFD-2013-000297
M3FT-13PN0810025 | M3 | 1.02.08.10.02 | PNNL | FT-13PN081002 | ST Storage and Transportation Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Perform Sensitivity Analysis Report | Perform Sensitivity Analysis Report | Perform Sensitivity Analysis Report. | 2013-08-16 06:00 | 2013-09-30 03:00 | 2013-09-24 03:00 | Milestone complete. | 2013 | Completed Late |  | Hanson, Brady | Hanson, Brady | None | FCRD-UFD-2013-000257 Cover Sheet.pdf FCRD-UFD-2013-000257.pdf | FCRD-UFD-2013-000257
M3FT-13PN0810027 | M3 | 1.02.08.10.02 | PNNL | FT-13PN081002 | ST Storage and Transportation Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Radiolysis model report | Radiolysis model report | Radiolysis model report. | 2013-09-20 06:00 |  | 2013-09-20 03:00 | Milestone complete | 2013 | Complete |  | Wittman, Rick | Hanson, Brady | None | FCRD-Document Cover Sheet_Hanson M3 Sep 20 2013.pdf FCRD_UFD_2013_000357.pdf | FCRD-UFD-2013-000357
M3FT-13PN0810029 | M3 | 1.02.08.10.02 | PNNL | FT-13PN081002 | ST Storage and Transportation Engineering Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Modify structural models report | Modify structural models report | Modify structural models report | 2013-09-27 06:00 |  | 2013-09-27 03:00 | Milestone complete. | 2013 | Complete |  | Hanson, Brady | Hanson, Brady | None | FCRD UFD 2013 000378 Cover Sheet.pdf FCRD UFD 2013 000378.pdf | FCRD-UFD-2013-000378
M3FT-13PN0813034 | M3 | 1.02.08.13.03 | PNNL | FT-13PN081303 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Finite Element Analysis for Shaker Table tests | Shaker Table Testing | Conduct FE analyses in support of the shaker table tests. | 2013-05-30 09:00 |  | 2013-06-01 03:00 |  | 2013 | Completed Late |  | Klymyshyn, Nicholas | Hanson, Brady | None | M3FT-13PN0813034_Ross_053013.pdf Shaker_final_2013.pdf | FCRD-UFD-2013-000168
M3FT-13SN0810032 | M3 | 1.02.08.10.03 | SNL | FT-13SN081003 | ST Storage and Transportation Engineering Analysis - SNL | Tikare, Veena | Sorenson, Ken | Develop and write a roadmap for hydride precipitation | Develop and write a roadmap for hydride precipitation | Prepare roadmap for predicting hydride precipitation in cladding during dry storage. | 2012-11-30 04:00 | 2012-12-17 02:00 | 2012-12-15 06:00 |  | 2013 | Completed Late |  | Tikare, Veena | Tikare, Veena | None | AppendixE.pdf UFDHydrideRoadmap.pdf | FCRD- UFD-2013-000068
M3FT-13SR0805072 | M3 | 1.02.08.05.07 | SRNL | FT-13SR080507 | ST Storage and Transportation Experiments - SRNL | Carter, Joe | Sorenson, Ken | Issue Used Fuel Characteristics Report | Issue Used Fuel Characteristics Report | Prepare a fuel characteristics report. | 2013-03-29 |  | 2013-03-27 |  | 2013 | Complete |  | Kesterson, Robert | Kesterson, Robert | None | Spent Fuel Characteristics_dwv-4-15-13-final.pdf | FCRD-UFD-2013-000130
M3FT-13SR0805074 | M3 | 1.02.08.05.07 | SRNL | FT-13SR080507 | ST Storage and Transportation Experiments - SRNL | Carter, Joe | Sorenson, Ken | Prepare a revision for balloting of the ASTM C1553 Drying Standard | Prepare a revison for the ballotting ASTM C1553 | Issue a revision for ASTM C26 Committee balloting of ASTM C1553-13 "Standard Guide for Drying Behavoir of Spent Nuclear Fuel". | 2013-08-30 |  | 2013-08-30 |  | 2013 | Complete |  | Sindelar, Robert | Sindelar, Robert | None | Standard Guide for Drying.pdf | FCRD-UFD-2013-000745
M4FT-13IN0810041 | M4 | 1.02.08.10.04 | INL | FT-13IN081004 | ST Storage and Transportation Engineering Analysis - INL | Marschman, Steve | Sorenson, Ken | Status report on FY13 activities and proposed work for FY14 | Status report on FY13 activities and proposed work for FY14 | Status report on FY13 activities and proposed work for FY14 | 2013-09-08 08:00 |  | 2013-09-11 02:00 | The report documents the technical aspects of this deliverable. The proposed work for FY 14 was captured via emails and the scope is captured in the FY 14 PICS input for this task | 2013 | Completed Late |  | Glazoff, Michael | Glazoff, Michael | None | MGlazoff-ZrHydrideByOxidation7-2013_FINAL-2_FCRD Format-1.pdf | FCRD-UFD-2013-000327 | thermodynamics modeling zirconium oxygen
M4FT-13IN0813011 | M4 | 1.02.08.13.01 | INL | FT-13IN081301 | ST Transportation - INL | Birk, Sandy | Sorenson, Ken | End of Year Summary Report from INL Transportation | End of Year INL Transportation Summary Report | This report will summarize the four tasks assigned to INL under the Transportation work package. It will be submitted to the CA lead Mr. Paul McConnell. | 2013-08-28 02:00 |  | 2013-08-28 02:00 |  | 2013 | Complete |  | Birk, Sandy | Birk, Sandy | None | FY 2013 INL SUMMARY REPORT ON UFDC TRANSPORTATION final.docx |  | Transportation, IAEA, Inspection Delivery Device
M4FT-13OR0805042 | M4 | 1.02.08.05.04 | ORNL | FT-13OR080504 | ST Storage and Transportation Experiments - ORNL | Howard, Rob | Sorenson, Ken | Post-Irradiation Characterization of Zr-4 Samples in Target Capsules HYCD-1 and HYCD-2 | Post-Irradiation Characterization of Zr-4 Samples in Target Capsules HYCD-1 and HYCD-2 | This activity includes post-irradiation characterization of pre-hydrided Zr-4 cladding material | 2013-03-29 |  | 2013-03-28 |  | 2013 | Complete |  | Yan | Howard, Rob | None | PIE_on_HYCD-1_and_HYCD-2_March 25_2013.pdf
M4FT-13OR0810013 | M4 | 1.02.08.10.01 | ORNL | FT-13OR081001 | ST Storage and Transportation Engineering Analysis - ORNL | Scaglione, John | Sorenson, Ken | Report documenting covariance data development | Report documenting covariance data development | Compile uncertainties for nuclear decay data and fission yields and develop covariance files. Prepare a report documenting the uncertainties and intended use. | 2013-03-29 |  | 2013-03-28 |  | 2013 | Complete |  | Pigni | Scaglione, John | None | FCRD-UFD-2013-000131.pdf | FCRD-UFD-2013-000131
M4FT-13OR0810015 | M4 | 1.02.08.10.01 | ORNL | FT-13OR081001 | ST Storage and Transportation Engineering Analysis - ORNL | Scaglione, John | Sorenson, Ken | End of Year Report on S&T Engineering Analysis Accomplishments | nd of Year Report on S&T Engineering Analysis Accomplishments | End of year summary report to document the Storage and Transportation Engineering Analysis Control Account Accomplishments from the lab team | 2013-09-30 |  | 2013-09-30 | Summary report documenting FY2013 ST Storage and Transportation Engineering Analysis accomplishments | 2013 | Complete |  | Scaglione, John | Scaglione, John | None | M4FT-13OR0810015-Eng Analysis Year End Status Report_9_30_13_Rev00.pdf
M4FT-13OR0813092 | M4 | 1.02.08.13.09 | ORNL | FT-13OR081309 | ST Transportation - ORNL | Scaglione, John | Sorenson, Ken | Assess impact of source term relocation for meeting transportation regulatory requirements | Assessment of potential fuel reconfiguration impacts with regards to source relocation | Report assessing impact of fuel material relocation with respect to satisfying the regulatory requirements for spent fuel storage and transportation systems in areas of besides subcriticality, such as shielding (dose rates), containment, and thermal criteria. | 2013-08-02 |  | 2013-09-04 | M4 Milestone Assessing impact of source term relocation for meeting transportation regulatory requirements completed. | 2013 | Completed Late |  | Radulescu, Georgeta | Scaglione, John | None | Letter-report-9-10-2013-Generic_JMS_updated_rev3.pdf |  | Transportation, shielding, dose
M4FT-13OR08220110 Supersedes M4FT-12OR08220317. | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Howard, Rob | Report documenting final UQ development, approach, and resultsulting M&S input | Used Fuel Transportation & Storage UQ Development, Approach, and Input Results | Develop report documenting final UQ development and approach, method of application, and resulting M&S input. | 2013-06-06 23:00 |  | 2013-06-06 |  | 2013 | Complete |  | Adkins, Harold | Howard, Rob | None | FCRD-UFD-2013-000173_M&S_Input.docx | FCRD-UFD-2013-000173
M4FT-13OR08220111 Supersedes M4FT-12OR08220316. | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Wagner, John | Documentation of data, material properties, modeling inputs and proposed analytical approaches | Supporting Data, Material Properties, and Modeling Input Information for Used Fuel Transportation & Storage Evaluations | Develop and document encompassing data, information, material properties, and modeling inputs yielded from literature searches. This information will form the foundation of the multi-physics evaluations. Literature search results will be assembled from material properties, loading boundary conditions, and methodologies and approaches used in previous evaluations/initiatives. Status of governing information feeding in to Linked Milestone. | 2013-03-16 21:00 |  | 2013-03-15 |  | 2013 | Complete |  | Adkins, Harold | Adkins, Harold | None | Supporting Material Properties and Modeling Inputs FCRD-UFD-2013-000123.pdf | FCRD-UFD-2013-000123
M4FT-13OR08220112 Supersedes M4FT-12OR08220318. | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Howard, Rob | Report documenting experimental activities | Used Fuel Transportation & Storage Supporting Experimental Activity Status | Develop and submit report documenting the status of supporting experimental activities that feed in to the M&S modeling. | 2013-06-06 12:00 |  | 2013-06-06 |  | 2013 | Complete |  | Adkins, Harold | Howard, Rob | None | FCRD-UFD-2013-000169_Vibration_Shock_Lit_Review.docx | FCRD-UFD-2013-000169
M4FT-13OR08220113 | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Documentation of selected M&S methodology, proposed application of UQ established data and information, and selected development path | Used Fuel Transportation & Storage M&S Performance Evaluation Methodology and UQ Development Basis | Develop report documenting activities regarding selected M&S methodology and UQ established input information feeding in to analytical evaluation. Final status of governing information to feed in to deterministic approach. | 2013-05-07 11:00 |  | 2013-05-07 |  | 2013 | Complete |  | Adkins, Harold | Adkins, Harold | None | Loading-MS Methodolody-Sensitivity-Failure and associated development strategies.docx | FCRD-UFD-2013-000155
M4FT-13OR0822019 | M4 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Wagner, John | Wagner, John | Finalize Method and Approach Document | RD&D Plan for Used Fuel Performance Modeling, Simulation and Experimental Integration | Finalize document that defines methodology and approach for coupling M&S and experimental efforts, including UQ, and the technical issue for which the methodology and approach will be demonstrated. | 2013-01-19 | 2013-01-31 02:00 | 2013-02-13 |  | 2013 | Completed Late |  | Adkins, Harold | Wagner, John | None | M4FT-13OR0822019_FT-13OR082201_UNF_Loading_and_Structural_Performance_Normal Transport_Final_R0.pdf
M4FT-13PN0805059 | M4 | 1.02.08.05.05 | PNNL | FT-13PN080505 | ST Storage and Transportation Experiments - PNNL | Hanson, Brady | Sorenson, Ken | FY13 Summary Report | FY13 Summary Report | FY13 Summary Report | 2013-09-13 09:00 |  | 2013-09-13 03:00 | Milestone complete. | 2013 | Complete |  | Hanson, Brady | Hanson, Brady | None | FCRD UFD 2013 000337.pdf M4FT 13PN0805059 Cover Sheet.pdf
M4FT-13PN0813032 | M4 | 1.02.08.13.03 | PNNL | FT-13PN081303 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Transportation for Hub and Spoke Model | Hub and Spoke Model Transportation Needs | Support development of L2 report for de-inventorying orphaned sites | 2013-10-01 02:00 |  | 2013-09-25 03:00 | Milestone completed early. | 2013 | Complete |  | Ross, Steven | Ross, Steven | None | FCT Document Cover Sheet_PNNL_M4FT-13PN0813032.pdf PNNL_Transportation_Modeling_Letter Report_Final_0925013.pdf
M4FT-13SR0805071 | M4 | 1.02.08.05.07 | SRNL | FT-13SR080507 | ST Storage and Transportation Experiments - SRNL | Carter, Joe | Sorenson, Ken | Host workshop on bolted closure joints at SRNL | S&T Experiments - Workshop on bolted closure joints at SRNL | Host technical workshop meeting at Savannah River National Laboratory for Bolted Joint Integrity for EST. This workshop will focus on radiation effects to cask polymeric material used as o-rings in bolted joints and as cask shielding materials. | 2012-12-31 02:00 |  | 2012-12-03 |  | 2013 | Complete |  | Sindelar, Robert | Sindelar, Robert | None | SRNL-RP-2012-00890 BAM-SRNL Meeting Minutes - 12.3.12 finaldoc.pdf |  | Bolted closure joints.
M4FT-13SR0805073 | M4 | 1.02.08.05.07 | SRNL | FT-13SR080507 | ST Storage and Transportation Experiments - SRNL | Carter, Joe | Sorenson, Ken | Prepare irradatiation test plan for polymeric materials for cask storage and transportation systems | Prepare Irradiation and Test Plan | An irraadiation and testing plan will be prepared and testing will be initiated in FY13 to address technical gaps in the information base in these areas. | 2013-04-30 |  | 2013-04-30 |  | 2013 | Complete |  | Sindelar, Robert | Sindelar, Robert | None | FCRD-UFD-2013-000152.pdf | FCRD-UFD-2013-000152 | Irradiation and Test Plan for Polymeric
M5FT-13IN0807062 | M5 | 1.02.08.07.06 | INL | FT-13IN080706 | Generic Natural System Evaluations - INL | Simpson, Michael | None | Document information used to support electrorefiner salt PA | Document information used to support electrorefiner salt PA Report | This will be a report that describes all of the assumptions that go into the PA calculations. | 2013-09-30 06:00 | 2013-10-07 02:00 | 2013-10-07 02:00 | Draft report submitted on 10/7 | 2013 | Expected Late |  | Simpson, Michael | Simpson, Michael | None | Update on Assessment of Direct Disposal of Electrorefiner Salt v2.docx |  | electrorefiner salt
M4FT-13LL08060327 Per Matt Brainard: Not uploaded to PICS:NE. Note: Submitted to DOE mgr and SNL WPM on due date of 7/26/13. Lab ID Tracking No.: LLNL-TR-641530. | M4 | 1.02.08.06.03 | LLNL | FT-13LL080603 | DR Generic Engineered Barrier System Evaluations - LLNL | Sutton, Mark | McMahon, Kevin | Np(V) Sorption and Diffusion on Montmorillonite Clay Progress Report | Np(V) Sorption and Diffusion on Montmorillonite Clay Progress Report | Progress report for Np(V) sorption and diffusion on/in montmorillonite clay. | 2013-07-26 14:00 |  | 2013-07-26 06:00 |  | 2013 | Complete |  | Zavarin, Mavrik | Zavarin, Mavrik | None |  |  | Neptunium, sorption, diffusion, clay, montmorillonite
M2FT-14AN0805012 | M2 | 1.02.08.05.01 | ANL | FT-14AN080501 | Experiments - ANL | Liu, Yung | Sorenson, Ken | Effects of Multiple Drying Cycles on High-Burnup PWR Cladding Alloys | Effects of Multiple Drying Cycles on HBU PWR Cladding Alloys | This report will document the data obtained on ring compression tests performed during FY14. The focus will be on examining the effects of re-wetting, multiple drying cycles, and thermal profile “memory” effects on high-burnup PWR cladding alloys. | 2014-09-26 05:00 |  | 2014-09-26 01:00 | The L2 report incorporated comments from peer review of the draft L3 rpeort, which has been has been technically reviewed and edited and received publication clearance from Argonne National Laboratory. | 2014 | Complete | Effects of Multiple Drying Cycles on High-Burnup PWR Cladding Alloys | Billone, Michael | Billone, Michael | AT |  | FCRD-UFD-2014-000052 | multiple drying cycles, high burnup fuel, DBTT, radial hydrides
M2FT-14ID0820012 | M2 | 1.02.08.20.01 | DOE-ID | FT-14ID082001 | High Burnup Cask Demo Project - DOE-HQ | Larson, Ned | Couch, Brad | Finalize Test Plan | Finalize Test Plan | Finalize Test Plan | 2014-02-28 06:00 |  | 2014-02-27 02:00 |  | 2014 | Complete | High Burnup Dry Storage Cask Research and Development Project Final Test Plan |  |  | None | DOE HBU Demo - Revised Test Plan Report - Rev 9 Clean.docx | FCRD-UFD-2014-000072
M2FT-14IN0802013 Available thru OSTI | M2 | 1.02.08.02.01 | INL | FT-14IN080201 | Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Strategy for fuel pin receipt, characterization, sample allocation for the demonstration sister pins | Strategy for fuel pin receipt, characterization, sample allocation for the demonstration sister pins | Strategy for fuel pin receipt, characterization, sample allocation for the demonstration sister pins25000 | 2014-03-31 20:00 |  | 2014-03-31 02:00 |  | 2014 | Complete | Strategy for Fuel Rod Receipt, Characterization, Sample Allocation for the Demonstration Sister Rods | Marschman, Steve | Marschman, Steve | None | Strategy for Fuel Rod Receipt Char Sister Rods Rev 0.docx | FCRD-UFD-2014-000048 | used fuel characterization, post irradiation examination
M2FT-14IN0802016 | M2 | 1.02.08.02.01 | INL | FT-14IN080201 | Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Status Report on Readiness to Receive Fuel Activities | Status Report on Readiness to Receive Fuel Activities | This report will document the status of the readiness to receive sister pins from the full-scale demonstration at a national laboratory. Begin the process of ensuring a receiving laboratory is ready to receive fuel. | 2014-09-26 08:00 |  | 2014-09-24 02:00 | Milestone has been completed | 2014 | Complete | Status Report on Readiness to Receive Fuel Activities | Marschman, Steve | Marschman, Steve | None | QA Document Cover Sheet Readiness to Receive work.pdf | FCRD-UFD-2014-000049 | used fuel, sister rod, R&D Project, plan
M2FT-14OR0805031 | M2 | 1.02.08.05.03 | ORNL | FT-14OR080503 | Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Results of Bend Tests | Results of Bend Tests | This report will document the data obtained in FY14 using the pure bend test apparatus at ORNL. Cladding segments containing fuel will be tested in a hot cell and the results will be compared to tests conducted on non-irradiated test samples. | 2014-09-26 |  | 2014-09-26 | this report documents the results of vibration testing in FY14 | 2014 | Complete | 2014 M2-FCRD-UFD-2014-000053 (CIRFT testing Results).pdf |  |  | None | 2014 M2-FCRD-UFD-2014-000053 (CIRFT testing Results).pdf | FCRD-UFD-2014-000053
M2FT-14PN0805041 | M2 | 1.02.08.05.04 | PNNL | FT-14PN080504 | Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Results of Fuel Transfer Options Studies | Results of Fuel Transfer Options Studies | This report will document the data obtained during FY14 testing. It will include procurement of various unirradiated cladding types from fuel vendors, hydriding of this cladding both uniformly and with a hydride rim, providing these hydride samples to other laboratories and universities for testing, and the results of burst testing performed at PNNL. The focus in on the effects of re-wetting, multiple drying cycles, and thermal profile “memory” effects. | 2014-08-30 04:00 |  | 2014-08-29 03:00 |  | 2014 | Complete | FY 2014 PNNL Zr Cladding Testing Status Report | Hanson, Brady | Hanson, Brady | None | FCRD-UFD-2014-000054.pdf | FCRD-UFD-2014-000054 | cladding; hydride
M2FT-14PN0810031 | M2 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Thermal profile analyses of in-situ industry storage systems identified for inspection. | Thermal profile analyses of in-situ industry storage systems identified for inspection. | This report will document the development and testing of a COBRA-SFS model of the TN-32B cask to be used for the Industry Demonstration project. The thermal analyses will be used to help identify which of the 37 potential assemblies should be loaded into the 32 spaces in the demonstration cask, identify sister pins for pre-test characterization, and help determine the location of thermocouple lances. | 2015-02-27 05:00 |  |  | On schedule. | 2014 | On Schedule |  |  |  | None |  | FCRD-UFD-2014-000064
M2FT-14SN0802051 | M2 | 1.02.08.02.05 | SNL | FT-14SN080205 | Field Demonstration Support - SNL | Stockman, Christine | Sorenson, Ken | Develop a UFD ST program plan | Develop a UFD ST program plan. | Develop a UFD ST program plan | 2014-08-09 13:00 |  | 2014-08-09 05:00 |  | 2014 | Complete | USED NUCLEAR FUEL EXTENDED STORAGE AND TRANSPORTATION RESEARCH AND DEVELOPMENT REVIEW AND PLAN | Stockman, Christine | Stockman, Christine | None | UFD S&T Plan and Review FCRD-UFD-2014-000050 signed.pdf | FCRD-UFD-2014-000050
M2FT-14SN0805051 | M2 | 1.02.08.05.05 | SNL | FT-14SN080505 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Results of Stainless Steel canister corrosion studies and environmental sample investigations. | Results of Stainless Steel canister corrosion studies and environmental sample investigations. | Results of Stainless Steel canister corrosion studies and environmental sample investigations. | 2014-09-26 12:00 |  | 2014-09-25 02:00 | The status report documents the results of stainless steel canister corrosion studies and environmental sample investigations carried out at Sandia National Laboratories in FY 2014. This L2 milestone was completed and submitted prior to the due date of 9/25/2014. | 2014 | Complete | Results of Stainless Steel Canister Corrosion Studies and Environmental Sample Investigations | Bryan, Charles | Bryan, Charles | None | FCRD-UFD-2014-000055-Final_Report_SNL_Canister_Corrosion_Studies.pdf | FCRD-UFD-2014-000055 | spent nuclear fuel, interim storage, dry storage cask, corrosion , loclaized corrosion, stress corrosion cracking; environment, dust composition, salt composition
M2FT-14SN0808033 | M2 | 1.02.08.08.03 | SNL | FT-14SN080803 | DR Generic Disposal System Analysis - SNL | Freeze, Geoff | Mackinnon, Robert | Generic Disposal System Modeling Report | Enhancements to Generic Disposal System Modeling Capabilities | Enhance the capability to develop and run PA models of generic disposal systems Prepare Generic Disposal System Modeling Report | 2013-11-27 04:00 |  | 2013-11-27 04:00 |  | 2014 | Complete | Enhancements to Generic Disposal System Modeling Capabilities | Freeze, Geoff | Freeze, Geoff | None | FCRD-UFD-2014-000062 GDSM Enhancements_Final.pdf | FCRD-UFD-2014-000062
M2FT-14SN0810021 | M2 | 1.02.08.10.02 | SNL | FT-14SN081002 | Analysis - SNL | Tikare, Veena | Sorenson, Ken | Documentation of Hybrid Hydride Model for Incorporation into Moose-Bison and Validation Strategy. | Documentation of Hybrid Hydride Model for Incorporation into Moose-Bison and Validation Strategy. | Documentation of Hybrid Hydride Model for Incorporation into Moose-Bison and Validation Strategy. | 2014-08-15 20:00 |  | 2014-08-15 02:00 |  | 2014 | Complete | Documentation of Hybrid Hydride Model for Incorporation into Moose- Bison and Validation Strategy | Tikare, Veena | Tikare, Veena | None | FCRD-UFD-2014-000063-Tikare-081414.pdf | FCRD-UFD-2014-000063
M2FT-14SN0813041 | M2 | 1.02.08.13.04 | SNL | FT-14SN081304 | Transportation - SNL | McConnell, Paul | Sorenson, Ken | Results of rail shock/vibration testing on shaker table | Results of rail shock/vibration testing on shaker table. | Results of shock/vibration testing of an assembly on shaker table or from over-the-road transport. | 2014-08-29 12:00 |  | 2014-08-29 02:00 |  | 2014 | Complete | Normal Conditions of Transport Truck Test of a Surrogate Fuel Assembly | McConnell, Paul | McConnell, Paul | None | M2FT-14SN0813041_.pdf | FCRD-UFD-2014-000066 | used nuclear fuel, fuel assembly, fuel rod, rod failure, normal conditions of transport
M3FT-14AN0805013 | M3 | 1.02.08.05.01 | ANL | FT-14AN080501 | Experiments - ANL | Liu, Yung | Sorenson, Ken | Draft report | Draft report | A draft report for the M2 deliverable will be provided for internal review. | 2014-08-29 03:00 | 2014-09-07 01:00 | 2014-09-07 01:00 | The draft report was uploaded on 9/7/2014. | 2014 | Completed Late | Effects of Multiple Drying Cycles on High-Burnup PWR Cladding Alloys | Billone, Michael | Billone, Michael | None | ANL_L3_ST Exp_090714.pdf | FCRD-UFD-2014-000312 | ring compression tests, radal hydrides, embrittlement, multiple drying cycles, ductility
M3FT-14IN0802071 | M3 | 1.02.08.02.07 | INL | FT-14IN080207 | Instrumentation Support - INL | Rempe, Joy | Sorenson, Ken | Report documenting proposed instrumentation R&D program to support spent fuel storage demonstration programs | Report documenting proposed instrumentation R&D program to support spent fuel storage demonstration programs | Report documenting proposed instrumentation R&D program to support spent fuel storage demonstration programs | 2014-09-25 04:00 |  | 2014-09-22 06:00 | Completed head of schedule | 2014 | Complete | White paper, presentation, and letter of transmittal have been transmitted to DOE fulfilling Level 3 Milestone M3FT-14IN0802071. | Rempe, Joy | Rempe, Joy | None |  |  | Report documenting proposed instrumentation R&D program to support spent fuel storage demonstration programs
M3FT-14IN0813013 | M3 | 1.02.08.13.01 | INL | FT-14IN081301 | Transportation - INL | Marschman, Steve | Sorenson, Ken | Transportation Sensitivity Analyses for Fuel Assemblies | Transportation Sensitivity Analyses for Fuel Assemblies | This report will document the results of the sensitivity analysis and their implications for evaluating used fuel transport under normal conditions of transport. INL will perform sensitivity studies on PWR assemblies to determine the affect these sensitivities have on response and strain levels during truck and rail transport. | 2014-09-30 02:00 |  | 2014-09-30 02:00 | This report fulfills this milestone. | 2014 | Complete | Used Fuel Disposition Transportation Sensitivity Analysis | Coleman, Justine | Coleman, Justine | None | FCRD_UFD_M3 FINAL.pdf | FCRD-UFD-2014-000325 | sensitivity analysis, transportation, used fuel transportation
M3FT-14LA0802031 | M3 | 1.02.08.02.03 | LANL | FT-14LA080203 | Field Demonstration Support - LANL | Ulrich, Timothy | Sorenson, Ken | Nonlinear Ultrasound Experiments | Technical Report on the Status of Nonlinear Ultrasonic Techniques for Non-Destructive Inspection | Conduct nonlinear ultrasound experiments on concrete and stainless steel for advancement of these techniques towards field deployment. | 2014-09-18 10:00 |  | 2014-09-18 04:00 | Progress report for LANL activities on the detection of SCC and concrete degradation in support of the UFD campaign. | 2014 | Complete | Technical Report on the Status of Nonlinear Ultrasonic Techniques for Non-Destructive Inspection | Ulrich, Timothy | Ulrich, Timothy | None | Storage Experimentation - LANL endyear.pdf | FCRD-UFD-2014-000307 | NDE SCC conrete degradation crack nonlinear ultrasound
M3FT-14OR0805032 | M3 | 1.02.08.05.03 | ORNL | FT-14OR080503 | Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Draft M2 on Bend Test Results | Draft M2 Report | Draft M2 report on the experimental testing of high burnup fuel; Hot cell vibration test data and analyses report | 2014-09-05 02:00 |  | 2014-09-04 | Document complete and submitted for review | 2014 | Complete | FY14 Status Report: CIRFT Testing Results on High Burnup UNF | Wang, Jy-An | Bevard, Bruce | None | 2014 M3 Status Report-DOE UFDC CIRFT Test_vf.pdf | FCRD-UFD-2014-000314 | High burnup fuel, vibration testing,
M3FT-14OR0810015 | M3 | 1.02.08.10.01 | ORNL | FT-14OR081001 | Analysis - ORNL | Scaglione, John | Sorenson, Ken | Thermal source term sensitivity analysis for conducting best-estimate evaluations | Thermal source term generation sensitivity analysis | Report documenting sensitivity analyses evaluating and identifying parameters of influence for development of best estimate results for thermal calculation models. | 2014-09-30 |  | 2014-09-23 | Milestone completed that investigated the potential impact of simplifying modeling assumptions and techniques on decay heat values calculated for used boiling water reactor (BWR) nuclear fuel using the SCALE computer code system. | 2014 | Complete | Decay Heat Sensitivity Studies for Used BWR Fuel Assemblies | Mueller, Don | Scaglione, John | None | FCRD-UFD-2014-000321_Decay Heat Sensitivity Studies-FINAL_JMS.pdf | FCRD-UFD-2014-000321 | thermal source, BWR
M3FT-14PN0802043 | M3 | 1.02.08.02.04 | PNNL | FT-14PN080204 | Field Demonstration Support - PNNL | Hanson, Brady | Sorenson, Ken | Support identification and development of external monitoring capabilities for canister SCC (integrate with LANL efforts) report | Support identification and development of external monitoring capabilities for canister SCC (integrate with LANL efforts) report | This document will provide a status of the testing and modeling performed in FY14 of non-destructive examination techniques used to detect SCC in canister welds. | 2014-09-12 15:00 |  | 2014-09-04 03:00 | This report documents FY14 efforts for two instrumentation subtasks under storage and transportation. These instrumentation tasks relate to developing effective nondestructive evaluation methods and techniques. | 2014 | Complete | Instrumentation: Nondestructive Examination for Verification of Canister and Cladding Integrity - FY2014 Status Update | Meyer, Ryan | Meyer, Ryan | None | FCRD-UFD-2014-000308.pdf | FCRD-UFD-2014-000308 | Nondestructive Examination, canister, cladding, instrumentation
M3FT-14PN0813031 | M3 | 1.02.08.13.03 | PNNL | FT-14PN081303 | Transportation - PNNL | Ross, Steven | Sorenson, Ken | Used Fuel Testing Transportation Modeling | Used Fuel Testing Transportation Modeling | This report identifies potential transportation options for the used nuclear fuel pieces and further investigates the best options for transportation. | 2014-09-30 20:00 |  | 2014-09-29 03:00 | This report fulfills the M3 Milestone (M3FT-14PN0813031). | 2014 | Complete | Used Fuel Testing Transportation Model | Ross, Steven | Ross, Steven | None | FCRD-UFD-2014-000326 Ross.pdf | FCRD-UFD-2014-000326 | transportation, casks, shipping packages
M3FT-14PN0813032 | M3 | 1.02.08.13.03 | PNNL | FT-14PN081303 | Transportation - PNNL | Ross, Steven | Sorenson, Ken | Support SNL developing Test Plan for over road and rail transport | Fuel Assembly Test Plan | Develop a test plan and associated test design information for determining the response of a fuel assembly to over road and rail transport. Rail testing to be conducted on TriCity Rail Yard (TCRY) track system and facilities and include collaboration with TTCI. | 2014-09-30 11:00 |  | 2014-09-29 03:00 | This report fulfills the requirements for milestone M3FT-14PN0813032 "Fuel Assembly Test Plan" under work package FT-14PN081303. | 2014 | Complete | Used Fuel Rail Shock and Vibration Testing Optional Analysis | Ross, Steven | Ross, Steven | None | FCRD-UFD-2014-000327_PNNL-23709.pdf | FCRD-UFD-2014-000327 | Rail shock, vibration testing, fuel assembly
M3FT-14PN0813034 | M3 | 1.02.08.13.03 | PNNL | FT-14PN081303 | Transportation - PNNL | Ross, Steven | Sorenson, Ken | Shaker Table Report | Shaker Table Report | Report that documents shaker table model modifications and additional analyses to support the program in FY14. | 2014-09-30 03:00 |  | 2014-09-30 03:00 | This fulfills Milestone M3FT-14PN0813034 - Shaker Table Report. | 2014 | Complete | Fuel Assembly Shaker and Truck Test Simulation | Klymyshyn, Nicholas | Hanson, Brady | None | FCRD-UFD-2014-000328 Shaker_Table_2014_final.pdf | FCRD-UFD-2014-000328 | modeling support, shaker table, fuel assembly
M3FT-14SN0802052 | M3 | 1.02.08.02.05 | SNL | FT-14SN080205 | Field Demonstration Support - SNL | Stockman, Christine | Sorenson, Ken | Dry Transfer Needs | Considerations for Dry Transfer Systems for Used Nuclear Fuel | Assess dry transfer needs and capabilities | 2013-11-27 |  | 2013-11-27 02:00 |  | 2014 | Complete | Considerations for Dry Transfer Systems for Used Nuclear Fuel | Stockman, Christine | Stockman, Christine | None | Considerations for Dry Transfer Systems for UNF.pdf | FCRD-UFD-2014-000309
M3FT-14SN0805052 | M3 | 1.02.08.05.05 | SNL | FT-14SN080505 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Draft of Level 2 Milestone Report: "Results of Stainless Steel canister corrosion studies and environmental sample investigations" | Draft Report: "Results of Stainless Steel canister corrosion studies and environmental sample investigations" | This deliverable is a draft of the Level 2 Milestone "Results of Stainless Steel canister corrosion studies and environmental sample investigations" to be provided for review prior to completion of the L2 milestone. This draft report, and the final L2 milestone, will document the data obtained by SETs under aqueous and humid air conditions on canister and weld materials, with emphasis on the effects of various salt quantities and composition on stress corrosion cracking. The report will also document the results of analyses of the dust samples taken from the EPRI-led in-service inspections on various dry storage canisters at existing ISFSIs. | 2014-09-05 10:00 |  | 2014-09-05 02:00 | This deliverable is a draft of the Level 2 Milestone "Results of Stainless Steel canister corrosion studies and environmental sample investigations" to be provided for review prior to completion of the L2 milestone. | 2014 | Complete | Draft Report: Results of Stainless Steel Canister Corrosion Studies and Environmental Sample Investigations | Bryan, Charles | Bryan, Charles | None | FCRD-UFD-2014-000316-Draft_Report_SNL_Canister_Corrosion_Studies_FINAL.pdf | FCRD-UFD-2014-000316 | spent nuclear fuel, interim storage, dry storage cask, corrosion , loclaized corrosion, stress corrosion cracking; environment, dust composition, salt composition
M3FT-14SR0805062 | M3 | 1.02.08.05.06 | SRNL | FT-14SR080506 | Experiments - SRNL | Carter, Joe | Sorenson, Ken | Effects of Irradiation on Polymeric Seals | Effects of Irradiation on Polymeric Seals | Test report on the irradiation and testing of the polymeric seals at conditions (irradiation, temperature) reflecting extended storage service | 2014-05-30 |  | 2014-05-30 |  | 2014 | Complete | Used Fuel Disposition Campaign Preliminary Report: Effects of Irradiation and Thermal Exposure on Elastomeric Seals for Cask Transportation and Storage | Verst, CG | Verst, CG | None | FCRD-UFD-2014-000317 - Final - Revision 0.pdf | FCRD-UFD-2014-000317 | Polymeric Seals
M3FT-14SR0805063 | M3 | 1.02.08.05.06 | SRNL | FT-14SR080506 | Experiments - SRNL | Carter, Joe | Sorenson, Ken | Degradation Evaluation and Aging Management of Bolted Closure Joints | Degradation Evaluation and Aging Management of Bolted Closure Joints | Prepare technical report to synthesize results of BAM and SRNL experimentation work on metallic and polymeric seal materials, and additional SRNL evaluation of aqueous and atmospheric corrosion of bolts, and prepare a generic aging management plan to ensure the integrity of the bolted under extended service. | 2014-09-30 02:00 |  | 2014-09-30 | The bolted closure joint of a bare spent fuel cask is susceptible to age-related degradation and potential loss of confinement function under long-term storage conditions. The degradation phenomena for the components of the joint, including metallic and polymeric seals, and bolting are summarized, and the aging material activities to quantify and predict the degradation are described. An aging management program to demonstrate maintenance of confinement in consideration of this degradation in long-term storage at normal service conditions is suggested. With completion of this work, the gap to provide the technical bases to understand materials degradation and degradation kinetics, and to provide an approach for aging management to ensure the efficacy of the bolted closure joint under long-term storage conditions is effectively closed. | 2014 | Complete | UFD Campaign: Preliminary Report - Degradation Evaluation and Aging Management of Bolted Closure Joints | Sindelar, Robert | Sindelar, Robert | None | FCRD-UFD-2014-000318-Degradation Evaluation and Aging Management.pdf | FCRD-UFD-2014-000318 | Degradation Evaluation and Aging
M4FT-14AN0802021 | M4 | 1.02.08.02.02 | ANL | FT-14AN080202 | Field Demonstration Support - ANL | Liu, Yung | Sorenson, Ken | Managing Aging Effects on Dry Cask Storage Systems for Extended Long-Term Storage and Transprtsation of Used Fuel, Revision 1 (Updated) | Managing Aging Effects on Dry Cask Storage Systems for Extended Long-Term Storage and Transportation of Used Fuel, Rev. 1 (Updated) | The Rev. 1 report will be updated incorporating lessons learned from substantive stakeholders' comments and new information on license renewal applications of ISFSIs/DCSSs, the NRC inspection reports and industry operation experience of DCSSs/ISFSIs. | 2014-09-30 02:00 |  | 2014-09-26 02:00 | The report incorporated changes made as a result of addressing stakeholder comments on the Rev. 1 report. | 2014 | Complete | Managing Aging Effects on Dry Cask Storage Systems for Extended Long-Term Storage and Transportation of Used Fuel, Rev. 2 | Chopra, Omesh | Liu, Yung | None | FCRD-UFD-2014-000476.pdf | FCRD-UFD-2014-000476 | aging management, dry cask storage systems, AMP, time-limited aging analysis, TLAA
M4FT-14IN0805023 | M4 | 1.02.08.05.02 | INL | FT-14IN080502 | Experiments - INL | Marschman, Steve | Sorenson, Ken | Results of NDE technique evaluation of clad hydrides | Results of NDE technique evaluation of clad hydrides | Report that summarizes the feasibility of evaluating hydrides using INL NDE techniques. Evaluate the feasibility of using multi-coil array eddy current analysis techniques developed at the INL that have shown promise for analyzing hydrides. | 2014-09-22 16:00 |  | 2014-09-26 02:00 | This milestone is complete. | 2014 | Completed Late | Results of NDE Technique Evaluation of Clad Hydrides | Kunerth, Dennis | Marschman, Steve | None | Hydride_-1 9-23-2014_dck2_.docx QA Document Cover Sheet Hydride work.pdf | FCRD-UFD-2014-000486 | eddy current, hydrides
M4FT-14IN0810052 | M4 | 1.02.08.10.05 | INL | FT-14IN081005 | Analysis - INL | Hales, Jason | Sorenson, Ken | Demonstration of correct integration of hybrid model into BISON | Demonstration of Correct Implementation | Generate evidence (computational results) showing that the implementation in BISON gives similar answers as the native implementation. | 2014-06-30 14:00 |  | 2014-06-30 02:00 |  | 2014 | Complete | Implementation of Hybrid Potts/Phase Field Model in SPPARKS/MBM | Hales, Jason | Hales, Jason | None | HybridPottsPhaseFieldWithSPPARKSAndMBM.pdf | FCRD-UFD-2014-000508 | Potts, phase field, MBM
M4FT-14IN0810053 | M4 | 1.02.08.10.05 | INL | FT-14IN081005 | Analysis - INL | Hales, Jason | Sorenson, Ken | Future work planning | Future Work Planning | Draft development plan for inclusion of further capabilities. This could include mechanical strain due to volumetric changes associated with phase transformations, a list of possible future applications of the technology, additional V&V needs, applications for UQ, and other items as identified within the other ST work packages. | 2014-09-15 18:00 |  | 2014-09-04 02:00 | Report on possible future work to develop a hydride capability in MBM. | 2014 | Complete | MBM UFD Development Plan | Hales, Jason | Hales, Jason | None | UFD_DevelopmentPlanSep2014.pdf | FCRD-UFD-2014-000509 | MBM; SPPARKS; hydride; cladding
M4FT-14LL0810044 | M4 | 1.02.08.10.04 | LLNL | FT-14LL081004 | Analysis - LLNL | Sutton, Mark | Sorenson, Ken | Input to SNL report on composition of available data | Analysis of Available Data Composition - Progress Report | Input to SNL report | 2014-07-07 09:00 | 2014-08-15 03:00 | 2014-08-15 03:00 |  | 2014 | Completed Late | LLNL Input to SNL Report on the Composition of Available Data for Used Nuclear Fuel Storage and Transportation Analysis | Sutton, Mark | Sutton, Mark | None | M4FT-14LL0810044-LLNL_Composition_of_Available_Data_R1.docx | FCRD-UFD-2014-000506 | Uncertainty quantification, Predictive Capability Maturity Model, Chloride-induced Stress Corrosion Cracking, Environmental Corrosion, Welded Cansiter
M4FT-14OR0805033 | M4 | 1.02.08.05.03 | ORNL | FT-14OR080503 | Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Status Report of Vibration Testing of Clad Fuel | Status Report on the Results of Vibration Testing of Fuel | Status report on vibration test progress and test results from both out of cell testing of simulated fueled clad and in hot cell testing of high burnup fuel | 2014-03-28 02:00 |  | 2014-03-28 08:00 |  | 2014 | Complete | FY 2014 Status Report: Vibration Testing of High- Burnup Clad/Fuel |  |  | None | 2014 M4_03_28_14_Final.pdf | FCRD-UFD-2014-000487
M4FT-14OR0810017 | M4 | 1.02.08.10.01 | ORNL | FT-14OR081001 | Analysis - ORNL | Scaglione, John | Sorenson, Ken | Validate FEA pin model | FEA validation report | Use NRC experimental data currently being generated to validate pin FEA model. Add detail including paellet patterns/shape, transition region information (bonding mechanisms) etc. This activity ensure that the FEA model represnts the actual interface conditions and responses noted in the NRC static and dynamic tests. | 2014-08-29 |  | 2014-08-29 |  | 2014 | Complete | FY 2014 Status Report: Using Finite Model Analysis and Out of Hot Cell Surrogate Rod Testing to Analyze High Burnup Used Nuclear Fuel Mechanical Properties | Wang, Jy-An | Scaglione, John | None | FINAL 2014 Status Report-Surrogate Rod_20140826_JMS_20140904.pdf
M4FT-14OR0810019 | M4 | 1.02.08.10.01 | ORNL | FT-14OR081001 | Analysis - ORNL | Scaglione, John | Sorenson, Ken | Quantification of CIRFT system biases and uncertainties | Bias and uncertainty for CIRFT system | This activity is t omatch out of cell experiments with FEA to understand machine biases due to friction, wear, and other factors | 2014-09-17 |  | 2014-09-17 | M4 milestone completed | 2014 | Complete | FY 2014 Status Report: Quantification of CIRFT System Biases and Uncertainties when Testing High-Burnup Spent Nuclear Fuel | Wang, Jy-An | Scaglione, John | None | CIRFT_bias.pdf |  | high burnup, FEA
M4FT-14OR0813021 | M4 | 1.02.08.13.02 | ORNL | FT-14OR081302 | Transportation - ORNL | Scaglione, John | Sorenson, Ken | Initial assessment and reccommendations for transportation of storage only canisters | Initial assessment for transporting storage only UNF canisters | Whitepaper documenting an initial assessment of options available and further research for obtaining regultary concurrence to transport storage-only canisters to a new location. | 2014-09-05 04:00 | 2014-09-18 | 2014-09-24 | M4 milestone completed | 2014 | Completed Late | Assessment of the Transportability of Storage-Only Used Nuclear Fuel Canisters | Bowen, D | Scaglione, John | None | FCRD_UFD Report_Transportability_Assessment_Final_09-24-2014_FINAL DGB FINAL_JMS.pdf | FCRD-UFD-2014-000511
M4FT-14PN08100311 | M4 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Structural Uncertainty | Structural Uncertainty | Structural Uncertainty | 2014-09-30 06:00 |  | 2014-09-30 03:00 | This report fulfills M4 milestone M4FT-14PN08100311 under work package FT-14PN081003. | 2014 | Complete | Structural Uncertainty of Used Nuclear Fuel in Dry Storage Canisters | Klymyshyn, Nicholas | Hanson, Brady | None | FCRD-UFD-2014-000617 Structural Uncertainty Report_final.pdf |  | dry storage canisters, casks, cladding, uncertainty, structural loads
M4FT-14PN0810037 | M4 | 1.02.08.10.03 | PNNL | FT-14PN081003 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Pre-inspection report | Pre-inspection report | Submit pre-test thermal analyses report. | 2014-07-31 12:00 |  | 2014-07-24 03:00 |  | 2014 | Complete | PRELIMINARY THERMAL MODELING OF HI-STORM 100 STORAGE MODULES AT DIABLO CANYON POWER PLANT ISFSI | Hanson, Brady | Hanson, Brady | None | Pre-Inspection_DiabloCanyon_FINAL.pdf | FCRD-UFD-2014-000505
M4FT-14SN0810024 | M4 | 1.02.08.10.02 | SNL | FT-14SN081002 | Analysis - SNL | Tikare, Veena | Sorenson, Ken | Draft of M2 report on integration of the hybrid hydride model into INL’s MBM framework for review | Draft of M2 report on integration of the hybrid hydride model into INL’s MBM framework for review | Draft is for review by other labs and DOE | 2014-07-02 14:00 |  | 2014-08-12 02:00 |  | 2014 | Completed Late | Draft of M2 Report on Integration of the Hybrid Hydride Model in INL's MBM Framework for Review | Tikare, Veena | Tikare, Veena | None | M4-DraftOfM2OnHydrideFormation.docx | FCRD-UFD-2014-000503
M4FT-14SN0810025 | M4 | 1.02.08.10.02 | SNL | FT-14SN081002 | Analysis - SNL | Tikare, Veena | Sorenson, Ken | Report on methodology to assess phenomena impacting UFD S&T R&D most highly | Report on methodology to assess phenomena impacting UFD S&T R&D most highly | UQ methodology development to quantify degradation mechanisms during storage and transportation of high burnup fuels and rank the likely degradation mechanism while identifying data gaps associated with these | 2014-09-15 08:00 | 2014-10-01 02:00 | 2014-10-01 02:00 | Complete | 2014 | Expected Late | Uncertainty quantification methodologies development for storage and transportation of used nuclear fuel: Pilot study on stress corrosion cracking of canister welds | Dingreville, Remi | Dingreville, Remi | None | UQ_UFD_PICSNE.pdf | FCRD-UFD-2014-000504 | Uncertainty Quantification
M5FT-14IN0818021 | M5 | 1.02.08.18.02 | INL | FT-14IN081802 | DR Salt R&D - INL | Frank, Steve | None | Provide input data to Sandia for PA calculations and transportation criticality issues | Milestone M5 Summary Report | Investigate primary salt packaging transportation criticality and salt/container interaction concerns. Provide input to Sandia for updated PA caluclations. Summary report for PA calculation input, packaging information and salt/container interactions. | 2014-09-19 12:00 |  | 2014-09-30 02:00 | Summary report outlining SNL calculations on criticality and transportation issues with direct disposal of ER salt completed. | 2014 | Completed Late | Summary Report - Criticality Analysis of Disposal and Transportation | Frank, Steve | Frank, Steve | None | Summary Report - Criticality Analysis of Disposal and Transportation.pdf |  | Direct Disposal, ER salt
M2FT-15AN0805011 | M2 | 1.02.08.05.01 | ANL | FT-15AN080501 | ST Experiments - ANL | Billone, Mike | Sorenson, Ken | The effects of lower drying-storage temperatures on the DBTT of high-burnup PWR cladding alloys | Lower Temperature Ring Compression Tests | Conduct ring compression tests on HBU PWR cladding alloys at 350 C. | 2015-08-28 14:00 | 2015-09-01 01:00 | 2015-09-01 01:00 | The milestone report was submitted to DOE sponsors and designated DOE-Lab personnel via email on September 1, 2015. It is being uploaded onto this website now rather than at the end of the September 2015 performance period because it is more timely to do so. | 2015 | Completed Late | Effects of Lower Drying-Storage Temperatures on the DBTT of High-Burnup PWR Cladding | Billone, Michael | Billone, Michael | None | FCRD-UFD-2015-000008_Final Report_S.pdf | FCRD-UFD-2015-000008 | Cladding, hydrides, embrittlement
M2FT-15IN0802013 | M2 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Evaluate the Frequency for Gas Sampling for the High Burn-up Storage Demonstration Project | Evaluate the Frequency for Gas Sampling for the High Burn-up Storage Demonstration Project | M2FT-15IN0802011. This milestone will provide the campaign recommendation for the frequency of gas sampling from the TN-32B cask that will be loaded with high burnup fuel in 2017. | 2015-05-22 16:00 |  | 2015-05-22 02:00 |  | 2015 | Complete | Evaluation of the Frequency for Gas Sampling for the High Burnup Confirmation Data Project | Stockman, Christine | Marschman, Steve | None | INL M2 Gas Sampling Frequency Rev 0.pdf | FCRD-UFD-2015-000051 | gas sampling, cask gas sampling, sampling frequency
M2FT-15OR0805031 | M2 | 1.02.08.05.03 | ORNL | FT-15OR080503 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Results of Bend Tests for Used Nuclear Fuel | Resuts of Bend Tests for Used Nuclear Fuel | Conduct cyclic bend tests of used nuclear fuel. | 2015-09-04 02:00 |  | 2015-09-04 | Final report on CIRFT testing completed in FY15; this report also includes the CIRFT test data completed in FY14 so that the report is in reality a complete compendium of all CIRFT testing | 2015 | Complete | CIRFT-M2-FCRD-UFD-2015-000101 | ORNL | Wang, Jy-An | None |  | FCRD-UFD-2015-000101 | CIRFT testing, vibration testing, transportation testing, hydride reorientation, S-N curve, clad testing,
M2FT-15SN0805051 | M2 | 1.02.08.05.05 | SNL | FT-15SN080505 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | Stress Corrosion Cracking Investigations on Full Scale Stainless Steel Canister Mock-up | Stress Corrosion Crackin Investigation on a Full Scale Stainless Steel Canister Mock-up | Conduct coupon testing to investigate residual stress levels and crack detection in a SS canister with welds. | 2015-08-21 08:00 |  | 2015-08-21 02:00 |  | 2015 | Complete | Status report: Characterization of Weld Residual Stresses on a Full-Diameter SNF Interim Storage Canister Mockup | Enos, David | Bryan, Charles | None | FCRD-UFD-2015-00123 - Mock-up WRS status report - Final.pdf | FCRD-UFD-2015-000123 | stress corrosion cracking, SNF interim storage, mockup, weld residual stress
M2FT-15SN0810051 | M2 | 1.02.08.10.05 | SNL | FT-15SN081005 | ST Analysis - SNL | Dingreville, Remi | Sorenson, Ken | Development of Uncertainty Quantification Methodology as Applied to Storage and Transportation R&D | Development of Uncertainty Quantification Methodology as Applied to Storage and Transportation R&D. | This document will include (i) a description of the UQ methodology in terms of its potential for application in the UFDC S&T Engineering Analysis work package and applicability across all the identified degradation mechanisms and associated cross-cutting needs, (ii) a description of the models used to simulated the degradation mechanisms of interest, and (iii) quantify and characterize the uncertainty associated with the degradation mechanisms impacting normal dry storage operations and normal conditions of transport, and provide an informed guidance on which needs have the greatest impact on meeting the UFD R&D objectives. | 2015-07-24 08:00 |  | 2015-07-24 02:00 |  | 2015 | Complete | Development of Uncertainty Quantification Methodologies as Applied to Storage and Transportation R&D: Study on Stress Corrosion Cracking of Canister Welds |  |  | None | M2FT-15SN0810051.pdf | FCRD-UFD-2015-000127
M2FT-15SN0813021 | M2 | 1.02.08.13.02 | SNL | FT-15SN081302 | ST Transportation - SNL | McConnell, Paul | Sorenson, Ken | Surrogate Assembly Test Simulating Normal Conditions of Rail Transport | Surrogate Assembly Test Simulating Normal Conditions of Rail Transport. | Conduct shock and vibration tests on a surrogate assembly to simulate loads from incident free rail transport. | 2015-09-11 10:00 |  | 2015-09-08 02:00 | The M2 milestone report, “Surrogate Fuel Assembly Multi-Axis Shaker Tests to Simulate Normal Conditions of Rail and Truck Transport”, due September 11, 2015 was submitted to Michele Oliveira, INL, for entry into DMS. The report file is too large to upload to PICS:NE. | 2015 | Complete | “Surrogate Fuel Assembly Multi-Axis Shaker Tests to Simulate Normal Conditions of Rail and Truck Transport”, FCRD-UFD-2015-00128, Revision 0, September 11, 2015. | McConnell, Paul | McConnell, Paul | None |  | FCRD-UFD-2015-000128 | PWR assembly; Normal Conditions of Transport; Transport of Used Nuclear Fuel
M3FT-15AN0805071 | M3 | 1.02.08.05.07 | ANL | FT-15AN080507 | Ultrasonic Temperature Probes - ANL | Liu, Yung | Sorenson, Ken | Bench scale design and testing of instrumentation for monitoring of internal cask environment | Bench scale design and testing of the instrumentation for monitoring of internal cask environment | The report will document the design, fabrication, and testing of the proposed instrumentation in support of high burnup cask demonstration program. The technical report will include description of the data collection and analysis methods for the three different sensors selected for initial evaluations. Suggestions will be provided regarding the path forward for future R&D activities on promising sensor technologies based on the results of those investigations. | 2015-09-30 02:00 |  | 2015-09-30 01:00 | The report completes the M3 milestone M3FT-15AN0805071. | 2015 | Complete | Bench scale design and testing of the instrumentation for monitoring of internal cask environment | Chien, H-T | Bakhtiari, S | None | FY15-Annual_ FCRD-UFD-2015-000768.pdf | FCRD-UFD-2015-000768 | ultrasonic temperture probe, acoustic and microwavw sensors
M3FT-15IN08020112 | M3 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Transportation Support | Analyses of Variables in UNF Transportation | This carryover activity addresses the impacts of transportation variables on the behavior of UNF. | 2015-09-25 09:00 |  | 2015-09-30 02:00 | The scope of work covered in this report includes: Use of MOOSE, MARMOT (microstructure evolution code), and BISON (fuel performance code) to determine the impact of hydride formation at the pellet-pellet-clad interface on UNF cladding cyclic fatigue. A discussion of modeling and simulation methodology is presented, and the implementation and criteria to assess fatigue failure in more detail (although this fatigue model does not degrade the material properties during dynamic simulation). Also presented is a modeling approach in ABAQUS to evaluate the cyclic fatigue of UNF including consideration of damage criteria that degrades the material properties during dynamic simulation. Benchmarking of the ABAQUS model to pure bending test performed at ORNL is also presented. | 2015 | Completed Late | Modeling and Simulation of Used Nuclear Fuel During Transportation with Consideration of Hydride Effects and Cyclic Fatigue |  | Marschman, Steve | None | FCRDUFD2015v14FINAL.pdf | FCRD-UFD-2015-000273 | Cyclic fatigue, MOOSE, BISON, MARMOT, modeling, simulation, hydrides, damage, sructural dynamics
M3FT-15IN0802014 | M3 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Status of Readiness to Receive and Store Sister Rods from the R&D Project | Status of Readiness to Receive and Store Sister Rods from the R&D Project | This documents the state of readiness to receive sister fuel rods at a national laboratory. | 2015-09-18 13:00 |  | 2015-09-30 02:00 | This report documents that status of readiness to receive the sister fuel rods from the EPRI-led HBU Confirmatory Data Project if that fuel were to be sent to Idaho National Laboratory. | 2015 | Completed Late | Status of Readiness to Receive and Store Sister Rods from the R&D Project | Marschman, Steve | Marschman, Steve | None | QA Document Cover Sheet M3FT-15IN0802014.docx Statusofreadiness930d.pdf | FCRD-UFD-2015-000274 | hotcell, NAC-LWT, readiness
M3FT-15IN0805023 Carryover from FY14: M3FT-14IN0805027 | M3 | 1.02.08.05.02 | INL | FT-15IN080502 | ST Experiments - INL | Marschman, Steve | Sorenson, Ken | SST Vessel Conceptual Design | Small-Scale Test Conceptual Design | This is a carryover deliverable from FY 2014. This will be a report documenting the conceptual design(s) for a small-scale test. | 2015-05-22 08:00 | 2015-09-28 02:00 | 2015-09-30 02:00 | This report describes the functional requirements for a small-scale test, the types of fuel that could be tested, proposes a method for testing, and provides a preliminary cost estimate for performing such a test. | 2015 | Completed Late | CONCEPTS FOR SMALL-SCALE TESTING OF USED NUCLEAR FUEL | Marschman, Steve | Marschman, Steve | None | small scale testing 09-29-2015a.pdf | FCRD-UFD-2015-000767 | small-scale test, BWR, UNF, demonstration
M3FT-15OR0810034 NOT OUO | M3 | 1.02.08.10.03 | ORNL | FT-15OR081003 | ST Analysis - ORNL | Scaglione, John | Sorenson, Ken | Report documenting thermal source term generation for demo cask and as-loaded casks | Thermal source term generation for selected as-loaded casks | Report documenting process used for generating detailed thermal source terms for as-loaded casks | 2015-08-31 | 2015-09-30 | 2015-09-30 | M3 milestone documenting thermal source term generation for the high burnup confirmatory data project completed | 2015 | Completed Late | Thermal Sources for the High Burnup Confirmatory Data Project | Liljenfeldt, Henrik | Scaglione, John | OUO |  | FCRD-UFD-2015-000433
M3FT-15PN08100412 supersedes M3FT-14PN0810035 | M3 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Hope Creek Post-inspection Report | Hope Creek Analysis Report | Hope Creek Analysis Report. Previously Fy13 M3FT-13PN0810023. | 2015-08-28 10:00 | 2015-09-07 03:00 | 2015-09-29 06:00 | This report documents pre-inspection predictions of canister surface temperatures and post-inspection comparisons to measured data obtained during the inspection of two modules at the Hope Creek Nuclear Generating Station Independent Spent Fuel Storage Installation. | 2015 | Completed Late | Post-Inspection Evaluation: Thermal Modeling of HI-STORM 100S-218 Version B Storage Modules at Hope Creek Nuclear Power Station ISFSI | Cuta, Judith | Hanson, Brady | None | Post-Inspection_HopeCreek_20150921-FINAL.pdf | FCRD-UFD-2015-000491 | Hope Creek, thermal modeling, HI-STORM
M3FT-15PN08100413 | M3 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Diablo Canyon Post-inspection Report | Post-inspection report | Perform posttest analyses and provide report on the third inspection. | 2015-09-11 07:00 |  | 2015-09-30 03:00 | Final report comparing thermocouple measurements and models for two systems at the Diablo Canyon ISFSI. | 2015 | Completed Late | POST-INSPECTION THERMAL MODELING OF HI-STORM 100 STORAGE MODULES AT DIABLO CANYON POWER PLANT ISFSI | Cuta, Judith | Hanson, Brady | None | Post-Inspection_DiabloCanyon_FINAL.pdf | FCRD-UFD-2015-000492 | Used Fuel, Inspection, Thermal analysis
M3FT-15PN0810047 | M3 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Structural Uncertainty Update | Structural Uncertainty Update | Report on structural uncertainty work in FY15. | 2015-09-11 16:00 |  | 2015-09-11 03:00 | This document is a progress report that describes the work that was performed in fiscal year 2015. The work is a broad task that considers a number of physical phenomena and uses sophisticated LS-DYNA finite element models to predict used fuel and DSC system response to dynamic loads. This year, three topics were investigated: options for modeling cladding in LS-DYNA, the effect of cladding thinning in the tip-over load case, and stress corrosion cracking in multipurpose canister welds. In each of these cases, significant progress was made. This report details the work that was done and identifies areas where more work is needed. | 2015 | Complete | Update: Structural Uncertainty of Used Nuclear Fuel in Dry Storage Canisters | Klymyshyn, Nicholas | Hanson, Brady | None | Structural Uncertainty Update 2015_final.pdf | FCRD-UFD-2015-000493 | structural uncertainty; used fuel cladding; dry storage canister
M3FT-15PN0813011 | M3 | 1.02.08.13.01 | PNNL | FT-15PN081301 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Modeling Support for Shaker Table/S&V Testing | Summary of Modeling Support of Shaker Table/Shock and Vibration Testing | Provide finite element modeling support for the shaker table tests and in support of planning for the shock and vibration testing. | 2015-09-30 17:00 |  | 2015-09-30 03:00 | This report documents a number of modeling and analysis tasks that were performed in support of the Sandia shaker table test campaign, which is a multi-year program that uses an instrumented fuel assembly surrogate to determine the shock and vibration loads associated with normal conditions of transport (NCT) of used nuclear fuel. | 2015 | Complete | Shaker Table Modeling Support Task 2015 | Klymyshyn, Nicholas | Ross, Steven | None | Shaker2015_final.pdf | FCRD-UFD-2015-000494 | shock and vibration, S&V Testing, fuel assembly
M3FT-15PN0813012 | M3 | 1.02.08.13.01 | PNNL | FT-15PN081301 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Support Shock and Vibration Testing Activitites | Summary of S&V Modeling, Planning, and Testing Activities | Conduct analysis and model development in support of rail test. | 2015-09-30 19:00 |  | 2015-09-30 03:00 | Completed M3 Milestone for Work Package Milestone M3FT-15PNO813012 | 2015 | Complete | FY15 Used Fuel Shock and Vibration Testing Planning Summary |  |  | None | PNNL_Rail Testing Plan_FCRD_UFD-2015-000495.pdf | FCRD-UFD-2015-000495
M3FT-15SN0802041 | M3 | 1.02.08.02.04 | SNL | FT-15SN080204 | ST Field Demonstration Support - SNL | Stockman, Christine | Sorenson, Ken | Draft Evaluation of the Frequency for Gas Sampling for the High Burn-up Storage Demonstration Project | Draft Evaluation of the Frequency for Gas Sampling for the High Burn-up Storage Demonstration Project | Assess the frequency for sampling gas from the storage demonstration cask once it is placed on the pad and is in operation. | 2015-03-26 16:00 |  | 2015-03-26 03:00 |  | 2015 | Complete | Draft Evaluation of the Frequency for Gas Sampling for the High Burnup Confirmatory Data Project | Stockman, Christine | Stockman, Christine | None | Gas Sampling Frequency.pdf | FCRD-UFD-2015-000509 | gas sampling frequency for the High Burnup Confirmatory Data Project
M3FT-15SN0802042 | M3 | 1.02.08.02.04 | SNL | FT-15SN080204 | ST Field Demonstration Support - SNL | Stockman, Christine | Sorenson, Ken | Evaluate the Frequencies for Canister Inspections for SCC | Evaluate the Frequencies for Canister Inspections for SCC | Evaluate technically defensible frequencies for canister inspections for SCC as a function of general site parameters. Specify the parameters most important to SCC degradation for selection of a “lead canister” for those inspections. | 2015-08-14 22:00 | 2015-09-30 06:00 | 2015-09-30 12:00 | This report reviews the current state of knowledge on the potential for stress corrosion cracking (SCC) of dry storage canisters. Models for the prediction of SCC by the Japanese Central Research Institute of Electric Power Industry (CRIEPI), the United States (U.S.) Electric Power Research Institute (EPRI), and Sandia National Laboratories (SNL) are summarized, and their limitations discussed. It is the opinion of the authors that at this time the data and modeling do not provide a defensible technical basis for predicting a low probability of SCC penetration in 40 years. Thus they have limited use in determining inspection frequency, and an operations-based and learning inspection frequency is necessary at this time. The Calvert Cliffs aging management plan and the example aging management plan provided in NUREG 1927 DFC R1 are reviewed. It is recommended that a comparison of the risk to the public from undetected through wall cracks and the dose to workers during inspections be performed to inform the frequency and sample size of inspections. | 2015 | Completed Late | Evaluation of the Frequencies for Canister Inspections for SCC | Stockman, Christine | Stockman, Christine | None | SCC SFE reviewed by Steve Marschman.docx | FCRD-UFD-2015-000510 | Inspection Frequency SCC
M3FT-15SN0805052 | M3 | 1.02.08.05.05 | SNL | FT-15SN080505 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | SNF Interim Storage Canister Corrosion and Surface Environment Investigations | SNF Interim Storage Canister Corrosion and Surface Environment Investigations | This report will document experimental work evaluating atmospheric corrosion of spent nuclear fuel storage canisters, and experimental and geochemical modeling work being evaluating the environment on the surface of the canisters, that is being conducted at Sandia National Laboratories | 2015-09-07 10:00 |  | 2015-09-07 02:00 | This milestone is a status report documenting work done at Sandia National Laboratories evaluating the corrosion performance of SNF interim storage canisters. It specifically addresses environmental studies, material characterization, and corrosion experimental work evaluating the potential for stress corrosion cracking. | 2015 | Complete | SNF Interim Storage Canister Corrosion and Surface Environment Investigations | Bryan, Charles | Bryan, Charles | None | FCRD-UFD-2015-00511--Status report SNL experimental work Final.pdf | FCRD-UFD-2015-000511 | stress corrosion cracking, spent nuclear fuel, dry storage, interim storage, dust weld residual stress
M3FT-15SN0805056 | M3 | 1.02.08.05.05 | SNL | FT-15SN080505 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | FY15 Status Report on the BWR Cask Simulator Experiment | FYT15 Status Report on the BWR Cask Simulator Experiment | This report will document the status of ongoing work on the BWR cask simulator experiment at the end of FY15. | 2015-09-18 08:00 |  | 2015-09-16 02:00 | This report documents the status of the BWR Cask Simulator project, which will produce a data set for testing the validity of assumptions associated with calculations currently used to estimate cladding temperatures in modern dry casks. | 2015 | Complete | Status Update of the BWR Cask Simulator | Lindgren, Eric | Durbin, Sam | None | FCRD-UFD-2015-0000795_BCS_Status_Update_Report_Final.pdf | FCRD-UFD-2015-000795 | BWR cask simulator, spent nuclear fuel, dry storage casks, long-term interim storage
M3FT-15SN0810056 | M3 | 1.02.08.10.05 | SNL | FT-15SN081005 | ST Analysis - SNL | Dingreville, Remi | Sorenson, Ken | Document modeling effort on hydridre-orientation and comparison with experiments | M3 report on rate-theory model and its calibration with respect to the hybrid model developed during the past FYs. | Document the rate-theory model and its calibration with respect to the hybrid model developed during the past FYs. This document will include comparisons between results obtained from the computational model and experiment data (Billone et al.) for unirradiated and irradiated samples. | 2015-09-18 10:00 | 2015-09-25 02:00 | 2015-09-25 02:00 | Completed on 9/25/2015. | 2015 | Completed Late | Modeling of hydride precipitation and reorientation | Tikare, Veena | SNL | None | UFD-M3-2015_Hydride_Reorienation.pdf | FCRD-UFD-2015-000512
M3FT-15SN0815011 Acceptance comment: “The QA Document Cover sheet has been up-loaded. The document is complete and is classified as NSI.” The main report is classified at the SNSI level and is maintained on the SNL SPN. | M3 | 1.02.08.15.01 | SNL | FT-15SN081501 | ST Security - SNL | Durbin, Sam | Sorenson, Ken | Investigations of Enhanced Security Configurations for Spent Nuclear Fuel Transport | Investigations of Enhanced Security Configurations for Spent Nuclear Fuel Transport | Milestone report for used fuel transportation security | 2015-07-24 08:00 |  | 2015-07-23 02:00 |  | 2015 | Complete | Security Evaluation of Spent Nuclear Fuel during Transport | Parks, Marcel | Durbin, Sam | None |  | FCRD-UFD-2015-000513 | Spent fuel, transportation, security
M3FT-15SR0805061 | M3 | 1.02.08.05.06 | SRNL | FT-15SR080506 | ST Experiments - SRNL | Carter, Joe | Sorenson, Ken | Issue white paper on "Hydrides in Zirconium Alloy Cladding and Assembly Components" | Issue white paper on "Hydrides in Zirconium Alloy Cladding and Assembly Components" | Prepare white paper (L3 milestone) with input from PNNL, ANL, SRNL technical team o The white paper purpose is to specify an ASTM International standard(s) development to establish common methods and approaches to characterize hydrides and hydride morphologies in zirconium alloys, and for measuring the effects of the hydrides and hydride reorientation on material performance in storage and transportation o The white paper information is synthesized information, and references thereto, from the 2014 zirconium hydride workshop | 2015-05-30 04:00 |  | 2015-05-29 |  | 2015 | Complete | White Paper Summary of 2nd ASTM International Workshop on Hydrides in Zirconium Alloy Cladding | Sindelar, Robert | Sindelar, Robert | None | FCRD-UFD-2015-000533 - White Paper 2nd ASTM Inter Worshop Rpt.pdf | FCRD-UFD-2015-000533 | Hydrides in Ziconium Alloy
M4FT-15IN08020110 | M4 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | UNF Analysis Support | Analysis of UNF Properties | Analysis of UNF properties to support Field Demonstration. | 2015-09-21 07:00 |  | 2015-09-21 02:00 | The actual report title is different than listed in PICS. | 2015 | Complete | On a Thermodynamic Approach to Material Selection for Service in Aggressive Multi-Component Gaseous and/or Vapor Environments | Glazoff, Michael | Marschman, Steve | None | Glazoff Report 9-21-15-1.pdf QA Document Cover Sheet M2FT-15IN08020110.docx | FCRD-UFD-2015-000590 | Thermodynamics, Ellingham diagrams, material selection
M4FT-15LA0802021 | M4 | 1.02.08.02.02 | LANL | FT-15LA080202 | ST Field Demonstration Support - LANL | Ulrich, Timothy | Sorenson, Ken | Application of nonlinear ultrasonics to inspection of stainless steel and concrete for dry storage | Application of nonlinear ultrasonics to inspection of stainless steel and concrete for dry storage | Conduct nonlinear ultrasonic (e.g., TREND and SPACE) experiments on cracked stainless steel and concrete (NRUS) in support of the development and deployment of new NDE techniques. | 2015-09-25 12:00 |  | 2015-09-08 02:00 | End of year technical report | 2015 | Complete | Application of Nonlinear Ultrasonics to Inspection of Stainless Steel for Dry Storage | Ulrich, Timothy | Ulrich, Timothy | None | Storage_Experimentation_LANL_End_Year.pdf | FCRD-UFD-2015-000601 | SCC, NDE, ultrasonic inspection
M4FT-15LA0819013 | M4 | 1.02.08.19.01 | LANL | FT-15LA081901 | DR Salt Field Testing - LANL | Stauffer, Philip | Mackinnon, Robert | Brine Transport Experiments in Run-of-Mine Salt | Brine Transport Experiments in Run-of-Mine Salt | Report on experimental studies of evaporation and heat pipe effects in run-of-min salt | 2015-08-31 04:00 |  | 2015-08-31 02:00 |  | 2015 | Complete | Brine Transport Experiments in Granular Salt | Stauffer, Philip | Stauffer, Philip | None | L4_Experiment_milestone_8-31-15.pdf | FCRD-UFD-2015-000604 | Salt Field Testing Preparation
M4FT-15LL0810022 | M4 | 1.02.08.10.02 | LLNL | FT-15LL081002 | ST Analysis - LLNL | Zavarin, Mavrik | Sorenson, Ken | Report on UQ and PCMM Analysis for UFD S&T Gaps | Report on UQ and PCMM Analysis for UFD S&T Gaps | LLNL input on UQ and PCMM analysis in support of UFD S&T high priority gaps, in support of M2FT-15SN0810051-Development of Uncertainty Quantification Methodology as Applied to Storage and Transportation R&D | 2015-06-26 09:00 | 2015-10-16 03:00 | 2015-10-07 03:00 | awaiting review comments from Sandia prior to finalizing document | 2015 | Late | Report on UQ and PCMM Analysis of Vacuum Drying for UFD S&T Gaps | Fluss, MJ | Zavarin, Mavrik | None | M4FT-15LL08010022_FINAL.pdf | FCRD-UFD-2015-000613 | Cask Drying, Uncertainty Quantification
M4FT-15OR0805033 | M4 | 1.02.08.05.03 | ORNL | FT-15OR080503 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Status Report on CIRFT testing of BWR SNF | Status Report on CIRFT testing of BWR SNF | Status report on the results of bend testing (CIRFT) on Limerick BWR fuel | 2015-04-30 |  | 2015-04-30 |  | 2015 | Complete | FY15 Status Report: CIRFT Testing of Used Nuclear Fuel Rods from the Limerick Generating Station Boiling Water Reactor | Bevard, Bruce | Wang, Jy-An | None | CIRFT Testing of Limerick (BWR) SNF.pdf | FCRD-UFD-2015-000635 | SNF; CIRFT; Vibration testing; BWR fuel testing; Testing of High burnup fuel
M4FT-15OR0810036 | M4 | 1.02.08.10.03 | ORNL | FT-15OR081003 | ST Analysis - ORNL | Scaglione, John | Sorenson, Ken | Quanitfy effects of power uncertainty on fuel assembly characteristics | Quantification of power uncertainty effects on used fuel characteristics | Detailed core follow data will not be available for all fuel assemblies for each cycle of operation. This study will evaluate and quantify the effects of power uncertainty on calculated fuel characteristics arising from operational history uncertainties, and general design attribute uncertainties. Essentially this analysis will begin to evaluate the range of uncertainty introduced when using standard models and assumptions versus ones that include detailed operating history information and proprietary design information. | 2015-09-30 |  | 2015-09-30 | M4 milestone "Rod Internal Pressure Quantification and Distribution Analysis Using FRAPCON" completed | 2015 | Complete | Rod Internal Pressure Quantification and Distribution Analysis Using FRAPCON | Bratton | Scaglione, John | None | RIP_Quantification_Final.pdf | FCRD-UFD-2015-000636 | rod internal pressure
M4FT-15PN0813013 | M4 | 1.02.08.13.01 | PNNL | FT-15PN081301 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Investigate potential of collaborating with the Navy and TTCI on S&V data collected for Navy cask. | Summary of Interface Activities with Navy/TTCI | Lead the effort to investigate the potential of collaborating with the Navy and TTCI to conduct tests on the Navy cask and rail car at the TTCI facility in Pueblo, Colorado. | 2015-09-30 09:00 |  | 2015-09-30 03:00 | Completed UFD Transportation Milestone M4FT-15PNO813013. | 2015 | Complete | SUMMARY OF TRANSPORTATION TECHNOLOGY CENTER, INC. TEST IMPLEMENTATION PLAN FOR MULTIPLE CAR TESTS OF NAVY M-290 CARS |  |  | None | Review_of_TTCI_Test_FCRD-UFD-2015-000700.pdf | FCRD-UFD-2015-000700
M4FT-15PN0813014 | M4 | 1.02.08.13.01 | PNNL | FT-15PN081301 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Transportation of Used Fuel Segments | Used Fuel Segments Transportation Update | Update status of Certificate of Compliance activities for the 9977 in support of transportation of high burnup used fuel segments. | 2015-09-30 09:00 |  | 2015-09-23 06:00 | Draft Report - This report evaluates available shipping packages/casks for use by the Used Nuclear Fuel Disposition Campaign Program to ship fuel rod pieces from high-burnup used nuclear fuel assemblies to and between US DOE research facilities for purposes of evaluation and testing in support of the high burnup nuclear fuel confirmatory demonstration. | 2015 | Complete | Used Fuel Testing Transportation Options | Ross, Steven | Ross, Steven | None | PNNL Transportation Modeling Report Final_2015_FCRD-UFD-2015-000701.pdf | FCRD-UFD-2015-000701 | Transportation options, used fuel segments, packages, casks
M4FT-15SN0805054 | M4 | 1.02.08.05.05 | SNL | FT-15SN080505 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | Test plan for characterization of welds on a full-scale stainless steel canister mockup | Test plan for characterization of welds on a full-scale stainless steel canister mockup | This test plan will summarize the planned tests for characterizing the residual stresses, degree of sensitization, and other material properties of welds and heat affected zones on the full-scale mockup that Sandia purchased in FY14. | 2014-11-28 02:00 | 2014-12-24 02:00 | 2014-12-24 01:00 |  | 2015 | Completed Late | Technical Work Plan: Characterization of Weld Regions on a Full-Scale Cylindrical Mockup of an Interim Storage Container | Enos, David | Bryan, Charles | None | FCRD-UFD-2014-000710_Test_Plan_for_Canister_Mockup.pdf | FCRD-UFD-2015-000710 | mockup, weld, heat affected zone, 304SS, stainless steel, interim storage canister
M4FT-15SR0805062 | M4 | 1.02.08.05.06 | SRNL | FT-15SR080506 | ST Experiments - SRNL | Carter, Joe | Sorenson, Ken | Issue revision to report "Degradation Evaluation and Aging Management of Bolted Closure Joints" | Issue revision to report "Degradation Evaluation and Aging Management of Bolted Closure Joints" | Issue revision (L4 milestone) to FY14 report on elastomerics/polymerics and bolting degradation and application to aging management with new input from BAM and additional BAM and SRNL testing to be performed in FY15 o BAM/SRNL meeting to review irradiation and testing work in conjunction with December 2014 ESCP meeting o Revise technical report to synthesize results of BAM testing and SRNL experimentation work on metallic and polymeric seal materials, and additional SRNL evaluation of aqueous and atmospheric corrosion of bolts, and prepare a generic aging management plan to ensure the integrity of the bolted under extended service. | 2015-08-30 |  | 2015-08-30 |  | 2015 | Complete | Degradation Evaluation and Aging Management of Bolted Closure Joints | Verst, CG | Sindelar, Robert | None | FCRD-UFD-2015-000739 Degradation Evaluation and Aging Management of Bolted Closure Joints.docx | FCRD-UFD-2015-000739 | Aging Management
M2FT-16AN080202011 | M2 | 1.02.08.02.02.01 | ANL | FT-16AN08020201 | ST Experiments - ANL | Billone, Mike | Sorenson, Ken | Documentation of Data Collection of Lower Temp Fuel Cladding Ring Compression Tests | Documentation of data collection of Lower Temp RCT Tests | Documentation of testing methodology and resulting data for ring compression tests for various high-burnup cladding materials at more realistic temperatures (e.g., 350º C). The goal is to collect as much data as possible in FY16 so that can resolve most, if not all, data gaps in the area of hydride-induced embrittlement of PWR cladding. If necessary, we can continue to analyze the data in FY17. | 2016-08-30 09:00 | 2016-09-10 02:00 | 2016-09-10 01:00 | The M2 milestone report FCRD-UFD-2016-000065 was completed on 9/10/2016. | 2016 | Completed Late | Effects of Lower Drying-Storage Temperature on the Ductility of High-Burnup PWR Cladding | Billone, Michael | Billone, Michael | None |  | FCRD-UFD-2016-000065
M2FT-16OR080202031 | M2 | 1.02.08.02.02.03 | ORNL | FT-16OR08020203 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Documentation of Data Collection of CIRFT Tests (update of FY15 report) | M2FT-16OR0202031 - Documentation of Data Collection of CIRFT Tests on Rod Ends | Conduct in-cell bend tests on lower burnup sections of high burnup spent fuel. The goal in FT16 will be to collect as much data in FY16 and remove our equipment from the hot cell. We can analyze the data in FY17. | 2016-09-15 04:00 |  | 2016-09-15 | Report includes resolution of comments to Fy16 M3 report. The M2 provides the combined results of all CIRFT testing to data. | 2016 | Complete | FY2016_M2_Documentation of Data Collection of CIRFT Tests (update of FY15 report).pdf | Wang, Jy-An | Bevard, Bruce | None |  | FCRD-UFD-2016-000066 | CIRFT, Vibration testing,
M2FT-16PN080201041 | M2 | 1.02.08.02.01.04 | PNNL | FT-16PN08020104 | ST Field Demonstration Support - PNNL | Hanson, Brady | Sorenson, Ken | Sister Pin Test Plan | Sister Pin Test Plan for the the High-Burnup Spent Fuel Data Project | Develop and document the Sister Pin Test Plan for obtaining baseline data of the fuel used in the High-Burnup Spent Fuel Data Project. | 2016-04-29 08:00 |  | 2016-04-28 03:00 |  | 2016 | Complete | High Burnup Spent Fuel Data Project Sister Rod Test Plan Overview | Hanson, Brady | Hanson, Brady | None | Sister Rod Test Plan Overview.pdf | FCRD-UFD-2016-000063 | Sister rod, high burnup spent fuel data, cask, fuel rods
M2FT-16PN080203031 Supersedes M2FT-15PN0810041. | M2 | 1.02.08.02.03.03 | PNNL | FT-16PN08020303 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | High Heat Load Thermal Analysis | High Heat Load Thermal Analysis | Conduct thermal analyses for NAC and TN-40 storage systems | 2016-09-29 03:00 |  | 2016-09-29 03:00 | As part of the Used Fuel Disposition Campaign of the U.S. Department of Energy, a high-burnup fuel storage demonstration is planned for a storage module in the North Anna Nuclear Station’s Independent Spent Fuel Storage Installation (ISFSI). The storage module selected for this demonstration is an AREVA TN-32B High Burnup cask. The main goals of this proposed test are to provide confirmatory data for model validation and potential improvement, support license renewals and new licenses for ISFSIs, and support transportation licensing for high burnup spent nuclear fuel (EPRI 2014). The focus of the Demonstration test is the performance of the high-burnup fuel. To support the High Burnup Spent Fuel Data Project, Pacific Northwest National Laboratory (PNNL) staff performed a detailed thermal analysis (Fort et al. 2016) of the TN-32B cask. It was found that when conservatisms were removed from the thermal models and especially from the calculated decay heats, the predicted peak cladding temperatures (PCTs) were significantly below the 400°C (752°F) regulatory guidance limit, as specified in Interim Staff Guidance 11, Revision 3, (U.S. NRC 2003). | 2016 | Complete | Thermal Modeling of a Loaded MAGNASTOR Storage System at Catawba Nuclear Station | Fort, James | Hanson, Brady | None | MAGNASTOR M2 Final.pdf | FCRD-UFD-2016-000068 | thermal modeling, MAGNASTOR, high burnup fuel storage, spent fuel
M2FT-16SN080202051 | M2 | 1.02.08.02.02.05 | SNL | FT-16SN08020205 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | Canister Mock-up weld Residual Stress Final Report. | Quantification of Canister Mock-up Weld Residual Stress | Quantify residual stresses on a full-scale (diameter) Stainless Steel dry storage canister mockup. | 2016-06-30 02:00 |  | 2016-06-30 02:00 |  | 2016 | Complete | Final Report: Characterization of Canister Mockup Weld Residual Stresses | Enos, David | Enos, David | None | FCRD-UFD-2016-000064 - Mock-up WRS Final Report.pdf | FCRD-UFD-2016-000064 | weld residual stress, spent nuclear fuel, interim storage canister, stress corrosion cracking
M2FT-16SN080204022 Final Report - not OUO | M2 | 1.02.08.02.04.02 | SNL | FT-16SN08020402 | ST Transportation - SNL | McConnell, Paul | Sorenson, Ken | Develop test plan for future rail transportation tests | Test plan for future rail transportation tests | Develop test plan for future rail transportation tests that will include collaboration with ENSA to temporarily obtain a rail cask to reduce the uncertainty in over-rail truck transport of UNF. | 2016-09-15 10:00 |  | 2016-09-13 02:00 | This Deliverable - a draft - is the test plan for the multi-modal (truck, ocean vessel, rail) tests of surrogate PWR fuel assemblies in an ENSA ENUN 32P rail cask planned for FY17. | 2016 | Complete | Test Plan for Rail-Cask: Equipos Nucleares S.A. and US Department of Energy: Normal-Conditions-of-Transport Tests of Surrogate PWR Fuel Assemblies in an ENSA ENUN 32P Cask | McConnell, Paul | McConnell, Paul | OUO |  | FCRD-UFD-2016-000067 | fuel assembly, fuel rods, normal conditions of transport
M3FT-16OR080202034 Per Matt Brainard: The upload is not a PDF or Word file, but a PNG file of some type of information page. In search for more information, please refer to the following: Deliverable Description: “Detailed results from all hot cell vibration (CIRFT) testing of high burnup SNF for FY15 and FY16 including hydride reorientation testing.” Notes: “The deliverable incorporates the M4 reports from FY16 as well as the data contained in the FY15 M2 report on CIRFT test results. The data includes the hydride reorientation test results, BWR and PWR high burnup fuel test results and an initial analysis of the test data - including correction factors determined to be applicable to the data.“ Document Owner: Jy-An Wang. DMS No. FCRD-UFD-2016-000426. Lab ID No. ORNL/SR-2016/329. | M3 | 1.02.08.02.02.03 | ORNL | FT-16OR08020203 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | M3FT-16OR0202034-Documentation of Data Collection of CIRFT Tests (Draft M2) | M3FT-16OR0202034-Documentation of Data Collection of CIRFT Tests (Draft M2) | Draft report of the M2 deliverable - M2FT-16OR0202031-Documentation of Data Collection of CIRFT Tests | 2016-08-18 22:00 |  | 2016-09-02 | This deliverable is a draft of the M2 deliverable due in September 2016. | 2016 | Completed Late | FY 2016 Status Report: Documentation of All CIRFT Data including Hydride Reorientation Tests (Draft M2) | Wang, Jy-An | Wang, Jy-An | None |  | FCRD-UFD-2016-000426
M3FT-16PN080201043 | M3 | 1.02.08.02.01.04 | PNNL | FT-16PN08020104 | ST Field Demonstration Support - PNNL | Hanson, Brady | Sorenson, Ken | Develop Sister Pin Test Plan | Develop Sister Pin Test Plan | Develop and document the Sister Pin Test Plan for obtaining baseline data of the fuel used in the High-Burnup Spent Fuel Data Project. | 2016-02-29 14:00 | 2016-03-18 03:00 | 2016-03-18 09:00 |  | 2016 | Completed Late | High Burnup Spent Fuel Data Project, Sister Rod Test Plan Overview (Draft) | Hanson, Brady | Hanson, Brady | None | Sister Rod Test Plan Overview DRAFT FINAL.pdf | FCRD-UFD-2016-000422 | Sister rod, High Burnup Spent Fuel, sister pin
M3FT-16PN080203033 | M3 | 1.02.08.02.03.03 | PNNL | FT-16PN08020303 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | High Heat Load Thermal Analyses | High Heat Load Thermal Analyses | Draft of M2. | 2016-09-01 01:00 |  | 2016-09-01 09:00 |  | 2016 | Complete | High Heat Load Thermal Analyses | Hanson, Brady | Hanson, Brady | None | M3FT_16PN080203033.PDF | FCRD-UFD-2016-000427
M3FT-16PN080203034 | M3 | 1.02.08.02.03.03 | PNNL | FT-16PN08020303 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Cask Drop Anlaysis | Cask Drop Analysis | Technical Report | 2016-01-15 22:00 |  | 2016-01-15 03:00 |  | 2016 | Complete | Used Nuclear Fuel Rail Package Normal Conditions of Transport (NCT) Drop Analysis | Klymyshyn, Nicholas | Klymyshyn, Nicholas | None | UFDC_Cask_Drop_M3FT-16PN080203034.pdf | FCRD-UFD-2016-000421 | fuel cladding, rail transportation, ENSA ENUN 32P design, LS-DYNA finite element model, cask drop analysis
M3FT-16PN080203035 | M3 | 1.02.08.02.03.03 | PNNL | FT-16PN08020303 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Structural Uncertainty | Structural Uncertainty | Structural Uncertainty Report. | 2016-09-17 04:00 |  | 2016-09-16 03:00 | The structural uncertainty research task uses numerical modeling to help close knowledge gaps associated with extended dry storage of used nuclear fuel. Modeling helps to predict the expected range of mechanical loading on used nuclear fuel and dry storage system components, which is needed to help guide materials research. | 2016 | Complete | Update: Structural Uncertainty of Used Nuclear Fuel in Dry Storage Canisters | Klymyshyn, Nicholas | Hanson, Brady | None | Structural Uncertainty Update 2016_final.pdf | FCRD-UFD-2016-000430 | structural uncertainty, numerical modeling, used nuclear fuel, dry storage system components
M3FT-16PN080204011 Need to save doc as PDF - is currently in PPT format in SNL S&T site. | M3 | 1.02.08.02.04.01 | PNNL | FT-16PN08020401 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Support the development of a comprehensive full-scale test plan | Rail Full-Scale Test Plan Supporting Information | Support the development of a full-scale test plan for rail shock and vibration testing using an ENSA rail cask. • Develop a test plan for future rail transportation tests that will include collaboration with ENSA to temporarily obtain a rail cask that will be shipped from Spain to the US, transferred to a railcar, instrumented, and moved over representative rail track in order to collect stress and strain measurements on the surrogate fuel. This will require close communication with ENRA and possibly other Spanish entities. | 2016-09-30 09:00 |  | 2016-09-28 03:00 | This report provides input to the Equipos Nucleares S.A. (ENSA)/U.S. Department of Energy (DOE) transport cask Shock and Vibration Test Plan, which is an M2 milestone. These tests will be conducted by Sandia National Laboratories, Pacific Northwest National Laboratory, Savannah River National Laboratory, ENSA, and Transportation Technology Center, Inc. (TTCI) under the auspices of the DOE Office of Nuclear Energy, Used Nuclear Fuel Disposition Program. | 2016 | Complete | ENSA/DOE Transport Shock and Vibration Test Plan | Ross, Steven | Ross, Steve | None | ENSA_DOE Transport Shock and Vibration Test Plan_PNNL-25720_Final.pdf | FCRD-UFD-2016-000424 | cask shock, stress profiles, gap closure, transport shock and vibration
M3FT-16PN080204012 | M3 | 1.02.08.02.04.01 | PNNL | FT-16PN08020401 | ST Transportation - PNNL | Ross, Steven | Sorenson, Ken | Finite Element and Modeling in Support of S&V Test Plan | Analysis and Model Development in Support of S&V Test Plan | • Conduct finite element analysis and model development in support of rail testing which includes used fuel modeling in transport using ANSYS, LSDYNA, and NUCARS? | 2016-09-30 12:00 |  | 2016-09-22 03:00 | Document was awaiting final approval by ENSA for free release. | 2016 | Complete | ENS/DOE Finite Element Modeling Support of the Test Plan |  |  | None | ENSA_DOE Finite Element Modeling Support of the Test Plan_FCRD-UFD-2016_000425.pdf | FCRD-UFD-2016-000425
M3FT-16SN080202055 | M3 | 1.02.08.02.02.05 | SNL | FT-16SN08020205 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | FY16 Status Report: Interim Storage Canister Corrosion and Surface Environment Investigations | FY16 Status Report: Interim Storage Canister Corrosion and Surface Environment Investigations | This report will document the status of experimental work and modeling being performed at Sandia National Laboratories to assess the potential occurrence and impact of stress corrosion cracking on SNF interim storage canisters. This work is necessary to accurately evaluate the potential impacts of SCC on long-term interim storage. | 2016-09-15 06:00 | 2016-11-04 02:00 | 2017-03-13 02:00 | 75% Complete. The milestone was delayed because several new tasks were identified in the last three months of the year, that were not included when planning the milestone. These include producing a white paper for Andy Griffith; analyzing dust samples from Maine Yankee, and analyzing samples of corrosion residue from the HBU demo cask. | 2016 | Expected Late | FY16 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | Bryan, Charles | Bryan, Charles | None | FCRD-UFD-2016-000429 FY16 Status Report SNF Interim Storage Canister Corrosion.pdf | FCRD-UFD-2016-000429 | spent nuclear fuel, long term interim storage, stress corrosion cracking
M3FT-16SN080202056 | M3 | 1.02.08.02.02.05 | SNL | FT-16SN08020205 | ST Experiments - SNL | Bryan, Charles | Sorenson, Ken | Preliminary Aboveground Test Report | Preliminary Aboveground Test Report | This report will provide the preliminary results of the BCS Aboveground tests. | 2016-09-29 06:00 |  | 2016-09-29 02:00 | This report documents the preliminary results of thermal testing experiments carried out at Sandia National Laboratories with the boiling water reactor dry cask simulator in the aboveground configuration. | 2016 | Complete | Results for the Aboveground Configuration of the Boiling Water Reactor Dry Cask Simulator | Durbin, Sam | Durbin, Sam | None | FCRD-UFD-2016-000433--Preliminary Aboveground Test Report.pdf | FCRD-UFD-2016-000433 | themal testing, boiling water reactor, spent nuclear fuel, cask simulator
M3FT-16SN080203042 | M3 | 1.02.08.02.03.04 | SNL | FT-16SN08020304 | ST Analysis - SNL | Dingreville, Remi | Sorenson, Ken | Development of Uncertainty Quantification Methodology as Applied to Stress Corrosion cracking | M3 report on UQ methodology for SCC of welded canister | Factors affecting site susceptibility to SCC, and the identification of vulnerable sites. For these sites what are the recommended inspection schedules? SNL-T2.2- Depending on the site susceptibility, what is the most appropriate inspection (NDE) technology? Using site susceptibility to determine the type of inspection and % coverage required prior to canister transport. For low-risk sites, low probability of detection (visual?) inspections may be sufficient. For high-risk sites it may be necessary to develop techniques requiring a higher probability of detection (eddy current, ultrasonic?) and resolution. | 2016-09-02 14:00 |  | 2016-10-13 02:00 | M# completed. | 2016 | 90 Day | Uncertainty Quantification Methodologies Development for Stress Corrosion Cracking of Canister Welds | Dingreville, Remi | Dingreville, Remi | None | M3_RPMD.docx | FCRD-UFD-2016-000428 | Uncertainty Quantification, Stress Corrosion Cracking, Pitting
M3FT-16SR080202061 | M3 | 1.02.08.02.02.06 | SRNL | FT-16SR08020206 | ST Experiments - SRNL | Carter, Joe | Sorenson, Ken | Continue the lead for the ASTM drying standard | ASTM drying standard | Support NDE assessment methodologies for the storage demonstration project. | 2016-09-30 05:00 |  | 2016-09-27 | The ASTM standard guide C1553 passed the ASME ballot in June. Although additional comments were received outside of the ballot process at the June meeting, a decision was made with ASTM to publish the standard with additional minor editorial changes. The standard will be immediately updated when additional data and results from the DOE NE IRP on drying are available. | 2016 | Complete | The Standard titled: C 1553-xx Standard Guide for Drying of Spent Nuclear Fuel | Sindelar, Robert | Sindelar, Robert | None | QA Cover - Sindelar.pdf | FCRD-UFD-2016-000434 | ASTM Drying Standard
M4FT-16OR080202032 | M4 | 1.02.08.02.02.03 | ORNL | FT-16OR08020203 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | M4FT-16OR0202032- Draft report on FY15 CIRFT data analyses | 4FT-16OR0202032- Draft report on FY15 CIRFT data analyses | Report on finite element analyses and evaluation of CIRFT biases and uncertainties and correction factors needed to translate test parameters into SNF strain | 2016-07-29 02:00 |  | 2016-08-01 |  | 2016 | Completed Late | FY 2016 Status Report: CIRFT Testing Data Analyses and Updated Curvature Measurements | Wang, Jy-An | Bevard, Bruce | None | FY2016_M4_Analyses-vf.pdf | FCRD-UFD-2016-000602
M4FT-16OR080202033 | M4 | 1.02.08.02.02.03 | ORNL | FT-16OR08020203 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | M4FT-16OR0202033 - Draft report on FY16 CIRFT tests on SNF | M4FT-16OR0202033 - Draft report on FY16 CIRFT tests on SNF | Report providing the draft results on CIRFT tests on TMI (low Sn Zirc-4) and Surry (Zirc-4)SNF | 2016-08-05 02:00 | 2016-08-26 | 2016-08-26 |  | 2016 | Completed Late | FY 2016 Status Report: CIRFT Testing on Spent Nuclear Fuels and Hydride Reorientation Study | Wang, Jy-An | Bevard, Bruce | None | FY 2016 Status Report_ CIRFT Testing on Spent Nuclear Fuels and Hydride Reorientation Study.pdf | FCRD-UFD-2016-000604
M4FT-16PN080201044 | M4 | 1.02.08.02.01.04 | PNNL | FT-16PN08020104 | ST Field Demonstration Support - PNNL | Hanson, Brady | Sorenson, Ken | Post-Drying Water Detection | Post-Drying Water Detection | Technical report documenting FY16 progress on post-drying water detection. | 2016-09-30 14:00 |  | 2016-08-15 06:00 |  | 2016 | Complete | Water Detection in Used Fuel Canisters M4 2016 Annual Report | Meyer, Ryan | Meyer, Ryan | None | Water Detection in Used Fuel Canisters M4 2016 Annual Report-withCoverLetter-081516a.pdf | FCRD-UFD-2016-000607 | Water detection, used fuel canisters, sensors, horizontal storage module
M4FT-16SR080204031 | M4 | 1.02.08.02.04.03 | SRNL | FT-16SR08020403 | ST Transportation - SRNL | England, Jeff | Sorenson, Ken | Explore licence amendment opportunities for the 9975 to support shipment of sister pin rodlets | Explore license amendment opportunities for the 9975 to support shipment of sister pins rodlets | Issue letter report on exploring amendment opportunities for the 9975 to support shipment of sister pins rodlets. | 2016-09-30 02:00 |  | 2016-09-07 | This report provides a preliminary content evaluation for use of the 10-160B and NAC-LWT for transporting those fuel rod pins from ORNL to PNNL. This report documents the acceptability of using these packagings to transport the fuel segments from ORNL to PNNL based on the following evaluations: • Enrichment • A2 Evaluation • Pu-239 FGE Evaluation • Heat Load • Shielding (both gamma and neutron) • Content Weight/Structural Evaluation | 2016 | Complete | Preliminary Content Evaluation of the North Anna High Burn-Up Sister Fuel Rod Segments for Transportation in the 10-160B and NAC-LWT | Ketusky, Ed | England, Jeff | None | FCRD-UFD-2016-000606 High Burn-up Pin.pdf QA Cover Sheet - FCRD-UFD-2016-000606 High Burn-up Pin.pdf | FCRD-UFD-2016-000606 | Sister Rod Fuel
M5FT-16LA080201021 | M5 | 1.02.08.02.01.02 | LANL | FT-16LA08020102 | ST Field Demonstration Support - LANL | Ulrich, Timothy | None | Deployability demonstration | UFD Annual Meeting Presentation | Conduct necessary modeling and measurement exercises to demonstrate deployability of nonlinear ultrasonic techniques in confined spaces. | 2016-09-30 08:00 |  | 2016-09-30 02:00 | Slides presented at the annual UFD meeting. This closes out this work package. | 2016 | Complete | NDE Solutions: Imaging SCC with Acoustic Techniques | Remillieux, Marcel | Ulrich, Timothy | None | 2016 UFD meeting slides.pdf | FCRD-UFD-2016-000702 | NDE nonlinear ultrasound acoustics SCC imaging
M2SF-17AN010201011 | M2 | 1.08.01.02.01.01 | ANL | SF-17AN01020101 | Experiments - ANL | Billone, Mike | Sorenson, Ken | Data Collection Report on Lower Temperature Ring Compression Tests | Data Collection Report on Lower Termperature Ring Compression Tests | Provide results of low temperature ring compression tests on irradiated zircaloy cladding. | 2017-08-30 05:00 | 2017-09-13 01:00 | 2017-09-13 | Milestone completed on 9/13/2017. | 2017 | Completed Late | Effects of Radial Hydrides on PWR Cladding Ductility following Drying and Storage |  |  | None | SFWD-SFWST-2017-000001_Final.pdf | SFWD-SFWST-2017-000001
M2SF-17OR010201021 | M2 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | Sorenson, Ken | Documentation of Non-destructive Tests on Sister Pins | Documentation of Non-destructive Tests on Sister Pins | Develop characterization data on high burnup assembly pins from North Anna in support of the High Burnup Data Project. | 2017-09-15 |  | 2017-09-15 | This deliverable provides the nondestructive examination details and analysis on all 25 Sister Rods completed in FY17 | 2017 | Complete | Sister Rod Nondestructive Examination Annual Report FY2017 | Montgomery, Rose | Scaglione, John | None | M2 - Sister Rod Exam Annual report 09152017b.pdf | SFWD-SFWST-2017-000002
M2SF-17SN010201041 | M2 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Stress Corrosion Cracking Report | Stress Corrosion Cracking Report | Report on data and analyses conducted to support detection and estimation of SCC crack growth rates in stainless steel canisters. | 2017-08-25 16:00 |  | 2017-08-25 02:00 |  | 2017 | Complete | FY17 Status Report: Research on Stress Corrosion Cracking of SNF Interim Storage Canisters | Bryan, Charles | Bryan, Charles | None | SFWD-SFWST-2017-000003_Status Report_SNL_SCC_Investigations.pdf | SFWD-SFWST-2017-000003 | stress corrosion cracking;spent nuclear fuel, long term interim storage
M2SF-17SN0102010411 | M2 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | SNL Experimental Work Evaluating SCC of SNF Interim Storage Canisters | SNL Experimental Work Evaluating SCC of SNF Interim Storage Canisters | Report documenting SNL experimental work evaluating SCC of SNF Interim Storage Canisters | 2018-09-28 04:00 |  |  | Work that will be reported in this milestone report continues on progress. | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000222
M2SF-17SN010202021 | M2 | 1.08.01.02.02.02 | SNL | SF-17SN01020202 | Transportation - SNL | McConnell, Paul | Sorenson, Ken | Initial Report for Full-scale Rail Cask Normal Condition of Transport Tests | Initial Report for Full-scale Rail Cask Normal Condition of Transport Tests | Write up initial results of the full-scale rail cask tests. | 2017-09-30 06:00 |  | 2017-09-29 | Milestone completed on 9/29/2017 | 2017 | Complete | Rail-Cask Tests: Normal Conditions of Transport Tests of Surrogate PWR Fuel Assemblies in an ENSA ENUN 32P Cask |  |  | None | M2SF-17SN01020201 Initial Report for Full-scale Rail Cask Normal Conditi....pdf | SFWD-SFWST-2017-000004
M3SF-17OR010201026 | M3 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Evaluate Data from FY15-16 Testing | Evaluation of test data generated during FY15 and 16 | Evaluate the CIRFT data collected in prior years testing and update the previous years' report | 2017-07-28 |  | 2017-07-28 |  | 2017 | Complete | FY 2017 Status Report: CIRFT Data Update and Data Analyses for Spent Nuclear Fuel Vibration Reliability Study | Bevard, Bruce | Wang, Jy-An | None | FY17_CIRFT-M3-08102017.pdf | SFWD-SFWST-2017-000030 | CIRFT, Vibration Testing of SNF, Hydride reorientation, Clad and fuel testing,S-N Curve,
M3SF-17PN010202032 | M3 | 1.08.01.02.02.03 | PNNL | SF-17PN01020203 | Transportation - PNNL | Hanson, Brady | Sorenson, Ken | Finite Element Modeling Support | ENSA/DOE Transport Cask Testing Finite Element Modeling Support | Provide finite element modeling support to the ENSA/DOE Test Program. | 2017-09-30 |  | 2017-09-29 03:00 | An email transmitting this milestone and confirming it was completed on time (9/29/17) was sent to the CAM and NTD on September 29, 2017. | 2017 | Complete | ENSA/DOE Test Plan Modeling and Analysis Support | Ross, Steven | Hanson, Brady | None | SWFD SFST 2017 000035.pdf | SFWD-SFWST-2017-000035 | ENSA, shock, vibration, loading conditions, transportation
M3SF-17SN010201044 | M3 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | BCS Below-ground Test Report | BCS Below-ground Test Report | This report will document the results of testing performed with the BWR Cast Simulator in the below-ground testing configuration. | 2017-08-19 02:00 | 2017-09-29 08:00 | 2017-09-29 02:00 | This report documents thermal-hydraulic testing and modeling of a mockup simulating dry cask storage of boiling water reactor fuel. The experiments were carried out as Sandia National Laboratories. Although originally intended to just summarize the below-ground testing, the scope was changed; this report is now the final report for both aboveground and belowground testing. | 2017 | Completed Late | Thermal-Hydraulic Results for the Boiling Water Reactor Dry Cask Simulator | Durbin, Sam | Durbin, Sam | None | SFWD-SFWST-2017-000033_DCS_Test_Report.pdf | SFWD-SFWST-2017-000033 | spent nuclear fuel; dry cask storage; interim storage; thermal hydraulic testing
M3SF-17SN010201048 | M3 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Data Book for BCS Thermal-Hydraulic Testing | Data Book for BCS Thermal-Hydraulic Testing | This report will document the exact setup and experimental procedures used int he BCS tests. | 2017-09-27 08:00 | 2017-11-30 04:00 | 2017-11-30 02:00 | The DCS aboveground and belowground testing has been completed, and a final report has been issued (9/29/2017). The data book is in progress and will be completed by the revised completion date. | 2017 | Expected Late | Materials and Dimensional Reference Handbook for the Boiling Water Reactor Dry Cask Simulator | Lindgren, Eric | Durbin, Sam | None | SFWD-SFWST-2017-000221_DCS_Handbook.pdf | SFWD-SFWST-2017-000221 | spent nuclear fuel; dry storage; thermo-hydraulic testing; dry cask simulator
M3SF-17SR010201051 | M3 | 1.08.01.02.01.05 | SRNL | SF-17SR01020105 | Experiments - SRNL | Carter, Joe | Sorenson, Ken | ASTM Drying Standard | ASTM Drying Standard | Lead ASTM Task Group in the revision of the C1553 standard; resolve comments for standard revision. | 2018-09-30 |  | 2017-09-26 | M3SF-17SR010201051 ASTM Drying Standard: An ASTM C26.13 task group meeting was held in June at PNNL offices in Richland. The drying standard C1553-16, had passed last year (June 2016) and is "on the books." Due to the receipt of comments on this standard from NRC and the international community, and in anticipation of results from the drying campaign in the High Burnup Demo Cask and from the University of South Carolina NE Integrated Research Project by the end of this year, a new revision of the drying standard will be prepared for the next task group meeting in January 2018. | 2017 | Complete | Designation C1553-16, Standard Guide for Drying Behavoir of Spent Nuclear Fuel1 | Sindelar, Robert | Sindelar, Robert | None | Closure Document C1553-16 - Standard Guide for Drying Behavoir of SNF.pdf QA Cover Sheet - C1553-16 Standard Guide Behavoir for Drying SNF.pdf | SFWD-SFWST-2017-000034 | Drying Behavoir
M2SF-18AN010201013 | M2 | 1.08.01.02.01.01 | ANL | SF-18AN01020101 | Sister Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | Results of Ring Compression Tests | Results of Ring Compression Tests | Document results of ring compression tests on defueled irradiated spent fuel cladding. | 2018-09-14 | 2018-09-28 02:00 | 2018-09-29 01:00 | Predicisional draft report was completed on 9/29/2018 and submitted via email enclosure to CAM and other required parties. It was uploaded into picsne on 9/30/2018. | 2018 | Completed Late | Results of Ring Compression Tests | Billone, Michael | Billone, Michael | None | SFWD-SFWST-2018-000510_PD.pdf | SFWD-SFWST-2018-000510 | ring compression tests, cladding, hydrides, embrittlement, ductility
M2SF-18PN010203024 | M2 | 1.08.01.02.03.02 | PNNL | SF-18PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Final Thermal Analysis Report on Demonstration Cask | Final Thermal Analysis Report on Demonstration Cask | Develop the input parameters for the Phase 2 study. Model the Demo cask using actual ambient conditions and times from the cask loading. Perform a "generic" cask model in cooperation with international collaborators. | 2018-09-28 |  | 2018-09-28 03:00 | An email transmitting this milestone and confirming it was completed on time (9/28/18) was sent to the CAM and NTD on September 28, 2018. | 2018 | Complete | Thermal Modeling of TN-32B CASK for High Burnup Spent Fuel Data Project | Fort, James | Hanson, Brady | None | PNNL-24549-Rev_2_FINAL.pdf |  | thermal modeling, high burnup, spent fuel, thermal analysis
M2SF-18SN010201049 | M2 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | SNL Experimental Work Evaluating SCC of SNF Interim Storage Canisters | SNL Experimental Work Evaluating SCC of SNF Interim Storage Canisters | Document work done on corrosion R&D experiments. | 2018-09-28 |  | 2018-09-28 02:00 | This level 2 milestone report documents experimental and modeling efforts, carried out at Sandia National Laboratories, to understand the canister surface environment and the potential for initiation and growth of SCC cracks. | 2018 | Complete | FY18 Status Report: SNL Research into Stress Corrosion Cracking of SNF Interim Storage Canisters | Bryan, Charles | Bryan, Charles | None | M2SF-18SN010201049_FY 18 Status Report on SNL Research into SNF Storage Canister SCC final.pdf |  | stress corrosion cracking, 304 stainless steel, spent nuclear fuel, interim storage
M2SF-18SN010202022 | M2 | 1.08.01.02.02.02 | SNL | SF-18SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | Data Analysis of ENSA/DOE Rail Tests | Data Analysis of ENSA/DOE Rail Tests | Document data analysis of the ENSA/DOE Rail Cask test. | 2018-07-27 |  | 2018-07-26 02:00 |  | 2018 | Complete | Data Analysis of ENSA/DOE Rail Cask Tests | Kalinina, Elena | Kalinina, Elena | None | SAND2018-13258 R SFWD-SFWST-2018-000494w.pdf | SFWD-SFWST-2018-000494 | Transportation, spent nuclear fuel, shock and vibration, shock response spectra, surrogate fuel assembly
M3SF-18OR0102010210 Per Bruce Bevard: The completion was actually the installation of the full length heater in the hot cell (slide attached). Per Matt Brainard; Document not available in PICS:NE. Submission comment made: “the deliverable was the actual installation of the furnace into the hot cell; there is no document for this milestone”. Main Document title entered as “Email to John Scaglione from Bruce Bevard (May 11, 2018) - Full length furnace was installed in the 3525 hot cell on May 4, 2018”. | M3 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Install Full Length Rod heater in hot cell | Complete installation of full rod heater into hotcell | build, test and install the full length rod heater in the ORNL hot cell | 2018-05-11 | 2018-05-04 | 2018-05-04 |  | 2018 | Complete | Email to John Scaglione from Bruce Bevard (May 11, 2018) - Full length furnace was installed in the 3525 hot cell on May 4, 2018 | Bevard, Bruce | Bevard, Bruce | None |  |  | Full Length furnace
M3SF-18OR010201028 | M3 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Prepare for and ship 10 full-length sister rods to PNNL | Preparation and shipment of 10 full-length sister rods to PNNL | Planning and shipment of 10 full-length sister rods to PNNL (no shipments of cladding to ANL) | 2018-09-28 |  | 2018-09-20 | The LWT with 10 Sister Rods was successfully loaded and transported to PNNL on schedule. | 2018 | Complete | Rods at PNNL | Bevard, Bruce | Bevard, Bruce | None | Rods at PNNL.pdf |  | Sister rods
M3SF-18SN010201047 supercedes M3SF-17SN0102010410 | M3 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Evaluation of Gas and Particle Transport through Stress Corrosion Cracks | Evaluation of Gas and Particle Transport through Stress Corrosion Cracks | The report will document the results of tests evaluating gas and particle transport through SCC cracks in spent nuclear fuel interim storage canisters. | 2018-09-19 |  | 2018-09-19 02:00 | This level 3 milestone report, "Measurement of Particulate Retention in Microchannel Flows" documents experimental work to evaluate particle transport through an engineered channel withe dimensions similar to those of stress corrosion cracks that could form in canisters in interim storage systems for spent nuclear fuel. Although the work is preliminary, it demonstrates that the test protocols and system designed for the experiment are an effective protocol for further work to be performed in FY19. | 2018 | Complete | Measurement of Particulate Retention in Microchannel Flows | Durbin, Sam | Durbin, Sam | None | Particulate_Retention_in_Microchannel_Flows_v1.pdf |  | particle transport, stress corrosion cracks, particle transport
M3SF-18SR010201051 | M3 | 1.08.01.02.01.05 | SRNL | SF-18SR01020105 | Stress Corrosion Cracking - SRNL | Carter, Joe | Saltzstein, Sylvia | ASTM Drying Standard | ASTM Drying Standard | Lead ASTM Task Group in the revision of the C1553 standard; resolve comments for standard revision. | 2018-09-30 |  | 2018-09-28 | SRNL is leading the next revision of the ASTM C1553-16 “Standard Guide for Drying Behavior of Spent Nuclear Fuel.” | 2018 | Complete | ASTM Drying Standard | Sindelar, Robert | Sindelar, Robert | None | ASTM Drying Standard.pdf |  | ASTM C1553
M4SF-18IN010201071 | M4 | 1.08.01.02.01.07 | INL | SF-18IN01020107 | Sister Pin Testing - INL | Jarrell, Josh | Saltzstein, Sylvia | Document potential INL R&D SNF opportunities | Potential INL R&D SNF opportunities | Report that investigates opening any of the INL casks to examine low burnup, potentially oxidized fuel and feasibility of the Demo cask going to INL after drying period. In addition, the report will document an Investigation of INL's surrogate assemblies for future testing. | 2018-07-27 |  | 2018-07-27 02:00 |  | 2018 | Complete | Potential Research and Development Opportunities for Light Water Reactor Spent Nuclear Fuel at INL | Winston, Philip | Jarrell, Josh | None | 2018-07-27_Dry-Stored-Commercial-LWR-SNF_INL-EXT-18-45988.pdf
M4SF-18OR010201022 File name shows M4SF-18OR010203013 supercedes M4SF-17OR0102010210 | M4 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Document RIP data and current DE test status | Status report on DE testing | Status report on current results of RIP measurements and any other DE exams to date | 2018-09-07 |  | 2018-09-07 | This report documents the results of the sister rod destructive examinations (DE) to date, including the full-length fuel rod heat treatment oven design and fabrication, heat treatments performed to date, rod internal pressure and free volume measurements, gas transmissibility tests (depressurization and transmission), and fission gas isotopic contents. It also includes a summary of the work completed to date on rod segmentation and aerosol collection capability. | 2018 | Complete | Sister Rod Destructive Examination Status Report | Montgomery, Rose | Bevard, Bruce | None | Sister Rod Destructive Testing Status Report _M4SF-18OR010203013.pdf |  | Sister rods, destructive testing, rod internal pressure, gas puncture, Heat treatment oven, free volume, gas transmissibility
M5SF-18SN010305027 | M5 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Hardin, Ernest | None | Independent review of DPC direct disposal strategies | Independent Review of DPC Direct Disposal Strategies | Perform a technical review of DPC criticality analyses to evaluate progress and resources needed to support successful licensing, and modifications to future DPCs that could expedite disposal. | 2018-04-27 |  | 2018-04-23 18:00 |  | 2018 | Complete | Independent Review of DPC Direct Disposal Strategies | Alsaed, Halim | Hardin, Ernest | None | Review of Criticality Evaluations for DPC Disposal - Final.docx | SFWD-SFWST-2018-000491 | spent fuel; geologic disposal; dual-purpose canisters
M5SF-18SN010305028 | M5 | 1.08.01.03.05.02 | SNL | SF-18SN01030502 | Direct Disposal of Dual Purpose Canisters - SNL | Rigali, Mark | None | Review of Requirements for DPC Fillers to Control Postclosure Criticality | Review of Requirements for DPC Fillers to Control Postclosure Criticality | Perform and document a review to identify pertinent requirements that would need to be addressed for adding a filler material to existing loaded DPCs. The assessment will include: a) effectiveness of filler introduction into different types of DPCs; b) the functions of filler materials and their longevity in disposal environments; c) quality control and how representations of quality could be made to a regulator; and d) impact of fillers on potential storage/aging, transportation, and waste retrieval from filled canisters. The scope includes applicability of regulations, orders, consensus standards, guidance documents, DPC operating procedures, and other literature. | 2018-07-31 |  | 2018-07-27 02:00 |  | 2018 | Complete | Technical and Regulatory Considerations for Use of Fillers in DPCs | Alsaed, Halim | Rigali, Mark | None | SFWD-SFWST-2018-000495 - Fillers Requirements Review Final.pdf | SFWD-SFWST-2018-000495 | spent nuclear fuel; geologic disposal; dual-purpose canister
M5SF-18SN010305051 | M5 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | None | Prepare Draft Outline and Staffing Plan | Analysis of DPC Disposal Solutions - Outline and Staffing Plan | Issue an outline for the final draft analysis of solutions report, and how the effort will be staffed (SNL staff, consultants, other labs). | 2018-09-18 |  | 2018-09-19 02:00 | Completed technical review and Sandia R&A. | 2018 | Completed Late | Technical & Programmatic Solutions for Direct Disposal of DPCs – Draft Outline and Staffing Plan | Hardin, Ernest | Hardin, Ernest | None | C:\Users\ehardin\Documents\DPC Crit Files\DPC disposal T&PS plan final 19Sept18.pdf |  | spent nuclear fuel;geologic disposal;dual-purpose canisters
M5SF-18SN010305054 | M5 | 1.08.01.03.05.05 | SNL | SF-18SN01030505 | Technical and Programmatic Solutions for Direct Disposal of DPCs - SNL | Hardin, Ernest | None | Engineering Cost Analysis Support - Scoping | Scoping Memo for Engineering and Cost Support - Analysis of DPC Disposal Solutions | Scoping memo describing approach to costing disposal options and modifications to DPCs. | 2018-09-06 |  | 2018-09-06 | Milestone completed on time. | 2018 | Complete | Technical & Programmatic Solutions for DPC Direct Disposal: Engineering Cost Analysis Support – Scoping (SFWD) | Hardin, Ernest | SNL | None | Engineering Support Scoping M5 Final.pdf
M2SF-19AN010201011 supercedes M2SF-18AN010201015 | M2 | 1.08.01.02.01.01 | ANL | SF-19AN01020101 | Sister Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | Initial Phase 1 Radial Hydride and Ring Compression Test Results | Final Report on Initial Phase 1 Radial Hydride and Ring Compression Test Results | Initial Phase 1 Radial Hydride and Ring Compression Test Results | 2019-03-31 | 2019-04-12 01:00 |  | Plans were to complete this milestone on time and receive shipment of defueled cladding from ORNL in mid-April. However, ORNL is ready to ship in mid-March, so effort was diverted to prepare for ANL to receive this shipment. This change in plans had a cascading effect on our testing schedule. On a relative scale, it is more important to the overall ANL program to receive the ORNL shipment of new cladding samples than to complete experimental-work/milestone-reporting by 3/31/19. | 2019 | Expected Late |  |  |  | None
M2SF-19PN010203021 Per Matt Brainard: Supersedes M2SF-18PN010203025 - Originally planned for FY19 completion on 1/25/2019. | M2 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | BWR Dry Cask Simulator Thermal Analysis Results | BWR Dry Cask Simulator Thermal Analysis Results | Document analyses done for the EPRI/ESCP Thermal Analysis Subcommittee Phase 1 round robin. | 2019-01-25 |  | 2019-01-25 09:00 |  | 2019 | Complete | Modeling of the Boiling Water Reactor Dry Cask Simulator | Hanson, Brady | Hanson, Brady | None | Modeling_of_Dry_Cask_Simulator_Final_for_Programmatic_Review.pdf |  | Boiling water reactor, dry cask simulator, peak cladding temperature, effective thermal conductivity
M2SF-19SN010203032 M3SF-18SN010203032 has been mapped into FY19 and elevated to an M2. It is now: “M2SF-19SN010203032 - Test Plan for Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator”. | M2 | 1.08.01.02.03.03 | SNL | SF-19SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Test Plan for Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator | Test Plan for Thermal-Hydraulic Investigations of a Horizontal Dry Cask Simulator | Test Plan for T-H testing of a horizontal dry cask simulator | 2019-02-22 |  | 2019-02-22 02:00 | Complete. | 2019 | Complete | Test Plan for the Horizontal Dry Cask Simulator | Durbin, Sam | Durbin, Sam | None | Horizontal_Dry_Cask_Simulator_Test_Plan_v1.pdf |  | spent nuclear fuel; dry storage; thermal-hydraulics
M2SF-19SN010401012 | M2 | 1.08.01.04.01.01 | SNL | SF-19SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Implement Baseline Cloud Environment and Services | Complete initial cloud baseline user acceptance testing report. | Implement Baseline Cloud Environment and Services | 2019-03-31 |  |  | Milestone is on schedule. | 2019 | 90 Day |  |  |  | None
M3SF-19SN010201047 supercedes M3SF-18SN0102010413 and M3SF-17SN010201046 | M3 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Final Report: Probabilistic Model for Stress Corrosion Cracking of Spent Nuclear Fuel Canisters | Final Report: Probabilistic Model for Stress Corrosion Cracking of Spent Nuclear Fuel Canisters | This final report will document the completed model for stress corrosion cracking of spent nuclear fuel canisters, summarizing the model development and use, and the final results. | 2019-03-22 |  | 2019-03-22 | This report is nearly ready for submission, and will be submitted by March 15th. | 2019 | Complete | Status Report: Uncertainty Quantification of Environmentally Assisted Stress Corrosion Cracking in Used Fuel Canisters | Remi Dingreville | Remi Dingreville | None |  |  | stress corrosion cracking, spent nuclear fuel, long term interim storage
M3SF-19SN010202021 | M3 | 1.08.01.02.02.02 | SNL | SF-19SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | Shaker Table Tests | Shaker Table Test | Data analysis of the shaker table tests. | 2019-03-29 |  |  | On schedule | 2019 | 90 Day |  |  |  | None
M3SF-19SN010203033 supercedes M3SF-18SN010203033 | M3 | 1.08.01.02.03.03 | SNL | SF-19SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | Advanced Thermal-Hydraulic Systems with Applications in Simulation of Dry Storage and Transport | 2019-03-29 |  |  | On schedule. | 2019 | 90 Day |  |  |  | None
M3SF-19SN010205012 Per Matt Brainard: has been mapped into FY19 and is now: “M3SF-19SN010205012 - Assessment of Security-Related Issues for Spent Nuclear Fuel”. SNSI- Report available on SCN | M3 | 1.08.01.02.05 | SNL | SF-19SN01020501 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Assessment of Security-Related Issues for Spent Nuclear Fuel | Assessment of Security-Related Issues for Spent Nuclear Fuel |  | 2019-03-08 |  | 2019-03-01 | Classified report (SNSI) completed for unmanned aerial systems threat assessment against spent fuel storage. Report available via SPN or SCN. | 2019 | Complete | Unmanned Aerial Systems Threat Analysis for Isolated and Consolidated Spent Fuel Storage Configurations (SAND2019-1843) | Mancel Jordan Parks | Samuel Durbin | SNSI |  |  | unmanned aerial systems; vulnerability analysis; spent nuclear fuel; dry storage cask
M4SF-19IN010204042 | M4 | 1.08.01.02.04.04 | INL | SF-19IN01020404 | Field Demonstration Support - INL | Jarrell, Josh | Saltzstein, Sylvia | Evaluation of opening spent fuel casks at INL | Evaluation of opening spent fuel casks at INL | Report that documents in greater detail how, when and where spent fuel casks could be opened with an initial focus on the REA-2023 cask and potentially the Castor cask. Specifically, additional refinement for the cost and time frames for unloading a cask will be developed. | 2019-05-31 |  |  | On Schedule | 2019 | On Schedule |  |  |  | None
M4SF-19OR010201025 supersedes M4SF-18OR0102010214, which superseded M5SF-17OR0102010212. | M4 | 1.08.01.02.01.02 | ORNL | SF-19OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Defuel and ship defueled cladding to ANL | Report detailing the specific cladding shipped to ANL | Defuel 3.5 inch segments of sister rod fuel and ship approximately 6 feet of defueled cladding to ANL | 2019-04-30 |  |  | All rod segments have been defueled; initial rad surveys have been accomplished and data provided to ANL; weighing samples will occur in March and all required information will then be provided to ANL for their use in acceptance paperwork preparation | 2019 | 90 Day |  |  |  | None
M4SF-19SN010201046 | M4 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Investigations of Aerosol Transmission through SCC | Investigations of Aerosol Transmission through SCC | This report will summarize experimental and modeling work evaluating potential gas and particle transport though SCC cracks. | 2019-03-15 |  |  | This L4 report is nearly completed, and will be submitted on or prior to march 15th. | 2019 | 90 Day |  |  |  | None
M2SF-19PN010201037 | M2 | 1.08.01.02.01.03 | PNNL | SF-19PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | PNNL Phase 1 Update on Sister Rod Destructive Examination Results | PNNL Phase 1 Update on Sister Rod Destructive Examination Results | PNNL Phase 1 Update on Sister Rod Destructive Examination Results | 2019-09-27 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M2SF-19PN010202014 | M2 | 1.08.01.02.02.01 | PNNL | SF-19PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | Finalize Updated MMTT Report | Final ENSA/DOE MMTT Model Report | Address comments and submit final M2 report. | 2019-09-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M2SF-19PN010203027 | M2 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Final Thermal Analysis Report for Demonstration Cask | Final Thermal Analysis Report for Demonstration Cask | Final Thermal Analysis Report for Demonstration Cask. Includes transient analysis and drying conditions. | 2019-09-28 |  |  | Transient analyses have begun as has analysis of temperatures of the Demo cask on the ISFSI pad. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010201034 | M3 | 1.08.01.02.01.03 | PNNL | SF-19PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | External Sensors for Water Detection | Detection of Water in DCSS Using External Sensors | Resume development of sensors to detect water in a dry cask storage canister | 2019-09-16 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010201082 | M3 | 1.08.01.02.01.08 | PNNL | SF-19PN01020108 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | SCC Consequence Modeling | Initial SCC Consequnce Model Report | Assist in the design and begin to develop a validated Dry Storage Canister Crack Detection model which will work to include Helium, radiation, particle release as well as crack depth and length. Support testing at SNL. | 2019-09-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010201085 | M3 | 1.08.01.02.01.08 | PNNL | SF-19PN01020108 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | CISCC Testing | Initial PNNL SCC Testing Results | Procure and install two systems for performing SCC testing with real time DCPD analysis. Support SNL testing. | 2019-09-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010201086 Per Matt Brainard: M3SF-19PN010201086: Update on Viability of Cold Spray and FSW for Canister Mitigation was delayed until 8/2/2019 due to “Report is almost complete, but PM has not been available to review due to health issues.” No deliverable to provide yet. | M3 | 1.08.01.02.01.08 | PNNL | SF-19PN01020108 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Update on Viability of Cold Spray and FSW for Canister Mitigation | Update on Investigations of Viability of Cold Spray and FSW as a Spent Nuclear Fuel Dry Storage Canister Mitigation Tool | Report on progress of implementation of cold spray and FSW and potentially of testing of samples. | 2019-07-12 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010202012 | M3 | 1.08.01.02.02.01 | PNNL | SF-19PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | 30 cm Drop Test Modeling | 30 cm Drop Test Model Report | Support SNL in the 30 cm drop test of the 1/3 scale ENSA cask and the follow on drop of the SNL assembly. | 2019-09-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19PN010203023 supercedes M3SF-18PN010203029 Per Matt Brainard: M3SF-19PN010203023: Sensitivity of High Heat Load MAGNASTOR was delayed until 7/12/2019 due to “Addressing vendor review comments and PNNL internal review, will then be sent for programmatic review.” | M3 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Sensitivity of High Heat Load MAGNASTOR | Decay Heat Sensitivity Study | Determine cladding temperatures for various heat loadings to determine how short cooled assembly loading affects PCT and distributions | 2019-03-29 | 43588.625 |  | Delay in February due to inclement weather shut downs at PNNL. | 2019 | Expected Late |  |  |  | None
M3SF-19PN010203026 | M3 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Small Scale Drying Testing | Small Scale Drying Test Report | Collaborate with SNL to design, build, and test a system with variable temperatures and water content to test the gas collection capability and determine how to appropriately interpret the results. | 2019-09-30 |  |  | On schedule. | 2019 | On Schedule |  |  |  | None
M3SF-19SR010201052 supercedes M3SF-18SR010201054 | M3 | 1.08.01.02.01.05 | SRNL | SF-19SR01020105 | Stress Corrosion Cracking - SRNL | Carter, Joe | Saltzstein, Sylvia | FY-18 Summary Report of Canister Corrosion Testing | FY-18 Summary Report of Canister Corrosion Testing | Summary Report of Canister Corrosion Testing | 2019-09-30 |  |  | On Schedule. | 2019 | On Schedule |  |  |  | None
M2SF-19OR010201026 | M2 | 1.08.01.02.01.02 | ORNL | SF-19OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | ORNL Phase 1 Update on Sister Rod Destructive Examination Results: Due September 27, 2019 | Sister Rod Destructive Examinations (FY19) | ORNL Phase 1 Update on Sister Rod Destructive Examination Results: Due September 27, 2019 | 2019-09-27 |  | 2019-09-27 | Testing on the sister rods continues; all fission gas testing and analyses are complete; all Phase 1 rods have been sectioned; initial CIRFT tests have been started; Instron mechanical tester will be moved in cell in late March/early April. The damaged HFIR core outer element testing will impact schedule of Sister Rod testing in that no sister rod tests will occur in May and the delay could extend into June. We will try to work around this issue. | 2019 | Complete |  |  |  | None
M2SF-19SN010201049 | M2 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Update of R&D on Chloride Induced Stress Corrosion Cracking of Spent Nuclear Fuel Dry Storage Canisters | FY19 Status Report- SNL Research into Stress Corrosion Cracking of SNF Dry Storage Canisters | Update of R&D on Chloride Induced Stress Corrosion Cracking of Spent Nuclear Fuel Dry Storage Canisters | 2019-09-20 |  | 2019-09-20 | This work continues on schedule. The mockup plate experiment continues , and a second experiment will be started in March. A thermodynamic database is being developed for Magnesium hydroxychlorides, and brine stability experiments continue. the two-year pitting experiment will be completed in June of this FY; characterization of the samples already collected continues. Rotating disc electrode experiments continue with NaCl, MgCl2, and seawater brines. Two journal articles are in development, on the dependence of pitting morphology on deliquescent brine relative humidity and composition, and on parameterization of the maximum pit size model for concentrated NaCl brines. | 2019 | Complete |  |  |  | None
M2SF-19SN010203034 | M2 | 1.08.01.02.03.03 | SNL | SF-19SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Update on the Thermal Hydraulic Investigations of a Horizontal Dry Cask Simulator | Update on the Thermal Hydraulic Investigations of a Horizontal Dry Cask Simulator | Update on the Thermal Hydraulic Investigations of a Horizontal Dry Cask Simulator | 2019-09-27 |  | 2019-09-27 | On schedule. The start date for testing has slipped, but built-in pad to the schedule remains. | 2019 | Complete |  |  |  | None
M2SF-19SR010201055 | M2 | 1.08.01.02.01.05 | SRNL | SF-19SR01020105 | Stress Corrosion Cracking - SRNL | Carter, Joe | Saltzstein, Sylvia | Consequence analysis of water in cask | Consequence analysis of water in cask | Develop consequence analysis of water in cask. | 2019-09-20 |  | 2019-09-20 | On Schedule. | 2019 | Complete |  |  |  | None
M3SF-20AN010201011 Supercedes: M3SF-19AN010201017 Per Matt Brainard: marked as “Expected Late” again during the November 2019 Performance Reporting Period in PICS:NE, with a new Revised Finish Date of 12/20/2019. The milestone narrative reads: “The final dataset for this report was generated on 11/22/19. The extension for the deliverable is to allow time to complete documentation of all data relevant to this M3 report." | M3 | 1.08.01.02.01.01 | ANL | SF-19AN01020101 | Sister Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | ANL FY18 Phase 1 Initial Phase 1 Radial Hydride and Ring Compression Test Results | ANL FY18 Phase 1 Initial Phase 1 Radial Hydride and Ring Compression Test Results | ANL FY18 Phase 1 Initial Phase 1 Radial Hydride and Ring Compression Test Results | 2019-09-27 |  | 2019-12-31 | Shipment of defueled cladding segments from ORNL is scheduled in March 2019. This allows ample time for testing and milestone reporting by the date scheduled assuming new funding is received in the May-June 2019 time frame to allow testing to continue as planned. | 2019 | Complete |  |  |  | None
M3SF-19OR010201027 | M3 | 1.08.01.02.01.02 | ORNL | SF-19OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Draft M2 Report on Destructive testing completed in FY19 | Sister Rod Destructive Test Results (FY19) | Draft Report providing testing results from ORNL Sister Rod testing conducted in FY19; | 2019-08-15 |  | 2019-08-15 |  | 2019 | Complete |  |  |  | None
M3SF-19SN0102010411 | M3 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Report on Corrosion Testing of Friction Stir Weld and Cold Spray Samples | Corrosion Testing of Friction Stir Weld and Cold Spray Samples | This report will document analysis of weld and weld repair samples provided by PNNL to determine corrosion susceptibility. | 2019-08-30 |  | 2019-08-30 | We have only received one sample from PNNL to date (we are only now beginning to get funding for this work). But we have determined what work will be done, and have identified resources. | 2019 | Complete |  |  |  | None
M3SF-19SN0102010415 | M3 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Update on Gas Sample Collection or CISCC Test Platform Activities | Status Report on Gas Sample Collection or CISCC Test Platform Activities | This report will document work to develop a full scale testing platform for CISCC detection and repair, or results of a canister gas sampling effort with industry. | 2019-08-06 |  |  | Funds redirected to another area. Memo in PICS:NE serving as replacement for the report. | 2019 | Cancelled |  |  |  | None
M3SF-20SN010202025 Supercedes: M3SF-19SN010202022 | M3 | 1.08.01.02.02.02 | SNL | SF-19SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | 30 cm Drop Test | 30 cm Drop Test | This test will include 30 cm drop test at BAM and full-scale assembly drop test at SNL | 2019-09-27 |  | 2019-12-17 | On schedule | 2019 | Complete |  |  |  | None
M3SF-19SN010203036 | M3 | 1.08.01.02.03.03 | SNL | SF-19SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Advanced concept for dry storage cask thermal-hydraulic testing with multiple fuel assemblies | Advanced concept for dry storage cask thermal-hydraulic testing with multiple fuel assemblies | Dry cask storage system experimental concept with multiple fuel assemblies | 2019-09-20 |  | 2019-09-20 |  | 2019 | Complete |  |  |  | None
M4SF-19OR010205032 Per Matt Brainiard: The Deliverable was considered a hardware functionality demonstration only (no report – Proof of Concept) | M4 | 1.08.01.02.05.03 | ORNL | SF-19OR01020503 | Security - ORNL | Scaglione, John | Saltzstein, Sylvia | MavNet video streaming demonstration | Proof of concept demonstration of technolgy integration | Technology demonstration that MAVNet has capability to stream live video | 2018-12-07 |  | 2018-12-07 |  | 2019 | Complete | NA - Hardware demonstration milestone | Stinson | Scaglione, John | None
M3SF-20OR010207031 Supercedes: M3SF-19OR010201073 | M3 | 1.08.01.02.01.07 | ORNL | SF-19OR01020107 | Stress Corrosion Cracking - ORNL | Scaglione, John | Saltzstein, Sylvia | Development and validation of phenomenological model on aerosol transport and plugging through stress corrosion cracks | A phenomenological model for the transport and plugging of aerosol through stress corrosion cracks with application to dry storage systems | Report documenting phenomenological model development, validation, needs and gaps | 2019-11-29 |  | 2019-11-29 | On schedule | 2020 | Complete |  |  |  | None
M3SF-20PN010207045 | M3 | 1.08.01.02.07.04 | PNNL | SF-20PN01020704 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Preliminary Deposition Modeling: For Determining the Deposition of Corrosive Contaminants on SNF Canisters | Developmental Model of salt and dust deposition on DCSS | M3 report documenting model development from FY19 and start of FY20 | 2020-01-24 |  | 2020-01-24 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on January 24, 2020. | 2020 | Complete
M2SF-20AN010201019 The preceding M3 version of this report was finalized on February 28, 2020 following technical review (QRL3) and uploaded into PICS:NE on March 24, 2020. It was converted to a draft M2 on March 25, 2020, sent out for policy review, and finalized the same day with no changes. The technical content of the M3 and M2 are identical. | M2 | 1.08.01.02.01 | ANL | SF-20AN01020101 | Sibling Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | Preliminary Destructive Examination Results for Sister Rod Cladding | Preliminary Destructive Examination Results for Sibling Pin Cladding |  | 2020-03-31 |  | 2020-03-25 | The preceding M3 version of this report was finalized on February 28, 2020 following technical review (QRL3) and uploaded into PICS:NE on March 24, 2020. It was converted to a draft M2 on March 25, 2020, sent out for policy review, and finalized the same day with no changes. The technical content of the M3 and M2 are identical. | 2020 | Complete
M2SF-20SN010203033 | M2 | 1.08.01.02.03 | SNL | SF-20SN01020303 | Thermal and Drying - SNL | Durbin, Sam | Saltzstein, Sylvia | Development of spent fuel mockups and instrumentation to investigate drying tests | Development of Mockups and Instrumentation for Spent Fuel Drying Tests |  | 2020-05-24 |  | 2020-05-22 | Drying mockups and instrumentation developed for future measurements of residual water inside spent fuel dry storage systems. Results documented in technical report on schedule. | 2020 | Complete | [6 empty] | spent nuclear fuel; dry storage; vacuum drying; forced helium dehydration; residual water
M4SF-20LB010301031 | M4 | 1.08.01.03.01 | LBNL | SF-20LB01030103 | Argillite Disposal R&D - LBNL | Rutqvist, Jonny | Camphouse, Chris | Investigation of Coupled Processes in Argillite Rock: FY20 Progress | Investigation of Coupled Processes in Argillite Rock: FY20 Progress | The report includes the results of investigations conducted by the LBNL modeling team related to various aspects of nuclear waste geologic disposal in argillite host rock. The FY2020 activities focused on improving conceptual understanding and modeling capability through analyzing and comparison of the results of modeling with experimental data obtained from the Full Scale Heater Experiment at the Mont Terri URL, Switzerland, and at ANDRA's URL in Bure, as well as the task on gas migration in clay barriers. The report also present fundamental research activities related to 1) field-scale fault slip experiments at Mont Terri, and 2) gas flow in rough fractures, 3) coupled microbial-abiotic processes in EBS and host rock materials, and 4) molecular modeling of radionuclide retention in clay. The report also includes a section on the integration of coupled THM processes models into the Geologic Disposal Safety Assessment (GDSA) and Performance Assessment (PA). | 2020-05-22 |  | 2020-05-21 |  | 2020 | Complete |  |  | Rutqvist, Jonny
M3SF-20LB010308062 | M3 | 1.08.01.03.08 | LBNL | SF-20LB01030806 | Engineered Barrier System International Collaborations - LBNL | Zheng, Liange | Camphouse, Chris | Engineered Barrier System Research Activities at LBNL: FY2020 progress report | Engineered Barrier System Research Activities at LBNL: FY2020 progress report | Progress in upgrading THMC simulator and application of THMC for generic argillite repository. Sorption and diffusion experiments on bentonite samples. Progress on an integrated set of experiments, molecular simulations, and thermodynamic modeling to develop a predictive understanding of ion exchange-driven swelling and collapse of montmorillonite clay. A research plan for a newly added research activity on the development and validation of a microscopic model of coupled transport processes in bentonite and using this model to determine cost effective augmentation strategies to increase the bulk thermal conductivity of hydrated bentonite. Progress in using coupled THMC modeling for understanding the THMC evolution of bentonite in FEBEX-DP. Numerical modeling in support of the HotBENT field test. A high tempereature benchtop-scale laboratory experiment, HotBENT-Lab, which provides a laboratory analog of the HotBENT experiment, to obtain a more comprehensive set of characterization and monitoring measurements. | 2020-06-04 |  | 2020-06-04 | The research activities have focused on understanding and modeling the evolution of the EBS bentonite and the associated coupled processes and impacts of high temperature on parameters and processes relevant to performance of a crystalline and argillite repository. The objective of the research work is developing modeling capability for reliable assessment of these processes and ultimately supporting GDSA model with detailed coupled THMC process models. | 2020 | Complete |  |  | Zheng, Liange |  |  |  | Bentonite alteration, THMC, EBS, numerical modeling, fundamental understanding
M3SF-20SN010207082 | M3 | 1.08.01.02.07 | SNL | SF-20SN01020708 | Canister Coatings for Prevention and Remediation - SNL | Bryan, Charles | Saltzstein, Sylvia | Summary of Coatings and Prevention Techniques for Stainless Steel Corrosion, and Preliminary Test Plan | Corrosion-Resistant Coatings for Mitigation and Repair of Spent Nuclear Fuel Dry Storage Canisters |  | 2020-07-31 |  | 2020-07-31 | This M3 report summarizes the results of a literature survey on coatings and surface treatments that are used to provide corrosion protection for exposed metal surfaces. The coatings are discussed in the context of being used on stainless steel spent nuclear fuel (SNF) dry storage canisters for potential prevention or repair of corrosion and stress corrosion cracking. Following the literature survey possible coatings for use on SNF dry storage canisters are identified, and a preliminary test plan for evaluating those coatings is presented. | 2020 | Complete | [6 empty] | spent nuclear fuel, stress corrosion cracking, corrosion potection coating
M3SF-20PN010203026 | M3 | 1.08.01.02.03 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Thermal Modeling of Horizontal DCS | Modeling of the Horizontal Boiling Water Reactor Dry Cask Simulator |  | 2020-07-30 |  | 2020-07-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on July 30, 2020. | 2020 | Complete | [6 empty] | thermal analysis models, dry cask simulator
M4SF-20PN020304031 | M4 | 1.08.02.03.04 | PNNL | SF-20PN02030403 | Rail Car Optimization - PNNL (IWM Funded) | Ross, Steven | Saltzstein, Sylvia | 8-Axle Railcar Prototype Design | 8-Axle Railcar Summary Report |  | 2020-09-30 |  | 2020-09-30 | Please find attached the report 8-Axle Railcar Prototype Design PNNL-30501, in fulfillment of milestone M42SF-20PN020304031 due 9/30/20. This is an IWM milestone, but managed under the SFWST CAM. | 2020 | Complete |  |  |  | None
M3SF-20PN010203025 | M3 | 1.08.01.02.03 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Small-Scale Drying: FY2020 Interim Report | Report on Sampling and Analysis of Small Scale Drying Tests |  | 2020-08-14 | 2020-09-18 | 2020-09-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on October 1, 2020. | 2020 | Complete |  | Heather Colburn | Brady Hanson | None |  |  | Small Scale Drying
M2SF-20PN010202012 | M2 | 1.08.01.02.02 | PNNL | SF-20PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | 30 cm Drop Modeling | Analyses of 30 cm Drop Test |  | 2020-09-30 |  | 2020-09-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 30, 2020. | 2020 | Complete |  | Nicholas Klymyshyn, Kevin Kadooka, Pavlo Ivanusa, Casey Spitz, James Fitzpatrick |  | None |  |  | 30 cm drop modeling;
M3SF-20PN010207091 | M3 | 1.08.01.02.07 | PNNL | SF-20PN01020709 | Canister Coatings for Prevention and Remediation - PNNL | Hanson, Brady | Saltzstein, Sylvia | Investigation of Cold Spray as a Dry Storage Canister Repair and Mitigation Tool | Cold Spray as a Canister Repair and Mitigation Tool |  | 2020-09-30 |  | 2020-09-29 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 29, 2020. | 2020 | Complete | Investigation of Cold Spray as a Dry Storage Canister Repair and Mitigation Tool | Brady Hanson, Ken Ross, Hellen Jiang, Morotolaowa Alabi, Carl Enderlin | Brady Hanson | None | M3SF-20PN010207091 Final.pdf |  | cold spray, storage canister
M3SF-20PN010203025 | M3 | 1.08.01.02.03 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Small Scale Drying Test Report | Report on Sampling and Analysis of Small Scale Drying Tests |  | 2020-08-14 | 2020-09-18 | 2020-09-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on October 1, 2020. | 2020 | Complete | Small-Scale Drying: FY2020 Interim Report | Heather Colburn | Brady Hanson | None | PNNL-30146 Rev. 0 FINAL.pdf |  | Small Scale Drying
M3SF-20SR010207025 | M3 | 1.08.01.02.07 | SRNL | SF-20SR01020702 | Water Consequences - SRNL | Carter, Joe | Saltzstein, Sylvia | Consequence analysis report that is update to FY19 preliminary report | Consequence of Water in Canisters | This report, Effects of Residual Water on Storage Canister Internal Components, satisfies the requirement for milestone M3SF-20SR010207025 that was due on September 30, 2020. | 2020-09-30 |  | 2020-09-30 | This report describes an evaluation of the spent nuclear fuel cladding and canister internal materials’ corrosion/oxidation due to (inadvertent) residual free water inside a dry storage canister post-dryout. Drying of spent nuclear fuel (SNF) and the impact of (inadvertent) residual water in a SNF canister is being addressed under the DOE-NE Spent Fuel and Waste Science and Technology (SFWST) program to ensure the safe extended dry storage and transportation of commercial SNF. | 2020 | Complete | Effects of Residual Water on Storage Canister Internal Components | Robert Sindelar/Pavan Shukla | Robert Sindelar/Pavan Shukla | None | Closure Document SRNL-STI-2020-00428 SRNL M3SF-20SR010207025.pdf |  | Effects of Residual Water
M2SF-20SN010203034 | M2 | 1.08.01.02.03 | SNL | SF-20SN01020303 | Thermal and Drying - SNL | Durbin, Sam | Saltzstein, Sylvia | Completion of Horizontal Dry Cask Simulator (HDCS) testing and validation exercises | Horizontal Dry Cask Simulator (HDCS) testing and validation exercises | M2 deliverable (SAND2020-10344 R) documenting testing with the Horizontal Dry Cask Simulator and validation exercises | 2020-09-25 |  | 2020-09-25 | M2 deliverable completed on schedule. | 2020 | Complete | Blind Modeling Validation Exercises Using the Horizontal Dry Cask Simulator | Ramon Pulido | Samuel Durbin | None | Blind_Modeling_Validation_Exercises_Using_the_Horizontal_Dry_Cask_Simulator_v5_SAND2020-10344R.pdf |  | spent nuclear fuel; dry storage; thermal hydraulics; computational fluid dynamics; model validation
M2SF-20SN010207016 | M2 | 1.08.01.02.07 | SNL | SF-20SN01020701 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Estimation of respirable aerosol release fractions through SCC-like geometries | Estimation of respirable aerosol release fractions through SCC-like geometries | This Level 2 milestone report documents work performed at Sandia National Laboratories evaluating gas and particle transport through a narrow slot, used as an analog for a stress corrosion crack. This work supports evaluation of possible releases from a spent nuclear fuel canister that has a through-wall stress corrosion crack. | 2020-08-28 |  | 2020-08-27 | This Level 2 milestone report documents work performed at Sandia National Laboratories evaluating gas and particle transport through a narrow slot, used as an analog for a stress corrosion crack. This work supports evaluation of possible releases from a spent nuclear fuel canister that has a through-wall stress corrosion crack. | 2020 | Complete | Estimation of respirable aerosol release fractions through SCC-like geometries | Sam Durbin | Sam Durbin | None | Estimation_of_Respirable_Release_Fractions_for_SCC-Like_Geometries_v1.pdf
M4SF-20PN010207047 | M4 | 1.08.01.02.07 | PNNL | SF-20PN01020704 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Modeling of SCC Breach Tests | Modeling of Breach Tests Using GOTHIC |  | 2020-08-14 |  | 2020-08-24 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on August 24, 2020. | 2020 | Complete | Summary of Progress: Modeling Compressible Flow in Microchannels | Mark S Lanza, Mie Azuma, Nathan Carstens, Andrew Casella | Brady Hanson | None | M4SF-20PN010207 Final.pdf |  | Aerosol-laden flow modeling, Generation of Thermal Hydraulic Information in Containment (GOTHIC)
M2SF-20AN010201012 | M2 | 1.08.01.02.01 | ANL | SF-20AN01020101 | Sibling Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | Demo Ring Compression Testing Results | Demo Ring Compression Testing Results |  | 2020-09-30 |  | 2020-09-29 | Milestone completed on 9/29/2020. It is in draft form sent out for policy review. | 2020 | Complete | Ductility of M5® and ZIRLO® Sibling Pin Cladding | M.C. Billone, T.A. Burtseva, Y. Chen, Z. Han | ANL | None
M2SF-20SN010202022 | M2 | 1.08.01.02.02 | SNL | SF-20SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | Drop Test Data Analysis | 30 cm Drop Test data Analysis | The 30 cm drop test with the full-scale surrogate assembly conducted in May 2020 was the last step needed for quantifying the strains on the surrogate assembly rods under normal conditions of transport. The test was conducted on May 7, 2020. The major conclusion that can be drawn from the 30 cm drop test is that the fuel rods will maintain their integrity during the 30 cm drop. | 7/32/2020 | 2020-09-30 | 2020-09-28 | Data analysis of the 30 cm drop test of a surrogate fuel assembly. | 2020 | Complete | Surrogate Assembly 30 cm Drop Test | Elena Kalinina | Elena Kalinina | None | 30 cm Drop Test FINAL_09_28_20.pdf |  | surrogate assembly;strain;accelerations;stess-strain curve;fatigue;normal conditions of transport
M2SF-20PN010207048 | M2 | 1.08.01.02.07 | PNNL | SF-20PN01020704 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | SCC Testing Results Report | Results from PNNL SCC TEsting |  | 2020-09-11 |  | 2020-09-11 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 11, 2020. | 2020 | Complete | Results from PNNL SCC Testing: FY20 | MB Toloczko, RA Bouffioux, FC Colon | Brady Hanson | None | M2SF-20PN010207048 PNNL SCC Testing Final 091120.pdf |  | Chloride-induced, stress corrosion crack growth rate
M2SF-20SN010207017 Superseded by- M2SF-21SN010207055 | M2 | 1.08.01.02.07 | SNL | SF-21SN01020705 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | FY20 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | FY20 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | This L2 milestone report documents research performed at Sandia National Laboratories in FY20, evaluating the chemical environment on the surface of spent nuclear fuel storage canisters and potential corrosion and stress corrosion cracking of the canisters. This includes the following: documentation of dust collection from an in-service storage system at the Maine Yankee ISFSI; calculations supporting definition of the canister surface environment for testing purposes; studies of magnesium chloride brine stability on the hot canister surface; results of pitting and corrosion experiments to evaluate the effects of brine composition on corrosion morphologies and rates; and a description of initial SCC crack growth experiments. | 2020-11-11 |  | 2020-11-11 | This L2 milestone report documents research performed at Sandia National Laboratories in FY20, evaluating the chemical environment on the surface of spent nuclear fuel storage canisters and potential corrosion and stress corrosion cracking of the canisters. This includes the following: documentation of dust collection from an in-service storage system at the Maine Yankee ISFSI; calculations supporting definition of the canister surface environment for testing purposes; studies of magnesium chloride brine stability on the hot canister surface; results of pitting and corrosion experiments to evaluate the effects of brine composition on corrosion morphologies and rates; and a description of initial SCC crack growth experiments. | 2020 | In progress | FY20 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | Rebecca Schaller/Charles Bryan, et al. | Rebecca Schaller/Charles Bryan/Andrew Knight/Brendan Nation | None | M2SF-21SN010207055_SNL_Canister_Environment_and_Corrosion_Studies_Final.pdf |  | spent nuclear fuel; stress corrosion cracking; long term interim storage
M3SF-20OR010207032 | M3 | 1.08.01.02.07.03 | ORNL | SF-20OR01020703 | Stress Corrosion Cracking - ORNL | Chatzidakis, Stylianos | Saltzstein, Sylvia | Progress report on model development and benchmarking | A phenomenological model for the aerosol transport, deposition and plugging of microcracks with application to dry storage systems | Report documenting progress on model development and benchmarking, needs and gaps | 2020-07-30 |  | 2020-07-31 | This report summarizes current progress (as of end of Q3 FY 2020) on the development of a phenomenological model of aerosol transport, deposition, and plugging through microchannels. The purpose is to introduce a generic, reliable numerical model for the prediction of aerosol transport, deposition, and plugging in leak paths while accounting for potential plugging formation. This report includes (1) an overview of recent additions and improvements on the recently developed numerical model to analyze the various deposition processes in leak paths, to provide quantitative estimates of penetration factors, and to gain an understanding of the variables that affect them and (2) a summary of recent benchmarking results of the model’s validity with recent experimental measurements from Sandia. | 2020 | Completed Late | Progress Report on Model Development for the Transport of Aerosol through Microchannels | Stylianos Chatzidakis | Stylianos Chatzidakis | None | M3SF-20OR010207032_Progress Report on Model for Aerosol Transport_08032020_0900_Final.pdf | Aerosol, microchannel, deposition
M3SF-20AN010201016 | M3 | 1.08.01.02.01.01 | ANL | SF-20AN01020101 | Sibling Pin Testing - ANL | Billone, Mike | Saltzstein, Sylvia | M3SF-20AN010201012 Demo Ring Compression Testing Results | Initial Phase 1 Radial Hydride and Demo Ring Compression Results | Radial hydride treatment of PNNL segments sent to ANL and ring compression test results for both ORNL and PNNL generated samples | 2020-08-30 | 2020-09-14 01:00 | 2020-09-29 | Milestone completed on 9/29/2020. Additional time was needed for the technical review to be completed and for reviewers’ comments to be addressed. This delay did not impact completion of the associated M2. | 2020 | Completed Late | Ductility of M5® and ZIRLO® Sibling Pin Cladding | M.C. Billone, T.A. Burtseva, Y. Chen, Z. Han | ANL | None | SFWD-SFWST-2020-M3 Final_093020.pdf
M3SF-20SR010207022 | M3 | 1.08.01.02.07.02 | SRNL | SF-20SR01020702 | Water Consequences - SRNL | Carter, Joe | Saltzstein, Sylvia | Summary report of the canister plate corrosion crack growth testing | Summary Report of the canister plate corrosion growth testing | Provide report of the canister plate corrosion crack growth testing. | 2020-09-05 |  | 2020-09-04 | This report provides a description of the testing (in progress at the Savannah River National Laboratory) to evaluate the corrosion behavior of a large section of welded plate material harvested from the Sandia National Laboratories’ full-size mockup of a spent nuclear fuel (SNF) dry storage canister. | 2020 | Complete | Large Plate Experiment of Chloride-induced Stress Corrosion Cracking in Spent Nuclear Fuel Storage Canisters | Poh-Sang Lam, Andrew Duncan, Robert Sindelar and Charles Bryan | Robert Sindelar | None | M3SF-20SR010207022 - Appendix E QA Cover Sheet - Robert Sindelar (004).pdf SRNL_M3_CISCC M3SF-20SR010207022 (SRNL-STI-2020-00315).pdf |  | Large Plate Experiment
M3SF-20SN010207018 | M3 | 1.08.01.02.07.01 | SNL | SF-20SN01020701 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Probabilistic Performance Assessment of Stress Corrosion Cracking of SNF Dry Storage Canisters | Probabilistic Performance Assessment of Stress Corrosion Cracking of SNF Dry Storage Canisters | This level 3 milestone report documents work done to support development of a probabilistic model for stress corrosion cracking of spent nuclear fuel dry storage canisters. Specifically, this report documents development of a phase-field model for initiation of corrosion pitting, a necessary preliminary step for stress corrosion cracking. | 2020-09-11 |  | 2020-09-11 02:00 | This level 3 milestone report documents work done to support development of a probabilistic model for stress corrosion cracking of spent nuclear fuel dry storage canisters. Specifically, this report documents development of a phase-field model for initiation of corrosion pitting, a necessary preliminary step for stress corrosion cracking. | 2020 | Complete | Status Report: Modeling of Pit Initiation | Remi Dingreville | Remi Dingreville | None | M3SF-20SN010207018 Probabilistic SCC model report final.pdf |  | stress corrosion cracking, phase-field, spent nuclear fuel, long term interim storage
M3SF-20SN010202023 | M3 | 1.08.01.02.02.02 | SNL | SF-20SN01020202 | Transportation - SNL | Kalinina, Elena | Saltzstein, Sylvia | Shaker Table Test Plan | Shaker Table Tests to Address Seismic Effects | Develop plan for shaker table testing to determine seismic effects on SSC and cladding performance | 2020-09-25 |  | 2020-09-24 02:00 | Shaker Table Test Plan, M3 report | 2020 | Complete | Shaker Table Test Plan | Elena Kalinina | Elena Kalinina | None | Earthquake_Shaker-Table_FINAL 09-24-20.pdf |  | earthquake;peak ground acceleration;shaker table;dry storage;fuel assembly
M3SF-20PN010203029 | M3 | 1.08.01.02.03.02 | PNNL | SF-20PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Thermal Modeling for International Round Robin | Demo Thermal International Round Robin Model Results | Report results of international round robin model | 2020-09-30 | 2020-10-30 15:00 | 2020-10-30 15:00 | Report is in internal review for release after having been submitted for programmatic review. | 2020 | Complete | Thermal Models of a TN-32B Cask for the International Benchmark | JA Fort, DJ Richmond, BJ Jensen | Brady Hanson | None | M3SF-20PN010203029 International Round Robin.pdf |  | TN-32B Cask, Thermal models
M3SF-20OR010201026 Superseded by M3SF-21OR010201033 | M3 | 1.08.01.02.01.02 | ORNL | SF-20OR01020102 | Sibling Pin Testing - ORNL | Montgomery, Rose | Saltzstein, Sylvia | Draft ORNL High Burnup Confirmatory Demo Sibling Rod Testing Results | Draft ORNL High Burnup Confirmatory Demo Sibling Rod Testing Results | Draft of the M2 deliverable documenting all work completed in FY20 | 2020-10-31 |  | 2020-10-30 | many sections of this report are in the ORNL publication review process | 2020 | Complete | Sister Rod Destructive Examinations (FY2) | Rose Montgomery | Rose Montgomery | None | Sister Rod Destructive Testing _10302020 - Main.pdf
M3SF-20PN010202014 Superseded by M3SF-21PN010202011 | M3 | 1.08.01.02.02.01 | PNNL | SF-20PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | Status of Development of Framework for Cumulative Effects Model | Status of Development of Cumulative Effects Model | Develop a cumulative effects model with SNL to combine dry storage stress corrosion cracking degradation with normal conditions of transport external loads. | 2020-11-20 |  | 2020-11-20 | An email transmitting this milestone and confirming its completion was sent to the NTD/CAM on November 20, 2020. | 2020 | Complete | Developing an Analytical Framework for Cumulative Effects | Nicholas Klymyshyn, Ben Jensen, Charlton Campbell, CJ Taylor Mason, Kevin Kadooka, James Fitzpatrick | Brady Hanson | None | M3SF-21PN010202011 Cumulative Effects.pdf |  | cumulative effects, spent nuclear fuel, cladding, storage
M4SF-20PN010201039 | M4 | 1.08.01.02.01.03 | PNNL | SF-20PN01020103 | Sibling Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | US Input to ESCP International Subcommittee Gap Analysis Report | US Input to ESCP International Subcommittee Gap Analysis | Combine previous gap reports into format for ESCP report | 2020-02-28 | 2020-06-18 03:00 | 2020-07-09 03:00 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on July 9, 2020. | 2020 | Completed Late | U.S. Input to the ESCP International Subcommittee Report on Extended Storage and Transportation Data Gaps | Brady Hanson | Brady Hanson | None | US Input to International Gap Report July 2020 Final.pdf |  | extended storage & transportation data gaps
M4SF-20OR010201024 | M4 | 1.08.01.02.01.02 | ORNL | SF-20OR01020102 | Sibling Pin Testing - ORNL | Montgomery, Rose | Saltzstein, Sylvia | BWR fuel planning report | Report on Obtaining BWR Fuel for PIE Testing to Close Data Gaps | Report documenting planning status, needs, and path forward regarding acquisition of BWR spent fuel for PIE | 2020-03-31 | 2020-05-01 | 2020-04-29 | This report describes key issues that have been addressed at ORNL to allow acceptance of a number of BWR fuel rods for PIE to supplement the examinations performed on PWR (Sibling Pins) SNF. Potential testing, schedule and costs are also discussed. | 2020 | Completed Late | BWR Spent Nuclear Fuel Acquisition and Testing to Support the DOE-NE High Burnup Spent Fuel Data Project | Bruce Bevard | Bruce Bevard | None | M4 Deliverable - M4SF-20OR010201024-BWR fuel planning report.pdf |  | BWR fuel; PWR fuel; spent nuclear fuel; PIE, non-destructive testing; Destructive Testing; Sister rods; Sibling Pins; High burnup;
M4SF-20IN010201042 | M4 | 1.08.01.02.01.04 | INL | SF-20IN01020104 | Sibling Pin Testing - INL | Jarrell, Josh | Saltzstein, Sylvia | Steps Needed and Timeline for Acceptance of Demo Cask to INL | Steps Needed and Timeline for Acceptance of Demo Cask to INL | Steps Needed and Timeline for Acceptance of Demo Cask to INL | 2020-09-11 | 2020-10-16 06:00 | 2020-10-16 06:00 | Expected 10/16/2020 | 2020 | Expected Late | High-Burnup Demo Cask Receipt at INL- Considerations for the Transport, Receipt, and Opening of the TN-32B High-Burnup Demo Cask |  |  | None | 60170 HBU Demo Cask Receipt at INL.pdf
M3SF-20PN0102070412 Supersedd by- M3SF-21PN010207025 | M3 | 1.08.01.02.07 | PNNL | SF-21PN01020702 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | Updated Deposition Model Report | Updated Deposition Model |  | 2020-12-18 |  | 2020-12-17 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on December 17, 2020. | 2021 | Complete | Status Update: Deposition Modeling for SNF Canister CISCC | Philip Jensen, Sarah Suffield, Ben Jensen | Brady Hanson | None | Deposition Modeling - FY 20 - Status Report - Final.pdf |  | Deposition modeling, SNF canister CISCC
M2SF-20OR010201023 Superseded by- M2SF-21OR010201032 | M2 | 1.08.01.02.01 | ORNL | SF-21OR01020103 | Fuel Integrity Testing and Analysis - ORNL | Montgomery, Rose | Saltzstein, Sylvia | FY2020 ORNL High Burnup Confirmatory Demo Sibling Rod Testing Results | ORNL Sibling Rod Testing Results (FY20) | Report documenting sister rod testing results completed to date | 2020-11-30 |  |  | Detailed results of the destructive testing conducted on the Phase 1 Sister Rods at ORNL thru September 2020. | 2021 | Complete | Sister Rod Destructive Examinations (FY20) | Rose Montgomery | Rose Montgomery | None | Sister Rod Destructive Testing _11302020 - Main.pdf |  | Sister rods, sibling pins, destructive testing, non-destructive testing, PIE, post irradiation examination, spent nuclear fuel, high burnup fuel, fuel cladding,fission gas, metallography,
M2SF-20PN010201036 Superseded by- M2SF-21PN010201055 | M2 | 1.08.01.02.01 | PNNL | SF-21PN01020105 | Fuel Integrity Testing and Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | FY20 Sibling Pin Testing Results | FY20 Sibling Pin Test Results |  | 2020-11-30 | 2021-03-05 | 2021-03-05 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on March 5, 2021. | 2021 | Complete | PNNL FY 2020 Sibling Pin Testing Results | Brady Hanson, RW Shimskey, JR Allred, SE Asmussen, SK Cooley, RC Daniel, MK Edwards, JGH Geeting, ZF Huber, PJ MacFarlan, LI Richmond, AM Westesen, BE Westman, & BD Hanson | Brady Hanson | None | PNNL FY20 Sibling Pin Testing Results.pdf
M3SF-21SN010208032 | M3 | 1.08.01.02.08.03 | SNL | SF-21SN01020803 | Canister Deposition Field Demonstration - SNL | Durbin, Sam | Saltzstein, Sylvia | Preliminary Test Design and Plan for a Lead Canister Field Demonstration | Preliminary Test Design and Plan for a Lead Canister Field Demonstration | Report to document a preliminary design for heaters, ancillary structures, instrumentation, control systems, and other supporting subsystems for a lead canister in a field demonstration. | 2020-11-20 |  | 2020-11-20 02:00 | SAND report (SAND2020-13075 R) completed on schedule. | 2021 | Complete | Preliminary Test Design and Plan for a Canister Deposition Field Demonstration | Sam Durbin | Sam Durbin | None | Preliminary_CDFD_Test_Plan_v0.pdf |  | spent nuclear fuel; dry storage; chloride induced stress corrosion crack; sampling; deposits
M4SF-21SR010203045 | M4 | 1.08.01.02.03.04 | SRNL | SF-21SR01020304 | Water Consequences - SRNL | Sindelar, Robert | Saltzstein, Sylvia | Crack Opening in Breached Fuel | Crack Opening in Breached Fuel | The crack extension and crack opening analysis under conditions of fuel oxidation in canister with inadvertent water, reported in the FY19 M2 milestone report (SRNL-STI-2019-00495), will be refined in a topical report. The work will support evaluation of canister radiological source term for breached fuel in canister with inadvertent free water. | 2021-02-08 |  | 2021-02-08 | This report describes the fracture mechanics formalism to evaluate the stability of cracks in a fuel cladding. | 2021 | Complete | Crack Opening in Breached Fuel | Robert Sindelar; Poh-Sang Lam | Robert Sindelar; Poh-Sang Lam | None | SRNL-STI-2021-00056.pdf |  | Crack Stability in Breached Fuel
M4SF-21SN010208034 | M4 | 1.08.01.02.08.03 | SNL | SF-21SN01020803 | Canister Deposition Field Demonstration - SNL | Durbin, Sam | Saltzstein, Sylvia | Progress on Sampling Measurement Techniques | Progress on Sampling Measurement Techniques | A report describing techniques and protocols for sampling of the deposits on the Canister Deposition Field Demonstration test canisters. | 2021-03-19 |  | 2021-03-18 02:00 | SAND report detailing proposed sampling techniques for the Canister Deposition Field Demonstration. | 2021 | 90 Day | Surface Sampling Techniques for the Canister Deposition Field Demonstration | Charles Bryan | Charles Bryan | None | M4SF-21SN010208034_Dust_Sampling_for_Canister_Deposition_Field_Demonstration.docx |  | spent nuclear fuel; dry storage; deposition; stress corrosion crack
M2SF-21SN010203032 | M2 | 1.08.01.02.03.03 | SNL | SF-21SN01020303 | Thermal and Drying - SNL | Durbin, Sam | Saltzstein, Sylvia | Thermal-Hydraulic Effects of Loss of Helium Backfill Using the HDCS | Thermal-Hydraulic Effects of Loss of Helium Backfill Using the HDCS | Report showing the effects of the loss of backfill in a dry storage canister system. | 2021-03-26 |  | 2021-03-26 | Completed report finished on schedule. | 2021 | Complete | Investigation of Thermal-Hydraulic Effects of Dry Storage Canister Helium Backfill Loss Using the Horizontal Dry Cask Simulator | Ramon Pulido | Ramon Pulido | None | TH_Effects_Loss_of_Helium_Backfill_HDCS_v4_SAND2021-3653R.pdf |  | spent nuclear fuel; dry storage; loss of backfill; thermal; hydraulics
M4SF-21SR010203044 | M4 | 1.08.01.02.03.04 | SRNL | SF-21SR01020304 | Water Consequences - SRNL | Sindelar, Robert | Saltzstein, Sylvia | Test Plan for Investigation of Hydrogen Generation in SNF Canisters | Test Plan for Investigation of Hydrogen Generation in SNF Canisters | The FY20 M3 milestone report "Evaluation of Hydrogen Generation in HBU Cask" SRNL-STI-2020-00268, predicted hydrogen buildup in the HBU cask materials system due to radiolysis of residual free and bound waters. This deliverable will describe a test plan for a laboratory-scaled gamma irradiation testing of Zr, SS, and Al materials systems in a mini-canister chamber. The outline of the test concept is contained in the FY20 report. The deliverable is the detailed plan for the testing. | 2021-03-26 |  | 2021-03-26 | This report presents a test plan to investigate radiolytic hydrogen generation in spent nuclear fuel (SNF) canisters containing Zr-based cladding materials. The initial primary contributor to the generation of radiolytic hydrogen is estimated to be the residual physisorbed water on the ZrO2 film, post-dryout. Over the longer term the primary hydrogen source is associated with the aluminum hydroxides and water vapor. This report fulfills the M4 milestone M4SF-21SR010203044, Test Plan for Investigation of Hydrogen Generation in SNF Canisters under Work Package Number SF-21SR01020304. | 2021 | Complete | Test Plan for Investigation of Hydrogen Generation in SNF Canisters | Robert Sindelar, A. d'Entremont, R. Kesterson | Robert Sindelar | None | SRNL-STI- 2021-00171 Test_Plan_for_Investigation_of_H2_Generation_in_SNF_Canisters.pdf |  | Test Plan Investigation
M3SF-21SN01020106 | M3 | 1.08.01.02.01 | SNL | SF-21SN01020106 | Fuel Integrity Support - SNL | Saltzstein, Sylvia | Saltzstein, Sylvia | Gap Analysis for ATF | Initial ATF Storage and Transportation Gap Analysis | This document provides information related to the Accident Tolerant Fuels and Advanced Fuels (ATF/AF) currently being irradiated in commercial reactors and other promising advanced fuel options. Once ATF/AF prototypes have reached EOL burnup, SWFST ST could test representative rods using the same processes and procedures used for testing the EPRI/DOE High Burnup Demonstration Sibling Pins. Significantly different fuel types (e.g., TRISO, uranium alloys) will require a different test plan. The current storage and transportation canister/cask systems should be able to manage the rod/assembly ATF fuel systems that are very similar to existing commercial fuel systems. Modifications to handle the fuel’s increased weight and greater thermal and ionizing radiation loads may be required. Significantly different fuel systems (e.g., TRISO, uranium alloys) will require a new storage, transportation, and disposal container design. | 2021-04-15 |  | 2021-04-15 | Accident Tolerant Fuel Gap Analysis for Spent Nuclear Fuel Storage and Transportation | 2021 | Complete | High-Level Gap Analysis for Accident Tolerant and Advanced Fuels for Storage and Transportation | Philip Honnold | Sylvia J. Saltzstein | None | ATF_High­_Level_Gap_Analysis_SAND2021-4732.pdf
M3SF-21SN010207072 | M3 | 1.08.01.02.07 | SNL | SF-21SN01020707 | Aerosol Source Term - SNL | Durbin, Sam | Saltzstein, Sylvia | Aerosol depletion estimates inside a spent fuel dry storage system using MELCOR | Aerosol depletion estimates inside a spent fuel dry storage system using MELCOR | SAND2021-5202 R titled "Interim Report on Aerosol Deposition Inside a Spent Fuel Transportation and Storage Canister" | 2021-04-16 | 2021-04-30 | 2021-04-29 | Technical report completed. | 2021 | Complete | Interim Report on Aerosol Deposition Inside a Spent Fuel Transportation and Storage Canister | Jesse Phillips | Jesse Phillips | None | MELCOR_Aerosol_Deposition_Inside_SNF_Storage.docx |  | spent nuclear fuel; aerosol; depletion; source term, MELCOR
M2SF-21SN010208033 | M2 | 1.08.01.02.08 | SNL | SF-21SN01020803 | Canister Deposition Field Demonstration - SNL | Durbin, Sam | Saltzstein, Sylvia | Status Update on the Canister Deposition Field Demonstration | Status Update on the Canister Deposition Field Demonstration | Sandia technical report. SAND2021-6471 R | 2021-05-28 |  | 2021-05-27 | SAND2021-6471 R completed on schedule to meet requirements of M2SF-21SN010208033. | 2021 | Complete | Status Update for the Canister Deposition Field Demonstration | Samuel Durbin | Samuel Durbin | None | CDFD_Status_Update_v1.pdf |  | spent nuclear fuel; stress corrosion crack; deposition; dry storage
M3SF-21PN010207042 | M3 | 1.08.01.02.07.04 | PNNL | SF-21PN01020704 | Aerosol Source Term - PNNL | Hanson, Brady | Saltzstein, Sylvia | GOTHIC aerosol source depletion studies | GOTHIC Aerosol Source Depletion Studies | Document results of GOTHIC models of aerosol transport, settling, and depletion within a canister | 2021-04-16 |  | 2021-04-16 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on 4/16/21. | 2021 | Complete | GOTHIC Aerosol Source Depletion Studies | Steve Ross, Mark Lanza, Mike Leimon, Mohamed Elsawi, Andrew Casella | Steve Ross, Brady Hanson | None | GOTHIC Aerosol Source Depletion Studies_M3SF-21PN010207042_Final.pdf |  | Aerosol; depletion studies; GOTHIC
M3SF-21SN010202022 | M3 | 1.08.01.02.02.02 | SNL | SF-21SN01020202 | External Load Testing and Analysis - SNL | Kalinina, Elena | Saltzstein, Sylvia | Shaker Table Inputs for Earthquakes | Shaker Table Inputrs for Earthquakes | Develop shaker table inputs for the earthquakes of different magnitudes and types. | 2021-06-30 |  | 2021-06-28 | Report documenting the development of the free-field ground motions and an approach to the soil-structure interactions. | 2021 | Complete | Ground Motion Inputs for the Seismic Shake Table Test | Elena Kalinina | Elena Kalinina | None | Ground_Motion_FINAL_w_Appendix_06-28-21.pdf |  | seismic loads; shake table test; ground motion response; spectra; spent nuclear fuel; dry storage
M11UF041401 | M1 | 1.02.08.04 | PNNL | FTPN11UF0414 | R&D Opportunities | [8 empty] | Milestone completed on June 30, 2011. | [6 empty] | Gap_Analysis_Final_Draft.pdf Gap_Analysis_Final_Draft_-_06-30-2011-pm_-_Rev per AAA.pdf
M2FT-13OR0914066 Supersedes M2FT-12OR08220217 same as M4FT-13OR0914065 | M2 | 1.02.09.14 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John
M31UF040602 | M3 | 1.02.08.04 | INL | FTIN11UF0406 | Transportation | [8 empty] | On target to complete milestone at 9/30/2011 | [6 empty] | inl end of year transportation transmittal.pdf INL_EXT-11-22559 Transportation Mod Exclusion Report Transmittal.pdf
M31UF040903 | M3 | 1.02.08.04 | ORNL | FTOR11UF0409 | Concept Evaluations | [8 empty] | On Schedule
M31UF041003 | M3 | 1.02.08.04 | ORNL | FTOR11UF0410 | R&D Opportunities | [8 empty] | This milestone report is in preparation and is expected to be completed on time. | [6 empty] | Transmittal_Package_FCRD-USED-2011-000270.pdf
M31UF041303 | M3 | 1.02.08.04 | PNNL | FTPN11UF0413 | Concept Evaluations | [8 empty] | Milestone completed 8/31/11. | [6 empty] | PNNL Concepts Evaluations FY-11 Year End Summary Report 8-31-11.pdf
M41UF040301 | M4 | 1.02.08.04 | INL | FTIN11UF0403 | Concept Evaluations | [8 empty] | Completed. | [6 empty] | concept evalaution mid year qa document.docx Concept Evaluationmilestone transmittal FCT DTS.docx FCRD concepts.pdf
M41UF040401 | M4 | 1.02.08.04 | INL | FTIN11UF0404 | R&D Opportunities | [15 empty] | FCRDR&D Opportunities.pdf
M41UF040601 | M4 | 1.02.08.04 | INL | FTIN11UF0406 | Transportation | [8 empty] | Mid year milestone completed March 14. Letter sent to P. McConnell at Sandia Transportation work package manager.
M41UF040902 | M4 | 1.02.08.04 | ORNL | FTOR11UF0409 | Concept Evaluations | [8 empty] | Mid-year report submitted on 3/31/11.
M41UF041002 | M4 | 1.02.08.04 | ORNL | FTOR11UF0410 | R&D Opportunities | [8 empty] | As ORNL's support in this area is fairly small, the existence of this milestone escaped the PI's attention, perhaps also partly due to the PI's recent focus on the Fukushima event. A revised finish date of 4/22/2011 is suitable. | [6 empty] | FTOR11UF0410_Storage_RD_Opportunities_Mid-Year_Status_Report_ORNL_April_21_2011_Final.pdf PNNL RD Opportunities Mid Year.pdf
M41UF041202 | M4 | 1.02.08.04 | ORNL | FTOR11UF0412 | Transportation | [8 empty] | The reason for the slippage is that the PI became very involved in ORNL's support of the DOE/NE Nuclear Emergency Response Team (NERT) and NRC’s Reactor Safety Team related to the events at Fukushima. The PI's involvement has primarily related to issues related to radiation dose and the potential for criticality. The DOE representative was previously made aware of this delay. | [6 empty] | FTOR11UF0412_Mid-Year_Status_Report_ORNL_FINAL.pdf
M41UF041602 | M4 | 1.02.08.04 | PNNL | FTPN11UF0416 | Transportation | [8 empty] | Milestone completed 3/31/11. | [6 empty] | Transportation_Interim Milestone Report_3_31_2011_PNNL-20289.pdf
M41UF041901 | M4 | 1.02.08.04 | SNL | FTSN11UF0419 | Security | [8 empty] | As required by the criteria for completion, the milestone report files were submitted to Ken Sorenson, Control Account Manager, via email on 3/31/2011. The milestone report, FCT cover sheet, and transmittal sheet files were submitted to Connie Bates (FCRD TIO) and Kevin McMahon (SNL QA POC) on 4/1/2011. The FCT cover sheet was resubmitted to Connie Bates (FCRD TIO) and Kevin McMahon (SNL QA POC) to correctly document the technical review of the milestone report. The milestone files were uploaded into FCPICS on 4/6/2011. The final milestone report was distributed to the Used Fuel Storage Security Team on 4/6/2011. | [6 empty] | M41UF041901 MilestoneFCTCoverSheet.pdf M41UF041901 MilestoneReport.pdf M41UF041901 MilestoneTransmittalSheet.pdf
M41UF042202 | M4 | 1.02.08.04 | SRNL | FTSR11UF0422 | R&D Opportunities | [8 empty] | No response reported on this milestone scheduled for completion on 9/30/11. SRNL is working on completing Level 4 milestone due 9/30/11.
M4508031302 | M4 | 1.5.08.03 | PNNL | PN1015080313 | Storage - R&D Opportunities
M4FT-13OR0914065 Same as M2FT-13OR0914066 | M4 | 1.02.09.14 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John
M2FT-12PN0803041 ULR. Draft | M2 | 1.02.08.03.04 | PNNL | FT-12PN080304 | ST R&D Investigations - PNNL | Hanson, Brady | Sorenson, Ken | High and Medium Technical Gap Priorities Report | High and Medium Technical Gap Priorities Report | This report will refine the suite of high and medium priorities in the FY11 data gap report based on impact on licensing. | 2012-04-30 13:00 |  | 2012-04-30 03:00 |  | 2012 | Complete |  | Hanson, Brady | Hanson, Brady | None | Gap Prioritization Report DRAFT Rev0.pdf | FCRD-USED-2012-000109
M2FT-12SN0802061 ULR. Draft. No SAND number on report. | M2 | 1.02.08.02.06 | SNL | FT-12SN080206 | Test Plan for Corrosion of Canisters in Marine Environments | Weiner, Ruth | Sorenson, Ken | Test plan for gathering on-site atmospheric data, including coastal data, and for conducting stainless steel canister corrosion tests. | Implementation Plan for Fielding an Operational Test and Validation Complex | This is a plan for testing and monitoring corrosion of stainlss steel canisters in a variety of atmospheric environments, primarily marine environments. | 2012-07-31 02:00 |  | 2012-07-30 02:00 |  | 2012 | Complete |  | Weiner, Ruth | Weiner, Ruth | None | Copy of M2Milestone_print_of_draft.pdf | FCRD-UFD-2012-000094
M3FT-12OR08160611 | M3 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Howard, Rob | Wagner, John | Preliminary Concept of Operations | Preliminary Used Fuel Management System Concept of Operations | Preliminary operational concepts for a complete waste management system will be developed by DOE UFD Campaign national laboratories.. These should include canister loading and on-site storage at nuclear utility sites, transportation activities, operations at a consolidated interim storage facility, repackaging, and operations at a geologic disposal facility. | 2012-06-29 |  | 2012-06-29 |  | 2012 | Complete |  | Howard, Rob | ORNL | None | Waste_Management_System_Concept_of Operations_6_29_2012_Final.pdf | FCRD-UFD-2012-000155
M3FT-12OR0816064 | M3 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Howard, Rob | Wagner, John | Final Implementation Plan on the Development and Licensing of Standardized Transportation, Aging, and Disposition Canisters and Feasibility of Direct Disposal of DPCs | Final Implementation Plan on the Development and Licensing of Standardized Transportation, Aging, and Disposition Canisters and Feasibility of Direct Disposal of DPCs | Final implementation plan on the development and licensing of standardized transportation, aging, and disposition canisters that incorporates comments from review of the draft implementation plan. | 2012-04-06 04:00 | 2012-04-27 | 2012-04-20 |  | 2012 | Completed Late |  | Howard, Rob | Howard, Rob | None | Combined_STAD_Implementation_DPC_Disposal_Plan_April_20_2012_final.pdf | FCRD-UFD-2012-000106
M3FT-12SN0802062 ULR. Draft. | M3 | 1.02.08.02.06 | SNL | FT-12SN080206 | Test Plan for Corrosion of Canisters in Marine Environments | Weiner, Ruth | Sorenson, Ken | Progress report for Test Plan | Progress Report for SS corrosion Test Plan Plan | This milestone will be a report on progress toward a 5-year and 10-year plamn to develop the TVC | 2012-04-01 |  | 2012-03-30 02:00 |  | 2012 | Complete |  | Weiner, Ruth | Weiner, Ruth | None | Progress report_Rev 1.pdf | FCRD-UFD-2012-000094 | corrosion, test plan, marine, environment, canister
M3FT-12SN0802063 ULR. | M3 | 1.02.08.02.06 | SNL | FT-12SN080206 | Test Plan for Corrosion of Canisters in Marine Environments | Weiner, Ruth | Sorenson, Ken | Dry Transfer System; Progress Report | Report on Support for Dry Transfer System | This report will document the progress that has been made to develop a dry transfer system (for used fuel transfer) between transportation and storage containers. | 2012-09-17 20:00 |  | 2012-09-10 02:00 |  | 2012 | Complete |  | Weiner, Ruth | Weiner, Ruth | None | dt milestone_rw (2).docx dt milestone_rw (2).docx | FCRD-UFD-2012-000687
M4FT-12IN0810012 ULR? No Lab report number on document. | M4 | 1.02.08.10.01 | INL | FT-12IN081001 | ST Engineering Analysis - INL | Birk, Sandy | Sorenson, Ken | Support for early analysis report | Support for early analysis report | Letter report documenting INL support for the early analysis report prepared by ORNL | 2012-06-30 06:00 | 41117.0833 | 2012-07-27 02:00 |  | 2012 | Completed Late |  | Birk, Sandy | Birk, Sandy | None | INL Mid Year Report.docx INL_Mid_Year_Report[1][1].pdf | FCRD-UFD-2012-000325
M4FT-12IN0810014 ULR? No Lab report number on document. | M4 | 1.02.08.10.01 | INL | FT-12IN081001 | ST Engineering Analysis - INL | Birk, Sandy | Sorenson, Ken | Status report for ORNL analyses activities | Status report for ORNL analysis activities | Status letter report to support proposed future analyses and analysis capabilities | 2012-08-30 08:00 | 41179.0833 | 2012-09-27 02:00 | complete | 2012 | Completed Late |  | Birk, Sandy | Birk, Sandy | None | EOY INL FY12 Status Report for ORNL.pdf | FCRD-UFD-2012-000324
M4FT-12OR0816061 | M4 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Wagner, John | Wagner, John | Draft Implementation Plan on the Development and Licensing of Standardized Transportation, Aging, and Disposition Canisters and Feasibility of Direct Disposal of DPCs | Draft Implementation Plan on the Development and Licensing of Standardized Transportation, Aging, and Disposition Canisters and Feasibility of Direct Disposal of DPCs | This is a multi-year implementation plan to develop and license standardized transportation aging and disposition canisters | 2012-03-15 04:00 |  | 2012-03-15 |  | 2012 | Complete |  | Howard, Rob | Howard, Rob | None | DRAFT_STAD_Implementation_Plan_March_16_2012.pdf | FCRD-UFD-2012-000106 | Standardized Canisters
M4FT-12OR0816069 Duplicate DMS number | M4 | 1.02.08.16.06 | ORNL | FT-12OR081606 | Standardized Canisters - ORNL | Wagner, John | Wagner, John | Draft Implementation Plan on the Feasibility of Direct Disposal of DPCs | Draft Implementation Plan on the Feasibility of Direct Disposal of DPCs | This is a multi-year implementation plan to assess the feasibility of direct disposal of DPCs | 2012-04-20 02:00 |  | 2012-04-20 |  | 2012 | Complete |  | Howard, Rob | Howard, Rob | None | Combined_STAD_Implementation_DPC_Disposal_Plan_April_20_2012_final.pdf | FCRD-UFD-2012-000106
M4FT-12PN0802053 ULR. Draft. | M4 | 1.02.08.02.05 | PNNL | FT-12PN080205 | Field Testing - PNNL | Buelt, James | Sorenson, Ken | Dry Transfer System Study | Contributions to Dry Transfer System Study Report | Provide input to the INL report on the dry transfer system | 2012-05-18 12:00 |  | 2012-05-18 03:00 |  | 2012 | Complete |  | Brady Raap, Michaele | Brady Raap, Michaele | None | PNNLinput_2012DTS.pdf | FCRD-UFD-2012-000130
M4FT-12SN0810053 ULR - No SAND number on report | M4 | 1.02.08.10.05 | SNL | FT-12SN081005 | ST Engineering Analysis - SNL | Tikare, Veena | Sorenson, Ken | Preliminary report | Preliminary report | Preliminary report identifying areas for modeling and analysis. | 2012-03-23 02:00 | 2012-04-30 04:00 | 2012-04-19 02:00 |  | 2012 | Completed Late |  | Tikare, Veena | Tikare, Veena | None | LetterReportWager4-19.pdf | FCRD-UFD-2012-000604
M5FT-12OR08220211 | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Finalize the UNF data request questionnaire | Data request questionnaire | b. Finalize the data request questionnaire that will be given to industry representatives. | 2012-07-27 |  | 2012-07-13 |  | 2012 | Complete |  | Scaglione, John | Scaglione, John | None | ReactorOperatingDataQuestionnaire_26June2012.pdf | FCRD-UFD-2012-000540
M5FT-12OR08220214 | M5 | 1.02.08.22.02 | ORNL | FT-12OR082202 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Scaglione, John | None | Finalize white paper describing benefits of data collection | White paper describing benefits of data collection | This will be a white paper describing benefits of data collection. The goal is to convince industry that it is worth their time to assist with this effort. | 2012-07-31 |  | 2012-07-13 |  | 2012 | Complete |  | Scaglione, John | Scaglione, John | None | White Paper Reactor Operating History Data 26June2012.pdf | FCRD-UFD-2012-000542
M3FT-13OR0822013 Supersedes M4FT-12OR0822039 ULR. Draft. | M3 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Wagner, John | Draft Modeling, Simulation and Experimental Integration RD&D Plan | Draft Used Fuel Performance Modeling, Simulation and Experimental Integration RD&D plan | Execution of RD&D Plan and Demonstration of Approach on Selected Technical Issue. | 2013-03-02 02:00 |  | 2013-03-02 |  | 2013 | Complete |  |  |  | None | Draft Modeling Simulation and Experimental Integration RDD Plan (2).pdf | FCRD-UFD-2013-000111
M3FT-13OR0822016 ULR. Draft. | M3 | 1.02.08.22.01 | ORNL | FT-13OR082201 | M&S and Experimental Integration with UQ - ORNL | Howard, Rob | Wagner, John | Draft Demonstration of Approach on Used Fuel Performance Characterization | Draft Used Fuel Performance UQ Focused Modeling, Simulation and Experimental Integration | Submission of draft Execution RD&D Plan and Demonstration of Approach on Selected Technical Issue. | 2013-08-31 |  | 2013-08-31 02:00 |  | 2013 | Complete |  | Adkins, Harold | Howard, Rob | None | FCRD-UFD-2013-000289_M3.pdf | FCRD-UFD-2013-000289
M3FT-13SN0805062 ULR. Draft. Charles Bryan: Note that the anoxic corrosion of copper report is a final report, but it was labeled draft, as a final version was eventually going to be issued.&nbsp; That never happened. | M3 | 1.02.08.05.06 | SNL | FT-13SN080506 | ST Storage and Transportation Experiments - SNL | Bryan, Charles | Sorenson, Ken | Final Report: Experimental evaluation of hydrogen generation by anoxic corrosion of copper | Final Report: Experimental evaluation of hydrogen generation by anoxic corrosion of copper | Recent controversial experiments have shown that copper may corrode under reducing conditions. This milestone report will document the results of experiments here at Sandia addressing the issue. The Sandia experiments evaluate a potential mechanism for explaining the controversial results within the accepted context of copper corrosion behavior. This topic has taken on added urgency with a request from the DOE that we support the European community in investigating copper corrosion behavior. | 2013-05-31 10:00 | 2013-08-30 10:00 | 2013-08-31 04:00 |  | 2013 | Completed Late |  | Enos, David | Bryan, Charles | None | FCRD-UFD-2013-000261_Anoxic_corrosion_of_copper.pdf | FCRD-UFD-2013-000261
M3FT-13SR0813051 ULR. Predecisional draft - link available in SNL S&T Site. Final report is M2FT-13PN0912022​, FCRD-NFST-2013-000238. | M3 | 1.02.08.13.05 | SRNL | FT-13SR081305 | ST Transportation - SRNL | Carter, Joe | Sorenson, Ken | Maintain dry storage database, update transportation cask issues and ISFSI shipment options reports | Update dry storage database, revise transportation cask issues and develop ISFSI shipment options | SRNL: shall maintain the database which extends the StoreFuel database to include details on transportation issues for all light water reactor assemblies in dry storage in the US. SRNL will develop/deploy a monitoring system for determining how often the cask environment is favorable for SCC in storage casks. | 2013-09-30 |  | 2013-09-30 | This report provides a preliminary evaluation of removing stranded used nuclear fuel from 12 shutdown sites. Shutdown sites are defined as those commercial nuclear power reactor sites where the nuclear power reactors have been shut down and the site has been decommissioned or is undergoing decommissioning. The shutdown sites are Maine Yankee, Yankee Rowe, Connecticut Yankee, Humboldt Bay, Big Rock Point, Rancho Seco, Trojan, La Crosse, Zion, Crystal River, Kewaunee, and San Onofre. | 2013 | Complete |  | PNNL | PNNL | None | FCRD-NFST-2013-000238_M2_Predecisional.pdf | FCRD-NFST-2013-000238
M3FT-14PN0805042 | M3 | 1.02.08.05.04 | PNNL | FT-14PN080504 | Experiments - PNNL | Hanson, Brady | Sorenson, Ken | Draft of the M2 Report | Draft of the M2 Report | Draft of the M2 Report | 2014-08-08 14:00 |  | 2014-08-08 06:00 |  | 2014 | Complete | Draft FY14 PNNL Zr Cladding Testing Status Report | Hanson, Brady | Hanson, Brady | None | FCRD-UFD-2014-000315.pdf | FCRD-UFD-2014-000315
M3FT-14SN0815011 | M3 | 1.02.08.15.01 | SNL | FT-14SN081501 | Security - SNL | Durbin, Sam | Sorenson, Ken | Used Fuel Transportation Security Planning, Risk Assessment and Technologies | Used Fuel Transportation Security Planning, Risk Assessment and Technologies | Milestone report for used fuel transportation security. | 2014-08-15 08:00 |  | 2014-08-15 02:00 |  | 2014 | Complete | Preliminary Security Assessment of Spent Nuclear Fuel during Rail Transport | Durbin, Sam | Durbin, Sam | None |  | FCRD-UFD-2014-000329 | Sabotage, spent nuclear fuel, dry casks, rail transport
M4FT-14IN0802018 ULR. Draft. | M4 | 1.02.08.02.01 | INL | FT-14IN080201 | Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Instrumentation Workshop with Industry | Summary of Instrumentation Workshop for | Conduct the workshop with the full-scale demonstration industry team by December 16, 2013 and document the recommendations. Coordinate with industry to determine if and what kind of instrumentation might be added to the full-scale demonstration cask while meeting the industry's operational and functional requirements. | 2014-09-30 02:00 | 2014-08-12 03:00 | 2014-08-12 14:00 |  | 2014 | Complete | Instrumentation Workshop with Industry | Marschman, Steve | Marschman, Steve | None | Pages from Instrumentation Workshop with Industry final.pdf | FCRD-UFD-2014-000475 | demonstration, monitoring, high burnup, workshop, gas monitoring
M4FT-14IN0810051 No SAND Number or DMS number on report. | M4 | 1.02.08.10.05 | INL | FT-14IN081005 | Analysis - INL | Hales, Jason | Sorenson, Ken | Draft V&V strategy for hydride model integration into BISON | Draft V&V Strategy | Develop an approach to show that the implementation of the hybrid model into BISON has been done correctly. Likewise, develop an approach to show that the integrated capability represents real phenomena. | 2014-04-30 22:00 |  | 2014-04-25 02:00 |  | 2014 | Complete | Verification and Validation Strategy for Implementation of Hybrid Potts-Phase Field Hydride Modeling Capability in MBM | Hales, Jason | Hales, Jason | None | VVHybrid.pdf | FCRD-UFD-2014-000507 | verification; validation; hydride; SPPARKS; MBM
M4FT-14SR0805064 | M4 | 1.02.08.05.06 | SRNL | FT-14SR080506 | Experiments - SRNL | Smith, Pat | Sorenson, Ken | ASTM C1553 revision | ASTM C1553 revision | Chair drying task group under C26.13 and shepherd the revised drying standard (C1553-14) through its ASTM approval. | 2014-07-31 02:00 |  | 2014-07-31 |  | 2014 | Complete | June 7, 2014 Closing, Balloted Version | Sindelar, Robert | Sindelar, Robert | None | June_7_2014_closing_balloted_version.pdf | FCRD-UFD-2014-000489 | ASME C1553 Revision
M2FT-15IN08020111 ULR. Preliminary Draft. No follow-on doc was done. | M2 | 1.02.08.02.01 | INL | FT-15IN080201 | ST Field Demonstration Support - INL | Marschman, Steve | Sorenson, Ken | Test Plan for Sister Rod Characterization and Testing | Sister Rod Test Plan | DOE has requested a test plan that describes what work will be done with each sister rod. | 2015-03-31 09:00 |  | 2015-03-31 02:00 |  | 2015 | Complete | Test Plan for Sister Rod Charactderization and Testing | Marschman, Steve | Marschman, Steve | None | Test Plan for Sister Rod Characterization & Testing Draft for Ext Review REV-1.pdf | FCRD-UFD-2015-000050 | used fuel, characterization, PIE, sister rods
M2FT-15PN0810049 ULR. Draft | M2 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Thermal Profiles to Support the High Burnup Fuel Cask R&D Program | Thermal profile analyses of in-situ industry storage systems identified for inspection. | This report will document the development and testing of a COBRA-SFS model of the TN-32B cask to be used for the Industry Demonstration project. The thermal analyses will be used to help identify which of the 37 potential assemblies should be loaded into the 32 spaces in the demonstration cask, identify sister pins for pre-test characterization, and help determine the location of thermocouple lances. | 2015-09-18 07:00 |  | 2015-09-18 03:00 | Preliminary analyses of the proposed as-loaded High Burnup Cask | 2015 | Complete | THERMAL MODELING OF PROPOSED TN-32B CASK FOR HIGH BURNUP FUEL STORAGE DEMONSTRATION PROJECT | Fort, James | Hanson, Brady | None | PNNL_Demo_Thermal_M2-Final Rev 0.pdf | FCRD-UFD-2015-000119 | Thermal analysis; high burnup fuel; peak clad temperature
M3FT-15PN08100411 ULR. Draft. Supersedes M3FT-14PN0810032. | M3 | 1.02.08.10.04 | PNNL | FT-15PN081004 | ST Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Draft of M2 Report | Draft of M2 Report | Submit draft M2 report for comment. | 2015-01-30 15:00 | 42237.375 | 2015-08-17 03:00 |  | 2015 | Completed Late | THERMAL MODELING OF PROPOSED TN-32B CASK FOR HIGH BURNUP FUEL STORAGE DEMONSTRATION PROJECT | Fort, James | Hanson, Brady | None | PNNL_Demo_Thermal_M3.docx | FCRD-UFD-2015-000490 | Thermal Analysis; Peak Clad Temperature
M4FT-15OR0805032 URL. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.08.05.03 | ORNL | FT-15OR080503 | ST Experiments - ORNL | Bevard, Bruce | Sorenson, Ken | Draft Report on Hydride Reorientation Testing of HBR Fuel | Draft Report on Hydride Reorientation Testing of HBR Fuel | Letter report on the results of reorienting the hydrides and testing 2-3 samples of HB Robinson high burnup SNF | 2015-05-21 02:00 | 2015-08-21 03:00 | 2015-08-21 |  | 2015 | Completed Late | FY 2015 Status Report: Draft Report on Hydride Reorientation Testing of H. B. Robinson Fuel | ORNL | Yan, Yong | None | ORNL_SPR-2015_404.pdf | FCRD-UFD-2015-000634
M2FT-16SN080308061 ULR. No SAND Number. Predecisional Draft. Replaced by one of Geoff Freeze's SAND Reports. MOVE to Disposal Spreadsheet. | M2 | 1.02.08.03.08.06 | SNL | FT-16SN08030806 | Site Geoscience Data Evaluation - SNL | Sassani, Dave | Mackinnon, Robert | Integrated Geoscience Data and Evaluation of Geologic Conditions for the Deep Borehole Field Test Site | Integrated Geoscience Data and Evaluation of Geologic Conditions for the Deep Borehole Field Test Site | This report will describe the synthesis of existing geoscience data for the DBFT site, including any additional collected site characterization data and laboratory data, and the development of a site geologic framework model that will be used as the basis for describing and evaluating thermal-hydro-mechanical-chemical (THMC) conditions at the site and at depth. | 2016-09-09 12:00 |  | 2016-09-09 02:00 | OUO report for milestone completed and emailed to internal DOE and UFD NTD etc. to complete | 2016 | Complete | Site Geoscience Guidelines and Data Evaluation for Deep Borehole Field Test | Sassani, David | Sassani, David | OUO |  | FCRD-UFD-2016-000073
M4FT-16SN080205011 OUO | M4 | 1.02.08.02.05.01 | SNL | FT-16SN08020501 | ST Security - SNL | Durbin, Sam | Sorenson, Ken | Investigations of the Economic Impact from Postulated Attacks against Spent Nuclear Fuel during Transport | Economic impact of an attack against spent nuclear fuel during transport | Report on the economic impact of an attack against spent nuclear fuel during transport. | 2016-07-29 10:00 | 2016-08-26 02:00 | 2016-08-26 02:00 |  | 2016 | Completed Late | Exploring Economic Impacts Associated with a Spent Nuclear Fuel Transportation Incident | Osborn, Doug | Osborn, Doug | OUO | QADocumentCover-SNF_Transport_Security_Econ_Eval.docx | FCRD-UFD-2016-000423 | spent nuclear fuel; sabotage; economics; consequence analysis
M2SF-17PN010203021 ULR. Predecisional Draft. Need to save in PDF format - is in Word format in SNL S&T Site. | M2 | 1.08.01.02.03.02 | PNNL | SF-17PN01020302 | Analysis - PNNL | Hanson, Brady | Sorenson, Ken | Updated Gap Analysis Report | Updated Gap Analysis Report | Gap Analysis Report Update | 2017-09-28 18:00 |  | 2017-09-28 06:00 | This is a DRAFT to go out to external review. Once comments are received and addressed, the document will be finalized, resubmitted, and made publicly available. | 2017 | Complete | Gap Analysis to Support Extended Storage and Transportation of Spent Nuclear Fuel: Five-Year Delta | Alsaed, Halim | Hanson, Brady | None | Gap Update Report DRAFT for External Review FINAL.pdf | SFWD-SFWST-2017-000005 | Gap Analysis
M3SF-17PN010202033 ULR. Predecisional Draft. | M3 | 1.08.01.02.02.03 | PNNL | SF-17PN01020203 | Transportation - PNNL | Hanson, Brady | Sorenson, Ken | ENSA/DOE Transport Cask Testing Support | Testing support | ENSA/DOE Transport Cask Testing Support | 2017-09-30 |  | 2017-09-28 03:00 | This report provides a high-level summary of a series of tests recently conducted of surrogate pressurized water reactor fuel assemblies in a transport cask during various modes of transportation. | 2017 | Complete | ENSA/DOE Rail Shock and Vibration Testing FY2017 Summary | Ross, Steven | Ross, Steven | None | ENSA Testing Summary_M3_092717.1pdf.pdf | SFWD-SFWST-2017-000036 | Rail shock, vibration testing, surrogate fuel rods, mechanical loads on fuel assembly components
M3SF-17SN0102010410 OUO. fed into M3SF-18SN010201047 | M3 | 1.08.01.02.01.04 | SNL | SF-17SN01020104 | Experiments - SNL | Bryan, Charles | Sorenson, Ken | Evaluation of Gas and Particle Transport through Stress Corrosion Cracks | Evaluation of Gas and Particle Transport through Stress Corrosion Cracks | The report will document the results of tests evaluating gas and particle transport through SCC cracks in spent nuclear fuel interim storage canisters. | 43362.25 |  |  | Planning and design have been initiated for these tests. | 2017 | On Schedule |  |  |  | None |  | SFWD-SFWST-2017-000224
M3SF-17SN010205011 | M3 | 1.08.01.02.05.01 | SNL | SF-17SN01020501 | Security - SNL | Durbin, Sam | Sorenson, Ken | Parametric economic evaluation of a security-related release of spent nuclear fuel during transport | Parametric economic evaluation of a security-related release of spent nuclear fuel during transport | SAND report | 2017-05-05 04:00 | 2017-06-30 04:00 | 2017-06-28 02:00 |  | 2017 | Completed Late | Exploring Economic Impacts Associated with a Spent Nuclear Fuel Dry Cask Storage Incident | Walton, Fotini | Walton, Fotini | None |  | SFWD-SFWST-2017-000038 | spent nuclear fuel; radiological sabotage; economics
M4SF-17OR010201024 | M4 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | Sorenson, Ken | Updated PIE report on NDE conducted in FY17 on the Sister Rods | FY17 PIE report | Report detailing all NDE results from testing conducted on the Sister Rods from March - August FY17. This report provides information on testing in the second half of the FY | 2017-08-25 |  | 2017-08-25 |  | 2017 | Complete | Sister Rod Nondestructive Examination Status Report FY2017 | Montgomery, Rose | Montgomery, Rose | None | M4SF - NDE Status report 2.pdf | SFWD-SFWST-2017-000088 | Sister Rods, NDE, Gamma Scan, Profilometry, Visual exams, crud,
M4SF-17OR010201025 | M4 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | Sorenson, Ken | Initial NDE testing Data on Sister Rods (Oct - March) FY17 | Mid-year status of NDE testing (Oct-March) | Report detailing the NDE test results collected from Oct - March on the Sister Rods | 2017-03-31 |  | 2017-03-31 |  | 2017 | Complete | Initial NDE testing Data on Sister Rods (Oct - March) FY17 | Montgomery, Rose | Montgomery, Rose | None | M4SF-17OR010201025 Sister Rod NDE Status Report (Oct to March 2017).pdf | SFWD-SFWST-2017-000089 | Sister Rods, Non-Destructive Examinations, NDE, Gamma Scans
M4SF-17OR010201028 ULR | M4 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John | Sorenson, Ken | Update Sister Rod Test Plan | Sister Rod DE Test Plan | utilizing input from PNNL and other stakeholders, update the Sister Rod test plan | 2017-01-27 |  | 2017-01-27 |  | 2017 | Complete | Post-Irradiation Examination Plan for High Burnup Demonstration Project Sister Rods | ORNL | Bevard, Bruce | None | Post Irradiation Examination Plan for High Burnup Demonstration Project_Draft.pdf | SFWD-SFWST-2017-000090 | Sister rods, spent nuclear fuel, post irradiation testing, NDE,
M5SF-17OR010201022 | M5 | 1.08.01.02.01.02 | ORNL | SF-17OR01020102 | Experiments - ORNL | Scaglione, John |  | Design Heater system for simulating dry cask storage vacuum drying | Heater System Conceptual Design | Conceptual design of the heater system that will be used to simulated the vacuum drying operation of dry cask storage | 2017-02-24 |  | 2017-02-24 |  | 2017 | Complete | Design of Heater System for Simulating Dry Cask Storage Environments on Fuel Rods | ORNL | Montgomery, Rose | None | Design Heater System - M5SF-17OR010201022 Rev. 0 final.pdf | SFWD-SFWST-2017-000166 | Full rod heater system; heated rod testing
M2SF-18PN010202014 | M2 | 1.08.01.02.02.01 | PNNL | SF-18PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | Structural Analyses of ENSA/DOE Rail Tests | Sturctural Analyses of ENSA/DOE Rail Tests | Document analyses conducted for the ENSA/DOE Rail Cask testing. | 2018-09-28 |  | 2018-09-28 03:00 | An email transmitting this milestone and confirming it was completed on time (9/28/18) was sent to the CAM and NTD on September 28, 2018. | 2018 | Complete | Modeling and Analysis of the ENSA/DOE Multimodal Transportation Campaign | Klymyshyn, Nicholas | Ross, Steven | None | Modeling M2 distribution.pdf |  | ENSA/DOE Multimodal Transportation, used nuclear fuel, model validation, specific transportation
M2SF-18SN0102010410 OUO, Export Control | M2 | 1.08.01.02.01.04 | SNL | SF-18SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | A Probabilistic Model for Stress Corrosion Cracking | A Probabilistic Model for Stress Corrosion Cracking | Document work done on development of crack propagation modeling. | 2018-09-21 |  | 2018-09-21 02:00 | This M2 report documents updates in the SNL probabilistic model for stress corrosion cracking of spent nuclear fuel storage canisters. This version of the model implements a more mechanistic model for dust deposition, and salt accumulation, onto the canister surfaces, as well as improved approaches for pit growth and crack initiation. | 2018 | Complete | Interim Report: Uncertainty Quantification of Environmentally Assisted Stress Corrosion Cracking in Used Fuel Canisters | O'Brien, CJ | Dingreville, Remi | None | M2SF-18SN0102010410.pdf |  | stress corrosion cracking, spent nuclear fuel, interim storage, probabilistic model
M5SF-18OR0102010213 | M5 | 1.08.01.02.01.02 | ORNL | SF-18OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | None | Aerosol Collection system requirements | Aerosol Collection System Requirements | Develop the requirements for the aerosol collection system | 2018-01-31 |  | 2018-01-31 |  | 2018 | Complete | Aerosol Collection System Requirements | Montgomery, Rose | Bevard, Bruce | None | M5SF-18OR0102010213 Aerosol Collection System Requirements.pdf | SFWD-SFWST-2018-000486 | Spent nuclear fuel; aerosol collection system, Destructive testing
M5SF-18OR010201083 | M5 | 1.08.01.02.01.08 | ORNL | SF-18OR01020108 | Stress Corrosion Cracking - ORNL | Scaglione, John | None | Literatue review and data compilation | Completion of literature review and data for model development | Literature review and compilation of available data on (i) DPC characteristics, e.g., pressure, temperature, heat load, environmental conditions, etc. (ii) particle size distribution within DPC for various scenarios, (iii) SCC crack characteristics, e.g., size, opening, roughness, etc., (iv) past experiments involving aerosol transport. | 2018-07-09 |  | 2018-07-09 |  | 2018 | Complete | Completion of Literature Review and Data for Model Development | Chatzidakis | Scaglione, John | None
M2SF-19OR010201028 Supersedes M2SF-18OR010201027 | M2 | 1.08.01.02.01.02 | ORNL | SF-19OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | ORNL FY18 Results of FY18 Sister Pin Destructive Tests | Sister Pin Destructive Examination Results (1st Half FY19) | ORNL FY18 Results of FY18 Sister Pin Destructive Tests | 2019-03-29 |  |  | The DE test results are being compiled and will be provided in the report on schedule. | 2019 | 90 Day |  |  |  | None
M2SF-19PN010201032 Predecisional Draft. | M2 | 1.08.01.02.01.03 | PNNL | SF-19PN01020103 | Sister Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | PNNL FY18 Phase 1 Initial Sister Rod Destructive Examination Results | PNNL Phase 1 Initial Sister Rod Destructive Examination Results | Cut segments, dissolve fuel, perform axial tensile, 4 pt bend, and burst tests. Perform metallography and total hydrogen content. Analyze data and write M2 report. | 2019-03-22 |  |  | On schedule. | 2019 | 90 Day |  |  |  | None
M2SF-19SN010203035 | M2 | 1.08.01.02.03.03 | SNL | SF-19SN01020303 | Analysis - SNL | Durbin, Sam | Saltzstein, Sylvia | Documentation of Validation Exercises from the Dry Cask Simulator | Documentation of Validation Exercises from the Dry Cask Simulator | Results from the DCS validation exercises | 2019-05-30 |  |  | On schedule. Major results and modeling descriptions received from contributors. Draft manuscript is 75%. | 2019 | On Schedule |  |  |  | None
M3SF-19SN0102010413 | M3 | 1.08.01.02.01.04 | SNL | SF-19SN01020104 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Provide information to SRNL for Consequence Analysis of Moisture After Drying | SNL Contribution to Consequence Analysis for Moisture Remaining in Dry Storage Canisters After Drying | This report will document work done at SNL in support of the consequence analysis of residual moisture in SNF storage canisters carried out by SRNL | 2019-07-12 |  |  | We are still determining the scope of this small project. | 2019 | On Schedule |  |  |  | None
M4SF-19OR0102010210 | M4 | 1.08.01.02.01.02 | ORNL | SF-19OR01020102 | Sister Pin Testing - ORNL | Scaglione, John | Saltzstein, Sylvia | Support Validation of CASL fuel performance codes | NDE and DE Data and Analyses Provided to CASL | Report documenting blind modeling results with existing CASL fuel performance codes (e.g., BISON, MAMBA). These results will be cross compared to PIE data for understanding modeling capabilites and uncertainties | 2019-06-28 |  |  | On schedule | 2019 | On Schedule |  |  |  | None
M4SF-19OR010201074 | M4 | 1.08.01.02.01.07 | ORNL | SF-19OR01020107 | Stress Corrosion Cracking - ORNL | Scaglione, John | Saltzstein, Sylvia | Summary report on model validation | Aerosol transport through cracks model validation | Report documenting model validation based on Sandia’s test results | 2019-06-30 |  |  | On schedule | 2019 | On Schedule |  |  |  | None
M2SF-19SN010401013 supercedes M2SF-18010401013 | M2 | 1.08.01.04.01.01 | SNL | SF-19SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Implement Search and Reporting Capability of Legacy Content | Complete user acceptance testing report for Search and Reporting Capability of Legacy Content | Implement Search and Reporting Capability of Legacy Content | 2019-08-31 |  |  | Milestone is on-schedule. | 2019 | Complete |  |  |  | None
M2SF-19SN010401015 | M2 | 1.08.01.04.01.01 | SNL | SF-19SN01040101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Design and Develop Priority One Legacy Application Functions | Complete design document to be used for development of Priorty one legacy applications based on requirements. | First phase of Design and Development of Priority One Legacy Application Functions | 2019-09-30 |  | 2019-09-30 |  | 2019 | Complete |  |  |  | None
M3SF-19OR010201072 supercedes M3SF-18OR01021082 | M3 | 1.08.01.02.01.07 | ORNL | SF-19OR01020107 | Stress Corrosion Cracking - ORNL | Scaglione, John | Saltzstein, Sylvia | Summary Report on Aerosol Transport Through Cracks Modeling | SCC Aerosol Transport Model Summary Report | Report documenting model development and validation needs and gaps. | 2018-12-20 |  | 2018-12-20 |  | 2019 | Complete | SCC Aerosol Transport Model Summary Report | Chatzidakis | Scaglione, John | None | Chatzidakis_SCC Aerosol Transport Model Report_20181220_Final.pdf |  | aerosol transport
M3SF-19OR010203016 | M3 | 1.08.01.02.03.01 | ORNL | SF-19OR01020301 | Analysis - ORNL | Scaglione, John | Saltzstein, Sylvia | Status report on sensitivity data file search capability development for UNF-ST&DARDS | Status report on sensitivity data file search capability development for UNF-ST&DARDS | Report documenting benchmark sensitivity data file development and search capability integration into UNF-ST&DARDS | 2019-09-02 |  | 2019-09-02 | On schedule | 2019 | Complete |  |  |  | None
M3SF-19PN010202013 | M3 | 1.08.01.02.02.01 | PNNL | SF-19PN01020201 | Transportation - PNNL | Hanson, Brady | Saltzstein, Sylvia | Updated MMTT Study | Updated ENSA/DOE MMTT Report | Perform additional modeling of the ENSA/DOE transportation test including modeling performance assuming an Atlas rail car. | 2019-08-16 |  | 2019-08-16 | On schedule. | 2019 | Complete |  |  |  | None
M3SF-19PN010203022 supercedes M3SF-18PN010203028 | M3 | 1.08.01.02.03.02 | PNNL | SF-19PN01020302 | Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | FAST/FRAPCON modeling of sister rods | FAST Models of Sister Rods | Use the FAST/FRAPCON code family to model end of life rod internal pressure, oxide layer and CRUD layer thicknesses, clad thinning, etc. and compare against NDE data from ORNL and rod puncture data. | 2018-11-16 |  | 2018-11-16 09:00 |  | 2019 | Complete | Sister Rod Thermomechanical Modeling with FAST | Geelhood, Kenneth | Hanson, Brady | None | Report of Sister Pin Modeling with FAST-finaldraft1.pdf |  | FAST, FRAPCON, sister rods, modeling, cask, fuel rods
M3SF-20PN010201038- Superseded by M3SF-21PN010201056 | M3 | 1.08.01.02.01.03 | PNNL | SF-20PN01020103 | Sibling Pin Testing - PNNL | Hanson, Brady | Saltzstein, Sylvia | Draft of M2 FY20 Sibling Pin Testing Results | Draft for Programmatic Review of FY20 Sibling Pin Testing Results | Document results of sibling pin testing performed during FY20 | 2020-10-30 |  |  | On schedule, but data will be limited due to COVID shutdown and delays. | 2020 | 90 Day |  |  |  | None
M2SF-20SN010201062 | M2 | 1.08.01.02.01 | SNL | SF-20SN01020106 | HBU Demo Support - SNL | Sassani, Dave | Saltzstein, Sylvia | Storage and Transportation R&D Five-Year Plan | Storage and Transportation R&D Five-Year Plan | This draft 5-Year R&D Plan is largely based on Teague et al. (2019), which is a condensed version of the previous gap reports (Hanson et al. 2012, Hanson and Alsaed 2019, with up-dated gap priority assessments. After addressing and resolving DOE Policy Review comments, this draft will become a final report. | 2020-08-28 |  | 2020-08-28 | Draft internal-use report. Technical review complete. Emailed to DOE LEad for DOE Policy review. After addressing and resolving DOE Policy Review comments, this draft will become a final report. | 2020 | Complete | Spent Fuel and Waste Science and Technology Storage and Transportation 5-Year R&D Plan | Sylvia Saltzstein | Sylvia Saltzstein | Draft report- internal use only
M3SF-20SR010207029 | M3 | 1.08.01.02.07.02 | SRNL | SF-20SR01020702 | Water Consequences - SRNL | Carter, Joe | Saltzstein, Sylvia | Radiolysis evaluation of bound water in hydrated oxides | Radiolysis evaluation of bound water in hydrated oxides | Radiolysis evaluation of bound water in hydrated oxides | 2020-08-01 |  | 2020-08-01 | This report provides a best-estimate evaluation of residual water content (post-dry out) in the High Burnup (HBU) LWR Spent Fuel Demonstration project TN-32 cask, and evaluates the radiolysis of the residual free water, and the physisorbed and chemisorbed waters on the surfaces of the fuel and cask internal contents. | 2020 | Complete | Evaluation of Hydrogen Generation in High Burnup Demonstration Dry Storage Cask | A. L. d'Entremont, R. L. Kesterson and R. L. Sindelar | R. L. Sindelar | None | SRNL-STI-2020-00268_000.pdf |  | Hydrogen Generation Dry Storage
M4SF-20OR010201052 | M4 | 1.08.01.02.01.05 | ORNL | SF-20OR01020105 | Studsvik Cladding Integrity Program - ORNL | Bevard, Bruce | Saltzstein, Sylvia | Status of Studsvik Testing Plan and Activities | Status of Studsvik Testing Plan and Activities | This report provides a general description of the planned work in SCIP-IV. | 2020-09-30 |  | 2020-09-30 | This report is a status update of the work that occurred in the SCIP0IV international cooperation. | 2020 | Complete | Status Update on the SCIP-IV Program in 2020 | Bruce Bevard | Bruce Bevard | None | PB2001173_SCIP-IV_Final.pdf |  | SCIP-IV; Spent Fuel testing; High Burnup; LOCA; Back end;
M4SF-21OR010205012- OUO | M4 | 1.08.01.02.05 | ORNL | SF-21OR01020501 | Security - ORNL | Connolly, Kevin | Saltzstein, Sylvia | UAS Risk Profile Report | UAS Risk Profile Report |  | 2020-12-18 |  | 2020-12-18 | This report examines the relative security of spent nuclear fuel (SNF) and high-level radioactive waste (HLRW) during rail transport; provides a description of threats presented by unmanned systems, the types of unmanned systems or drones, and counter-measures to unmanned systems; and examines basic rail operations and operational planning for rail shipments of SNF and HLRW. This report also discusses several ways drone technology can be used against a shipment of SNF/HLRW. Further research, testing, and implementation of counter–unmanned system technology are crucial to the future security of SNF and HLRW. The US Department of Energy’s Oak Ridge National Laboratory and its partners have the resources and personnel to lead this effort in the rail transport space. | 2021 | Complete | Drone Considerations for Rail Conveyance Report | Oak Ridge National Laboratory | Kevin Connolly | OUO |  |  | drone, UAS, rail, SNF, transportation
M3SF-20OR0103050126- Superseded by M3SF-21OR010305125 | M3 | 1.08.01.03.05 | ORNL | SF-21OR01030512 | DPC Reactivity and Criticality Modeling - ORNL | Banerjee, Kaushik | Freeze, Geoff | DPC criticality analysis with fuel/basket modification | DPC criticality analysis with fuel/basket modification | This report uses three of the most reactive canisters that have been analyzed to-date using UNF-ST&DARDS to examine the performance of three potential reactivity suppression technologies under disposal conditions. Three already loaded canisters were analyzed using as-loaded contents including TSC-37 and MPC-32 pressurized water reactor (PWR) dual-purpose canisters (DPCs) and the MPC-89 DPCs. The reactivity suppression technologies considered were the B4C-filled disposal control rod assembly (DCRA) and the advanced neutron absorber (ANA)–based chevron insert for the PWR canisters and the ANA-based fuel channel replacement absorber for the MPC-89. For each combination of absorber concept and DPC, various insert patterns and absorber material concentrations were considered. The results of the analysis show that the DCRA concept has promise for providing reactivity hold-down for PWR DPCs, and the ANA fuel channel replacement absorber has promise for providing reactivity hold-down in BWR DPCs. The ANA chevron basket insert showed mixed results, providing sufficient reactivity hold-down in the lower reactivity canister, but failing to do so in the higher reactivity canister considered herein. | 2021-01-29 |  | 2021-01-29 | This report uses three of the most reactive canisters that have been analyzed to-date using UNF-ST&DARDS to examine the performance of three potential reactivity suppression technologies under disposal conditions. | 2021 | Complete | Basket Modification Concepts for Disposal Reactivity Control of Dual Purpose Canisters | Justin Clarity | Kaushik Banerjee | None | basket_modification_final.pdf
M3SF-21OR010207011 | M3 | 1.08.01.02.07.01 | ORNL | SF-21OR01020701 | Aerosol Source Term - ORNL | Montgomery, Rose | Saltzstein, Sylvia | Computational Model for Predicting Aerosol Retention in Cracks | Computational Model for Predicting Aerosol Retention in Cracks | Continue deposition modeling (note this is separate from and in addition to the deposition modeling as part of the SONGS lead canister). This modeling will focus on vertical systems and continue to apply various phenomena not currently in the model. Begin to validate against small scale data. | 2021-04-16 |  | 2021-04-16 | Complete | 2021 | Complete | Progress Report on Model Development for the Transport of Aerosol through Microchannels | Stylianos Chatzidakis, Yadu Sasikumar | Yadu Sasikumar | None | M3SF-21OR010207011_Progress Report on Model for Aerosol Transport_04162021.pdf |  | Aerosol; Canister Crack
M31UF042101 Need to doublecheck - Is this ULR? | M3 | 1.02.08.04 | SRNL | FTSR11UF0421 | Concept Evaluations | [8 empty] | Milestone revised by direction of CAM. A BCP is being processed. This milestone was moved to April, 2011 in order to allow sufficient review time by the cognizant laboratories. This move has been approved by the NTD. On schedule.
M41UF041703 ULR | M4 | 1.02.08.04 | SNL | FTSN11UF0417 | Concept Evaluations | [8 empty] | The milestone is on schedule -- there is no variance. | [6 empty] | FY11 rmdyear reportrev 0.docx
M4508031601 | M4 | 1.5.08.03 | SNL | SN1015080316 | Storage - Concept Evaluation
M4SF-21PN010208013 | M4 | 1.08.01.02.08.01 | PNNL | SF-21PN01020801 | Canister Deposition Field Demonstration - PNNL | Hanson, Brady | Saltzstein, Sylvia | Functions and Requirements for Lead Canister Field Test | Functions and Requirements for Lead Canister Field Test | Develop the Functions and Requirements for the lead canister to inform the test design. Document the results of the thermal and deposition modeling. | 2020-10-30 | 2021-08-30 |  | PowerPoint presentation prepared and presented to industry partners. Need to turn it into a report. | 2021 | Late |  |  |  | None
M3SF-21PN010203021 | M3 | 1.08.01.02.03.02 | PNNL | SF-21PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Thermal Sensitivity to Canister Internal Environment | Thermal Sensitivity to Canister Internal Environment | Report results of thermal modeling looking at component temperature changes as a function of canister internal pressure and composition. | 2021-05-28 | 2021-08-31 03:00 | 2021-08-30 | Delayed until 8/31/21 so staff can focus on the Deposition Demonstration models and to cover additional scope for this model. NTD and CAM gave concurrence. | 2021 | Complete | Sensitivity of Spent Fuel Temperatures to Variable Canister Backfills | CL Grant, CF Campbell, DJ Richmond | Brady Hanson | None | M3SF-21PN010203021_Canister_Enviroment_Sensitivity_Report_Final.pdf |  | thermal modeling, STAR-CCM+, COBRA-SFS, Canister Backfills
M4SF-21SR010203043- This milestone was completed with the submission of the drying standard for ballot per email. | M4 | 1.08.01.02.03.04 | SRNL | SF-21SR01020304 | Water Consequences - SRNL | Sindelar, Robert | Saltzstein, Sylvia | Revision to ASTM drying standard C1553 | Revision to ASTM drying standard C1553 | The revision to ASTM C1553-16 will be balloted in December. Comment resolution is expected at the February and the June ASTM C26.13 Fuels Task Group meetings. The Standard Guide C1553-21 is expected to be accepted for publication in August. | 2021-07-16 |  | 2021-07-13 | Comments from the May 2021 ASTM Joint C26 Main/Subcommittee Ballot process, and from the June 2021 Subcommittee C26.13 meeting were resolved. The ASTM C26 editor declared the changes made to be beyond editorial, and the standard re-re-balloting is in progress, closing September 6. Approval for publication of the revised standard guide as C1553-21 (2021 revision) is expected. | 2021 | Complete |  | Robert Sindelar | Robert Sindelar | None | This milestone was completed with the submission of the drying standard for ballot per email. |  | Ballpt
M2SF-21SN010207071 | M2 | 1.08.01.02.07.07 | SNL | SF-21SN01020707 | Aerosol Source Term - SNL | Durbin, Sam | Saltzstein, Sylvia | Continued Investigations of Respirable Release Fractions for SCC-Like Geometries | Continued Investigations of Respirable Release Fractions for SCC-Like Geometries | Report on source term evaluations from dry cask storage systems. | 2021-07-29 |  | 2021-07-29 | SAND Report | 2021 | Complete | Continued Investigations of Respirable Release Fractions for Stress Corrosion Crack-Like Geometries | Samuel Durbin | Samuel Durbin | None | Continued_Investigations_of_Respirable_Release_Fractions_for_SCC-Like_Geometries_v1.pdf |  | aerosol transmission; source term; stress corrosion crack; dry storage
M3SF-21PN010203029 | M3 | 1.08.01.02.03.02 | PNNL | SF-21PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Small scale drying tests | Small Scale Drying Test Update | Documentation of small scale drying tests | 2021-07-30 |  | 2021-08-06 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on August 5,2021. | 2021 | Complete | Small Scale Drying: FY21 Interim Report | Heather Colburn | Brady Hanson | None | M3SF-21PN010203029 FY21 Small Scale Drying Final.pdf |  | small scale drying tests
M3SF-21SN010207057 | M3 | 1.08.01.02.07.05 | SNL | SF-21SN01020705 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | Probabilistic Stress Corrosion Cracking Model for SNF Dry Storage Canisters | FY21 Status Report: Probabilistic Stress Corrosion Cracking Model for SNF Dry Storage Canisters | The M3 Milestone report will document work on the Sandia Probabilistic Model for Stress Corrosion Cracking of SNF Dry Storage Canisters. | 2021-07-30 |  | 2021-07-29 | This Level 3 milestone report documents updates to the Sandia National Laboratories probabilistic model for stress corrosion cracking. Specifically, it addresses changes in the submodels for stress corrosion crack growth rate, and in the maximum pit size model. Modifications to the approach for addressing dust/salt deposition also addressed; the existing model lacked sufficient data for parameterization, so a parametric approach ahs been implemented instead. | 2021 | Complete | FY21 Status Report: Probabilistic SCC Model for SNF Dry Storage Canisters | Nathan Porter, Dusty Brooks, Charles Bryan, Ryan Katona, Rebecca Schaller | Charles Bryan | None | SCC_FY21_M3SF-21SN010207057_SNL_Probabilistic_SCC_model.docx |  | stress corrosion cracking; spent nuclear fuel, long-term interim storage
M3SF-21SN010205023- Report notin PICS, emailed Sam Durbin | M3 | 1.08.01.02.05.02 | SNL | SF-21SN01020502 | Security - SNL | Durbin, Sam | Saltzstein, Sylvia | Radiation Effects on UAS Electronics | Investiagations of unmanned aerial systems (UAS) as part of adversary toolkit for transportation security-based scenarios | Classified or OUO report on UAS attacks against spent fuel transport | 2021-08-20 |  | 2021-08-20 | M3 deliverable on UAS camera performance in radiation fields of interest for spent fuel storage and transportation security events completed on schedule. | 2021 | Complete | Unmanned Aircraft System Component Radiation Effects | Luke Gilbert | Sam Durbin | None |  |  | spent nuclear fuel; unmanned aerial systems; cameras; radiation effects
M3SF-21AN010201016 | M3 | 1.08.01.02.01.01 | ANL | SF-21AN01020101 | Fuel Integrity Testing and Analysis - ANL | Billone, Mike | Saltzstein, Sylvia | Completion of Sibling Pin Ring Compression Testing (Ductility of Sibling Pin Cladding) | Ductility of Sibling Pin Cladding | Characterization and ring compression testing of sibling pin cladding with emphasis on ductility. | 2021-08-24 | 2021-10-27 |  | Testing is on schedule for generating data needed to meet this milestone. Therefore, the M3 is on schedule. | 2021 | On Schedule |  |  |  | None
M3SF-21PN010202014 | M3 | 1.08.01.02.02.01 | PNNL | SF-21PN01020201 | External Load Testing and Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Modeling and Analysis for Spent Nuclear Fuel Seismic Testing | Modeling and Analysis for Spent Nuclear Fuel Seismic Testing |  | 2021-08-27 |  | 2021-08-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on August 30, 2021. | 2021 | Complete | Modeling and Analysis for Spent Nuclear Fuel Seismic Testing | Nicholas Klymyshyn, Pavlo Ivanusa, Casey Spitz, Kevin Kadooka, CJ Taylor Mason, Ben Jensen, Judith Bamberger, Charlton Campbell, Deborah K Fagan | Brady Hanson | None | M3SF-21PN010202014 Seismic Test Plan PNNL.pdf |  | nuclear fuel; seismic testing
M3SF-21PN010208021 | M3 | 1.08.01.02.08.02 | PNNL | SF-21PN01020802 | SONGS Filter Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Filter Analysis | Filter Analysis for Particulate Release | Receive filters from SONGS, perform counting to determine radionuclide content, perform particle size analysis, and document in a report. | 2021-08-27 |  | 2022-08-26 | On schedule. This milestone replaces M3SF-20PN010207071. | 2021 | On Schedule |  |  |  | None
M3SF-21PN010207032- Not in PICS, emailed Brady Hanson | M3 | 1.08.01.02.07.03 | PNNL | SF-21PN01020703 | Canister Coatings for Prevention and Remediation - PNNL | Hanson, Brady | Saltzstein, Sylvia | M3 Cold Spray Update Report | FY21 Cold Spray Update | Document results from FY21 activities for cold spray | 2021-08-31 | 2021-09-30 |  | On schedule but scope will be greatly reduced due to COVID restrictions limiting access to the laboratory. | 2021 | On Schedule |  |  |  | None
M3SF-21SR010207082 | M3 | 1.08.01.02.07.08 | SRNL | SF-21SR01020708 | Stress Corrosion Cracking - SRNL | Sindelar, Robert | Saltzstein, Sylvia | Summary Report of the Canister Large Plate Crack Growth Testing | Summary Report of the Canister Large Plate Crack Growth Testing | The SRNL large plate testing, as report in FY20 M3 milestone SRNL-STI-2020-00315 will be completed. The plate will be NDE and DE examined, and a final report with the testing details and results will be issued. | 2021-08-31 |  | 2021-08-31 | This report is the comprehensive description of the completed experiment to evaluate the corrosion behavior of a large section of welded plate material harvested from the Sandia National Laboratories’ (SNL) full-size mockup of a spent nuclear fuel (SNF) dry storage canister. The plate was subjected to conditions aggressive to chloride-induced stress corrosion cracking for a total time of 2 years. The details of the establishment of this experiment, and the corrosion results are reported. This work is intended to inform aging management programs for SNF canisters under conditions of extended dry storage. | 2021 | Complete | Large Plate Experiment of Chloride-induced Stress Corrosion Cracking in Spent Nuclear Fuel Storage Canisters | Robert Sindelar | Robert Sindelar | None | SRNL_M3_CISCC M3SF-21SR010207022 (SRNL-STI-2021-00412)_00.pdf |  | Large Plate; Spent Nuclear Fuel
M4SF-21SR010205032- OUO and won't be uploaded to PICS | M4 | 1.08.01.02.05.03 | SRNL | SF-21SR01020503 | Security - SRNL | Carter, Joe | Saltzstein, Sylvia | Summary of Potential Mitigation Actions | Summary of Potential Mitigation Actions for UAS Attack | Summary of Potential Mitigation Actions for UAS Attack | 2021-08-31 |  | 2021-08-18 | The purpose of this report is to expand upon the report entitled Mitigating Unmanned Aerial System Attack and Rules of Engagement (SRNL-RP-2020-00335), dated August 25, 2020. Unmanned Aerial Systems (UAS) technology continues to evolve and pose significant risks to critical infrastructure and facilities. This report provides additional information on mitigating security related risks from UAS attack(s). | 2021 | Complete | Unmanned Aerial Systems Mitigation for Spent Nuclear Fuel Storage | Steven Whitcomb | Joe Carter | None
M2SF-21PN010208014 | M2 | 1.08.01.02.08.01 | PNNL | SF-21PN01020801 | Canister Deposition Field Demonstration - PNNL | Hanson, Brady | Saltzstein, Sylvia | Canister Deposition Field Demo Thermal and Deposition Modeling | Canister Deposition Field Demo Thermal and Deposition Modeling |  | 2021-09-03 |  | 2021-08-31 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on August 31, 2021. | 2021 | Complete | Thermal and Deposition Modeling of the Canister Deposition Field Demonstration | SR Suffield, PJ Jensen, BJ Jensen, R Ekre, JA Fort, WA Perkins, C Grant, BD Hanson, SB Ross | Brady Hanson | None | M2SF-21PN010208014 CDFD Thermal and Deposition Modeling PNNL.pdf |  | thermal & deposition modeling; spent nuclear fuel; canister deposition
M3SF-21SN010207062 | M3 | 1.08.01.02.07.06 | SNL | SF-21SN01020706 | Canister Coatings for Prevention and Remediation - SNL | Bryan, Charles | Saltzstein, Sylvia | SNF Canister Coatings for Corrosion Prevention and Mitigation | SNF Canister Coatings for Corrosion Prevention and Mitigation | This M3 report will document the status of work at Sandia National Laboratories to evaluate coatings for SNF dry storage canisters to mitigate or prevent canister SCC. | 2021-09-03 |  | 2021-09-02 | The M3 milestone documents research at Sandia National Laboratories evaluating coatings for spent nuclear fuel dry storage canisters to mitigate or repair stess corrosion cracking. In FY 21, this work largely consisted of issuing a request for information, identifying interested companies, and establishing an MOU with them for prepartion of samples to be tested at SNL. In addition, equipment for testing the coatings was purchased and preliminary testing to gain familiarity with the test methods was initiated. These are docmented in the milestone report. | 2021 | Complete | FY21 Status Report: SNF Canister Coatings for Corrosion Prevention and Mitigation | Andrew Knight, Brendan Nation, Chalres Bryan, Rebecca Schaller | Andrew Knight | None | M3SF-21SN010207062_Corrosion_Coatings_Report_FY2021_Final.pdf |  | stress corrosion cracking; corrosion-resistant coatings; mitigation; spent nuclear fuel; dry storage
M2SF-21PN010207027 | M2 | 1.08.01.02.07.02 | PNNL | SF-21PN01020702 | Stress Corrosion Cracking - PNNL | Hanson, Brady | Saltzstein, Sylvia | PNNL Stress Corrosion Cracking Testing Update | FY21 Effect of Environment and Material Condition on CISCC Growth of Stainless Steels |  | 2021-09-10 |  | 2021-09-10 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 10, 2021. | 2021 | Complete | Results form PNNL SCC Testing: FY2021 | MB Toloczko, FC Colon, RA Bouffioux | Brady Hanson | None | M2SF-21PN010207027_Results from PNNL SCC Testing_FY21_Final.pdf |  | chloride-induced stress corrosion crack measurement
M3SF-21PN0102030211 | M3 | 1.08.01.02.03.02 | PNNL | SF-21PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Sensor Development for Detection of Water | Sensor Development for Detection of Water | Documentation of FY21 work for detection of water remaining after drying. | 2021-09-10 |  | 2021-09-16 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 16, 2021. | 2021 | Complete | Sensor Development for Liquid Water Detection in Dry Storage Casks: FY2021 Status | Ryan M Meyer, Naveen Karri, Cody Christiansen, Morris S. Good | Brady Hanson | None | M3SF-21PN0102030211 PNNL Water Detection FY21 Final.pdf |  | Liquid water detection; ultrasonic sensing; dry storage casks
M3SF-21SN010202023 | M3 | 1.08.01.02.02.02 | SNL | SF-21SN01020202 | External Load Testing and Analysis - SNL | Kalinina, Elena | Saltzstein, Sylvia | Shaker Table Test Plan | Shaker Table Test Plan | Develop shaker table test plan | 2021-09-13 |  | 2021-09-13 | This report is a preliminary test plan of the seismic shake table test. | 2021 | Complete | Seismic Shake Table Test Plan | Elena Kalinina | Elena Kalinina | None | Seismic_Shake_Table Test_Plan_FINAL.pdf |  | shake table; ground motions; dry storage canister; storage overpack; spent nuclear fuel; surrogate assembly
M2SF-21SN010203033 | M2 | 1.08.01.02.03.03 | SNL | SF-21SN01020303 | Thermal and Drying - SNL | Durbin, Sam | Saltzstein, Sylvia | Simulation of Commercial Drying of Spent Nuclear Fuel | Simulation of Commercial Drying of Spent Nuclear Fuel | A report detailing the results from a near prototypic fuel assembly for drying cycle investigations. | 2021-09-23 |  | 2021-09-23 | Technical report completed on schedule. | 2021 | Complete | Update on the Simulation of Commercial Drying of Spent Nuclear Fuel | Samuel Durbin | Samuel Durbin | None | M2_Simulation_of_Commerical_Drying_of_SNF_v2.pdf |  | spent nuclear fuel; dry storage; drying; residual water
M2SF-21AN010201012- Not in PICS, emailed Mike Billone | M2 | 1.08.01.02.01.01 | ANL | SF-21AN01020101 | Fuel Integrity Testing and Analysis - ANL | Billone, Mike | Saltzstein, Sylvia | Completion of Sibling Pin Ring Compression Testing (Sibling Pin Ring Compression Results) | Sibling Pin Ring Compression Results | Conduct characterization and ring compression tests for defueled sibling pin cladding. | 2021-09-24 | 2021-10-29 |  | As the M3 for this milestone is on schedule, so is the M2. | 2021 | On Schedule |  |  |  | None
M2SF-21SN010207056 | M2 | 1.08.01.02.07.05 | SNL | SF-21SN01020705 | Stress Corrosion Cracking and Dry Storage Investigations - SNL | Bryan, Charles | Saltzstein, Sylvia | FY21 Status Report: SNF Storage Canister Corrosion Research at SNL | FY21 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | The M2 status report will summarize SNF storage canister investigations at Sandia National Laboratories in FY 21. | 2021-09-24 |  | 2021-09-24 | This L2 milestone report documents research performed at Sandia National Laboratories in FY21, supporting evaluation of stress corrosion cracking of spent nuclear fule dry storage canisters. The experimental and modeling work performed includes evaluation of potential canister surface environments, as well as corrosion testing to determine controlling factors for pitting and stress corrosion crack initiation and growth, as well as phrnomena controlling pit-to-crack transition. Finally, collaborative work wiht PNNL was also initiated, evaluating cold spray as a SCC mitigation technique. | 2021 | Complete | FY21 Status Report: SNF Interim Storage Canister Corrosion and Surface Environment Investigations | Charles Bryan, Rebecca Schaller, Andrew Knight, and others | Charles Bryan | None | M2SF-21SN010207056_SNL_Stress_Corrosion_Status_Report_FINAL.pdf |  | stress cororsion cracking; spent nuclear fuel; long-term interim storage
M3SF-21PN010202016 | M3 | 1.08.01.02.02.01 | PNNL | SF-21PN01020201 | External Load Testing and Analysis - PNNL | Hanson, Brady | Saltzstein, Sylvia | Mechanical Loads in the General 30 cm Cask Drop Scenario | Mechanical Loads in the General 30 cm Cask Drop Scenario |  | 2021-09-30 |  | 2021-09-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 30, 2021. | 2021 | Complete | Mechanical Loads on Spent Nuclear Fuel in the General 30 cm Package Drop Scenario | Nicholas Klymyshyn, Kevin Kadooka, Casey Spitz, James Fitzpatrick, Philip Jensen | Brady Hanson | None | M3SF-21PN010202016_Mechanical Loads in the General 30cm Cask Drop Scenario_FINAL.pdf |  | mechanical loads; package drop sccenario
M3SF-21PN010203025 | M3 | 1.08.01.02.03.02 | PNNL | SF-21PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Wind Effects on Horizontal Storage Temperatures | Wind Effects on Horizontal Storage Temperatures | Report on models of effects of wind on horizontal storage temperatures. | 2021-09-30 |  | 2021-09-30 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on September 30, 2021. | 2021 | Complete | Modeling Environmental Effects on Ventilated Spent Fuel Storage Systems | Ben Jensen, Sarah Suffield, Megan Higley, Brian Hom, James Fort | Brady Hanson | None | M3SF-21PN010203025_Wind_Effects_Thermal_and_Flow_Modeling_FINAL.pdf |  | external environment wind effects; spent nuclear fuel; dry storage systems.
M3SF-21PN010203027 | M3 | 1.08.01.02.03.02 | PNNL | SF-21PN01020302 | Thermal and Drying - PNNL | Hanson, Brady | Saltzstein, Sylvia | Uncertainty Analysis for Thermal Modeling | Uncertainty Analysis for Thermal Modeling | Documentation of uncertainty analysis | 2021-09-30 | 2022-02-18 03:00 |  | Delayed until FY22 (2/18/22) with concurrence of NTD and CAM. | 2021 | Expected Late |  |  |  | None
M3SF-21OR010201038 | M3 | 1.08.01.02.01.03 | ORNL | SF-21OR01020103 | Fuel Integrity Testing and Analysis - ORNL | Montgomery, Rose | Saltzstein, Sylvia | FY2021 ORNL Report on High Burnup Sibling Pin Testing Results | ORNL Sibling Rod Testing Results (FY21) | M3 report (draft for the M2 Deliverable listed separately) of the testing results achieved in FY21 | 2021-10-29 |  | 2021-10-29 | The M3 provides a draft report of FY21 activities and accomplishments for programmatic review and comment. | 2021 | Complete | Sister Rod Destructive Examinations (FY21) | Rose Montgomery | Rose Montgomery | None | Sister Rod Destructive Testing _ Main 10292021_final.pdf |  | high burnup spent fuel data project

## NE 82 FY13-FY21
Milestone ID Number | Level | WBS | Site | WP Number | WP Title | WPM | CAM | Milestone Title | Deliverable Title | Deliverable Description | Estimated Finish | Revised Finish | Actual Finish | Narrative | FY | Status | Main Document Title | Document Author/Creator | Document Owner | CUI Type | Uploaded Document Name | DMS Tracking Number | Keywords
M4FT-13AN09020125 | M4 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL | Nutt, Mark | Nutt, Mark | TSL Assessment (Worker Exposure, Blending/Aging) | TSL Assessment (Worker Exposure, Blending/Aging) | Report describing TSL Assessment of worker exposure and blending/aging using FY12 System Architecture Cases | 2013-08-30 07:00 | 2013-09-30 01:00 | 2013-09-25 01:00 | Analyses were completed on 9/25/03 concurrent with completion of M3FT-13AN09020127 | 2013 | Completed Late |  | Not Applicable | Not Applicable | None
M4FT-13AN09020135 | M4 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL |  | Nutt, Mark | TSM Version 7 Support Documents | TSM Version 7 Support Documents | Documents supporting TSM Version 7. 1) TSM Version 7 Requirements Traceability Matrix, 2) TSM Version 7 Design Documents, 3) TSM Version 7 Validation Reports | 2014-01-17 03:00 |  |  | On schedule | 2013 | On Schedule |  |  |  | None
M4FT-13AN09020136 | M4 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL |  | Nutt, Mark | TSM Development Documents | TSM Development Documents | TSM Management Plan, TSM Procedure for CI Chagnes | 2014-01-17 02:00 |  |  | On schedule | 2013 | On Schedule |  |  |  | None
M4FT-13AN0902064 | M4 | 1.02.09.02.06 | ANL | FT-13AN090206 | Execution Strategy Analysis - ANL |  | Nutt, Mark | Success Precedence Diagram | Success Precedence Diagram and Description | Completed Success Precedence Diagram and Description | 2013-10-31 05:00 |  |  | On schedule | 2013 | 90 Day |  |  |  | None
M4FT-13AN0902065 | M4 | 1.02.09.02.06 | ANL | FT-13AN090206 | Execution Strategy Analysis - ANL |  | Nutt, Mark | Risk Elicitation | Risk Elicitation Summary Report | Risk Elicitation Summary Report | 2013-11-29 03:00 |  |  | Not yet begun | 2013 | 90 Day |  |  |  | None
M4FT-13OR0902023 | M4 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | Conduct Pool Density Sensitivity Study on Facility Size and Operations | Pool Density Sensitivity Study on Waste Management Facility Sizes and Operations | This study will evaluate the potential implications of "open-rack" pool configurations and densly packed pool configurations on size and operations for wet (pool) storage consolidated storage facility concepts and repackaging facility concepts described in the FY2012 Systems Architecture Study | 2013-08-30 02:00 |  | 2013-08-30 02:00 |  | 2013 | Complete |  |  |  | None
M4FT-13OR0902028 | M4 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | Initial Draft Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilities | Draft Preliminary Site Factors and Considerations for Used Nuclear Fuel Interim Storage Facilities | Update information originally captured in the Preliminary Site Requirements and Considersations for Monitoried Retrieable Storage Facility (DOE/RW-0315P) using input from current regulatory requirements, U.S. experience over the paste two decades (e.g., PFS), international experience and the evolving policy for managaging used nuclear fuel. | 2013-08-30 04:00 |  | 2013-08-30 02:00 |  | 2013 | Complete |  |  |  | None
M4FT-13OR0903033 | M4 | 1.02.09.03.03 | ORNL | FT-13OR090303 | Data collection and database synthesis in support of waste acceptance - ORNL | Scaglione, John | Nutt, Mark | Status of Vendor meeting outcome and proposed path forward for data acquisition | Whitepaper on Vendor Data Collection Efforts | Whitepaper on meeting outcome with Vendors and how to proceed forward | 2013-09-30 | 2013-12-20 | 2014-05-06 | Ready FY14 pending funding | 2013 | Expected Late | NFST Project Summary-NEI | Scaglione, John | Scaglione, John | None
M4FT-13OR0904031 | M4 | 1.02.09.04.03 | ORNL | FT-13OR090403 | Standard Canisters - ORNL | Howard, Rob | Wagner, John | Revise Implimentation Plan for Standardized Canisters and Feasibility of Direct Disposal of DPCs | Plan for the Development and Evaluation of Standardized Canister Concepts | 1. Revise "Implementation Plan for the Development and Licensing of Standardized Transportation, Aging, and Disposal Canisters and the Feasibility of Direct Disposal of Dual Purpose Canisters," FCRD-UFD-2012-000106 to reflect DOE’s evolving approach with industry involvement and separate Standardized Canister System activities from Direct Disposal of Dual Purpose Canisters into separate documents (ORNL lead, ANL and SNL support) | 2013-01-25 02:00 |  | 2013-01-25 |  | 2013 | Complete |  | Howard, Rob | ORNL | None |  | FCRD-NFST-2013-000089
M4FT-13OR09140620 | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Update report documenting UNF assembly models | Updated report documenting UNF assembly models | Update M4 deliverable to document new assembly models that have been incorporated into the database system | 2013-09-13 02:00 | 2013-11-01 | 2014-01-15 | Document is in internal review | 2013 | Expected Late | Fuel Assembly Modeling for the Modeling and Simulation Toolset | Smith, | Scaglione, John | None
M4FT-13OR09140621 | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Update report documenting models for criticality analyses | Updated report documenting models for criticality evaluations | Updated report documenting new criticality models that have been added to overall database system | 2013-09-30 02:00 |  | 2013-09-30 | Milestone complete | 2013 | Complete |  | Banerjee, Kaushik | Scaglione, John | None |  |  | criticality, storage, cask, burnup credit
M4FT-13OR09140623 | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL |  | Wagner, John | Letter report documenting model templates for vaccuum drying | Vaccuum drying model template report | Letter report, documenting template file development including test cases and expected test case results, identification of parameters necessary for performing detailed evaluations, and establishing rule-based methodology for determining appropriate bounding estimates for these parameters if detailed drying data information is not available. | 2013-09-30 | 2013-10-31 |  | Document on track for completion by revised finish date of 10/31/2013. | 2013 | Expected Late |  |  |  | None
M4FT-14AN09020511 | M4 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | Status Report: Assessment of Advanced Re-Packaging Techniques and R&D Gaps (Dry, Automated, Remote) | Status Report: Assessment of Advanced Re-Packaging Techniques and R&D Gaps (Dry, Automated, Remote) | Status report on the continued assessment of advanced re-packaging techniques. | 2014-07-31 05:00 | 2014-08-15 01:00 | 2014-08-14 01:00 |  | 2014 | Completed Late | Simulation and Assessment of Advanced UNF Handling Techniques | Park, Young | Park, Young | None |  | FCRD-NFST-2014-000525
M4FT-14AN09020523 | M4 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | TSM Version 7 Supporting Documents | TSM Version 7 Support Documents | Documents supporting TSM Version 7. 1) TSM Version 7 Requirements Traceability Matrix, 2) TSM Version 7 Design Documents, 3) TSM Version 7 Validation Reports | 2014-01-17 04:00 |  | 2014-01-17 03:00 |  | 2014 | Complete | ?TSM Version 7 Supporting Documents | Terranear PMC | Terranear PMC | None |  | FCRD-NFST-2014-000527
M4FT-14AN09020524 | M4 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | TSM Development Documents | TSM Development Documents | TSM Management Plan, TSM Procedure for CI Chagnes | 2014-01-17 04:00 |  | 2013-12-30 01:00 |  | 2014 | Complete | ?TSM Development Documents | Terranear PMC | Terranear PMC | None |  | FCRD-NFST-2014-000528
M4FT-14AN0902112 | M4 | 1.02.09.02.11 | ANL | FT-14AN090211 | Execution Strategy Analysis - ANL | Nutt, Mark | Nutt, Mark | Risk Elicitation | Risk Elicitation Summary Report | Risk Elicitation Summary Report | 2013-11-29 05:00 |  | 2013-11-21 01:00 |  | 2014 | Complete | ?Risk Elicitation |  |  | None |  | FCRD-NFST-2014-000536
M4FT-14OR0902092 | M4 | 1.02.09.02.09 | ORNL | FT-14OR090209 | Waste Management Functional and Operational Requirements - ORNL | Howard, Rob | Nutt, Mark | ORNL Input on Functions and Requirements Rationale and Bases | ORNL Input on Functions and Requirements Rationale and Bases | ORNL will provide a brief status report on Functions and Requiremments Rationale and Bases Development | 2014-04-30 |  | 2014-04-30 |  | 2014 | Complete | ORNL Input on Functions and Requirements Rationale and Bases FCRD-NFST-2014-000534 | Singley, Paul | Howard, Rob | None |  | FCRD-NFST-2014-000534 | Fleet Maintance Facility Requirememts
M4FT-14OR0905016 | M4 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Draft assessment of NFST safety analysis capabilities for selected shutdown reactor sites | Draft assessment of NFST safety analysis capabilities for selected shutdown reactor sites | Draft M2 report documenting nuclear safety characteristics of as-loaded casks | 2014-08-12 02:00 | 2014-09-03 | 2014-09-03 | Draft report completed 9/3/2014 | 2014 | Completed Late | Safety Analysis Capabilities Assessment of the Used Nuclear Fuel Storage, Transportation& Disposal Analysis Resource and Data System For Selected Shutdown Reactor Sites (DRAFT) | ORNL | Scaglione, John | None |  | FCRD-NFST-2014-000541
M4FT-14OR0910012 | M4 | 1.02.09.10.01 | ORNL | FT-14OR091001 | Storage Design - ORNL | Howard, Rob | Carter, Joe | ORNL Status Report on Design Concept Trade Studies | ORNL Status Report on Design Option Trade Studies | ORNL status report on Design Concept Trade Studies | 2014-02-28 |  | 2014-02-28 |  | 2014 | Complete | Status Report On Design Concept Trade Studies: Fleet Maintenance Functional Requirements and Technical Trades | Singley, Paul | Howard, Rob | None | Fleet_Maintenance_Requirements draft R2c.docx | FCRD-NFST-2014-000542 | Rail Car,AAR-2043, Fleet Maintenance
M4FT-14SN0912042 | M4 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Sorenson, Ken | Feldman, Matt | Online "help" utility in RADCAT | Online RADTRAN hELP | Appropriate sections of the User Ghuide will be adapted to an online format and a Help utility will be designed and implemented in RacDat | 2014-05-16 22:00 | 2014-07-18 02:00 | 2014-07-31 02:00 |  | 2014 | Completed Late | This deliverable is not a report |  |  | None |  | FCRD-NFST-2014-000547
M4FT-14SN0912044 | M4 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Sorenson, Ken | Feldman, Matt | Succession plan for RADTRAN | Succession pland report | The milestone is a report naming a potential successor, the assessment of his or her suitability, and further plans for his or her responsibilities. Succession planning is an integral part of the activities in this work package, so relatively little extra description is needed. | 2014-07-14 14:00 |  | 2014-07-31 02:00 |  | 2014 | Completed Late | Deliverable is not a report. |  |  | None |  | FCRD-NFST-2014-000548
M4FT-15AN0902042 | M4 | 1.02.09.02.04 | ANL | FT-15AN090204 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM Phase 2 – Prototype 1 | Demonstration of Phase 2 – Prototype 1 | Development of NGSAM Phase 2 - Prototype 1 | 2015-02-20 12:00 |  | 2015-02-18 01:00 |  | 2015 | Complete | MF4T-15AN0902042 NGSAM Phase 2 – Prototype 1 |  |  | None |  | FCRD-NFST-2015-000556
M4FT-15AN0902043 | M4 | 1.02.09.02.04 | ANL | FT-15AN090204 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM Phase 2 – Prototype 2 | Demonstration of Phase 2 – Prototype 1 | Development of NGSAM Phase 2 - Prototype 2 | 2015-09-18 13:00 |  | 2015-09-18 05:00 | Completed the NGSAM Phase 2 - Prototype 2 "At-Reactor" software with link to the Unified DB | 2015 | Complete | Transition Plan for Next-Generation Waste Management System Analysis Modeling Tool |  |  | None |  | FCRD-NFST-2015-000557 | NGSAM, Phase 2, System Analysis
M4FT-15AN0907012 | M4 | 1.02.09.07.01 | ANL | FT-15AN090701 | NEPA - ANL | Nutt, Mark | Carter, Joe | Draft Environmental Considerations Report Outline | Draft Environmental Considerations Report Outline | Draft of table of contents and outline | 2015-07-17 03:00 |  | 2015-07-15 01:00 |  | 2015 | Complete | Draft Outline: ENVIRONMENTAL CONSIDERATIONS FOR FUTURE CONSOLIDATED INTERIM STORAGE OF SPENT NUCLEAR FUEL | NFST ECR Team | Macdonell, Margaret | None |  | FCRD-NFST-2015-000813
M4FT-15ID09110211 | M4 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Conduct START Training Workshop | Conduct START Training Workshop | Conduct START Training Workshop | 2015-08-31 06:00 |  | 2015-08-03 02:00 |  | 2015 | Complete | Conduct START Training Workshop |  |  | None |  | FCRD-NFST-2015-000565
M4FT-15ID0912054 | M4 | 1.02.09.12.05 | DOE-ID | FT-15ID091205 | TR: Operational - DOE-ID | Helvey, Elizabeth | Feldman, Matt | Develop and Release START Version 1.2 User/Technical Manual | START Version 1.2 User/Technical Manual | Develop and Release START Version 1.2 User/Technical Manual | 2015-06-30 06:00 | 2015-07-03 04:00 | 2015-06-30 04:00 |  | 2015 | Complete |  |  |  | None |  | FCRD-NFST-2015-000567
M4FT-15OR0902077 | M4 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Waste Management Systems Analysis Data ID, Collection, and Verification, Revision 2 | Data Report #2 | Continue to identify, collect, and verify input data needed to conduct integrated waste management system analyses. Integrate with UNF-ST&DARDS database development. Potential areas to assess are listed below: -Reactor site physical characteristics (i.e., pool capacity, crane capacity, rail access) -Reactor site dry storage cask mapping -Transportation logistics and costs. Review and update the document "Data Identification and Verification for Waste Management System Analyses," Revision 1 by addressing to identify gaps, address the gaps, and then issue the results as Revision 2. | 2015-09-30 01:00 |  | 2015-09-30 | The current revision of this document represents a major rewrite and expansion of many of the sections included in this text. In particular an effort was made towards crafting a document that would be more useful to the systems analyst who will require the data described herein. | 2015 | Complete | Data Identification and Verification for Waste Management System Analyses | van den Akker, Bret | Jarrell, Josh | None | 2015-09-30_WMS_Data_ID-Rev2_M4.pdf | FCRD-NFST-2015-000647
M4FT-15OR0903013 | M4 | 1.02.09.03.01 | ORNL | FT-15OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Joseph, Robby | Jarrell, Josh | Update CURIE User Manual | Update CURIE User Manual | Update the CURIE User Manual. | 2015-09-30 01:00 |  | 2015-09-30 | The attached document entitled “CURIE User Manual” satisfies the Level 4 Milestone, M4FT-15OR0903013, entitled “Update CURIE User Manual.” This document presents the user manual for using the Centralized Used Fuel Resource for Information Exchange (CURIE) website. It is intended to help users find resources, upload documents, and generally work more effectively with CURIE. | 2015 | Complete | CURIE User Manual |  |  | None | CURIE_Manual_Final_09_30_15.pdf | FCRD-NFST-2015-000652
M4FT-15OR0905013 | M4 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Incorporate fuel projection methodology into UNF-ST&DARDS | Incorporate fuel projection methodology into UNF-ST&DARDS | Automate fuel projection methodology in UNF-ST&DARDS based on SRNL deliverable to facilitate dynamic scenario updating. | 2015-06-30 04:00 | 2015-09-30 | 2015-09-30 | The projection methodology will be implemented in UNF-ST&DARDS version 3 (M2FT-16OR090105011) with the help of Savannah River National Laboratory | 2015 | Completed Late | N/A |  |  | None |  | FCRD-NFST-2015-000656
M4FT-15OR0906012 | M4 | 1.02.09.06.01 | ORNL | FT-15OR090601 | Regulatory - ORNL | Howard, Rob | Carter, Joe | Initital Regulatory Scope of Topical Safety Analysis Report | Initital Regulatory Interactions Summary Report | Letter Report documenting the results of preliminary discussions with Nuclear Regulatory Commission Staff regarding regulatory issues associated with a potential Topical Safety Analysis Report for a Pilot ISF. | 2015-01-30 01:00 | 2015-08-31 | 2015-07-15 |  | 2015 | Completed Late | Strategy for Licensing a Consolidated Interim Used Fuel Storage Facility | Howard, Rob | Howard, Rob | OUO |  | FCRD-NFST-2015-000658
M4FT-15PN0912037 | M4 | 1.02.09.12.03 | PNNL | FT-15PN091203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Revised Draft Shutdown Sites Report | Revised Draft Shutdown Sites Report | Revised shutdown sites draft report. | 2015-07-24 03:00 |  | 2015-07-23 03:00 |  | 2015 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Maheras, Steve | Maheras, Steve | None | FCRD-NFST-2015-000704_M4_signed.pdf | FCRD-NFST-2015-000704 | Used nuclear fuel, shutdown sites, on-site infrastructure, near-site transportation infrastructure
M4FT-15SR0904042 | M4 | 1.02.09.04.04 | SRNL | FT-15SR090404 | CX: Standardization and Integration - SRNL | Carter, Joe | Howard, Rob | Summary of STAD Disposal Concept Cost Estimates | Summary of STAD Disposal Concept Cost Estimates | Summarize the various STAD disposal concept cost estimates (developed by UFD) for use in the standarization study | 2015-05-29 01:00 |  | 2015-05-29 |  | 2015 | Complete | Summary of STAD Disposal Concept Cost Estimates | Severynse, Tom | Severynse, Tom | None |  | FCRD-NFST-2015-000742 | STAD Disposal
M4FT-15SR0904043 | M4 | 1.02.09.04.04 | SRNL | FT-15SR090404 | CX: Standardization and Integration - SRNL | Carter, Joe | Howard, Rob | Summary of TO 16 STAD Receipt and Storage Concept Cost Estimates | Summary of TO 16 STAD Receipt and Storage Concept Cost Estimates | Provide a summary of the STAD receipt and storage concepts cost estimates developed under TO 16. | 2015-05-29 01:00 | 2015-06-19 | 2015-05-29 |  | 2015 | Complete | Summary to 16 STAD Receipt and Storage Concept Cost Estimates" | Severynse, Tom | Severynse, Tom | None |  | FCRD-NFST-2015-000743 | 16 STAD Receipts and Storage
M4FT-15SR0910039 | M4 | 1.02.09.10.03 | SRNL | FT-15SR091003 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | Aging Management Input Report | Aging Management inpurt report | Provide an input report to the ANL M3 end of year report | 2015-08-31 02:00 |  | 2015-08-30 |  | 2015 | Complete | Degradation Evaluation and Aging Management of Bolted Closure Joints | Verst, CG | Sindelar, Robert | None | FCRD-UFD-2015-000739 Degradation Evaluation and Aging Management of Bolted Closure Joints.docx | FCRD-NFST-2015-000747 | Aging Management
M5FT-15OR0902051 | M5 | 1.02.09.02.05 | ORNL | FT-15OR090205 | Waste Management System Analysis Tool Development and Maintenance - ORNL | van den Akker, Bret | None | JTOM Conceptual Design | JTOM Conceptual Design | Conceptual Design of Java-based transportation operations model (JTOM) with phased-steps to complete and data requirements – Inputs (NGSAM data and user defined parameters) and Outputs (JTOM schedule results based on quarterly (not annual) basis | 2014-11-21 04:00 |  | 2014-12-01 |  | 2015 | Completed Late | JTOM Conceptual Design Document |  |  | None | JTOM Conceptual Design.docx | FCRD-NFST-2015-000749
M5FT-15OR0902076 | M5 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | None | Waste Management System Analysis Data ID, Collection, and Verification (Data Report Revision 1) | Data Identification and Verification for Waste Management System Analyses, Revision 1 | Continue to identify, collect, and verify input data needed to conduct integrated waste management system analyses. Integrate with UNF- ST&DARDS database development. Potential areas to assess are listed below. -Reactor site physical characteristics (i.e., pool capacity, crane capacity, rail access) -Reactor site dry storage cask mapping -Transportation logistics and costs. Review "Data Identification and Verification for Waste Management System Analyses," Revision 0 to identify gaps and issue Revision 1 of the data report. | 2015-06-30 02:00 |  | 2015-06-30 |  | 2015 | Complete | Data Identification and Verification for Waste Management System Analyses | van den Akker, Bret | Josh Jarrell | None |  | FCRD-NFST-2015-000750
M5FT-15SR0904044 | M5 | 1.02.09.04.04 | SRNL | FT-15SR090404 | CX: Standardization and Integration - SRNL | Carter, Joe | None | Update ISF facility system analysis input data | ISF Facility input data | Use information from Task orders 11, 14, 16, and any other information sources to update the input data. Document the bases for the revised data in a sections for incorporation in "Data Identification and Verification for Waste Management System Analyses". | 2015-05-30 04:00 | 2015-05-29 | 2015-05-29 |  | 2015 | Complete | ISF Facility Input Data | Severynse, Tom | Severynse, Tom | None |  | FCRD-NFST-2015-000756 | ISF Facility Input Data
M5FT-15SR0904045 | M5 | 1.02.09.04.04 | SRNL | FT-15SR090404 | CX: Standardization and Integration - SRNL | Carter, Joe | None | Update Re-packaging Facility system analysis input data | Repacking facility system analysis input data update | Use information from Task orders 11, 14, 16, and any other information sources to update the input data. Document the bases for the revised data in a sections for incorporation in "Data Identification and Verification for Waste Management System Analyses". | 2015-05-30 02:00 |  | 2015-05-29 |  | 2015 | Complete | Repackaging Facility System Analysis Input Data Update | Severynse, Tom | Severynse, Tom | None |  | FCRD-NFST-2015-000757 | Repackaging Facility
M4FT-16AN090102031 | M4 | 1.02.09.01.02.03 | ANL | FT-16AN09010203 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM Demonstration and NFST Analyst Training (Release: Phase 2.1 - Prototype 1) | NGSAM Demonstration and NFST Analyst Training | Phase 2.1 - Prototype 1 will incorporate logic/algorithms for (1) At-Reactor Transportation Cask Thermal and Radiation Exposure; (2) Initial logic to support At-ISF Operations; and (3) NGSAM Feature Requests identified in the System Architecture Analysis WP (M5FT-16AN0102044 due November 6, 2015). This demonstration and training will be provided to NFST Analysts and NFST management. | 2016-03-25 11:00 |  | 2016-03-25 05:00 |  | 2016 | Complete | Next-Generation System Analysis Model (NGSAM) Overview & Demonstration |  |  | None | NGSAM-Overview and Demonstration 2016-03-28 Version 4.pdf | FCRD-NFST-2016-000646 | System Analysis, NGSAM
M4FT-16ID090201061 | M4 | 1.02.09.02.01.06 | DOE-ID | FT-16ID09020106 | CB: Siting Process - DOE-ID (Northwind) | Helvey, Elizabeth | Howard, Rob | Draft Siting Process Design Stakeholder Engagement Plan Development | Draft Siting Process Design Stakeholder Engagement Plan Development | Development of a Stakeholder Engagement Plan for the design of a consent based siting process for nuclear waste management facilities. | 2015-11-30 10:00 |  | 2015-11-30 02:00 |  | 2016 | Complete | Draft Siting Process Design Stakeholder Engagement Plan |  |  | None |  | FCRD-NFST-2016-000653
M4FT-16ID090201063 | M4 | 1.02.09.02.01.06 | DOE-ID | FT-16ID09020106 | CB: Siting Process - DOE-ID (Northwind) | Helvey, Elizabeth | Howard, Rob | Preliminary Input on "What We've Heard" Document | Preliminary Input on "What We've Heard" Document | Develop draft input for the initial draft of the "What We've Heard" Document on Siting Process Design | 2016-09-30 02:00 |  | 2016-07-15 02:00 |  | 2016 | Complete | Preliminary Input on "What We've Heard" Document |  |  | None |  | FCRD-NFST-2016-000656
M4FT-16ID090201064 | M4 | 1.02.09.02.01.06 | DOE-ID | FT-16ID09020106 | CB: Siting Process - DOE-ID (Northwind) | Helvey, Elizabeth | Howard, Rob | Preliminary Input on Siting Process Guiding Principles Document | Preliminary Input on Siting Process Guiding Principles Document | Provide Preliminary Input on Siting Process Guiding Principles Document to be used as part of the development of the next phase of siting process design. This is expected to be a small document (approx. 20 pages or less) | 2016-07-15 06:00 |  | 2016-07-15 02:00 |  | 2016 | Complete | Preliminary Input on Siting Process Guiding Principles Document |  |  | None |  | FCRD-NFST-2016-000655
M4FT-16ID090401042 | M4 | 1.02.09.04.01.04 | DOE-ID | FT-16ID09040104 | TR: Institutional - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | Draft Status Report on Transportation Planning Framework issue resolution | Draft Report on Transportation Planning Framework | This draft report will be a status update on discussions with industry and stakeholders regarding development of transportation planning protocols. It includes the analysis and development of issue papers related to transportation planning activities and support to related stakeholder interactions. | 2016-02-19 04:00 | 2016-03-25 02:00 | 2016-03-22 |  | 2016 | Completed Late | Draft Status Report on Transportation Planning Framework issue resolution |  |  | None |  | FCRD-NFST-2016-000667
M4FT-16ID090401043 | M4 | 1.02.09.04.01.04 | DOE-ID | FT-16ID09040104 | TR: Institutional - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | Draft Status Report on Development of Routing Methodology for SNF | Draft Routing Methodology Status Report | Deliver an M4 draft Status Report on the Development of a Standardized Routing Methodology. This includes research, analysis, and development of issue papers related to designing a routing methodology and the support of stakeholder engagement activities related to the development of a routing methodology. | 2016-05-13 02:00 |  | 2016-05-13 02:00 |  | 2016 | Complete | Draft Status Report on Development of Routing Methodology for SNF |  |  | None |  | FCRD-NFST-2016-000669
M4FT-16ID090402055 | M4 | 1.02.09.04.02.05 | DOE-ID | FT-16ID09040205 | TR: Operational - DOE-ID (Northwind) | Helvey, Elizabeth | Feldman, Matt | Description of Improvements for START Version 2.0 | Description of Improvements for START Version 2.0 | Write a very brief description of the improvements and changes made to START Version 2.0. | 2016-04-29 06:00 | 2016-05-02 02:00 | 2016-04-02 02:00 |  | 2016 | Complete | Description of Improvements for START 2.0 |  |  | None |  | FCRD-NFST-2016-000668
M4FT-16OR090103031 | M4 | 1.02.09.01.03.03 | ORNL | FT-16OR09010303 | Shutdown Reactor SNF Data Capture and Preservation - ORNL | Joseph, Robby | Jarrell, Josh | Proposed Shutdown Reactor SNF Data Capture and Preservation Plan | Proposed Shutdown Reactor SNF Data Capture and Preservation Plan | Produce a proposed shutdown reactor SNF data capture and preservation plan. | 2016-02-19 |  | 2016-02-19 |  | 2016 | Complete | Shutdown Site Spent Nuclear Fuel Data Capture and Preservation Plan |  |  | None |  | FCRD-NFST-2016-000643
M4FT-16OR0901050110 | M4 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Thermal Model Sensitivity Analysis | UNF-ST&DARDS Thermal Model Sensitivity Analysis | UNF-ST&DARDS Thermal Model sensitivity analysis to understand the importance of various parameters used for thermal calculation | 2015-12-09 02:00 |  | 2015-12-09 |  | 2016 | Complete | COBRA SFS Modeling Sensitivities for a Spent Nuclear Fuel Cask Employing Heat Transfer Disks | Robb, Kevin | Scaglione, John | None | COBRA-SFS_Sensitivity_Final__12-09-15.pdf | FCRD-NFST-2016-000641 | COBRA-SFS, Modeling Sensitivity
M4FT-16OR090105014 | M4 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Facility dose analysis capability of UNF-ST&DARDS | Facility dose analysis capability of UNF-ST&DARDS | Initial implementation of facility (e.g., ISF) dose analysis capability in UNF-ST&DARDS | 2016-05-27 02:00 | 2016-08-31 | 2016-08-31 |  | 2016 | Completed Late | Initial Implementation of On-the-Fly Dose Analysis | Davidson, Gregory | Scaglione, John | None | DoseCalcBySourceSuperposition_FinalSigned.pdf | FCRD-NFST-2016-000649 | Dose, on-the-fly, unf-st&dards
M4FT-16OR090301012 | M4 | 1.02.09.03.01.01 | ORNL | FT-16OR09030101 | ST: Regulatory - ORNL | Howard, Rob | Carter, Joe | Update Strategy for Licensing Consolidated Storage | Strategy for Licensing Consolidated Storage | Update the "Strategy for Licensing Consolidated Storage" FCRD-NFST-2015-000442 as appropriate based on emerging issues. | 2016-07-22 06:00 |  | 2016-07-11 |  | 2016 | Complete | Strategy for Licensing a Consolidated Used Fuel Interim Storage Facility |  |  | OUO |  | FCRD-NFST-2016-000664
M3SF-17SR020201041 | M3 | 1.08.02.02.01.04 | SRNL | SF-17SR02020104 | Storage Design Concepts - SRNL | Carter, Joe | Carter, Joe | Activity 1 Project Concept Update | A Project Concept for Nuclear Fuels Storage and Transportation, rev 2 | Update “A Project Concept for Nuclear Fuels Storage and Transportation” report. This report uses the work performed by industry and national laboratories and configures system components to meet the requirements of the Administration’s Strategy for a pilot and larger ISF. The project concept provides guidance for the next stage of design development as well as supporting the consent based siting process being undertaken by DOE. The project concept includes a pilot interim storage facility, a larger interim storage facility, and the transportation system and equipment needed to move used nuclear fuel and high-level radioactive waste from current locations to interim storage and then to a future permanent geologic repository. This report was last updated in June 2013. Since that time, several additional Advice and Assistance contract task orders have been completed, including Task Order 16 for the design concepts related to receipt and storage of SNF in dry storage canisters. Additional National Laboratory studies for bare fuel receipt and storage and packaging for disposal concepts have also been completed. | 2017-05-26 |  | 2017-05-25 |  | 2017 | Complete | A Project Concept for Nuclear Fuels Storage and Transportation | Severynse, Tom | Severynse, Tom | None | Project Concept 5-26-17 Rev 2 -M3SR020201041 QA Sheet (Signed).pdf Project Concept 5-26-17 Rev 2 -M3SR020201041(FINAL).pdf | SFWD-IWM-2017-000057 | Project Concept
M4SF-17AN020403012 | M4 | 1.08.02.04.03.01 | ANL | SF-17AN02040301 | MOEF Application - ANL | Samsa, Michael | Jarrell, Josh | Deliver Integrated Assessment of ISF Deployment Scenarios Report (Draft) | Integrated Assessment of ISF Deployment Scenarios Report (Draft) | This report will document an integrated assessment of ISF deployment scenarios using MOEF, ESA, and NGSAM or TSL-CALVIN tools. | 2017-07-31 06:00 |  | 2017-07-31 02:00 |  | 2017 | Complete | FY2017 Integrated Assessment of Alternative ISF Deployment Scenarios (Preliminary Report) | Samsa, Michael | Samsa, Michael | None | FY2017 Integrated Assessment (Draft) 2017-07-31.pdf | SFWD-IWM-2017-000066 | scenario, ISF, deployment, alternatives, integrated, assessment
M4SF-17AN020403083 | M4 | 1.08.02.04.03.08 | ANL | SF-17AN02040308 | NGSAM Development and Application - ANL | St. Aubin, Jim | Jarrell, Josh | Release NGSAM (Version 2.2.1.0) | Release NGSAM (Version 2.2.1.0) | Enhanced NGSAM database & application software release - no report deliverable | 2017-01-20 14:00 |  | 2017-03-01 01:00 |  | 2017 | Completed Late | Email and Release Notes (refer to attachments) that verify January 20, 2017 NGSAM release on scheduled target date |  |  | None |  | SFWD-IWM-2017-000146
M4SF-17ID020402121 | M4 | 1.08.02.04.02.12 | DOE-ID | SF-17ID02040212 | Transportation Communications - DOE-ID (North Wind) (CLOSED) | Helvey, Elizabeth | Jarrell, Josh | Draft Transportation Outreach Strategy and Media Communications Plan | Draft Transportation Outreach Strategy and Media Plan | Develop a outreach strategy and media communications plan | 2017-05-31 03:00 | 2017-10-31 |  |  | 2017 | Late |  |  |  | None |  | SFWD-IWM-2017-000141
M4SF-17OR0201010211 | M4 | 1.08.02.01.01.02 | ORNL | SF-17OR02010102 | Siting Process Design - ORNL (CLOSED) | Howard, Rob | Howard, Rob | Evaluate EPA's EJSCREEN GIS tool for use in CBS related activities | Evaluation of EJSCREEN for Support of Consent Based Siting Activities | Perform an evaluation of EPA's EJSCREEN GIS tool for use in Consent Based Siting Related Activities. This includes evaluation of the GIS layers that are used and screening logic and how this information could supplement information in existing facility siting tools. | 2017-03-15 | 2017-07-31 | 2017-05-01 |  | 2017 | Completed Late | Deliverable Title Evaluation of EJSCREEN for Support of Consent Based Siting Activities |  |  | OUO |  | SFWD-IWM-2017-000121
M4SF-17OR020101101 | M4 | 1.08.02.01.01.10 | ORNL | SF-17OR02010110 | Siting Process Design - ORNL (Contractor) | Howard, Rob | Howard, Rob | Annotated Outline for Plan for Community Capacity Building | Annotated Outline for Community Capacity Building. | Develop an annotated outline for a Plan for Community Capacity Building | 2017-03-15 | 2017-10-31 |  | This milestone was eliminated when work package was closed. | 2017 | Late |  |  |  | None |  | SFWD-IWM-2017-000217
M4SF-17OR020301013 | M4 | 1.08.02.03.01.01 | ORNL | SF-17OR02030101 | Transportation: Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | Conduct a Routing Workshop | Conduct a Routing Workshop | Develop various shipping scenarios and evaluate how the funding formula is impacted by them. | 2017-09-30 |  | 2017-08-25 |  | 2017 | Complete | N/A | N/A | N/A | None |  | SFWD-IWM-2017-000023
M4SF-17OR020302026 | M4 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Transportation Incident Database Path Forward Report | Transportation Incident Database Path Forward Report | Report detailing proposed path forward for development of a Type B Package transportation incident database | 2017-06-16 | 2017-10-31 |  | late. | 2017 | Late |  |  |  | None |  | SFWD-IWM-2017-000190
M4SF-17OR020403111 | M4 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Howard, Rob | Howard, Rob | Dry Storage Loading Optimization and algorithmic development | Dry Storage Optimization Algorithm Report | Development of an optimization algorithm to provide ability to unload a spent fuel pool in a manner that facilitates minimization of worker dose as well as early transportation of storage packages. | 2017-09-29 |  | 2017-09-29 | To address the evolving needs of dry storage, this research developed an optimization methodology to identify loading configurations to minimize the number of casks, their heat load, and the time when they meet transportation requirements. | 2017 | Complete | ADAPTABLE LONG-TERM OPTIMIZATION OF DRY CASK STORAGE LOADING PATTERNS | Spencer, Kristina | Joseph, Robby | OUO |  | SFWD-IWM-2017-000148 | SNF canister loading
M4SF-17SR020501062 | M4 | 1.08.02.05.01.06 | SRNL | SF-17SR02050106 | Systematic Studies Involving Canisters - SRNL | Carter, Joe | Nutt, Mark | "As-is" and overpack alternative documentation | "As-is" and overpack alternatives | Identify Equipment needs for packaging non-transportable canister fuel | 2017-07-31 |  | 2017-07-31 |  | 2017 | Complete | As-Is and Overpack Alternatives | Severynse, Tom | Severynse, Tom | None | Closure Document - As-is and Overpack Alternatives.pdf QA Cover Sheet - As-is and overpack alternatives.pdf | SFWD-IWM-2017-000211 | As Is and Overpack Alternative
M5SF-17AN020403014 | M5 | 1.08.02.03.01.04 | DOE-ID | SF-17ID02030104 | Transportation: Intergovernmental and External Engagement - DOE-ID (North Wind) | Helvey, Elizabeth | None | Scenario Definitions for Integrated Assessment ISF Deployment Alternatives (Draft) | Scenario Definitions for Integrated Assessment ISF Deployment Alternatives (Draft) | This report will document the ESA and System Analysis scenarios to be included in the multi-objective evaluation of alternative interim storage approaches. It will be the joint effort of the ESA, Systems Analysis, and MOEF teams. | 2016-11-18 02:00 |  | 2016-11-18 02:00 |  | 2017 | Complete | Scenario Definitions for an Integrated Assessment of ISF Deployment Alternatives | Samsa, Michael | Samsa, Michael | None | Scenario Definitions for Assmt of ISF Deploy Alts 2016-11-18 (Draft).pdf | SFWD-IWM-2017-000167 | scenario, ISF, deployment, alternatives, integrated
M5SF-17ID020501033 | M5 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Jarrell, Josh | None | Assess Remote Weld Inspection and Treatment | Assess Remote Weld Inspection and Treatment | Assess Remote Weld Inspection and Treatment | 2017-06-28 | 2017-07-06 02:00 | 2017-07-11 02:00 |  | 2017 | Completed Late | Assess Remote Weld Inspection and Treatment |  |  | None | RPT-5155689-ME-0001rA-Technology Feasibility Assessment-final.pdf TM-5155689-EG-0003.pdf | SFWD-IWM-2017-000250
M5SF-17OR020403094 | M5 | 1.08.02.05.01.02 | ORNL | SF-17OR02050102 | Systematic Studies Involving Canisters- ORNL | Scaglione, John | None | JTOM improvements incorporated | JTOM Improvements completed and tested | JTOM improvements included and tested. | 2017-07-28 |  | 2017-07-28 |  | 2017 | Complete | JTOM Improvements Incorporated | Ingrid Busch |  | None |  | SFWD-IWM-2017-000248
M4SF-18AN020402015 | M4 | 1.08.02.04.02.01 | ANL | SF-18AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | Integrated Waste Management Facility Configuration Evaluation: Draft Annotated Outline | Integrated Waste Management Facility Configuration Evaluation: Draft Annotated Outline | Annotated outline for L-2 Integrated Waste Management Facility Configuration Evaluation | 2018-10-31 |  |  | on schedule | 2018 | 90 Day |  |  |  | None
M4SF-18AN020402022 | M4 | 1.08.02.04.02.02 | ANL | SF-18AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.4.0) | Release NGSAM (Version 2.3.4.0) | Enhanced NGSAM database and application software release - No report deliverable | 2018-11-02 |  |  | On Schedule | 2018 | 90 Day |  |  |  | None
M4SF-18AN020402024 | M4 | 1.08.02.04.02.02 | ANL | SF-18AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.5.0) | Release NGSAM (Version 2.3.5.0) | Enhanced NGSAM database and application software release - No report deliverable | 2018-12-21 |  |  | On Schedule | 2018 | 90 Day |  |  |  | None
M4SF-18ID020301032 | M4 | 1.08.02.03.01.03 | DOE-ID | SF-18ID02030103 | Intergovernmental and External Engagement - DOE-ID (North Wind) | Helvey, Elizabeth | Feldman, Matt | Progress Report on Negotiations with SRG+T on Emergency Response Planning | Progress Report on Negotiations with SRG+T on Emergency Response Planning | The progress report will capture the issues discussed between DOE and the State Regional Groups and Tribal Caucus, any recommended resolutions to each issue, and next steps required to resolve each issue. | 2019-02-28 |  |  | This milestone is on schedule. | 2018 | On Schedule |  |  |  | None
M4SF-18ID0203030411 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 6: Truck Assemblies Fabrication and Inspection Complete | Truck Assemblies Fabrication & Inspection Report | CLIN 3 Event 6: Truck Assemblies Fabrication & Inspection Complete | 2018-12-16 |  |  | On schedule. | 2018 | 90 Day |  |  |  | None
M4SF-18ID0203030412 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 7: Prototype Railcars Accepted | Prototype Railcars Accepted Report | CLIN 3 Event 7: Prototype Railcars Accepted | 2019-03-29 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18ID0203030413 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 8: Prototype Railcars Delivered | Prototype Railcars Delivery Receipt | CLIN 3 Event 8: Prototype Railcars Delivered | 2019-04-20 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18IN020409012 | M4 | 1.08.02.04.09.01 | INL | SF-18IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Document past licensing efforts related to the Standard Canister | Document past licensing efforts related to the Standard Canister | Report documenting past licensing and certification efforts that involve the DOE-EM standard canister. Specific past efforts include packaging and storage licenses, disposal licenses, as well as transportation topical safety analysis reports. | 2018-08-31 |  | 2018-08-31 02:00 |  | 2018 | Complete | Brief on the Technical Status of DOE’s Standardized Canister Development for DOE- Owned SNF | Birk, Sandra | Jarrell, Josh | None | M4SF-18IN02040912_Standard-Canister-History_DOE-submittal_2018-08-31.docx
M4SF-18IN020409017 | M4 | 1.08.02.04.09.01 | INL | SF-18IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Initial storage configuration alternative study | Initial storage configuration alternative study |  | 2019-09-30 |  |  |  | 2018 | On Schedule |  |  |  | None
M4SF-18OR020104033 | M4 | 1.08.02.01.04.03 | ORNL | SF-18OR02010403 | Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis - ORNL | Joseph, Robby | Howard, Rob | Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis Annotated Outline | Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis Annotated Outline | Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis Annotated Outline | 2017-11-15 |  | 2017-11-15 |  | 2018 | Complete | Functions, Attributes, and Options Analysis Annotated Outline |  |  | None | Functions and Attributes_Annotated_Outline_20171113.docx
M4SF-18OR0203020410 | M4 | 1.08.02.03.02.04 | ORNL | SF-18OR02030204 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Incident-Case Dose Factors Methodology Development Report | Transportation Incident-Case Dose Factors Methodology Development Report | Initial report on development of methodology for incident-case dose factors for SNF transport that could be integrated into the START tool. | 2019-02-08 |  |  | On schedule. | 2018 | On Schedule |  |  |  | None
M4SF-18OR020303024 | M4 | 1.08.02.03.03.02 | ORNL | SF-18OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Interface Control Document | Atlas Railcar Interface Control Document | The Interface Control Document identifies, manages and controls the transportation system interactions between the railcar transportation equipment and external activities including vendor-supplied SNF transportation casks and cradles. | 2019-01-31 |  |  | Activity is on schedule. | 2018 | On Schedule |  |  |  | None
M4SF-18OR020402061 | M4 | 1.08.02.04.02.06 | ORNL | SF-18OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | Approach, Assumptions, Scenarios: IWM Facility Configuration Evaluation | Approach, Assumptions, Scenarios: IWM Facility Configuration Evaluation | Develop the approach, assumptions, and scenarios for the evaluations of the potential future integrated waste management systems for a range of deep geologic repository and consolidated interim storage facility configurations | 2018-08-10 |  | 2018-08-10 |  | 2018 | Complete | Draft Approach, Assumptions, and Scenarios for Select Integrated Waste Management System Configuration Evaluations |  |  | None | Draft Scenarios and Assumptions_8_10.docx
M4SF-18OR020403012 | M4 | 1.08.02.04.03.01 | ORNL | SF-18OR02040301 | Standardization and Integration - ORNL | Howard, Rob | Howard, Rob | STAD Canister System Status Report | STAD Canister System Concept Status Report | The status report will identify any changes necessary to the Standardized Transportation, Aging, and Disposal Canister Systems, FCRD-NFST-2014-000579, and Rationale for the Performance Specification for Standardized Transportation, Aging, and Disposal Canister Systems, FCRD-NFST-2015-000106, as a result of the review. | 2018-12-21 |  |  | This deliverable is on track | 2018 | 90 Day |  |  |  | None
M4SF-18PN020302056 | M4 | 1.08.02.03.02.05 | PNNL | SF-18PN02030205 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | COBRA-SFS Code Modernization | Update of COBRA-SFS. | Modernize COBRA-SFS. | 2019-01-25 |  |  | on schedule | 2018 | On Schedule |  |  |  | None
M4SF-18SR020201025 | M4 | 1.08.02.02.01.02 | SRNL | SF-18SR02020102 | Storage Design - SRNL | Carter, Joe | Carter, Joe | Initial Test Plan for Phase 1 Testing | Initial Test Plan for Phase 1 Testing | initial Test Plan | 2018-10-31 |  |  | on schedule | 2018 | 90 Day |  |  |  | None
M4SF-18SR020402071 | M4 | 1.08.02.04.02.07 | SRNL | SF-18SR02040207 | System Architecture Analysis - SRNL | Carter, Joe | Howard, Rob | Review draft TSAR and GDR for cost info | Documentation (e-mail) of task completion | Review draft TSAR and GDR for cost info and other data that should be added to UDB and produce inputs in a format provided by ORNL staff- | 2018-10-15 |  |  | on schedule | 2018 | 90 Day |  |  |  | None
M5SF-18ID020404032 | M5 | 1.08.02.04.04.03 | DOE-ID | SF-18ID02040403 | Knowledge Capture and Preservation - DOE-ID (North Wind) | Helvey, Elizabeth | None | Progress Report on Knowledge Capture and Preservation | Progress Report on Knowledge Capture and Preservation | Write a report that describes the work accomplished since June 1, 2018. The document should include the information captured, the research methods used, and suggest potential next steps and any difficulties encountered in the research. | 2019-02-28 |  |  | This milestone is on schedule. | 2018 | On Schedule |  |  |  | None
M5SF-18ID020404033 | M5 | 1.08.02.04.02.06 | ORNL | SF-18OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | None | Work Plan for Knowledge Capture and Preservation | Work Plan for Knowledge Capture and Preservation | Write a brief description of the scope the project and the research methods that will be used to identify, gather, and preserve program knowledge. | 2018-06-29 |  | 2018-06-19 |  | 2018 | Complete | Work Plan for Knowledge Capture and Preservation |  |  | None | M5SF-18ID02040433_Work Plan for Knowledge Capture and Preservation_June 2018.pdf
M5SF-18OR020402065 | M5 | 1.08.02.04.04.03 | DOE-ID | SF-18ID02040403 | Knowledge Capture and Preservation - DOE-ID (North Wind) | Helvey, Elizabeth | None | Implement improvements to the JTOM Portion of NGSAM | Implement improvements to the JTOM Portion of NGSAM | Perform improvements to the JTOM portion of NGSAM | 2018-12-07 |  |  | on track | 2018 | 90 Day |  |  |  | None
M4SF-19AN020402021- No milestone report required. | M4 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.4.0) | Release NGSAM (Version 2.3.4.0) | Enhanced NGSAM database and application software release - No report deliverable | 2018-11-02 |  | 2018-11-02 02:00 |  | 2019 | Complete | Email announcing NGSAM 2.3.4.0 release | ANL NGSAM Development team | Argonne National Lab (ANL) | None | NGSAM-2340-RELEASE-EMAIL.docx |  | NGSAM, spent nuclear fuel
M4SF-19AN020402022- No milestone report required | M4 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.5.0) | Release NGSAM (Version 2.3.5.0) | Enhanced NGSAM database and application software release - No report deliverable | 2018-12-21 |  | 2018-12-21 01:00 | No milestone report. Supporting docs in PICS. | 2019 | Complete | NGSAM supporting documentation (not a milestone) for the NGSAM 2.3.5.0 tool release |  |  | None | NGSAM version 2.3.5.0 Release Email 21-Dec-2018.msg
M4SF-19AN020402025- - No milestone report required | M4 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.6.0) | Release NGSAM (Version 2.3.6.0) | Enhanced NGSAM database and application software release - No report deliverable | 2019-06-21 |  | 2019-06-21 | NGSAM 2.3.6.0 software release. No milestone reports. | 2019 | Complete | Not Applicable | Olson and Vander Wall | Jim St. Aubin | None | Not Applicable |  | NGSAM, release
M4SF-19ID020302013- Screenshot only no report | M4 | 1.08.02.03.02.01 | DOE-ID | SF-19ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Develop Batch Run Capability | Develop Batch Run Capability | Develop a Batch Run capability in START. This capability will allow a user to request specific START Output data sets (routes, attributes, etc.) for a batch of origin/destination pairs through a single input file. The capability will allow for at least 100 origin/destination pairs to be requested through a single input request and will return the START Output data sets for each of the origin/destination pairs in an organized file structure. | 2019-05-24 |  | 2019-05-24 | Completed on schedule. | 2019 | Complete | Screen capture of the current version of START that users can access. In the upper right-hand corner of the page is a link to the Batch Routes. |  |  | None | START batch routes.pptx
M4SF-19OR020404013- No report. Updated map link in PICS | M4 | 1.08.02.04.04.01 | ORNL | SF-19OR02040401 | CURIE and Visual Tool Development and Improvement | Joseph, Robby | Howard, Rob | Update CURIE Map | Update CURIE Map | The CURIE Map will updated based upon the latest public release of the SRNL produced SNF and HLW inventory report (currently Rev. 5). | 2019-01-18 |  | 2019-01-18 |  | 2019 | Complete | Update CURIE Map |  |  | None
M4SF-19SN020402132- OUO. No report in PICS. | M4 | 1.08.02.04.02.13 | SNL | SF-19SN02040213 | ESA Development and Application - SNL | Sassani, Dave | Howard, Rob | Input to ESA system analyses | Inputs for ESA Tool Development | Inputs for ESA Tool development | 2019-01-31 | 2019-02-28 04:00 | 2019-02-22 02:00 | This was informal input of draft material provided directly and review of draft documentation (all input was OUO draft materials). | 2019 | Completed Late | none |  |  | OUO
M4SF-19SR020402083- no matching records found in PICS | M4 | 1.08.02.04.02.08 | SRNL | SF-19SR02040208 | System Architecture Analysis - SRNL | Carter, Joe | Howard, Rob | Input to ESA Sensitivity Analyses | Input to ESA Sensitivity Analyses | Provide input to ESA sensitivity studies based on insights gained from initial ESA repository scenarios; this may include additional cost information for different repository geologies/concepts. | 2019-05-31 |  |  |  | 2019 | On Schedule |  |  |  | None
M5SF-19OR020402063- No report for this milestone | M5 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | None | Implement improvements to the JTOM Portion of NGSAM | Implement improvements to the JTOM Portion of NGSAM | Perform improvements to the JTOM portion of NGSAM | 2018-12-07 |  | 2018-12-07 | Completed the M5 milestone M5SF-19OR020402063 entitled “Implement Improvements to the JTOM Portion of NGSAM.” Requested changes to the JTOM portion of NGSAM to improve functionality and meet sponsor requests and analyst needs were completed. | 2019 | Complete | Implement improvements to the JTOM Portion of NGSAM |  |  | None
M5SF-19PN0203020416- Reached out to Steve Maheras for document | M5 | 1.08.02.04.09.01 | INL | SF-19IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | None | START Verification and Validation Plan (12) | START Verification and Validation Plan | Initiate verification and validation of START by producing verification and validation plan. | 2019-11-01 |  |  |  | 2019 | On Schedule |  |  |  | None
M5SF-19PN0203020425- Reached out to Steve Maheras for document | M5 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve |  | Master List of Nuclear Power Plant Site Evaluation and Interaction Questions | Master List of Nuclear Power Plant Site Evaluation and Interactions Questions | Master List of Nuclear Power Plant Site Evaluation and Interactions Questions | 2019-11-30 |  |  | on schedule | 2019 | 90 Day |  |  |  | None
M3SF-19OR0203020357- Reached out to Matt Feldman for document. | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Commercial Nuclear Power Plant De-Inventory Queue Analysis Report | Commercial Nuclear Power Plant De-Inventory Queue Analysis Report | Revised report on analysis of various options, including multiple destinations, for acceptance queues from pick-up of spent nuclear fuel from commercial nuclear power plants. | 2019-10-25 |  |  | On schedule. | 2019 |  |  |  |  | None
M3SF-19OR0203020358- Reached out to Matt Feldman for document | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #9 | Site Specific De-Inventory Report #9 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-11-15 |  |  |  | 2019 |  |  |  |  | None
M3SF-19OR0203020359- Reached out to Matt Feldman for document | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #10 | Site Specific De-Inventory Report #10 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-11-15 |  |  |  | 2019 |  |  |  |  | None
M3SF-19OR0203020360- - Reached out to Matt Feldman for document | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #11 | Site Specific De-Inventory Report #11 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-11-15 |  |  |  | 2019 |  |  |  |  | None
M3SF-19OR020408016- Reached out to Rob Howard for document | M3 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Report documenting status of MERF and capability demonstration | Summary update on MERF design and capability development | Report documenting progress on MERF design and repair demonstration capabilities | 2019-09-30 | 2019-11-08 |  |  | 2019 |  |  |  |  | None
M3SF-19PN0203020423- Reached out to Steve Maheras for document | M3 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Shutdown Sites Report -- FY2019 Revision | Shutdown Sites Report -- FY2019 Revision | Revision of the shutdown sites report. | 2019-09-30 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M4SF-19AN020402026- No report applicable | M4 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Expand NGSAM Technical Infrastructure | Expand NGSAM Technical Infrastructure | Enhanced NGSAM database and application software framework - No report deliverable | 2019-07-31 |  | 2019-06-21 | Release Client/Server 2.0 enhancement allowing system analysts to run 15 simultaneous simulations. | 2019 | Complete | Not Applicable - supporting documentation included with technical infrastructure release | Brian Craig and Lucas Vander Wal | Jim St. Aubin | None | Client Server 2.0 Notes.pdf |  | Client, Server, NGSAM
M4SF-19AN020402028- Reached out to Rob Howard for document | M4 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.7.0) | Release NGSAM (Version 2.3.7.0) | Enhanced NGSAM database and application software release - No report deliverable | 2019-12-06 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19ID020301042- Document contains contract-sensitive information. Please contact Erica Bickford (NE-82, erica.bickford@nuclear.energy.gov) before sharing or releasing. | M4 | 1.08.02.03.01.04 | DOE-ID | SF-19ID02030104 | Intergovernmental and External Engagement - DOE-ID (CSG - ERC) | Jones, Jay | Feldman, Matt | Quarterly Reports Oct. 2018 - Sept. 2019 | CSG-ERC Quarterly Reports | CSG-ERC submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2018 - Sept. 2019 into one M4 milestone. | 2019-09-30 |  | 2019-10-25 | All four quarterly reports from CSG-ERC were submitted on schedule. | 2019 | Complete | DE-NE0008603 CSG-ERC Quarterly Progress Reports FY19 | Uldis Vanags | CSG-ERC | None | DE-NE0008603 CSG-ERC Quarterly Progress Reports FY19.pdf |  | Quarterly Report
M4SF-19ID020301062- Document contains contract-sensitive information. Please contact Erica Bickford (NE-82, erica.bickford@nuclear.energy.gov) before sharing or releasing. | M4 | 1.08.02.03.01.06 | DOE-ID | SF-19ID02030106 | Intergovernmental and External Engagement - DOE-ID (CSG - Midwest) | Jones, Jay | Feldman, Matt | Quarterly Reports Oct. 2018 - Sept. 2019 | CSG-MW Quarterly Reports | CSG-MW submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2018 - Sept. 2019 into one M4 milestone. | 2019-09-30 |  | 2019-10-31 | All four quarterly reports from CSG-Midwest were submitted on schedule. | 2019 | Complete | DE-NE0008604 CSG-MW Quarterly Progress Reports FY19 | Lisa Janairo | CSG-Midwest | None | DE-NE0008604 CSG-MW Quarterly Progress Reports FY19.pdf
M4SF-19ID020301072- Document contains contract-sensitive information. Please contact Erica Bickford (NE-82, erica.bickford@nuclear.energy.gov) before sharing or releasing. | M4 | 1.08.02.03.01.07 | DOE-ID | SF-19ID02030107 | Intergovernmental and External Engagement - DOE-ID (SSEB) | Jones, Jay | Feldman, Matt | Quarterly Reports Oct. 2018 - Sept. 2019 | SSEB Quarterly Reports | SSEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2018 - Sept. 2019 into one M4 milestone. | 2019-09-30 |  | 2019-10-30 | All four quarterly reports from SSEB were submitted on schedule. | 2019 | Complete | DE-NE0008605 SSEB Quarterly Progress Reports FY19 | Chris Wells | SSEB | None | DE-NE0008605 SSEB Quarterly Progress Reports FY19.pdf
M4SF-19ID020301082- Document contains contract-sensitive information. Please contact Erica Bickford (NE-82, erica.bickford@nuclear.energy.gov) before sharing or releasing. | M4 | 1.08.02.03.01.08 | DOE-ID | SF-19ID02030108 | Intergovernmental and External Engagement - DOE-ID (WIEB) | Jones, Jay | Feldman, Matt | Quarterly Reports Oct. 2018 - Sept. 2019 | WIEB Quarterly Reports | WIEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2018 - Sept. 2019 into one M4 milestone. | 2019-09-30 |  | 2019-10-31 | All four quarterly reports from WIEB were submitted on schedule. | 2019 | Complete | DE-NE0008601 WIEB Quarterly Progress Reports FY19 | Melanie Snyder | WIEB | None | DE-NE0008601 WIEB Quarterly Progress Reports FY19.pdf
M4SF-19ID020301092- Document contains contract-sensitive information. Please contact Erica Bickford (NE-82, erica.bickford@nuclear.energy.gov) before sharing or releasing. | M4 | 1.08.02.03.01.09 | DOE-ID | SF-19ID02030109 | Intergovernmental and External Engagement - DOE-ID (NCSL) | Jones, Jay | Feldman, Matt | Quarterly Reports Oct. 2018 - Sept. 2019 | NCSL Quarterly Reports | NCSL submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2018 - Sept. 2019 into one M4 milestone. | 2019-09-30 |  | 2019-10-29 | All four quarterly reports from NCSL were submitted on schedule. | 2019 | Complete | DE-NE0008586 NCSL Quarterly Progress Reports FY19 | Kim Tyrrell | NCSL | None | DE-NE0008586 NCSL Quarterly Progress Reports FY19.pdf
M4SF-19ID020302014- Reached out to Matt Feldman for report. | M4 | 1.08.02.03.02.01 | DOE-ID | SF-19ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Completed Transition to Cloud Server | Completed Transition to Cloud Server | This task involves the transition to serving START through the Amazon Cloud Server rather than at INL, and subsequently hosting and troubleshooting Amazon web services for a 12-month period. | 2019-07-26 | 2019-11-29 |  | I spoke with Mark Abkowitz on Monday, March 11 and he confirmed he is on schedule to meet all current milestones. | 2019 | Delayed |  |  |  | None
M4SF-19OR020401013- Reached out to Rob Howard for document | M4 | 1.08.02.04.01.01 | ORNL | SF-19OR02040101 | Project Management - ORNL | Howard, Rob | Howard, Rob | Final Information Security Assessment Report | Final Information Security Assessment Report | Builds on the initial assessment report by providing assessment results and recommendations based on Case 2 (assumes use of a postulated future version of UNF-ST&DARDS). | 2019-06-28 | 2019-11-15 |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19OR020404012- No report for this milestone. | M4 | 1.08.02.04.04.01 | ORNL | SF-19OR02040401 | CURIE and Visual Tool Development and Improvement | Joseph, Robby | Howard, Rob | CURIE Architecture Upgrade | CURIE Architecture Upgrade | The core software, Drupal, for which CURIE is run, will be updated to Drupal 8. This will require the database to be migrated to the new code base. Also, this will allow the development team to remove unused code and simplify various components for easier maintenance. Upgrading versions moving forward will also be more streamlined after this change is made. | 2019-09-20 |  | 2019-09-13 | The M4 milestone (M4SF-19OR020404012) entitled ‘CURIE Architecture Upgrade’ has been completed. NO REPORT. The core software, Drupal, from which CURIE is run, has been updated to Drupal 8. This required the database to be migrated to the new code base. Also, this allowed the development team to remove unused code and simplify various components for easier maintenance. Upgrading versions moving forward will also be more streamlined now after this change has been made. | 2019 | Complete | No report for this milestone. |  |  | None | No report for this milestone.
M4SF-19OR020408018- Reached out to Rob Howard for document | M4 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Construct and perform initial testing of versatile remediation module | Completion of initail fabrication and operational testing of versatile remediation arm | Build and test versatile remediation module | 2019-09-11 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19PN0203020420- Reached out to Steve Maheras for document | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #3 | Thermal Template #3 | Thermal template #3. | 2019-11-29 |  |  |  | 2019 | On Schedule |  |  |  | None
M4SF-19PN0203020421- Reached out to Steve Maheras for document | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #4 | Thermal Template #4 | Thermal template #4. | 2019-11-29 |  |  |  | 2019 | On Schedule |  |  |  | None
M3SF-19ID020303046 Report and all appendices on DOE website. | M3 | 1.08.02.03.03 | DOE | SF-19ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) | CLIN Completion Letter: CLIN 2 |  | 2019-05-20 |  | 2019-05-19 | Phase 3 of the Atlas Railcar Design Project was completed on May 19, 2019. | 2019 | Complete | The Atlas Railcar Phase 3 Final Report, including all the appendices, is now on the DOE website. |  |  | None
M4SF-19OR010205033- No document, technology development milestone | M4 | 1.08.01.02.05 | ORNL | SF-19OR01020503 | Security - ORNL | Scaglione, John | Saltzstein, Sylvia | Local streaming over WiFi | Proof of concept demonstration to technology integration | A physical demonstration of the capability was made. | 2019-03-29 |  | 2019-03-29 | System performance goal accomplished-Local streaming over wifi was successfully demonstrated. | 2019 | Complete | NA-Technology demonstration milestone | stinson | Scaglione | None | NA-Technology demonstration milestone
M4SF-19AN030102011- 1.08.03 milestones not needed for SDA site | M4 | 1.08.03.01.02 | ANL | SF-19AN03010201 | Quality Assurance - ANL | Riel, Roberta | Brainard, Matt | ANL QA Surveillance | ANL QA Surveillance |  | 2019-05-31 |  | 2019-05-17 | Assessment report SFWD-IA-19-001 | 2019 | Complete | Spent Fuel and Waste Disposition (SFWD) Assessment Checklist (SFWD-IA-19-001), Milestone M4SF-19AN030102011 | Roberta Riel | Roberta Riel | None | SFWD-IA-19-001.pdf
M2SF-19OR020302032- OUO. No report in PICS | M2 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Cost Estimate Database Report | Transportation Cost Estimate Database Report | Level 2 milestone report detailing up-to-date logistics and capital costs associated with SNF transport. | 2019-01-25 |  | 2019-01-25 |  | 2019 | Complete | Transportation Cost Estimate Database Report | Matt Feldman | Matt Feldman | OUO |  | Transportation, JTOM, Cost Data, UDB, NGSAM
M2SF-19OR020405013- No report for this milestone | M2 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Release of UNF-ST&DARDS Version 4.0 | UNF-ST&DARDS Version 4.0 | This deliverable includes UNF-ST&DARDS Version 4.0 software code with up-to-date user documentation. Version 4.0 is planned to be a general-purpose (rather than test & evaluation only) version with capabilities for use in performing thermal analysis in addition to those capabilities previously included in Version 3.1.1. Version 4.0 is currently planned to be a limited release through the Radiation Safety Information Computational Center (RSICC) and, similar to previous versions released through RSICC, will not include data in the unified database (UDB). | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | UNF-ST&DARDS Version 4.0 | Kaushik Banerjee | Kaushik Banerjee | None
M3SF-19OR020408019- Reached out to Rob Howard for document | M3 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites (MERF) - ORNL | Scaglione, John | Howard, Rob | FMEA on new design concept | FMEA on MERF design concpet | Perform and FMEA on the latest design concpet and concpet of operations | 2019-11-29 |  |  | will be canceled based on new direction for FY20 | 2019 | 90 Day |  |  |  | None
M4SF-19OR020403014- Reached out to Rob Howard for document | M4 | 1.08.02.04.03.01 | ORNL | SF-19OR02040301 | Standardization and Integration - ORNL | Howard, Rob | Howard, Rob | Draft Description Document for Development and Testing on a Range of Potential Neutron Absorber Materials for use in Triple Purpose SNF canisters: | Neutron Absorber Evaluation Plan | Draft Neutron Absorber Material Evaluation Description document should include: A. A range of post-closure chemical environments /service conditions. This should include chemical conditions in anoxic and oxidizing environments as well as account for chemical evolution associated with water contacting steel waste package materials, spent nuclear fuel, and spent nuclear fuel assembly components. B. A range of materials to be considered for evaluation and corrosion testing. C. Identification and discussion of available existing mechanical, degradation, and failure data available D. Identification and consideration of advanced manufacturing approaches for neutron absorber material production. E. Cost estimates, estimated durations, and implementation approaches/options that recognize the amount of funding to evaluate neutron materials may vary widely from year to year and allow the evaluation to adapt to changes in funding. | 2019-07-31 | 2019-10-30 |  | Milestone delayed due to resource constraints | 2019 | Late |  |  |  | None
M4SF-19OR0204080110- Reached out to Rob Howard for document | M4 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites (MERF) - ORNL | Scaglione, John | Howard, Rob | Modeling of dose and temperatures during repair operations | Dose and temaperture assessment fo actual as-loaded canister | Develop and document computational models of dose to equipment and potentail streaming paths, as well as effects of insulation on thermal response fo canister. | 2019-11-29 |  |  | will be canceled based on new direction for FY20 | 2019 | 90 Day |  |  |  | None
M3SF-19AN020402015- no matching records in PICS for this milestone number under FY19, 20, or 21 | M3 | 1.08.02.04.02.01 | ANL | SF-19AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | Sensitivities analysis for IWMS configurations | Sensitivities analysis for IWMS configurations | Report describing sensitivities analysis for IWM configurations, looking Into different scenarios, including but not limited to comparing different medias | 2019-08-30 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M4SF-19ID020301031- no matching records in PICS | M4 | 1.08.02.03.01.03 | DOE-ID | SF-19ID02030103 | Intergovernmental and External Engagement - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Progress Report on Development of a Reciprocal Rail Safety Inspection Protocol for SNF Carrying Trains | Progress Report on Development of a Reciprocal Rail Safety Inspection Protocol for SNF Carrying Trains | Progress Report on Development of a Reciprocal Rail Safety Inspection Protocol for SNF Carrying Trains | 2019-08-31 |  |  | This milestone will be canceled. | 2019 | On Schedule |  |  |  | None
M4SF-19PN0203020411- no matching records in PICS | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Continue Cultural Resource Reviews -- Draft (11.2) | Draft Report on Cultural Resources | Prepare summaries of known cultural resources, status of Section 106 consultation, and potential issues. | 2019-06-28 |  |  | start delayed | 2019 | On Schedule |  |  |  | None
M3SF-19ID020403051- Reached out to Jack Wheeler for document | M3 | 1.08.02.04.03 | DOE- Idaho Operations Office | SF-19ID02040305 | Standardization and Integration - DOE-ID (Task Order 8) | Wheeler, Jack | Howard, Rob | Complete Final Study Report(s) for Task Order 8 | Task Order 8 Final Report(s) |  | 2020-05-29 |  |  |  | 2020 |  |  |  |  | None
M2SF-20SN020801011- The deliverable is for internal DOE use only and has been provided directly to the DOE Program Manager without being uploaded to PICS-NE. | M2 | 1.08.02.08.01 | SNL | SF-20SN02080101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Analyze Priority One Legacy Application Functionality | Document analysis status/migration path for Legacy applications |  | 2020-03-27 |  | 2020-03-10 | Analysis of P1 systems is complete. The remaining proposals will be delivered to DOE for approval. A copy of the proposals with a summarized cover letter are being prepared to upload to PICs prior to the end of March. | 2020 | Complete | NWM P1 System Analysis Report |  |  | None | NFCSC_QAPD_Rev 6_Appendix_E Analysis Submittal.pdf
M3SF-20OR020408014- OUO will not be uploaded to PICS. | M3 | 1.08.02.04.08.01 | ORNL | SF-20OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites (MERF) - ORNL | Chatzidakis, Stylianos | Howard, Rob | MERF Versatile Remediation Module final operational testing results | MERF Versatile Remediation Module final operational testing results | Report documenting MERF Versatile Remediation Module final operational testing results. | 2020-02-28 |  | 2020-02-28 | This report describes the Versatile Remediation Module (VRM) prototype and its design features, components, weld repair qualification tests, neutron diffraction residual stress measurements, operational procedures, and final demonstration results. A remote (i.e., 100 ft away from the simulated radiative environment) demonstration of the VRM was successfully performed on a full-scale mock-up welded stainless-steel canister. | 2020 | Complete | Versatile Remediation Module Final Operational Testing Results | Stylianos Chatzidakis | Stylianos Chatzidakis | OUO | Program Controls Note: Deliverable File removed at CAM's request on 6/29/2020 due to the OUO nature of the final report. OUO files should not be uploaded into PICS:NE. (M. Brainard) |  | Remediation, repair, welding
M3SF-20SN0208010140 No document in PICS. OUO. | M3 | 1.08.02.08.01.01 | SNL | SF-20SN02080101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Prepare and Submit ATO for DOE AO Approval | Submit ATO for approval & upload copy of approval request letter to DOE CIO | Copy of ATO Approval Request Letter sent to DOE CIO for AO approval. | 2020-08-31 |  | 2020-08-31 02:00 | ATO approval request was submitted and approved by the DOE CIO. | 2020 | Complete | NWM ATO Approval Request Letter to DOE AO | Cynthia Huber | Cynthia Huber | OUO
M3SF-20IN020409014 No document in PICS. OUO | M3 | 1.08.02.04.09.01 | INL | SF-20IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Develop Weld/NDE/Repair Equipment for DOE Standard Canisters | Develop Weld/NDE/Repair Equipment for DOE Standard Canisters | Develop or procure the equipment design for remotely performing welding, non-destructive evaluation, and weld repair on circumferential closure welds between DOE Standard Canister shells and Lid Assemblies | 2020-09-03 |  | 2020-09-03 08:00 | Deliverable submitted on scheduled date | 2020 | Complete | DOE SNF Packaging Demonstration Project - Remote Closure System Design for DOE Standard Canisters | Daniel A. Thomas | Josh J. Jarrell | OUO
M3SF-20OR0204050110- No report for this milestone | M3 | 1.08.02.04.05.01 | ORNL | SF-20OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Demonstration of the web-interface | Demonstration of the web-interface | Demonstrate the web-interface to relevant parties including deputy NTD, NTD, federal managers, and EIA representatives. | 2020-09-25 | 2020-10-30 |  | This demonstration was divided in to two parts after discussion with federal manager. Part I demonstration was already provided and part II demonstration is currently scheduled on 22 October. | 2020 | Expected Late |  |  |  | None
M3SF-20PN0203020423- Reached out to Steven Maheras for document. | M3 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Project Plan For Accelerating Transportation System Development | Draft Project Plan For Accelerating Transportation System Development | Develop Draft Project Plan For Accelerating Transportation System Development. | 2020-09-30 | 2020-10-30 03:00 |  | revised deliverable date was discussed with the sponsor | 2020 | Expected Late |  |  |  | None
M3SF-20PN020405032- Reached out to David Richmond for document. | M3 | 1.08.02.04.05.03 | PNNL | SF-20PN02040503 | COBRA-SFS Code Development - PNNL | Richmond, David | Howard, Rob | COBRA-SFS Version 6.0 and Users Manual | COBRA-SFS Version 6.0 and Revised Users Manual | Release of COBRA-SFS Version 6.0 and the revised Users Manual | 2020-11-20 |  |  | On schedule. | 2020 | 90 Day |  |  |  | None
M4SF-20AN020402021- No report for this milestone. Software tool. | M4 | 1.08.02.04.02.02 | ANL | SF-20AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Release NGSAM (Version 2.3.7.0) | Release NGSAM (Version 2.3.7.0) | Enhanced NGSAM database and application software release - No report deliverable | 2019-11-29 |  | 2019-11-27 01:00 | NGSAM 2.3.7.0 Software with notes documentation | 2020 | Complete |  | Chuck Olson | Chuck Olson | None |  |  | NGSAM, tool
M4SF-20SN020302062- No report uploaded. OUO. | M4 | 1.08.02.03.02.06 | SNL | SF-20SN02030206 | Transportation: Operational - SNL | Durbin, Sam | Feldman, Matt | Transportation Sabotage Analysis Recommendations | Transportation Sabotage Analysis Recommendations | The Transportation Sabotage Analysis Recommendations report will document the review of the transportation sabotage analysis performed for the Yucca Mountain EIS and will contain recommendations on if there is a need to update the YM transportation sabotage analysis and if so a project plan (including costs), and also an unclassified summary of the review and recommendations will be provided for upload to PICSNE. | 2020-01-31 |  | 2020-01-31 02:00 | (OUO) SAND2020-1337 R: report completed | 2020 | Complete | Updated Release Analysis for Dry Casks in Security-Related Scenarios | Sam Durbin | Sam Durbin | OUO |  |  | spent nuclear fuel; sabotage; source term; release fraction
M4SF-20AN020402025- No document for this milestone | M4 | 1.08.02.04.02.02 | ANL | SF-20AN02040202 | NGSAM Development and Application - ANL | Craig, Brian | Howard, Rob | Release NGSAM (Version 2.3.8.0) | Release NGSAM (Version 2.3.8.0) | Enhanced NGSAM database and application software release - No report deliverable. | 2020-09-30 |  | 2020-09-30 01:00 | NGSAM 2.3.8.0 was deployed to the NGSAM cluster and website on 9/30. NTD and DOE was informed upon completion of the deployment process. | 2020 | Complete |  |  |  | None
M4SF-20ID020301042- Reached out to Erica Brickford for document | M4 | 1.08.02.03.01.04 | DOE-ID | SF-20ID02030104 | Intergovernmental and External Engagement - DOE-ID (CSG - ERC) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | CSG-ERC Quarterly Reports | CSG-ERC submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-02 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M4SF-20ID020301062- Reached out to Erica Brickford for document | M4 | 1.08.02.03.01.06 | DOE-ID | SF-20ID02030106 | Intergovernmental and External Engagement - DOE-ID (CSG - Midwest) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | CSG-MW Quarterly Reports | CSG-MW submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-02 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M4SF-20ID020301072- Reached out to Erica Brickford for document | M4 | 1.08.02.03.01.07 | DOE-ID | SF-20ID02030107 | Intergovernmental and External Engagement - DOE-ID (SSEB) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | SSEB Quarterly Reports | SSEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-02 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M4SF-20ID020301082- Reached out to Erica Brickford for document | M4 | 1.08.02.03.01.08 | DOE-ID | SF-20ID02030108 | Intergovernmental and External Engagement - DOE-ID (WIEB) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | WIEB Quarterly Reports | WIEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-02 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M4SF-20ID020301092- Reached out to Erica Brickford for document | M4 | 1.08.02.03.01.09 | DOE-ID | SF-20ID02030109 | Intergovernmental and External Engagement - DOE-ID (NCSL) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | NCSL Quarterly Reports | NCSL submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-02 |  |  | on schedule | 2020 | 90 Day |  |  |  | None
M3SF-20IN020409015- no notes in PICS on why report is missing | M3 | 1.08.02.04.09.01 | INL | SF-20IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Develop technical basis and requirements for a Storage Module system for DOE Standard Canisters | Develop technical basis and requirements for a Storage Module system | Develop and document the technical basis and requirements for procuring a Storage Module system for DOE Standard Canisters. This will be of use for a potential RFP and for any technical evaluation of proposals. | 2020-09-30 | 2020-12-18 10:00 |  | On track for revised date | 2020 | Expected Late |  |  |  | None
M3SF-20OR0204050112- no notes in PICS on why report is missing | M3 | 1.08.02.04.05.01 | ORNL | SF-20OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Implement on-the-fly dose analysis methodology in UNF-ST&DARDS | UNF-ST&DARDS on-the-fly dose analysis capability | Implement on-the-fly methodology for as-loaded shielding analysis. This analysis approach will allow quick shielding analysis of a given system by changing loading maps. Initial implementation will include one system (e.g., HI-STAR 190 + MPC 37) with the goal to quickly add additional systems in the future. | 2020-12-11 |  |  | On Schedule | 2020 | 90 Day |  |  |  | None
M3SF-20PN020304032- no notes in PICS on why report is missing | M3 | 1.08.02.03.04.03 | PNNL | SF-20PN02030403 | Rail Car Optimization - PNNL (IWM Funded) | Ross, Steven | Saltzstein, Sylvia | 8-axle Railcar Support | 8-Axle Railcar Summary | 8-axle railcar support | 2020-12-31 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20ID020302012- no notes in PICS on why report is missing | M4 | 1.08.02.03.02.01 | DOE-ID | SF-20ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Complete Transition to Cloud Server | Completed Transition to Cloud Server | This task involves the transition to serving START through the Amazon Cloud Server rather than at INL, and subsequently hosting and troubleshooting Amazon web services for a 12-month period. | 2020-03-27 | 2020-12-31 12:00 |  | On schedule to meet revised milestone completion date. | 2020 | Late |  |  |  | None
M4SF-20OR020303029- no notes in PICS on why report is missing | M4 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | ISSMS Project Plan | SSMS Project Plan | Prepare a detailed project plan to include system requirements, interface requirements, and coordination between all design organizations. Will include a detailed Microsoft Project plan for the three project phases. | 2020-12-31 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20PN020402132- no notes in PICS on why report is missing | M4 | 1.08.02.04.02.13 | PNNL | SF-20PN02040213 | Advanced Fuel Cycle Waste Form Management and Planning - PNNL | Nutt, Mark | Howard, Rob | Advanced Fuel Cycle Waste Form Management and Planning Status Report | Advanced Fuel Cycle Waste Form Management and Planning Status Report |  | 2021-01-31 |  |  | Not yet started | 2020 | On Schedule |  |  |  | None
M4SF-20OR0203030210- no notes in PICS on why report is missing | M4 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | ISSMS Initial System Design | ISSMS Initial System Design | Document the initial system design for the ISSMS. | 2021-02-28 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-20OR020405046- no notes in PICS on why report is missing | M4 | 1.08.02.04.05.04 | ORNL | SF-20OR02040504 | Web-application for GC-859 Data - ORNL | Banerjee, Kaushik | Howard, Rob | Functional requirements and specifications document for the web-application | Functional requirements and specifications document for the web-application | This report documents revision and refinement of the functional requirements and specifications of the web-application based on testing feedbacks. | 2021-03-01 |  |  |  | 2020 | On Schedule |  |  |  | None
M5SF-20PN020303036- no notes in PICS on why report is missing | M5 | 1.08.02.03.03.03 | PNNL | SF-20PN02030303 | Transportation: Hardware - PNNL | Maheras, Steve |  | Atlas Railcar Suspension Pad Testing Report | Atlas Railcar Suspension Pad Testing Report | Report documenting the non-destructive and mechanical properties testing of the Atlas railcar suspension pads. | 2021-03-31 |  |  | on schedule | 2020 | On Schedule |  |  |  | None
M3SF-20OR0204050111- Superseded by M3SF-21OR020401015 Contact Kaushik Banerjee for report | M3 | 1.08.02.04.01 | ORNL | SF-21OR02040101 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Develop new criticality templates | Enhancement of UNF-ST&DARDS Criticality Analysis Capability |  | 2021-01-15 |  |  | On Schedule | 2021 | 90 Day |  |  |  | None
M3SF-21IN020403012- no report uploaded to PICS | M3 | 1.08.02.04.03.01 | INL | SF-21IN02040301 | DOE Managed SNF for Transport - INL | Thomas, Dan | Jarrell, Josh | Technical Basis for Modular Storage System for DOE Standard Canisters | Technical Basis for Modular Storage System for DOE Standard Canisters | Develop technical basis and requirements for a Modular Storage Module and Transport system for DOE Standard Canisters, to be used for the DOE SNF Packaging Demonstration Project. | 2020-12-18 |  | 2020-12-17 08:00 | Send via email to Federal Manager and National Technical Director. | 2021 | Complete | Technical Basis for Modular Storage Systems for DOE Standard Canisters | Daniel A. Thomas | Josh J. Jarrell | None
M4SF-21OR020303054- prototype system design report (PSDR) that will be published in September 2021. | M4 | 1.08.02.03.03.05 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | ISSMS Initial System Design | ISSMS Initial System Design | Document the initial system design for the ISSMS. | 2021-02-28 |  | 2021-02-28 | ISSMS Initial System Design report | 2021 | Complete | Integrated Security & Safety Monitoring System: Initial System Design | Bill Reich | Bill Reich | OUO |  |  | ISSMS, system design, Atlas railcar
M4SF-21AN020401073- No document to upload for this milestone | M4 | 1.08.02.04.01.07 | ANL | SF-21AN02040107 | NGSAM Development and Application - ANL | Craig, Brian | Howard, Rob | NGSAM Release 2.3.9.0 | NGSAM 2.3.9.0 | Develop the 2.3.9.0 that will include the following model improvements: ISF_DET.csv report improvements Update scenario file structure Multi-mode transport to railhead Support User Edits via Website Improve how we track route files Reduce output file size for most simulation runs Generate All GUI Reports Postrun Add ability to pack to dry storage from the ISF pool DOE Same-type package blending | 2021-04-16 |  | 2021-04-16 | Completed version 2.3.9.0 and deployed to the NGSAM cluster. Email sent to CAM and NTD acknowledging completion and deployment of the latest version of NGSAM. | 2021 | 90 Day | No document | None | None | None | None |  | None
M5SF-21IN020301131- No document uploaded for this milestone | M5 | 1.08.02.03.01.13 | INL | SF-21IN02030113 | Intergovernmental and External Engagement - INL | Carlsen, Brett |  | Develop outline for Transportation Communication Program Proposal | Develop outline for Transportation Communication Program Proposal | Develop outline/strawman for Transportation Communication Program Proposal. | 2021-04-30 |  | 2021-04-29 | Outline transmitted with 4/29 email, brett.carlsen@inl.gov to mathew.feldman@pnnnl.gov | 2021 | 90 Day |  |  |  | None
M2FT-13OR0914061 Per Matt Brainard: M2FT-12OR0822021 - Originally planned for FY13 completion on 3/22/2013. It was superseded by M2FT-13OR0914061: Complete Initial Commercial UNF Database and Documentation and completed on 3/22/2013. Deliverable not uploaded into PICS:NE. The deliverable form was submitted and approved blank. Document Author: “ORNL, PNNL, SRNL”. Document Owner: “John Scaglione”. DMS No. FCRD-NFST-2013-000117. No other notes provided. | M2 |  | ORNL | [11 empty] | 2013 |  |  | Peterson, Josh | Scaglione, John |  |  | FCRD-NFST-2013-000117
M3FT-13AN09020127 ULR. Predecisional Draft. | M3 | 1.02.09.02.01 | ANL | FT-13AN090201 | Systems Architecture - ANL | Nutt, Mark | Nutt, Mark | Preliminary Draft of Update of UFD System Architecture Evaluation | Update of UFD System Architecture preliminary draft for M2FT-13AN0902012 | Preliminary Draft of Update of UFD System Architecture Evaluation | 2013-09-30 04:00 |  | 2013-09-25 02:00 | DRAFT report "Used Fuel Management System Architecture Evaluation, Fiscal Year 2013, FCRD-NFST-2013-000377 | 2013 | Complete |  | Nutt, Mark | Nutt, Mark | None
M3FT-13OR0902022 ULR. DRAFT. | M3 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | Develop Cask and Fleet Maintences Facility Concepts for System Architecture | Cask and Fleet Maintenance Facility Concepts | Develop Cask and Fleet Maintenance Facility Concepts that could by integrated into a waste management system architecture. | 2013-05-31 02:00 |  | 2013-05-31 |  | 2013 | Complete |  | Howard, Rob | Howard, Rob | None | Cask_Fleet_Maintenance_draft.docx
M3FT-13OR0902025 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M3 | 1.02.09.02.02 | ORNL | FT-13OR090202 | Systems Architecture - ORNL | Howard, Rob | Nutt, Mark | Develop Preliminary Process Flow Diagrams and Process Node Descriptions | Status Report on System Architecture Integration Activities and Preliminary Process Flow Diagrams and Process Node Descriptions for Waste Management System Architecture | This Activity will develop process flow diagrams and process node descriptions for the various material flow operations described in the waste management system architecture studies and information gained from integration actiivities with DOE's industry contractors working on consolidated storage concepts and standard cansister concepts. | 2013-09-20 04:00 |  | 2013-09-20 | Process Flow Diagrams and Node Descriptions (PFDND) are being developed in Microsoft® Visio and Microsoft® Word in order to examine the possible options and processes in the transportation and storage of used nuclear fuel (UNF) from a reactor to its final disposition at a repository. | 2013 | Complete |  | Howard, Rob | Howard, Rob | None | Node Descriptions 9-20-2013.docx Process Flow Diagrams 9-20-2013.vsd Status_Report_on_Process_Flow_Nodes_09202013_M3.pdf | FCRD-NFST-2013-000298
M3FT-13OR0903012 ULR. Draft. No DMS #. | M3 | 1.02.09.03.01 | ORNL | FT-13OR090301 | Collaborative Document and Data Management System - ORNL | Jarrell, Josh | Nutt, Mark | Preliminary Report | Preliminary Report | Draft of M2 Report for review | 2013-07-13 02:00 |  | 2013-07-12 |  | 2013 | Complete |  | Josh Jarrell | Josh Jarrell | None | FCRD-Report-CURIE-M3_07-12-2013.pdf
M3FT-13OR0903032 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M3 | 1.02.09.03.03 | ORNL | FT-13OR090303 | Data collection and database synthesis in support of waste acceptance - ORNL | Scaglione, John | Nutt, Mark | Report on realistic safety margins for Maine Yankee, Connecticut Yankee, and Rancho Seco casks | Realistic safety margin assessment for Maine Yankee, Connecticut Yankee, and Rancho Seco casks | Report documenting assessment of site-specific casks with regards to transportability to alternate location as-is or the need to invoke compensatory measures | 2013-09-27 | 2013-10-25 | 2013-10-31 | Nearly complete. Currently in internal review process. | 2013 | Expected Late |  | Banerjee, Kaushik | Scaglione, John | None | Realistic_Safety_Margin_Final.pdf
M3FT-13OR0904033 | M3 | 1.02.09.04.03 | ORNL | FT-13OR090403 | Standard Canisters - ORNL | Howard, Rob | Wagner, John | Revise “Preliminary Used Fuel Management System Concept of Operations Including Options for Standardized Transportation, Aging, and Disposal Canisters, and Direct Disposal of Dual Purpose Canisters,” FCRD-UFD-2012-000155, as appropriate | Preliminary Used Fuel Management System Concept of Operations Including Options for Standardized Transportation, Aging, and Disposal Canisters, and Direct Disposal of Dual Purpose Canisters,” FCRD-UFD-2012-000155, | 3. Revise “Preliminary Used Fuel Management System Concept of Operations Including Options for Standardized Transportation, Aging, and Disposal Canisters, and Direct Disposal of Dual Purpose Canisters,” FCRD-UFD-2012-000155, as appropriate based on industry input and ongoing co-ordination with the Systems Architecture Studies and Direct Disposal of DPC Feasibility Studies. (ORNL – Lead, ANL and SNL support) [L3 Milestone July 19 2013] | 2013-07-19 04:00 |  | 2013-07-19 |  | 2013 | Complete |  | Howard, Rob | Howard, Rob | None | Waste_Management_System_Concept_of Operations_FY13_update_07-19-2013.docx | FCRD-NFST-2013-000221
M3FT-13OR0912065 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M3 | 1.02.09.12.06 | ORNL | FT-13OR091206 | TRAGIS Capability Development and Maintenance - ORNL | Tuttle, Mark | Feldman, Matt | FY 13 Updated GIS Layers for TRAGIS | FY2013 Updated GIS Layers for TRAGIS | End of FY13 Letter Report that documents • An up-to-date highway network GIS layer in TRAGIS, including o Identification by attribute and state, all designated HRCQ routes o Identification by attribute and state all heavy-haul truck routes o Information on state level transportation planners and approving authorities for both hazmat and heavy haul trucking in route output o Improvements to highways topology • An updated waterways network, including o New origin and destination locations for barge traffic o Improved topological accuracy of the waterways links to conform to the actual waterway and shipping lane topology | 2013-09-30 04:00 |  | 2013-09-30 | Updated GIS Layers report. | 2013 | Complete |  | Tuttle, Mark | Tuttle, Mark | None | M4FT-13OR0912065_GISLayers.pdf | FCRD-NFST-2013-000398
M3FT-13OR0912067 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​​ | M3 | 1.02.09.12.06 | ORNL | FT-13OR091206 | TRAGIS Capability Development and Maintenance - ORNL | Tuttle, Mark | Feldman, Matt | FY2013 Intermodal Feasibility Study for TRAGIS | FY2013 Intermodal Feasibility Study for TRAGIS | Intermodal routing feasibility study for TRAGIS to include o Identification of sources for a node dataset identifying intermodal transfer locations o Analysis of required coding updates and estimate of LOE for implementing in TRAGIS | 2013-09-30 04:00 |  | 2013-09-30 | Completed Multimodal Feasibility Study | 2013 | Complete |  | Tuttle, Mark | Tuttle, Mark | None | M4FT-13OR0912067_Multi.pdf | FCRD-NFST-2013-000399
M3FT-13OR0913011 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​​ | M3 | 1.02.09.13.01 | ORNL | FT-13OR091301 | TR Hardware - ORNL | Feldman, Matt | Feldman, Matt | Preliminary Hardware Alternatives Analysis | Preliminary Hardware Alternatives Analysis Report | Report detailing recommended transportation hardware acquisition alternatives to address rolling stock, casks, and ancillary equipment necessary for transport of UNF and GTCC at a nominal rate of 3000 MTHM/yr. | 2013-09-30 02:00 |  | 2013-09-30 | Completed on time | 2013 | Complete |  | Feldman, Matt | Feldman, Matt | None | FCRD-NFST-2013-000382_preliminary_final.docx
M3FT-13OR0914077 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M3 | 1.02.09.14.07 | ORNL | FT-13OR091407 | SCALE Capability Development and Maintenance - ORNL | Rearden, Brad | Nutt, Mark | Year-end Report on SCALE Maintenance and Development Activities | SCALE Annual Report | Year-end report documenting SCALE maintenance and development activities | 2013-09-30 |  | 2013-09-27 | The SCALE Annual Report summarizes the maintenance and development activities performed for the SCALE code system during fiscal year 2013. The primary goal of the SCALE maintenance activities is to ensure that the SCALE code system continues to meet the needs of sponsors and users by providing verified and validated results and remaining current with state-of-the-art computing technology. This effort improves reliability by identifying and correcting discrepancies, providing enhancements to current capabilities, and programming for portability to different computing platforms. A thorough software configuration management process is used in performing these activities to assure adequate testing, documentation, and software control. Development activities involve major enhancements to existing modules as well as development of new modules, data libraries, and user interfaces. The current public version of SCALE is 6.1, which was released in July 2011. An initial beta release of SCALE 6.2 was released to select early testers in August 2013. | 2013 | Complete |  | Rearden, Brad | Rearden, Brad | None | M3FT-13OR0914077 SCALE Annual Report.pdf |  | SCALE, Maintenance, Development, Modeling and Simulation
M3FT-13SN0905012 | M3 | 1.02.09.05.01 | SNL | FT-13SN090501 | CX Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Wagner, John | Evaluation of Public Preferences Related to Storage, Transportation, and Disposal | Public Preferences Related to Siting, Characterization, and Operation of Radioactive Waste Management Facilities | Evaluate public preferences related storage at decommissioned sites, transportation and siting of centralized storage facility, and transportation and siting of disposal facility | 2013-09-30 16:00 |  | 2013-09-30 02:00 | Report was completed on time. Report is ready for DOE HQ and DOE GC review prior to public release. | 2013 | Complete |  | Rechard, Rob | Rechard, Rob | None | Methodology Report QA Review Form 09-30-2013.pdf |  | Public Survey; Interim Storage Facility; Transportation; Radioactive Waste Management
M3FT-13SN0905012 | M3 | 1.02.09.05.01 | SNL | FT-13SN090501 | CX Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Wagner, John | Evaluation of Public Preferences Related to Storage, Transportation, and Disposal | Public Preferences Related to Siting, Characterization, and Operation of Radioactive Waste Management Facilities | Evaluate public preferences related storage at decommissioned sites, transportation and siting of centralized storage facility, and transportation and siting of disposal facility | 2013-09-30 16:00 |  | 2013-09-30 02:00 | Report was completed on time. Report is ready for DOE HQ and DOE GC review prior to public release. | 2013 | Complete |  | Rechard, Rob | Rechard, Rob | None | Methodology Report QA Review Form 09-30-2013.pdf |  | Public Survey; Interim Storage Facility; Transportation; Radioactive Waste Management
M3FT-13SN0905014 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.05.01 | SNL | FT-13SN090501 | CX Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Nutt, Mark | Summary of past findings on consent-based siting of facilities for radioactive waste management | Summary of Findings on Consent-Based Siting of Facilities for Radioactive Waste Managment | Write report that summarizes previous projects conducted by Sandia and University of Oklahoma on stakeholder interactions for radioactive waste managment facilities. Also summarize related documents in the siting experience database. | 2013-03-31 04:00 |  | 2013-03-31 02:00 |  | 2013 | Complete |  | Rechard, Rob | Rechard, Rob | None | Approach for Consent Based Sitting Cover Sheet 03-31-13.pdf.pdf Approaches for Consent-Based Siting of Nuclear Waste Management Facilities 03-31-13.pdf | FCRD-NFST-2013-000113
M3FT-13SN0905015 | M3 | 1.02.09.05.01 | SNL | FT-13SN090501 | CX Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Nutt, Mark | General principales and guidance for conducting consent-based siting of facilities for radioactive waste management | General Principles and Guidance for Conducting Consent-Based Siting of Facilities for Radioactive Waste Management | Prepare report the develops general principals and recommended guidance for conducting consent-based siting of facilities for radioactive waste management | 2013-08-31 08:00 |  | 2013-08-31 02:00 |  | 2013 | Complete |  | Rechard, Rob | Rechard, Rob | None | Guidance from US Surveys FCRD Review Form.pdf |  | Consent-Based Siting, Radioactive Waste Management, Public Preference Survey, Interim Storage Facilities, Radioactive Waste Transportation
M3FT-13SN0905023 same as M3FT-12SN0814102 | M3 | 1.02.09.05.02 | SNL | FT-13SN090502 | Siting Experience Database - SNL | Price, Laura | Wagner, John | Status Memo | Interim Status of Siting Experience Archive | Memo to DOE describing the status of the archive. | 2012-11-30 08:00 |  | 2012-11-28 02:00 |  | 2013 | Complete |  | Price, Laura | Price, Laura | None |  |  | siting experience, nuclear waste facility siting
M3FT-13SN0912051 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ No SAND number on report. | M3 | 1.02.09.12.05 | SNL | FT-13SN091205 | RADTRAN Capability Development and Maintenance - SNL | Weiner, Ruth | Feldman, Matt | RADTRAN Model and Calculation of Occupational Dose From a Transportation Accident | RADTRAN Model and Calculation of Occupational Dose From a Transportation Accident | Model of the radiation field near a cask breach | 2013-08-09 04:00 | 2013-08-31 | 2013-10-01 02:00 | The project is essentially complete. It was more difficult than it had initially been thought to be. | 2013 | Late |  | Weiner, Ruth | Weiner, Ruth | None | RadtranReport.pdf | FCRD-NSFT-2013-000310
M3FT-13SN0912053 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M3 | 1.02.09.12.05 | SNL | FT-13SN091205 | RADTRAN Capability Development and Maintenance - SNL | Weiner, Ruth | Feldman, Matt | RADTRAN Status Report and Development Plan | RADTRAN Status Report and Development Plan | Report on RADTRAN status and plans for the future | 2013-09-30 10:00 |  | 2013-10-01 02:00 | The status report is complete | 2013 | 90 Day |  | Weiner, Ruth | Weiner, Ruth | None | RADTRAN STATUS REPORT.docx | FCRD-NSFT-2013-000400
M3FT-13SN0912072 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M3 | 1.02.09.12.07 | SNL | FT-13SN091207 | Package Performance Study Path Forward - SNL | Sorenson, Ken | Wagner, John | Final Report of Review of Full Scale Rail Cask Severe Accident Test Studies | Review of Full Scale Rail Cask Severe Accident Test Studies | Final letter report. | 2013-07-26 04:00 |  | 2013-08-05 04:00 |  | 2013 | Completed Late |  | Durbin, Samuel | Sorenson, Ken | None | RD_Needs_for_Transportation_Safety_v2.docx | FCRD-NFST-2013-000240
M3FT-13SR0908055 ULR. Rev. 0 and 3 are Predecisional Draft. | M3 | 1.02.09.08.05 | SRNL | FT-13SR090805 | Technical Support for Storage Design Concepts Evaluation - SRNL | Smith, Pat | Wagner, John | Develop a project UNF Inventory base line document. | Develop a project UNF Inventory baseline document. | Develop and document an inventory baseline for the NFST project. Maintain the inventory database under change control processes. Ensure all programs use the approved baseline. | 2013-09-30 |  | 2013-08-28 |  | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | NFST Inventory Rev 0.pdf | FCRD-NFST-2013-000263
M3FT-13SR0908057 ULR. Rev. 2 is Predecisional Draft. | M3 | 1.02.09.08.05 | SRNL | FT-13SR090805 | Technical Support for Storage Design Concepts Evaluation - SRNL | Smith, Pat | Wagner, John | Complete the inital draft of a Project Functions and Requirements. | Complete the initial draft of a Project Functions and Requirements. | The Requirements Management Plan will outline the processes for Functions and Requirement (F&Rs) control including those levels of F&R which will be maintained by the project sponsor and those that will be delegated to the design agent. An intial draft of the F&R will be developed and documented. | 2013-09-30 |  | 2013-09-30 | This document provides the top-level governing laws and regulations (e.g., NWPA, 10 Code of Federal Regulations (CFR) Part 63, 10 CFR Part 71, etc.) along with policies, performance requirements, interface requirements, and system architecture that are unique to the NFST mission. This document may be updated, as appropriate, in the future to incorporate specific changes in technical scope or performance requirements that may have significant program implications. Such changes may include changes to the program mission, operational capability and stakeholder issues. | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | NFST Requirements Document (Rev 0).pdf | FCRD-NFST-2013-000330
M3FT-13SR0912041 Per Matt Brainard: Maintain Stranded Fuel Database and project documentation deliverables, attached and satisfied by a Level 2 Deliverable. Narrative: “This report provides a preliminary evaluation of removing stranded used nuclear fuel from 12 shutdown sites. Shutdown sites are defined as those commercial nuclear power reactor sites where the nuclear power reactors have been shut down and the site has been decommissioned or is undergoing decommissioning. The shutdown sites are Maine Yankee, Yankee Rowe, Connecticut Yankee, Humboldt Bay, Big Rock Point, Rancho Seco, Trojan, La Crosse, Zion, Crystal River, Kewaunee, and San Onofre.” ULR. Predecisional Draft. | M3 | 1.02.09.12.04 | SRNL | FT-13SR091204 | TR Operational - Shutdown Sites - SRNL | Carter, Joe | Feldman, Matt | Maintain Stranded Fuel Database and project documentation deliverables. | Maintain Stranded Fuel Database and project documentation deliverables. | SRNL shall produce and maintain a stranded fuel database. SRNL will produce a report to document the | 2013-09-30 02:00 |  | 2013-09-30 | This report provides a preliminary evaluation of removing stranded used nuclear fuel from 12 shutdown sites. Shutdown sites are defined as those commercial nuclear power reactor sites where the nuclear power reactors have been shut down and the site has been decommissioned or is undergoing decommissioning. The shutdown sites are Maine Yankee, Yankee Rowe, Connecticut Yankee, Humboldt Bay, Big Rock Point, Rancho Seco, Trojan, La Crosse, Zion, Crystal River, Kewaunee, and San Onofre. | 2013 | Complete |  | PNNL | PNNL | None | FCRD-NFST-2013-000238_M2_Predecisional.pdf | FCRD-NFST-2013-000238
M4FT-13OR0903013 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.03.01 | ORNL | FT-13OR090301 | Collaborative Document and Data Management System - ORNL | Jarrell, Josh | Nutt, Mark | Documentation of System Capabilities | Documentation of System Capabilities | Documentation of System capabilities including search functionality, map-based functions, and analysis tool integration | 2013-06-28 04:00 |  | 2013-06-28 |  | 2013 | Complete |  | ORNL | Josh Jarrell | None | CURIE_Content_final.pdf
M4FT-13OR0903014 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.03.01 | ORNL | FT-13OR090301 | Collaborative Document and Data Management System - ORNL | Jarrell, Josh | Nutt, Mark | User Interface guidelines | User Interface guidelines | General use guidelines including how to access and utilize the System capabilities | 2013-06-28 04:00 |  | 2013-06-28 |  | 2013 | Complete |  | ORNL | Josh Jarrell | None | CURIE_Manual_final.pdf
M4FT-13OR0903031 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.03.03 | ORNL | FT-13OR090303 | Data collection and database synthesis in support of waste acceptance - ORNL | Scaglione, John | Nutt, Mark | Status Report on data acquired and available through centralized database | Status Report on data available through centralized database | Status report | 2013-09-20 | 2013-10-11 | 2013-10-11 | Partially completed, but still needs to be finalized. | 2013 | Expected Late |  | Peterson and Miller | Scaglione, John | None | Status Report on data acquired and available through unified database_October_2013.pdf
M4FT-13OR0903034 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.03.03 | ORNL | FT-13OR090303 | Data collection and database synthesis in support of waste acceptance - ORNL | Scaglione, John | Nutt, Mark | Incorporate and update inventory projection data into UNF-ST&DARDS | Updated inventory projection data in UNF-ST&DARDS | Incorporation of inventory projection data into UNF-ST&DARDS with depletion and decay data available for use | 2013-09-20 | 2013-10-04 | 2013-10-04 | Milestone complete | 2013 | Expected Late |  | Radulescu, Jarrell, and Miller | Scaglione, John | None | FuelProjectionStatus-2013.pdf |  | inventory, projection, used fuel
M4FT-13OR0912062 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.12.06 | ORNL | FT-13OR091206 | TRAGIS Capability Development and Maintenance - ORNL | Tuttle, Mark | Howard, Rob | Preliminary Updated Highway Network For States/Regions with ISFSI's at Shutdown Reactor Sites | Preliminary GIS Layer of Highway Network For TRAGIS | • A preliminary updated highway network GIS layer in TRAGIS for those states with ISFSIs at Shutdown Reactor Sites, including o Identification by attribute and state, all designated High Route Controlled Quantity(HRCQ) routes o Identification by attribute and state all heavy-haul truck routes o Information on state level transportation planners and approving authorities for both hazmat and heavy haul trucking in route output | 2013-05-31 04:00 |  | 2013-06-01 |  | 2013 | Completed Late |  | Geographic Information Sciences and Technology Group | Tuttle, Mark | None | M4FT-13OR0912062_Highway.pdf | FCRD-NFST-2013-000180
M4FT-13OR0912063 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.12.06 | ORNL | FT-13OR091206 | TRAGIS Capability Development and Maintenance - ORNL | Tuttle, Mark | Howard, Rob | Preliminary Updated Waterway Network focused on States/Regions with ISFSIs at Shutdown Reactor Sites | Preliminary GIS Layer of Waterway Network | • An updated waterways network, including o New origin and destination locations for barge traffic o Improved topological accuracy of the waterways links to conform to the actual waterway and shipping lane topology | 2013-05-17 06:00 |  | 2013-06-01 |  | 2013 | Completed Late |  | Geographic Informations Sciences and Technology Group | Tuttle, Mark | None | M4FT-13OR0912063_Waterway.pdf | FCRD-NFST-2013-000181
M4FT-13OR0912066 No DMS No.ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.12.06 | ORNL | FT-13OR091206 | TRAGIS Capability Development and Maintenance - ORNL | Tuttle, Mark | Howard, Rob | Preliminary Intermodal Feasibility Study for TRAGIS | Preliminary Intermodal Feasibility Study for TRAGIS | • Intermodal routing feasibility study for TRAGIS to include o Identification of sources for a node dataset identifying intermodal transfer locations o Analysis of required coding updates and estimate of LOE for implementing in TRAGIS | 2013-06-21 06:00 |  | 2013-06-21 |  | 2013 | Complete |  | Steve Peterson | Tuttle, Mark | None | M4FT-13OR0912066_PrelimMultimodal.pdf
M4FT-13OR09140611 Supersedes M4FT-12OR08220226 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Report documenting UNF assembly models | Report documenting UNF assembly models | Report documenting UNF assembly models developed. | 2012-11-30 04:00 |  | 2012-11-30 |  | 2013 | Complete |  | Harlod Smith | Scaglione, John | None | Assembly_Modeling_final_12_6_12_JMS.pdf |  | burnup, assemblies, depletion
M4FT-13OR09140619 Supersedes M4FT-12OR08220234 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities | preliminary assessment of realistic safety margins | Complete preliminary assessment of realistic safety margins based on integrated analysis capabilities | 2013-02-22 04:00 |  | 2013-02-27 |  | 2013 | Completed Late |  | William Marshall | Scaglione, John | None | realistic_assessment_UNF_template_FINAL.pdf
M4FT-13OR09140622 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Updated report documenting models for thermal analyses | Updated report documenting models for thermal analyses | Updated report documenting new thermal models that have been added to the database system | 2013-09-30 02:00 |  | 2013-09-30 | Milestone completed | 2013 | Complete |  | Robb, | Scaglione, John | None | M4FT-13OR09140622-Updated report documenting models for thermal analyses.pdf |  | Thermal, used fuel, cask, storage
M4FT-13OR0914065 completion of the M2 milestone M2FT-13OR0914066, Complete Initial Version of UNF M&S Toolset, and the M4 milestone M4FT-13OR0914065, Beta version of UNF database​ ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.14.06 | ORNL | FT-13OR091406 | UNF Data and M&S Toolset Development and Demonstration - ORNL | Wagner, John | Wagner, John | Beta version of UNF database | Beta version of UNF database | This will be the second internal version of the database and will included additional data, as compared to the Sept version, and corrections, as needed. | 2012-12-21 04:00 |  | 2012-12-21 |  | 2013 | Complete |  | Scaglione, John | Scaglione, John | None | M2FT-13OR0914066-12-21-2012.pdf
M4FT-13OR0914071 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.14.07 | ORNL | FT-13OR091407 | SCALE Capability Development and Maintenance - ORNL | Rearden, Brad | Nutt, Mark | Report on UNF Characterization Enhancements in SCALE | Report onUNF Characterization Enhancements in SCALE | Letter report on updated features of SCALE that provide acceleration and memory reduction for UNF Characterization analysis capability used in determination of nuclide inventories in used nuclear fuel | 2013-09-30 02:00 |  | 2013-09-27 | NFST staff members use the TRITON lattice physics sequence of SCALE to generate assembly-specific libraries that quantify discharge nuclide concentrations of individual assemblies for use in cask-specific criticality safety and thermal analyses. Realization of the desired NFST analysis methodology will require thousands of individual calculations for each desired fuel type and condition. Initial testing of high-fidelity nuclear fuel modeling with explicit treatment of materials, geometry, and neutron energy with SCALE 6.2 demonstrated undesirably long run-time and large memory requirement for each calculation. In this task, ongoing capability enhancements were accelerated, which result in a more efficient approach for the desired solution strategy. With the new implementation, runtimes are reduced by up to 60% and memory requirements are reduced by as much as a factor of 50. Importantly, the new implementation enables highest fidelity cases that previously exceeded the capacity of the compute nodes used for testing run to completion. The modified approach has been tested for accuracy and demonstrated to produce only insignificant numerical effects on the solutions of the SCALE quality assurance regression test suite. When fully integrated for production use in SCALE, these enhanced capabilities will allow NFST staff members to generate libraries with explicit tracking of hundreds of nuclides for every pin in a used fuel assembly. The final implementation of the enhanced capability within TRITON is expected in the next fiscal year. | 2013 | Complete |  | Bradley T. Rearden | Bradley T. Rearden | None | M4FT-13OR0914071 Report on UNF Characterization Enhancements in SCALE.pdf |  | SCALE, TRITON, Used Nuclear Fuel Characterization
M4FT-13OR0914074 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.14.07 | ORNL | FT-13OR091407 | SCALE Capability Development and Maintenance - ORNL | Rearden, Brad | Nutt, Mark | Report on Monte Carlo Acceleration in SCALE | Report on Monte Carlo Acceleration in SCALE | Letter report on updated features of SCALE that provide acceleration of continuous-energy Monte Carlo capabilities for criticality safety analysis | 2013-09-30 02:00 |  | 2013-09-27 | For some criticality safety applications, reliably achieving convergence in the Monte Carlo eigenvalue simulations can be challenging. Inadequate source convergence typically corresponds to an underestimation of the effective neutron multiplication factor (keff) – a very troublesome possibility in the field of criticality safety. To reduce the likelihood of this possibility, a new automated source convergence sequence (Sourcerer) has been developed in SCALE to deterministically compute the fission distribution and to use it as the starting source in the Monte Carlo eigenvalue calculation. In addition to decreasing the probability of underpredicting keff due to inadequate source convergence, the sequence eliminates the guesswork associated with defining an appropriate, problem-dependent starting source. Furthermore, Sourcerer can increase the efficiency of the overall simulation by decreasing the number of generations (cycles) that must be skipped prior to keff accumulation. To evaluate its effectiveness, Sourcerer was applied to an actual used nuclear fuel canister that had previously demonstrated source convergence difficulties due to significant variation in loaded assembly burnup values and significant neutronic decoupling between assemblies. Compared to the common use of a starting source distributed uniformly in all fissionable regions, the use of Sourcerer increased the reliability of the keff calculation for all cases in which the number of skipped cycles was below ~350; for cases with higher numbers of skipped cycles the reliability was essentially equivalent. Additionally, for a fixed uncertainty objective, the use of Sourcerer increased the efficiency of the keff calculation by 71% compared to a Monte Carlo calculation with a uniform starting source. Sourcerer is available to NFST staff in SCALE 6.2. | 2013 | Complete |  | Bradley T. Rearden | Bradley T. Rearden | None | M4FT-13OR0914074 Report on Monte Carlo Acceleration in SCALE.pdf |  | SCALE, Criticality Safety, Source Convergence, Used Nuclear Fuel
M4FT-13SN0912054 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.12.05 | SNL | FT-13SN091205 | RADTRAN Capability Development and Maintenance - SNL | Weiner, Ruth | Feldman, Matt | RADTRAN Training Workshop | Report of RADTRAN Workshop | The Workshop includes presentation or RADTRAN and the input file generator RADCAT,the basic equations, how to implement input parameters, and interpretation of output. | 2013-04-17 08:00 | 2013-08-29 16:00 | 2013-10-01 04:00 | There was a considerable delay in scheduling, but the workshop was completed. | 2013 | Late |  | Ruth Weiner | Ruth Weiner | None | DOWNLOADING RADTRAN.docx NRCworkshop.pptx |  | RADTRAN, TRANSPORTATION RISK. ROUTINE TRANSPORTATION, TRANSPORTATION ACCIDENTS
M4FT-13SN0912071 ULR. DRAFT. | M4 | 1.02.09.12.07 | SNL | FT-13SN091207 | Package Performance Study Path Forward - SNL | Sorenson, Ken | Wagner, John | Draft Report on Review of Full Scale Rail Cask Severe Accident Test Studies | Draft Report on the Review of Full Scale Rail Cask Severe Accident Test Studies | This will be a draft letter report that will be distributed to funding sponsors for review and comment. | 2013-06-07 04:00 |  | 2013-06-06 02:00 |  | 2013 | Complete |  | Sam Durbin | Ken Sorenson | None | RD_Needs_for_Transportation_Safety_Final_Draft.docx |  | Package Performance Study
M4FT-13SR0902041 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M4 | 1.02.09.02.04 | SRNL | FT-13SR090204 | Systems Architecture - SRNL | Carter, Joe | Nutt, Mark | Evaluate alternatives for bare fuel storage at the consolidated storage facility | Evaluate alternatives for bare fuel storage at CSF | Report describing various approaches for bare fuel storage at a Consolidated Storage Facility | 2013-03-29 02:00 |  | 2013-03-27 |  | 2013 | Complete |  | SRNL | Joe Carter | None | Bare Fuel Storage Options (Final).pdf |  | Bare Fuel Storage
M4FT-13SR0902043 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.02.04 | SRNL | FT-13SR090204 | Systems Architecture - SRNL | Carter, Joe | Nutt, Mark | Conduct pool density sensitivity study on facility size and operations | Conduct pool density sensitivitiy study on facility size and operations | Joint report with ORNL describing cask/fleet maintenance facilities required for a CSF. This study will evaluate the potential implications of "open-rack" pool configurations and densly packed pool configurations on size and operations for wet (pool) storage consolidated storage facility concepts and repackaging facility concepts described in FY12 Systems Architecture Study. | 2013-08-30 02:00 |  | 2013-08-30 |  | 2013 | Complete |  | Joe T. Carter | Joe T. Carter | None | M4FT-13SR0902043.pdf |  | Pool Density Sensitivity
M5FT-13OR0913014 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M5 | 1.02.09.14.07 | ORNL | FT-13OR091407 | SCALE Capability Development and Maintenance - ORNL | Rearden, Brad | None | Report on Disposition of NTRC Library Material | NTRC Library Material Disposition | Provide a brief summary report of the disposition of the items from the NTRC Packaging Library that are germane to NFST | 2013-09-30 |  | 2013-09-30 | Completed on time | 2013 | Complete |  | Matt Feldman | Matt Feldman | None | NTRC_UFT_Documents.pdf
M5FT-13OR0914073 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M5 | 1.02.09.14.07 | ORNL | FT-13OR091407 | SCALE Capability Development and Maintenance - ORNL | Rearden, Brad | None | Status Report on UNF Characterization Enhancements in SCALE | Status Report on UNF Characterization Enhancements in SCALE | Status report on updated features of SCALE that provide acceleration and memory reduction for UNF Characterization analysis capability used in determination of nuclide inventories in used nuclear fuel | 2013-06-30 02:00 |  | 2013-06-30 01:00 |  | 2013 | Complete |  | Kevin T. Clarno | Bradley T. Rearden | None | CharacterizationStatusReport.pdf |  | SCALE, UNF Characterization
M5FT-13OR0914075 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M5 | 1.02.09.13.01 | ORNL | FT-13OR091301 | TR Hardware - ORNL | Feldman, Matt | None | Status Report on Monte Carlo Acceleration in SCALE | Status Report on Monte Carlo Acceleration in SCALE | Status report on updated features of SCALE that provide acceleration of continuous-energy Monte Carlo capabilities for criticality safety analysis | 2013-06-30 |  | 2013-06-30 01:00 |  | 2013 | Complete |  | Bradley T. Rearden | Bradley T. Rearden | None | MonteCarloStatusReport20130630.pdf
M2FT-14AN0902011 ULR. Predecisional Draft. | M2 | 1.02.09.02.01 | ANL | FT-14AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Nutt, Mark | Initial Waste Management Decision Support Framework | Initial Waste Management Decision Support Framework | Report describing initial decision analysis activities regarding 1) scope of the Pilot ISF, and 2) standardization. | 2014-06-30 09:00 |  | 2014-06-30 05:00 |  | 2014 | Complete | Decision Support Framework Conceptual Design and Process | Samsa, Michael | Samsa, Michael | None |  | FCRD-NFST-2014-000076 | decision support framework conceptual design process software aiding
M2FT-14AN0902031 ULR. PREDECISIONAL DRAFT | M2 | 1.02.09.02.03 | ANL | FT-14AN090203 | Next Generation Waste Management Logistics Simulation Tool - ANL | Samsa, Michael | Nutt, Mark | Next Generation Waste Management Systems Analysis Tool Status Report | Next Generation Waste Management Systems Analysis Tool Status Report | Next Generation Waste Management Systems Analysis Tool Status Report | 2014-07-31 12:00 |  | 2014-07-24 02:00 |  | 2014 | Complete | Status Report for Next-Generation Waste Management System Analysis Modeling Tool | St. Aubin, Jim | Samsa, Michael | None |  | FCRD-NFST-2014-000077 | NGSAM Status Report Logistics Model
M2FT-14AN0902032 ULR. PREDECISIONAL DRAFT | M2 | 1.02.09.02.03 | ANL | FT-14AN090203 | Next Generation Waste Management Logistics Simulation Tool - ANL | Nutt, Mark | Nutt, Mark | Waste Management Systems Analysis Capabilities and Data Requirements | Waste Management Systems Analysis Capabilities and Data Requirements | Waste Management Systems Analysis Capabilities and Data Requirements | 2013-12-13 10:00 |  | 2013-12-12 01:00 |  | 2014 | Complete | Waste Management Systems Analysis Capabilities and Data Requirements | Nutt, Mark | Nutt, Mark | None |  | FCRD-NFST-2014-000078
M2FT-14AN0902051 ULR. Predecisional Draft. | M2 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | Expanded Waste Management System Architecture Analyses | FY14 Waste Management System Architecture Analyses | Report describing additional waste management system analyses completed in FY14 that build on the FY12 and FY13 analyses. | 2014-09-30 09:00 |  | 2014-09-26 01:00 | Used Fuel Management System Architecture Evaluation, Fiscal Year 2014 | 2014 | Complete | Used Fuel Management System Architecture Evaluation, Fiscal Year 2014 | Nutt, Mark | Nutt, Mark | None | FY14 SA Report - FINAL (M2FT-14AN0902051) Rev 1.pdf FY14 SA Report - FINAL (M2FT-14AN0902051).docx | FCRD-NFST-2014-000079
M2FT-14HQ0911021 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.11.02 | DOE-HQ | FT-14HQ091102 | TR: Institutional - Industry Contract (Northwind) - DOE-HQ | Bates, Melissa | Feldman, Matt | Section 180(c) Table Top Exercise Package | Revise Section 180(c) Policy | Issue Section 180(c) Table Top Exercise Package | 2014-09-30 04:00 |  | 2014-09-29 06:00 | Complete | 2014 | Complete | Section 180(c) Table Top Exercise Package |  |  | None | Milestone lvl2_Section 180(c) Exercise Proposal.pdf | FCRD-NFST-2014-000088
M2FT-14HQ0911022 ULR. Draft. | M2 | 1.02.09.11.02 | DOE-HQ | FT-14HQ091102 | TR: Institutional - Industry Contract (Northwind) - DOE-HQ | Bates, Melissa | Feldman, Matt | Complete National Transportation Plan, Revision 0 | Complete National Transportation Plan, Revision 0 | Complete National Transportation Plan, Revision 0 | 2014-09-30 02:00 |  | 2014-09-29 04:00 | Complete | 2014 | Complete | Complete National Transportation Plan, Revision 0 |  |  | None | Final Draft DOE National Transportation Plan Deliverable clean rev1_092714.pdf | FCRD-NFST-2014-000089
M2FT-14HQ0912051 OUO | M2 | 1.02.09.12.05 | DOE-HQ | FT-14HQ091205 | TR: Operational - DOE-HQ | Bates, Melissa | Feldman, Matt | Develop User's Manual documenting the process for using the routing analysis tool | Develop User's Manual documenting the process for using the routing analysis tool | Develop User's Manual documenting the process for using the routing analysis tool | 2014-09-30 18:00 |  | 2014-09-29 04:00 | Complete | 2014 | Complete | Develop User's Manual documenting the process for using the routing analysis tool |  |  | None | START Version 1 1 User Manual - Final.pdf | FCRD-NFST-2014-000092
M2FT-14OR0901021 ULR. DRAFT. | M2 | 1.02.09.01.02 | ORNL | FT-14OR090102 | Project Management - ORNL | Wagner, John | Nutt, Mark | Nuclear Fuels Storage and Transportation Program Plan | Nuclear Fuels Storage and Transportation Program Plan | Nuclear Fuels Storage and Transportation Program Plan | 2014-06-30 06:00 |  | 2014-06-30 |  | 2014 | Complete |  |  |  | None |  | FCRD-NFST-2014-000075
M2FT-14OR0903011 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.03.01 | ORNL | FT-14OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Nutt, Mark | Expanded Functionality and Data Accessibility in CURIE | Expanded Functionality and Data Accessibility in CURIE | Expanded Functionality and Data Accessibility in CURIE | 2014-07-30 06:00 |  | 2014-07-30 |  | 2014 | Complete | Expanded Functionality and Data Accessibility in CURIE | Jarrell, Josh | Jarrell, Josh | None |  | FCRD-NFST-2014-000082
M2FT-14OR0904021 ULR. Predecisional Draft. | M2 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Complete Standardization Assessment Roadmap | Complete Standardization Assessment Roadmap | Complete Standardization Assessment Roadmap | 2014-02-22 04:00 |  | 2014-02-22 |  | 2014 | Complete | Project Plan for an Assessment of Standardized Canister Systems | Jarrell, Josh | Jarrell, Josh | None |  | FCRD-NFST-2014-000083
M2FT-14OR0905011 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Deployment of UNF Database and Analysis System, Version 1.0 | Deployment of UNF Database and Analysis System, Version 1.0 | Deployment of UNF Database and Analysis System, Version 1.0 | 2014-09-30 04:00 |  | 2014-09-30 02:00 | The Used Nuclear Fuel Storage Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS) Unified Database and Graphical User Interface have been distributed via digital versatile disc (DVD) to the control account managers within the Nuclear Fuels Storage and Transportation Planning Project and appropriate Department of Energy managers to fulfill the milestone completion criteria. | 2014 | Complete | Deployment of Used Nuclear Fuels (UNF) Database and Analysis System, Version 1.0 | Scaglione, John | Scaglione, John | None |  | FCRD-NFST-2014-000085 | database, used fuel
M2FT-14OR0905012 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Complete initial version of UNF database requirements document | Complete initial version of UNF database requirements document | Complete initial version of UNF database requirements document | 2014-03-31 02:00 |  | 2014-03-31 |  | 2014 | Complete | Requirements Document for UNF-ST&DARDS Unified Database | Peterson, Josh | Scaglione, John | None |  | FCRD-NFST-2014-000086 | unified database, requirements, UNF-ST&DARDS
M2FT-14OR0911012 | M2 | 1.02.09.11.01 | ORNL | FT-14OR091101 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | Report documenting the routing analysis for shipments from shutdown reactor sites | Report documenting the routing analysis for shipments from shutdown reactor sites | Report documenting the routing analysis for shipments from shutdown reactor sites | 2014-09-30 02:00 |  | 2014-09-30 04:00 | Level-2 milestone M2FT-14OR0911012, Report documenting the routing analysis for shipments from shutdown reactor sites (work package FT-14OR091101, TR: Institutional - ORNL, WBS No. 1.02.09.11) was completed and submitted. The report Proposed Standard Route Selection Process for Shipments of Spent Nuclear Fuel from Shutdown Sites provides a pathway to selection of routes for future shipments that satisfies regulatory requirements, takes applicable guidance and past experiences into account, and engages stakeholders in a collaborative process. | 2014 | Complete | Report documenting the routing analysis for shipments from shutdown reactor sites | Runyon, Tim | Feldman, Matt | None | Proposed Route Selection Process_93014_Final.pdf |  | Routing, Rail Routing, Route selection
M2FT-14OR0913011 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M2 | 1.02.09.13.01 | ORNL | FT-14OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | S-2043 Compliant Railcar System Requirements Document | S-2043 Compliant Railcar System Requirements Document | S-2043 Compliant Railcar System Requirements Document | 2014-03-31 06:00 |  | 2014-03-31 |  | 2014 | Complete | AAR S-2043 Cask Railcar System Requirements Document | Feldman, Matt | Feldman, Matt | None |  | FCRD-NFST-2014-000093
M2FT-14PN0912021 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M2 | 1.02.09.12.02 | PNNL | FT-14PN091202 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Revision 2 of Shutdown Sites Report | Revision 2 of Shutdown Sites Report | Revision 2 of Shutdown Sites Report | 2014-08-30 13:00 |  | 2014-08-28 03:00 |  | 2014 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Maheras, Steve | Maheras, Steve | None | FCRD-NFST-2014-000091_M2_red.pdf | FCRD-NFST-2014-000091 | Used nuclear fuel, shutdown sites, characterization of the used nuclear fuel, on-site infrastructure, near-site transportation
M2FT-14SR0902101 ULR. DRAFT | M2 | 1.02.09.02.10 | SRNL | FT-14SR090210 | Waste Management Functional and Operational Requirements - SRNL | Carter, Joe | Nutt, Mark | Waste Management System Functional and Operational Requirements | Waste Management System Functional and Operational Requirements | Waste Management System Functional and Operational Requirements | 2014-06-30 02:00 |  | 2014-06-30 |  | 2014 | Complete | Nuclear Fuels Storage and Transportation Requirements Document | Carter, Joe | Carter, Joe | None | NFST Requirements Document (Rev 1 - Final ).pdf | FCRD-NFST-2014-000081 | Nuclear Fuel Storage and Transportation
M3FT-14AN0901012 | M3 | 1.02.09.01.01 | ANL | FT-14AN090101 | Project Management - ANL | Nutt, Mark | Nutt, Mark | DRAFT Nuclear Fuels Storage and Transportation Program Plan | DRAFT Nuclear Fuels Storage and Transportation Program Plan | DRAFT Nuclear Fuels Storage and Transportation Program Plan | 2014-05-30 05:00 |  | 2014-05-30 01:00 |  | 2014 | Complete | Nuclear Fuel Storage and Transportation Planning Project (NFST): Near-Term Implementation Plan (Level-3 draft) | Nutt, Mark | Nutt, Mark | None |  | FCRD-NFST-2014-000343
M3FT-14AN0902013 ULR. Predecisional Draft. | M3 | 1.02.09.02.01 | ANL | FT-14AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Nutt, Mark | DRAFT Initial Waste Management Decision Support Framework | DRAFT Initial Waste Management Decision Support Framework | DRAFT of report describing initial decision analysis activities regarding 1) scope of the Pilot ISF, and 2) standardization. | 2014-05-30 14:00 |  | 2014-05-30 01:00 |  | 2014 | Complete | Nuclear Fuel Storage and Transportation Decision Support Framework Conceptual Design and Process | Samsa, Michael | Samsa, Michael | None |  | FCRD-NFST-2014-000344 | decision support framework, decision analysis, NFST
M3FT-14AN0902014 Per Matt Brainard: M3FT-13AN0902057 - Decision Roadmap was originally planned for FY14 completion on 11/29/2013 and was superseded by M3FT-14AN0902014 - Decision Roadmap, which was completed on 11/27/2013. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “The decision roadmap is a high level representation of the major decisions that will be required in the implementation of the Administration’s Strategy as it is currently interpreted.” Document Author/Owner: “Michael Samsa”. DMS Number: “FCRD-NFST-2014-000345”. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.02.01 | ANL | FT-14AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Nutt, Mark | Decision Roadmap | Decision Roadmap | The “decision roadmap” will outline major decision or “choice” milestones that require or are candidates for decision-analytic support. The decision roadmap will be a living document, updated as necessary to track future decision support requirements. | 2013-11-29 04:00 |  | 2013-11-27 02:00 |  | 2014 | Complete |  | Samsa, Michael | Samsa, Michael | None |  | FCRD-NFST-2014-000345
M3FT-14AN09020311 Per Matt Brainard: M3FT-13AN0902071 - Next Generation UNF Simulation Tool Development Plan was originally planned for FY14 completion on 10/31/2013 and was superseded by M3FT-14AN09020311 Next Generation UNF Simulation Tool Development Plan, which was completed on 12/13/2013. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Review draft of Next Generation Waste Management Logistics Simulation Tool Development Plan completed and delivered on schedule.” Document Author/Owner: “James St. Aubin, ANL”. Main Document Title: “Next Generation UNF Simulation Tool Development Plan”. DMS Number: “FCRD-NFST-2014-000346”. | M3 | 1.02.09.02.03 | ANL | FT-14AN090203 | Next Generation Waste Management Logistics Simulation Tool - ANL | Samsa, Michael | Nutt, Mark | Next Generation UNF Simulation Tool Development Plan | Next Generation UNF Simulation Tool Development Plan | Next Generation UNF Simulation Tool Development Plan | 2013-11-29 03:00 | 2013-12-13 03:00 | 2013-12-13 03:00 |  | 2014 | Completed Late | Next Generation UNF Simulation Tool Development Plan | St. Aubin, James | St. Aubin, James | None |  | FCRD-NFST-2014-000346
M3FT-14AN0902039 ULR. Draft | M3 | 1.02.09.02.03 | ANL | FT-14AN090203 | Next Generation Waste Management Logistics Simulation Tool - ANL | Samsa, Michael | Nutt, Mark | DRAFT Next Generation Waste Management Systems Analysis Tool Status Report | DRAFT Next Generation Waste Management Systems Analysis Tool Status Report | DRAFT Next Generation Waste Management Systems Analysis Tool Status Report | 2014-05-30 10:00 |  | 2014-05-29 02:00 |  | 2014 | Complete | Status Report for Next-Generation Waste Management System Analysis Modeling Tool | St. Aubin, James | Samsa, Michael | None |  | FCRD-NFST-2014-000347 | Next-Generation System Analysis Model,NGSAM, status report, NFST
M3FT-14AN0902052 ULR. Predcisional Draft. | M3 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | DRAFT Expanded Waste Management System Architecture Analyses | DRAFT FY14 Waste Management System Architecture Analyses | Draft of report describing additional waste management system analyses completed in FY14 that build on the FY12 and FY13 analyses. | 2014-08-29 09:00 |  | 2014-08-29 03:00 |  | 2014 | Complete | Used Fuel Management System Architecture Evaluation, Fiscal Year 2014 (L-3 Draft) | Nutt, Mark | Nutt, Mark | None | FY14 SA Report - Draft (M3FT-14AN0902052).docx.zip | FCRD-NFST-2014-000348
M3FT-14AN09020522 ULR. Per Matt Brainard: TSM Version 7 was originally planned for FY14 completion on 1/31/2014 and was superseded by M3FT-14AN09020522 - Total System Model Version 7 Development, which was completed on 1/31/2014. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Completion of TSM Version 7. TSM Version 7 is the initial operating version of the Total System Model. The milestone includes: 1) TSM Version 7, 2) TSM Version 7 User Manual, 3) TSM Version 7 Preprocessor User Manual.” Document Author/Owner: “Terranear PMC”. Main Document Title: “Total System Model Version 7 Development”. DMS Number: “FCRD-NFST-2014-000349”. | M3 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | Total System Model Version 7 Development | TSM Version 7 | Completion of TSM Version 7. TSM Version 7 is identified as the initial operating version of the model. The milestone will include: 1) TSM Version 7, and 2) TSM Version 7 User Manual. | 2014-01-31 06:00 |  | 2014-01-31 01:00 |  | 2014 | Complete | ?Total System Model Version 7 Development | Terranear PMC | Terranear PMC | None |  | FCRD-NFST-2014-000349
M3FT-14AN09020525 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | Total System Model Version 8 | TSM Version 8 | Completion of TSM Version 8. Will include 1) Users Manual, 2) Design Documents, 3) Validation Reports | 2014-09-30 07:00 |  | 2014-09-30 01:00 | Total System Model Version 8. Documents include: TSM User Manual: FCRD-NFST-2014-000632 TSM Pre-Processor User Manual: FCRD-NFST-2014-000350 These are NFST internal project reports and shall not be released for broad dissemination, including to OSTI. TSM Version TSM Version 8 installation files are posted to curie.ornl.gov for NFST use. | 2014 | Complete | Total System Model Version 8 | Gillespie, Scott | Gillespie, Scott | None | TSM-UM-01-8.0-00_20140925_Signed.docx TSM-UM-02-8.0-00_20140923_Signed.docx | FCRD-NFST-2014-000350
M3FT-14AN0902114 Per Matt Brainard: M3FT-13AN0902067 - Initial Execution Strategy Analysis Final Report was originally planned for FY14 completion on 3/31/2014 and was superseded by M3FT-14AN0902114 - Initial Execution Strategy Analysis Final Report, which was completed on 3/30/2014. Deliverable Form was submitted and subsequently approved in PICS:NE without an uploaded document. Deliverable is missing. Other information from the Deliverable Form includes: Narrative: “Report describing demonstration phase development of the NFST Execution Strategy Analysis tool.” Document Author/Owner: “Predicus LLC”. Deliverable Description: “Report describing demonstration phase development of the NFST Execution Strategy Analysis tool.” Main Document Title: “Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Demonstration Tool Development”. DMS Number: “FCRD-NFST-2014-000352”. Lab ID No - Other: “curie.ornl.gov”. Notes: “Transmitted to DMS via e-mail (wnutt@anl.gov to fctdms@inl.gov) on March 30, 2014”. ULR. NFST Working Document: External Release Requires DOE-NE approval ​ | M3 | 1.02.09.02.11 | ANL | FT-14AN090211 | Execution Strategy Analysis - ANL | Nutt, Mark | Nutt, Mark | Initial Execution Strategy Analysis Final Report | Initial Execution Strategy Analysis Final Report | Initial Execution Strategy Analysis Final Report | 2014-03-31 06:00 |  | 2014-03-30 01:00 |  | 2014 | Complete | Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Demonstration Tool Development | Predicus | Predicus | None |  | FCRD-NFST-2014-000352
M3FT-14AN0902115 This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.02.11 | ANL | FT-14AN090211 | Execution Strategy Analysis - ANL | Nutt, Mark | Nutt, Mark | Revised Execution Strategy Analysis Tool | FY13 Execution Strategy Analysis Final Report | Revised Execution Strategy Analysis Report - FY13 | 2014-10-31 05:00 |  |  | On schedule | 2014 | 90 Day |  |  |  | None
M3FT-14HQ0912054 ULR. Draft. | M3 | 1.02.09.12.05 | DOE-HQ | FT-14HQ091205 | TR: Operational - DOE-HQ | Bates, Melissa | Feldman, Matt | Develop Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD), Revision 0 | Develop Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD), Revision 0 | Develop Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD), Revision 0 | 2014-08-01 06:00 | 2014-10-30 | 2014-10-30 02:00 | Completed on 10/30/2014. | 2014 | Late | Requirements Document for Stakeholder Tool for Assessing Radioactive Transportation (START) |  |  | None | START Requirement Document.docx
M3FT-14OR0903019 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.03.01 | ORNL | FT-14OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Nutt, Mark | Preliminary Expanded Functionality and Data Accessibility in CURIE | Preliminary Expanded Functionality and Data Accessibility in CURIE | Preliminary Demonstration of new CURIE functionalities and capabilities | 2014-06-27 04:00 |  | 2014-06-05 |  | 2014 | Complete | CURIE Preliminary Demonstration | Josh Jarrell | Josh Jarrell | None |  | FCRD-NFST-2014-000354
M3FT-14OR09050112 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Report documenting models for dose rate analyses | Report documenting models for dose rate analyses | Report documenting models for dose rate analysis | 2014-08-29 |  | 2014-08-29 |  | 2014 | Complete | Models for Dose Rate Analyses | Radulescu, Georgeta | Scaglione, John | None | FCRD-NFST-2014-000358.pdf | FCRD-NFST-2014-000358
M3FT-14OR0905017 | M3 | 1.02.09.05.01 | ORNL | FT-14OR090501 | Characterization and Assessment - ORNL | Scaglione, John | Nutt, Mark | Complete assessment of NFST safety analysis capabilities for selected shutdown reactor sites | Safety Analysis Assessment for Selected Shutdown Reator Sites | Safety analysis assessment for selected shutdown reactor sites | 2014-09-12 04:00 |  | 2014-09-12 | M3 milestone completed documenting the nuclear safety analysis capabilities of Used Nuclear Fuel (UNF) Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). | 2014 | Complete | Safety Analysis Capabilities of the Used Nuclear Fuel Storage, Transportation and Disposal Analysis Resource and Data System | Banerjee, Kaushik | Scaglione, John | OUO |  | FCRD-NFST-2014-000360
M3FT-14OR09120123 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.12.01 | ORNL | FT-14OR091201 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Dose rates from selected loaded transportation casks | Analysis of actual transportation package including specific content | Report documenting model development and analysis of a selected transportation package from at least one of the 9 shutdown sites with actual as-loaded contents. Analysis results will include dose rates of the actual cask system during transportation, as well as temperatures of the fuel and cask components. Comparisons quantifying the difference between expected dose rates/temperatures and those assumed in routing and system modeling activities will be made where appropriate. | 2014-08-13 04:00 |  | 2014-08-13 |  | 2014 | Complete | Dose Rates for Selected Transportation Casks | Radulescu, Georgeta | Radulescu, Georgeta | None | FCRD-NFST-2014-000366-final.pdf | FCRD-NFST-2014-000366
M3FT-14PN0912024 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M3 | 1.02.09.12.02 | PNNL | FT-14PN091202 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Optimizing shutdown sites shipping campaigns | Optimizing shutdown sites shipping campaigns | Develop factors and considerations for optimizing shutdown sites shipping campaigns. | 2014-03-31 08:00 |  | 2014-03-31 06:00 |  | 2014 | Complete | Optimizing shutdown Sites Shipping Campaigns | Maheras, Steve | Maheras, Steve | None |  | FCRD-NFST-2014-000369
M3FT-14PN0912025 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M3 | 1.02.09.12.02 | PNNL | FT-14PN091202 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Site-specific campaign plan templates and SOWs | Site-specific campaign plan templates and SOWs | Prepare template and SOWs for site-specific campaign plans. | 2014-07-18 03:00 |  | 2014-07-18 03:00 |  | 2014 | Complete | PLANS FOR TRANSPORTATION CAMPAIGNS TO SHIP UNF AND GTCC WASTE FROM SHUTDOWN NUCLEAR POWER PLANT SITES | Maheras, Steve | Maheras, Steve | None | FCRD-NFST-2014-000370_M3.pdf FCRD-NFST-2014-000370_M3_Cover_Sheet.pdf FCRD-NFST-2014-000370_M3_Document_Review_Record.pdf FCRD-NFST-2014-000370_M3_Information_Release.pdf | FCRD-NFST-2014-000370
M3FT-14PN0912028 | M3 | 1.02.09.12.02 | PNNL | FT-14PN091202 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Rev 2 of Shutdown Sites Report | Draft Rev 2 Shutdown Sites Report | Draft of Rev 2 Shutdown Sites REport for review and comment | 41845 |  | 2014-07-25 03:00 |  | 2014 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Maheras, Steve | Maheras, Steve | None | FCRD-NFST-2014-000372_M3.pdf FCRD-NFST-2014-000372_M3_Cover_Sheet.pdf FCRD-NFST-2014-000372_M3_Information_Release.pdf | FCRD-NFST-2014-000372
M3FT-14SN0909012 | M3 | 1.02.09.09.01 | SNL | FT-14SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Nutt, Mark | Draft Report on Insights for Public Preference Surveys Related to Transportation and Siting of Radioactive Waste Management Facilities | Insights on Conducting Consent-Based Siting of Radioactive Waste Management Facilities | Submittal of draft of Guidance for Consent-Based Siting of Radioactive Waste Management Facilities to DOE for review | 2014-08-31 04:00 | 2014-09-17 10:00 | 2014-09-17 02:00 | Draft report submitted for programmatic review by CAM and NTD | 2014 | Completed Late | Insights of Conducting Consent-Based Siting of Radioactive Waste Management Facilities: Evidence from a Nationwide Survey of US Residents | Rechard, Rob | Rechard, Rob | None | EE Survey Analysis Draft 9 17 14.pdf | FCRD-NFST-2014-000363 | consent-based siting, radioactive waste management facilities, national preference survey
M3FT-14SN0909013 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.09.01 | SNL | FT-14SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Nutt, Mark | Siting Archive Database Update | Status Report on Progress in Siting of Nuclear Waste Facilities | Maintain the usefulness of the Siting Archive Database (accessed through CURIE at ORNL)by including (1) new formal reports and journal articles related siting activities throughout the world; and (2) activities reported in the press and social media on consideration of siting by various political and/or public interest bodies | 2014-09-30 06:00 |  | 2014-09-30 02:00 | Report submitted on the status in siting nuclear waste facilities in the international community as an update to the siting archive database | 2014 | Complete | Progress in Siting Nuclear Waste Facilities | Price, Laura | Rechard, Rob | None | Status on Siting of Nuclear Waste Facilities 10-30-14.pdf
M3FT-14SN0909014 ULR. NFST Working Document External Release Requires DOE-NE Approval​ | M3 | 1.02.09.09.01 | SNL | FT-14SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Howard, Rob | Study of the Evolution of Nuclear Energy Narratives in Multiple News Sources | Evolution of Narratives about Nuclear Energy and Nuclear Waste Management using Multiple Media Sources | Track and understand the flow of information on social media and mainstream news media outlets about issues related to nuclear energy, with special emphasis on nuclear waste management. | 2014-12-31 10:00 |  | 2014-12-29 02:00 | Work is progressing on evaluation of narratives in news outlests | 2014 | On Schedule | Study of Nuclear Narrativies Using Multiple Streams of Data | Jenkins-Smith, Hank | Rechard, Rob | None | Nuclear Narrative Report_12-21-14.pdf | FCRD-NFST-2014-000660 | US Public Perceptions; Radioactive Waste; Nuclear Energy
M3FT-14SN0912043 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. No SAND number | M3 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Weiner, Ruth | Feldman, Matt | Complete coupling of near-field model with RADTRAN | Coupling of Near Field Model With RADTRAN | The basic near-field model is complete, but coupling it to RADTRAN/RadCat remains to be done. This coupling will be completed in this milestone. | 2014-07-31 |  | 2014-07-30 02:00 |  | 2014 | Complete | The Impact of Cask Wake on Materials Released From a Type B Cask. | Weiner, Ruth | Clutz, Christopher | None | Report_ wake_impact.pdf | FCRD-NFST-2014-000374 | near field, wind wake, dispersion, fluid dynamics
M3FT-14SN0912049 | M3 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Sorenson, Ken | Feldman, Matt | Report on Unit Risk Factors for START | Report on Unit Risk Factors for START | The expanded Unit Risk Factor Report is a L3 milestone and will include an internal SNL review as well as an NSFT review. | 2014-07-02 02:00 | 2014-08-22 02:00 | 2014-08-01 06:00 |  | 2014 | Completed Late | RADTRAN Example Unit Risk Factors for START | Weiner, Ruth | Matthew Feldman | None | URFs_4_9_14_rev 3_7_7_28.docx URFs_4_9_14_rev 3_7_7_28.pdf |  | unit risk, RADTRAN, RAIL, HEAVY HAUL TRUCK, BARGE
M3FT-14SR0902104 ULR. Predecisional Draft. | M3 | 1.02.09.02.10 | SRNL | FT-14SR090210 | Waste Management Functional and Operational Requirements - SRNL | Carter, Joe | Nutt, Mark | DRAFT Waste Management System Functional and Operational Requirements | Draft Waste Management System Functional and Operational Requirements | DRAFT Waste Management System Functional and Operational Requirements | 2014-05-30 |  | 2014-05-29 |  | 2014 | Complete | Nuclear Fuels Storage and Transportation Requirements Document | Delley, Alexcia | Delley, Alexcia | None |  | FCRD-NFST-2014-000351 | Functional Requirements
M3FT-14SR0905023 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M3 | 1.02.09.05.02 | SRNL | FT-14SR090502 | Characterization and Assessment - SRNL | Smith, Pat | Nutt, Mark | NFST Inventory Report Revision 2 | NFST Inventory Report Revision 2 | Report submitted to the NTD and NFST Director. | 2014-09-15 |  | 2014-09-15 | This report provides information on the inventory of commercial spent fuel, referred in this report as used nuclear (UNF), as well as Government-owned UNF and HLW in the U.S. Department of Energy (DOE) complex. This revision 2 contains some corrections and updates to inventory data with regard to current storage locations for UNF discharged through 2013. The updated inventory is primarily due to the commencement of dry storage operations at Fermi 2, as well ongoing transitions at multiple reactor sites of fuel from wet storage to dry storage. The dry storage inventory data are current as of September 1, 2014. | 2014 | Complete | Nuclear Fuel Storage and Transportation Planning Project Inventory Basis, Revision 2 | Carter, Joe | Carter, Joe | None | FCRD-NFST-2013-000263 Rev. 2 - NFST Inventory Rev 2.pdf | FCRD-NFST-2014-000362 | Nuclear Fuel Storage and Transportation
M3FT-14SR0905024 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M3 | 1.02.09.05.02 | SRNL | FT-14SR090502 | Characterization and Assessment - SRNL | Carter, Joe | Nutt, Mark | Develop Next Generation Fuel Forecast Tool | Fuel Forecast Tool | Develop the next generation Fuel forecast tool. The existing tool is obsolete and must be revised to incorporate the GC-859 data when it becomes available. | 2014-09-30 02:00 |  | 2014-09-30 | This report provides information on the development of a revised tool to make projections of commercial spent nuclear fuel (SNF) discharges and inventory with time from commercial reactors. Described herein is the calculation methodology used in the tool. This projection tool utilizes historical, demographic, and dry storage input data from various sources, described herein, as well the Energy Information Administration (EIA) projected Annual Energy Outlook (AEO) report data to predict SNF discharges over time from individual reactors. | 2014 | Complete | A Revised Tool for Projecting of U.S. Commercial Spent Nuclear Fuel Inventory | Dennis Vinson | Dennis Vinson | None | FCRD-NFST-2014-000643 -A Revised Tool for Projecting of US.pdf |  | Revised Tool for Spent Nuclear Fuel
M3FT-14SR0905025 | M3 | 1.02.09.05.02 | SRNL | FT-14SR090502 | Characterization and Assessment - SRNL | Carter, Joe | Nutt, Mark | Cask Inventory Assessment | Cask Inventory Assessment | Complete a transportation and storage cask inventory assessment | 2014-08-29 02:00 |  | 2014-09-01 | This report uses the data contained in FCRD-NFST-2013-000263 to define the existing inventory of UNF in dry storage. UNF in wet storage (i.e. pools) is excluded from this assessment. This information is integrated with data on dry storage casks from the report, Storage and Transport Cask Data for Used Commercial Nuclear Fuel, 2013 U. S. Edition (ATI-TR-13047, August 9, 2013), in a Microsoft Access database. The database is used to produce queries for assessing the various systems used for the existing inventory of dry storage casks. The queries and reports developed include the following: • Storage casks (canistered and bare fuel) used at existing dry storage sites • Canister designs used at existing dry storage sites • Transfer casks applicable to the canisters used at existing dry storage sites • Transportation casks applicable to the canisters used at existing dry storage sites The database and this report will be revised in the future as the inventory of fuel in dry storage changes and as additional information becomes available. Section 2 provides a brief summary of the current inventory of dry storage casks for UNF as reported in FCRD-NFST-2013-000263. Section 3 describes the integrated database used for the assessment. Section 4 provides the results of the queries listed above. The database developed for this assessment is planned to be provided to the Oak Ridge National Laboratory (ORNL) for possible incorporation into the Nuclear Fuels Storage and Transportation (NFST) Unified Database. | 2014 | Completed Late | Dry Storage Cask Inventory Assessment | Robert H. Jones | Robert H. Jones | None | FCRD-NFST-2014-000602 Dry Storage Cask Inventory Assessment FINAL DRAFT Rev 0 9-2-14.pdf |  | Cask Inventory Assessment
M3FT-14SR0910021 ULR. Draft. | M3 | 1.02.09.10.02 | SRNL | FT-14SR091002 | Storage Design - SRNL | Smith, Pat | Carter, Joe | Complete preliminary, evaluation and documentation of bare fuel receipt and storage design concepts | Complete preliminary, evaluation and documentation of selected generic storage design concepts | Complete preliminary, evaluation and documentation of bare fuel receipt and storage design concepts | 2014-09-30 02:00 |  | 2014-09-29 | The objective of this study is to evaluate alternative generic design concepts for receiving, storing, handling, and repackaging spent nuclear fuel (SNF) canisters to enable systems analyses needed to provide quantitative estimates of the system benefits and/or impacts associated with potential future changes to the waste management system, including integration of storage into the waste management system and standardization of dry cask storage and/or transportation systems. | 2014 | Complete | Bare Fuel Receipt and Storage Design Concepts | Carter, Joe | Carter, Joe | None | FCRD-NFST-2014-00364 Bare Fuel Receipt and Storage Design Concept Revision 0 (Draft).pdf QA Cover -M3FT-14SR0910021.pdf | FCRD-NFST-2014-000364 | Bare Fuel Receipt
M4FT-14AN09020512 ULR. NFST Working Document: External Release Requires DOE-NE Approval | M4 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | TSL Modifications | Revised TSL-CALVIN Users Manual | Completed TSL Modifications needed to support NFST system analyses | 2014-07-31 05:00 |  | 2014-04-22 01:00 |  | 2014 | Complete | Transportation- Storage Logistics Model – CALVIN (TSL-CALVIN): Users Manual | William Nutt | William Nutt | None |  | FCRD-NFST-2014-000526 | Waste Management System Analysis, TSL-CALVIN, CALVIN
M4FT-14AN09020526 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.02.05 | ANL | FT-14AN090205 | Waste Management System Architecture Analysis - ANL | Nutt, Mark | Nutt, Mark | TSM Version 8 Support Documents | TSM Version 8 Support Documents | Documents supporting TSM Version 8. 1) TSM Version 8 Requirements Traceability Matrix, 2) TSM Version 8 Design Documents, 3) TSM Version 8 Validation Reports | 2014-09-17 04:00 |  | 2014-09-30 01:00 | Support documentation for the release of the Total System Model, Version 8. Developed by Terranear PMC. Documents are: Total System Model Maintenance Plan: FCRD-NFST-2014-000528 Rev. 1 Total System Model Version 8 Requirements Traceability Matrix: FCRD-NFST-2014-000529 Total System Model Version 8 Requirements Traceability Matrix: FCRD-NFST-2014-000529 TSM Version 8 Glossary: FCRD-NFST-2014-000633 TSM Version 8 CISF and Repository Design and Bases: FCRD-NFST-2014-000634 TSM Version 8 Transportation Design and Bases: FCRD-NFST-2014-000635 TSM Version 8 Preprocessor Database Design and Bases: FCRD-NFST-2014-000636 TSM Version 8 Validation Report: FCRD-NFST-2014-000637 TSM Version 8 Preprocessor Validation Report: FCRD-NFST-2014-000638 TSM Version 8 Report Generators Validation Report: FCRD-NFST-2014-000639 TSM Version 8 Work Order Algorithm Validation Report: FCRD-NFST-2014-000640 These are NFST internal project reports and shall not be released for broad dissemination, including to OSTI. | 2014 | Completed Late | Total System Model Version 8 Support Documents | Scott Gillespie (Terranear PMC) | Scott Gillespie (Terranear PMC) | None | TSM-DD-01-8.0-00_20140923_Signed.docx TSM-DD-02-8.0-00_20140916_Signed.docx TSM-DD-05-8.0-00_20140927_Signed.docx TSM-MP-01_052314.docx TSM-RTM-8.0-00_052814.docx TSM-UM-03-8.0-00_20140922_Signed.docx TSM-VAL-01-8.0-00_20140919_Signed.docx TSM-VAL-02-8.0-00_20140930_Signed.docx TSM-VAL-03-8.0-00_20140930_Signed.docx TSM-VAL-04-8.0-00_20140926_Signed.docx | FCRD-NFST-2014-000529 | Waste Management System Analysis, Total System Model
M4FT-14HQ0912055 | M4 | 1.02.09.12.05 | DOE-HQ | FT-14HQ091205 | TR: Operational - DOE-HQ | Bates, Melissa | Feldman, Matt | Develop Draft Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD) | Develop Draft Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD) | Develop Draft Stakeholder Tool for Assessing Radioactive Transport (START) System Requirements Document (SRD) | 2014-07-02 04:00 | 2014-10-30 | 2014-10-30 02:00 | Completed on 10/30/2014. | 2014 | Late | Requirements Document for Stakeholder Tool for Assessing Radioactive Transportation (START) |  |  | None | START Requirement Document_Draft.docx
M4FT-14OR0902043 ULR. Predecisional Draft. | M4 | 1.02.09.02.04 | ORNL | FT-14OR090204 | Next Generation Waste Management Logistics Simulation Tool - ORNL | Howard, Rob | Nutt, Mark | Next Generation Waste Management Systems Analysis Tool Status Report:ORNL Input | ORNL Input to Next Generation Waste Management Sytems Analysis Tool Status Report | Draft Input from ORNL on Next Generation Systems Analyses Status Report | 2014-05-16 |  | 2014-05-14 |  | 2014 | Complete | Integrating Unified Database with Next Generation Waste Management Systems Analysis Tool Status Report- FCRD-NFST-2014-000524 | Paul Miller | Robert Howard | None | Next Gen Logistics Status Report_M4_final_051614.docx | FCRD-NFST-2014-000524
M4FT-14OR0902061 ULR. Predecisional Draft. | M4 | 1.02.09.02.06 | ORNL | FT-14OR090206 | Waste Management System Architecture Analysis - ORNL | Howard, Rob | Nutt, Mark | Waste Management System Analysis Data ID, Collection, Verification | Waste Management System Analysis Data ID, Collection, Verification | Identification, Collection, and V&V of data needed for system analysis. | 2014-07-31 03:00 |  | 2014-07-31 |  | 2014 | Complete | Data Identification and Verification for Waste Management System Analyses | Bret van den Akker | Robert Howard | None | data-needs-verification_fcrd-nfst-2014-000530_31July2014.docx | FCRD-NFST-2014-000530
M4FT-14OR0902068 ULR. Predecisional Draft. | M4 | 1.02.09.02.06 | ORNL | FT-14OR090206 | Waste Management System Architecture Analysis - ORNL | Howard, Rob | Nutt, Mark | Expand and Refine Process Flow Diagram/Process Description | Expand and Refine Process Flow Diagram/Process Description | Expand and Refine Process Flow Diagram/Process Description | 2014-07-31 05:00 |  | 2014-07-31 |  | 2014 | Complete | Status Report on the Process Flow Diagrams and Node Descriptions Effort | Robby Joseph | Robert Howard | None | Status_Report_PFDNDs_July_31_2014.pdf | FCRD-NFST-2014-000531
M4FT-14OR0902069 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M4 | 1.02.09.02.06 | ORNL | FT-14OR090206 | Waste Management System Architecture Analysis - ORNL | Howard, Rob | Nutt, Mark | Worker Exposure Methodology and Parameters | Worker Exposure Methodology and Parameters | Complete worker exposure methodology and parameters for implementation into system models | 2014-05-30 03:00 |  | 2014-05-30 |  | 2014 | Complete | Worker Exposure Methodology for Incorporation in System Architecture Studies | Robby Joseph | Robby Joseph | None | M4FT-14OR0902069_Worker_Exposure_Methodology_and_Parameters_30May2014.docx | FCRD-NFST-2014-000532
M4FT-14OR09030110 ULR. Predecisional Draft. | M4 | 1.02.09.03.01 | ORNL | FT-14OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Jarrell, Josh | Nutt, Mark | Update CURIE documentation with new functionality | Update CURIE documentation with new functionality | Update "Centralized Used Fuel Resource for Information Exchange (CURIE)", FCRD-NFST-2013-000222 with new layout and additional search functionality. | 2013-11-22 06:00 |  | 2013-11-22 |  | 2014 | Complete | Update CURIE documentation with new functionality | Josh Jarrell | Josh Jarrell | None |  | FCRD-NFST-2014-000537
M4FT-14OR0904027 URL. DRAFT. NFST Working Document: Review Required Prior to External Release or Reference | M4 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Revise Concept of Operations Report | Revise Concept of Operations Report | Revise "Preliminary Used Fuel Management System Concept of Operations Including Options for Standardized Transportation, Aging, and Disposal Canisters, and Direct Disposal of Dual Purpose Canisters," FCRD-NFST-2013-000221 | 2014-10-24 02:00 |  |  | On Schedule | 2014 | 90 Day |  |  |  | None |  | FCRD-NFST-2014-000540
M4FT-14OR0910013 ULR. Predecisional Draft. | M4 | 1.02.09.10.01 | ORNL | FT-14OR091001 | Storage Design - ORNL | Howard, Rob | Carter, Joe | ORNL Input on Design Concept Trade Studies Report | ORNL Input to Design Options Studies | ORNL will provide draft text and figures as requested by SRNL to support the completion of the SRNL Level 3 and Level 2 milestones | 2014-06-30 |  | 2014-06-30 |  | 2014 | Complete | ORNL Input on Design Concept Trade Studies Report: Cask Maintenance Facility (CMF) Functions, Requirements and Concepts | Robert Howard | Robert Howard | None | Cask__Maintenance_facility_Final.docx | FCRD-NFST-2014-000543 | Cask Maintenance Facility Design
M4FT-14OR09120110 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​​ | M4 | 1.02.09.12.01 | ORNL | FT-14OR091201 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Identification of required Critical Infrastructure layers | Report Detailing Identification of required Critical Infrastructure layers | Report detailing identification of required Critical Infrastructure layers | 2014-01-17 04:00 |  | 2014-02-01 |  | 2014 | Completed Late | Identification of Required Critical Infrastructure Layers |  |  | None |  | FCRD-NFST-2014-000544
M4FT-14OR0912018 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.12.01 | ORNL | FT-14OR091201 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Intermodal Location Selection | Report detailing Intermodal Location Selection | Completion of Intermodal (transshipment) location selection, appropriately attributed, and in a geospatial format | 2014-01-31 06:00 |  | 2014-02-01 |  | 2014 | Completed Late | Intermodal Location Selection Status Report | Mark Tuttle | Mark Tuttle | None |  | FCRD-NFST-2014-000546 | TRAGIS, routing
M4FT-14OR09130118 | M4 | 1.02.09.13.01 | ORNL | FT-14OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Provide final generic SOW for Stranded Site Hardware Needs Analyses | Provide final generic SOW for Stranded Site Hardware Needs Analyses | Develop a generic statement of work for contractors to provide an analysis of a stranded sites hardware needs for the de-inventory process. | 2014-08-31 02:00 |  | 2014-08-29 |  | 2014 | Complete | Stament of Work - Initial Site-Specific De-Inventory Implementation Plan | Matthew Feldman | Matthew Feldman | None | FCRD-NFST-2014-000551_final_signed.pdf | FCRD-NFST-2014-000551
M4FT-14OR09130120 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M4 | 1.02.09.13.01 | ORNL | FT-14OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Report Documenting S-2043 related information including standard development and use histories and implementation requirements | Report Documenting S-2043 related information including standard development and use histories and implementation requirements | Document S-2043 related information including standard development and use histories and implementation requirements | 2014-01-31 02:00 |  | 2014-01-31 |  | 2014 | Complete | Report Documenting S-2043 related information including standard development and use histories and implementation requirements |  |  | None |  | FCRD-NFST-2014-000552
M4FT-14SN09120410 ULR. DRAFT. | M4 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Weiner, Ruth | Feldman, Matt | Draft of URFs in START | Draft of URFs in START | L4 milestone to predate l3 milestone | 2014-05-19 10:00 | 2014-07-01 02:00 | 2014-06-03 08:00 |  | 2014 | Completed Late | RADTRAN Unit Risk Files (Draft) | Weiner, Ruth | Weiner, Ruth | None | URFs_5_3_14_rev 1.pdf |  | radtran, unit risk, transportation, output
M4FT-14SN0912045 | M4 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Sorenson, Ken | Feldman, Matt | Package Performance Study progress report | Package Performance Study Progress Report | Provide a status report of the work done to date supporting stakeholder discussions and documentation of full-scale test protocols and alternatives. | 2014-03-28 08:00 |  | 2014-03-28 02:00 |  | 2014 | Complete | Full-scale tests Supporting transportation v.1 | Samuel Durbin | Samuel Durbin | None | Full-Scale_Tests_Supporting_Transportation_v1.pdf | FCRD-NFST-2014-000549 | package, cask, full scale test, drop test, package performance
M4FT-14SN0912047 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. No SAND number​ | M4 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Weiner, Ruth | Feldman, Matt | Provide unit risk files to Routing/Decision Support Tool | Unit Risk Files | Design Sufficient RADTRAN unit risk files to fulfil the needs of the Routing/Decision Support Tool | 2013-10-31 16:00 | 2013-11-20 04:00 | 2013-11-18 02:00 |  | 2014 | Completed Late | RADTRAN Unit Risk Files, Part 1 | Ruth Weiner | Ruth Weiner | None | URFsPart 1.docx | FCRD-NFST-2014-000568
M2FT-15AN0902011 ULR. Preliminary Draft. | M2 | 1.02.09.02.01 | ANL | FT-15AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Jarrell, Josh | Fiscal Year 2015 Application of NFST Decision Support Framework (Final) | Fiscal Year 2015 Application of NFST Decision Support Framework (Final) | FY15 Application of Waste Management Decision Support Framework | 2015-09-30 14:00 |  | 2015-09-22 02:00 | Adoption of a standardized canister system would impact the priority interests of reactor sites, the ISF operator, and the public. The motivation for this multi-objective evaluation is to better understand and quantify the relative value of incorporating SNF canister standardization into the waste management system from these different priority perspectives. The ultimate goal is to identify an alternative that creates the greatest value for the stakeholders who will be affected by the choice of a canister standardization policy should one be adopted. The multi-objective evaluation is based on three distinctly different priority perspectives – Reactor Priority; ISF Priority; and a Balanced Priority perspective. The Balanced Priority is intended to represent a broad and balanced public policy perspective. | 2015 | Complete | Multi-Objective Evaluation of the FY15 Canister Standardization Scenarios | Samsa, Michael | Samsa, Michael | None | Multi-Criteria Evaluation of Can Std Scenarios 2015-09-30 Final Rev 0 (2015-09-03 Results).pdf | FCRD-NFST-2015-000009 | decision analysis, multi-objective evaluation framework, canister standardization, stakeholders, objectives, scenarios
M2FT-15AN0902061 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M2 | 1.02.09.02.06 | ANL | FT-15AN090206 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Fiscal Year 2015 Waste Management System Architecture Analyses | Fiscal Year 2015 Waste Management System Architecture Analyses | Report describing waste management system architecture analyses performed in FY15 | 2015-09-30 05:00 |  | 2015-09-30 01:00 | This is the submission of the FY15 systems architecture report. | 2015 | Complete | Fiscal Year 2015 Waste Management System Architecture Analyses | Trail, Casey | Trail, Casey | None | 20150930-FY15WasteManagmentSystemArchitectureAnalysis.docx | FCRD-NFST-2015-000010 | Systems Architecture, Systems Analysis
M2FT-15ID0912051 | M2 | 1.02.09.12.05 | DOE-ID | FT-15ID091205 | TR: Operational - DOE-ID | Bates, Melissa | Feldman, Matt | Release of a fully functional Version 1.2 of START to the START user community | Version 1.2 of START | Release of a fully functional Version 1.2 of START to the START user community | 2015-05-27 04:00 |  | 2015-05-27 |  | 2015 | Complete | START Version 1.2 Rollout | Abkowitz, Mark | Abkowitz, Mark | None | START 1 2 Rollout.pdf | FCRD-NFST-2015-000019 | START
M2FT-15OR0901021 | M2 | 1.02.09.01.02 | ORNL | FT-15OR090102 | CX: Project Management - ORNL | Howard, Rob | Howard, Rob | Fiscal Year 2014 Nuclear Fuels Storage and Transportation Program Accomplishment Report | Fiscal Year 2014 Nuclear Fuels Storage and Transportation Program Accomplishment | Report summarizing key FY2014 NFST accomplishments. | 2014-12-17 04:00 |  | 2014-12-17 |  | 2015 | Complete | Nuclear Fuels Storage and Transportation Planning Project Fiscal Year 2014 Accomplishments Report | Howard, Rob | Howard, Rob | None | FY14 NFST Accomplishments_M2_final.pdf | FCRD-NFST-2015-000102
M2FT-15OR0901022 | M2 | 1.02.09.01.02 | ORNL | FT-15OR090102 | CX: Project Management - ORNL | Howard, Rob | Jarrell, Josh | Update Nuclear Fuels Storage and Transportation Program Plan | Nuclear Fuels Storage and Transportation Program Plan | Update FY14 NFST program plan to support out-year budget planning, including preparation for FY 2016 work planning, factoring in recent accomplishments and any new guidance from DOE. | 2015-06-30 08:00 |  | 2015-06-30 |  | 2015 | Complete | Nuclear Fuel Storage and Transportation Planning Project Near Term Implementation Plan | Howard, Rob | Howard, Rob | OUO |  | FCRD-NFST-2015-000103
M2FT-15OR0902071 ULR. Draft. | M2 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Interim Storage Facility Cost-Benefit Analysis | Interim Storage Facility Cost-Benefit Analysis | Report detailing the ISF cost-benefit analysis. | 2015-01-30 05:00 |  | 2015-01-30 |  | 2015 | Complete | Cost Implications of an Interim Storage Facility in the Waste Management System | Jarrell, Josh | Jarrell, Josh | None | M2FT-15OR0902071_ISF Cost Benefit Analysis_final.pdf | FCRD-NFST-2015-000104
M2FT-15OR0904021 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M2 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | FY15 Standardization Assessment Update | FY15 Standardization Assessment Update | Complete additional quantitative evaluation of transitioning to standardized canisters, building on FY14 results. | 2015-09-30 02:00 |  | 2015-09-30 | This evaluation builds on the Initial Standardized Canister System Evaluation (FY14 Level 2 Report), which focused on scenarios in which standardized canisters designed for storage, transportation, and disposal are loaded at reactors before being stored onsite or shipped to an interim storage facility (ISF) or repository. Instead, this evaluation focuses on shipment of bare fuel to an ISF and loading standardized canisters for storage and subsequent transportation and disposal from that point forward. New scenarios were developed and analyzed that focused on (1) bare SNF transported from reactors to an ISF in reuseable bare SNF casks with deployment of a standardized canister system deferred to the ISF, (2) alternative acceptance priority rankings based on conclusions from previous systems architecture studies, and (3) the impact of having to accommodate spent fuel in canisters of different sizes based on different repository geologies. | 2015 | Complete | Intermediate Standardized Canister System Evaluation | Jarrell, Josh | Jarrell, Josh | None | Intermediate_Standardized_Canister_System_Evaluation_Final.pdf | FCRD-NFST-2015-000105
M2FT-15OR0911011 ULR. Predecisional Draft. Rev 0: ULR. Attorney-Client Privilege and Predecisional. CURIE shows milestone number as M2FT-13ID911033 ​ | M2 | 1.02.09.11.01 | ORNL | FT-15OR091101 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | Issue Draft of the National Transportation Plan, Revision 3 | Draft National Transportation Plan, Revisions 3 | Issue Draft of the National Transportation Plan, Revision 3 | 2015-03-27 04:00 |  | 2015-03-27 |  | 2015 | Complete | Transportation Planning Framework for Removal of Commercial Spent Nuclear Fuel from Shutdown Reactors | Holm, Judith | Feldman, Matt | None | TPF_FCRD-NFST-2015-000108.pdf | FCRD-NFST-2015-000108 | Transportation, transportation planning, NTP
M2FT-15OR0911012 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M2 | 1.02.09.11.01 | ORNL | FT-15OR091101 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | Issue 180(c) Policy Implementation Exercise Lessons Learned Report | 180(c) Policy Implementation Exercise Lessons Learned Report | Issue Tabletop Exercise Lessons Learned Report | 2015-09-30 04:00 |  | 2015-09-30 | The report "Section 180(c) Proposed Policy Implementation Exercise DRAFT Interim Lessons Learned" provides a brief summary of the lessons learned to date during the ongoing Nuclear Waste Policy Act Section 180(c) Policy Implementation Exercise (the Exercise). The Exercise began last year and is scheduled to be completed in May 2016. A group of state and tribal officials has worked closely with DOE to design, participate in, and evaluate the results of this Exercise. Although the Exercise is not yet complete, several issues have already arisen that have led to discussions, and in many cases resolutions, between the participants and DOE. This report documents the resulting lessons learned to this point in the Exercise and will be updated upon the completion of the Exercise. Furthermore, it is anticipated that the knowledge gained from conducting the Exercise will inform future Section 180(c) policy and process development. | 2015 | Complete | Section 180(c) Proposed Policy Implementation Exercise DRAFT Interim Lessons Learned | Helvey, Elizabeth | Holm, Judith | None | Lessons learned_draft_9_29_15.pdf | FCRD-NFST-2015-000109 | NWPA, 180(c)
M2FT-15OR0912021 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Initial Shutdown Site Campaign Plan Report for Site #1 | Initial Shutdown Site Campaign Plan Report for Site #1 | Issue Initial Shutdown Site Campaign Plan Report for Site #1 | 2015-09-30 |  | 2015-09-30 | The report “Connecticut Yankee De-Inventory Study” was completed by AREVA Federal Services under subcontract #4000138474 issued by UT-Battelle in order to assist the US Department of Energy in laying the groundwork for implementing interim storage of spent nuclear fuel and high level radioactive waste, including associated transportation. Initial efforts to removed SNF from commercial nuclear power plants are expected to focus on the shutdown sites, sites at which all nuclear reactors have permanently ceased. This report is focused on the Connecticut Yankee (Haddam Neck) site in Haddam, Connecticut. Site information is provided using information from a variety of sources. The SNF inventory is detailed, and the site itself is described, including maps and pictures. Contact information is provided for the Connecticut officials who would need to be notified prior to the commencement of the de-inventory of the Connecticut Yankee site. Contacts are also provided for potential transportation contractors, including heavy-haul services, railroads, barge operators, and transportation cask suppliers. The concept of operations is detailed, including operations at the site and operations during transport. Loading of SNF into transportation casks is described, followed by a description of the heavy-haul trucking to a transload facility onto railcars. A timeline was also provided for mobilization of equipment and coordinating with the various entities which will participate in the de-inventory efforts, including heavy-haul providers, rigging providers, potentially maritime transport providers, and railroads. Safety and security plans are also outlined, along with an emergency response procedure. Finally, budget estimates are provided. Fees and state permits are estimated, along with labor, security, and management costs. Equipment, transportation services, and other site operations are included in the total figures. The estimate for the de-inventory of the site is $20.5M for a campaign expected to take 18 months. The information included in this report will be useful to NFST as it continues to lay the groundwork for interim storage of SNF, including associated transportation, by analyzing shutdown sites and developing needs assessments for equipment to be used in the removal of SNF from these sites. | 2015 | Complete | Connecticut Yankee De-Inventory Study | AREVA | Feldman, Matt | None | CY Cover memo complete_signed.pdf | FCRD-NFST-2015-000110 | Connecticut Yankee, Haddam Neck, de-inventory, campaign, transportation, shutdown site
M2FT-15OR0912022 This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M2 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Initial Shutdown Site Campaign Plan Report for Site #2 | Initial Shutdown Site Campaign Plan Report for Site #2 | Issue Initial Shutdown Site Campaign Plan Report for Site #2 | 2015-09-30 |  | 2015-09-30 | The report “Big Rock Point De-Inventory Study” was completed by AREVA Federal Services under subcontract #4000138474 issued by UT-Battelle in order to assist the US Department of Energy in laying the groundwork for implementing interim storage of spent nuclear fuel and high level radioactive waste, including associated transportation. Initial efforts to remove SNF from commercial nuclear power plants are expected to focus on the shutdown sites, sites at which all nuclear reactors have permanently ceased. This report is focused on the Big Rock Point site in Charlevoix, Michigan. Site information is provided using information from a variety of sources. The SNF inventory is detailed, and the site itself is described, including maps and pictures. Contact information is provided for the Michigan officials who would need to be notified prior to the commencement of the de-inventory of the Big Rock Point site. Contacts are also provided for potential transportation contractors, including heavy-haul services, railroads, barge operators, and transportation cask suppliers. The concept of operations is detailed, including operations at the site and operations during transport. Loading of SNF into transportation casks is described, followed by a description of the heavy-haul trucking to a transload facility onto railcars. A timeline was also provided for mobilization of equipment and coordinating with the various entities which will participate in the de-inventory efforts, including heavy-haul providers, rigging providers, potentially maritime transport providers, and railroads. Safety and security plans are also outlined, along with an emergency response procedure. Finally, budget estimates are provided. Fees and state permits are estimated, along with labor, security, and management costs. Equipment, transportation services, and other site operations are included in the total figures. The estimate for the de-inventory of the site is $8.3M for a campaign expected to take 8 months. The information included in this report will be useful to NFST as it continues to lay the groundwork for interim storage of SNF, including associated transportation, by analyzing shutdown sites and developing needs assessments for equipment to be used in the removal of SNF from these sites. | 2015 | Complete | Big Rock Point De-Inventory Study | AREVA | Feldman, Matt | None | M2FT-15OR0912022-BRP De-Inventory Plan.pdf | FCRD-NFST-2015-000111 | Big Rock Point, transportation, de-inventory, campaign, shutdown site
M3FT-15AN0901011 | M3 | 1.02.09.01.01 | ANL | FT-15AN090101 | CX: Project Management - ANL | Nutt, Mark | Nutt, Mark | DRAFT Fiscal Year 2014 Nuclear Fuels Storage and Transportation Program Accomplishment Report | DRAFT Fiscal Year 2014 Nuclear Fuels Storage and Transportation Program Accomplishment Report | Draft of report summarizing key FY2014 NFST accomplishments. | 2014-11-17 04:00 |  | 2014-11-16 |  | 2015 | Complete | Draft of Nuclear Fuel Storage and Transportation Planning Project FY14 Accomplishments Report | William Nutt | William Nutt | None | FY14 NFST Accomplishments_M3_Nov16Draft.docx | FCRD-NFST-2015-000161 | NFST, accomplishments
M3FT-15AN0902012. U LR. Predecisional Draft. | M3 | 1.02.09.02.01 | ANL | FT-15AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Jarrell, Josh | Fiscal Year 2015 Application of NFST Decision Support Framework (Draft) | Fiscal Year 2015 Application of NFST Decision Support Framework (Draft) | Documentation of pilot application of the decision Support framework | 2015-07-31 06:00 |  | 2015-07-22 04:00 |  | 2015 | Complete | Multi-Objective Evaluation of the FY15 Canister Standardization Scenarios | Michael Samsa | Michael Samsa | None |  | FCRD-NFST-2015-000163 | canister, standardization, decision support, multi-objective, evaluation, stakeholder
M3FT-15AN0902031 ULR. Predecisional Draft. | M3 | 1.02.09.02.03 | ANL | FT-15AN090203 | Execution Analysis Strategy - ANL | Saraeva, Natalia | Jarrell, Josh | FY15 Execution Strategy Analysis Tool Development and Application | FY15 Execution Strategy Analysis Tool Development and Application | Report detailed FY15 Execution Strategy Analysis tool development and application. | 2015-08-31 05:00 |  | 2015-08-31 |  | 2015 | Complete | Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Tool Development and Enhancements | Natalia V. Saraeva | Natalia V. Saraeva | None |  | FCRD-NFST-2015-000164 | ESA, NFST, Execution Strategy Analysis
M3FT-15AN0902044 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.02.09.02.04 | ANL | FT-15AN090204 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | FY15 Next-Generation Waste Management Systems Analysis Tool Status Report | FY15 Next-Generation Waste Management Systems Analysis Tool Status Report | Report describing the development of the Next-Generation Waste Management Systems Analysis tool in FY15. | 2015-09-30 07:00 |  | 2015-09-30 05:00 | FY15 Next-Generation Waste Management Systems Analysis Tool Status Report | 2015 | Complete | NFST FY2015 NGSAM Status Report | James St Aubin | James St Aubin | None | NFST FY2015 Status Report - FINAL-ver 2.pdf | FCRD-NFST-2015-000165 | NGSAM, System Analysis
M3FT-15AN0902062 | M3 | 1.02.09.02.06 | ANL | FT-15AN090206 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Draft Fiscal Year 2015 Waste Management System Architecture Analyses | DRAFT Fiscal Year 2015 Waste Management System Architecture Analyses | Draft report describing waste management system architecture analyses performed in FY15. This includes any needed TSL modifications. | 2015-08-31 09:00 |  | 2015-08-31 02:00 |  | 2015 | Complete | Draft Fiscal Year 2015 Waste Management Systems Architecture Analysis | Trail, Casey | Trail, Casey | None | 20150831-FY15SystemsArchitectureReport .docx | FCRD-NFST-2015-000166
M3FT-15AN0907011 Special Submission Note: “Internal working draft of the NFST NEPA Strategy. DO NOT DISTRIBUTE.” | M3 | 1.02.09.07.01 | ANL | FT-15AN090701 | NEPA - ANL | Nutt, Mark | Carter, Joe | NEPA Strategies/Approaches | Approaches for Addressing NEPA Requirements | Complete report describing alternatives for meeting NEPA requirements. | 2015-09-30 03:00 |  | 2015-09-30 01:00 | Internal working draft of the NFST NEPA Strategy | 2015 | Complete | Internal working draft of the NFST NEPA Strategy | Margaret Macdonell | Margaret Macdonell | None | NFST NEPA Strategy_internal draft_9-30-15pm.docx | FCRD-NFST-2015-000167
M3FT-15AN0910011 | M3 | 1.02.09.10.01 | ANL | FT-15AN091001 | ST: Storage Design - ANL | Liu, Yung | Carter, Joe | Aging Management Needs for the Pilot Interim Storage Facility and Beyond | Aging Management Needs for Pilot Interim Storage Facility and Beyond | The aging management needs for Pilot Interim Storage Facility and beyond will be established based on review of the existing aging management practices at both shutdown and renewed ISFSI sites, as well as updated guidance in NEI 14-03, NUREG-1927 and the new NRC NUREG on storage aging management to be released in the next 15 months. | 2015-09-30 11:00 |  | 2015-09-29 01:00 | The report completes the M3 milestone M3FT-15AN0910011 | 2015 | Complete | Aging Management Needs for the Pilot Interim Storage Facility and Beyond | Diercks, DR | Liu, YY | None | FCRD-NFST-2015-000769_092915.pdf | FCRD-NFST-2015-000769 | Aging management, pilot interim storage facility
M3FT-15IN0908012 | M3 | 1.02.09.08.01 | INL | FT-15IN090801 | CX: Communication Products - INL | Lientz, Amy | Jarrell, Josh | Draft Communication Strategy | Draft Communication Strategy | Develop draft strategy for communication of nuclear waste management to a variety of stakeholders. This draft will be reviewed by NFST and DOE staff prior to being finalized. | 2015-07-31 04:00 |  | 2015-07-31 06:00 |  | 2015 | Complete | SNF/HLW COMMUNICATION PLAN FINAL DRAFT - V.7 |  |  | None | COM-STRATEGY and PLANNING v7 May 2015 Costs Estimates.docx | FCRD-NFST-2015-000796
M3FT-15OR09050110 ULR. Predecisional Draft. | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Shielding Model Development and Implementation | UNF-ST&DARDS Shielding Model Development and Implementation | Shielding model development, testing and implementation for selected shutdown sites | 2015-08-20 02:00 |  | 2015-08-20 |  | 2015 | Complete | UNF-ST&DARDS Shielding Model Development and Implementation | Georgeta Radulescu | John M. Scaglione | None |  | FCRD-NFST-2015-000435
M3FT-15OR09050119 ULR. Predecisional Draft. Supersedes M3FT-14OR09050116. | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Howard, Rob | Report documenting status of characteristics database update activities | Status report on characteristics database update activities | Status report on characteristics database update activities | 2014-12-19 |  | 2014-12-19 |  | 2015 | Complete | Progress Report on the Update of the Characteristics of Potential Repository Wastes Database | Bret van den Akker | John M. Scaglione | None | Progress Report on the Update to the Characteristics of Potential Repository Wastes Database.pdf | FCRD-NFST-2015-000436 | CDB
M3FT-15OR09050120 Supersedes M3FT-14OR09050117. | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Assessment of newly acquired fuel characteristics data | Assessment of fuel characteristics data and recommendations for further data supplements | Report document conclusions of efforts associated with the newly acquired data from the fuel vendors and small set of utilities, and recommendations regarding the need for, benefits of, and estimated costs associated with acquiring additional information, e.g. NDRs for remaining plants and/or cycles of operation, to inform any future data requests. | 2015-06-19 | 2015-08-28 | 2015-09-11 | This report contains an assessment of the Crystal River Unit 3 (CR3) data provided by AREVA on June 18, 2015 | 2015 | Completed Late | Assessment of Newly Acquired Fuel Characteristics Data and Progress Report on the Characteristics Database Update | van den Akker, Bret | Scaglione, John | None | Assessment of Newly Acquired Fuel Characteristics Data and Progress Report v6[5].pdf | FCRD-NFST-2015-000437
M3FT-15OR0905014 | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Enhancement of Unified Database | Enhancement of Unified Database | Expansion of UDB to support system analysis tools, supplement CDB, and user interface development through Curie | 2015-08-31 02:00 |  | 2015-08-31 |  | 2015 | Complete | Unified Database Release Notes | Kaushik Banerjee | John M. Scaglione | None | unified_database_release_notes_Final.pdf | FCRD-NFST-2015-000438
M3FT-15OR0905015 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | User information document for UNF-ST&DARDS | User information document for UNF-ST&DARDS | Develop and maintain integrated user manual for UNF-ST&DARDS | 2015-07-15 04:00 |  | 2015-07-15 |  | 2015 | Complete | UNF-ST&DARDS User Manual | Kaushik Banerjee | John M. Scaglione | OUO |  | FCRD-NFST-2015-000439 | UNF-ST&DARDS, manual
M3FT-15OR0905018 This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M3 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Criticality Model Development and Implementation | UNF-ST&DARDS Criticality Model Development and Implementation | Criticality model development, testing and implementation for selected shutdown sites | 2015-07-31 04:00 |  | 2015-07-31 |  | 2015 | Complete | Criticality Process, Modeling and Status for UNF-ST&DARDS | Justin B. Clarity | John M. Scaglione | OUO |  | FCRD-NFST-2015-000440
M3FT-15OR0906014 ULR. Predecisional Draft. | M3 | 1.02.09.06.01 | ORNL | FT-15OR090601 | Regulatory - ORNL | Howard, Rob | Carter, Joe | Develop Draft ISF and associated Transportation Licensing Strategy | Draft Licensing Strategy for the ISF and Associated SNF Transportation to the ISF | Documented Licensing Strategy for the Pilot ISF and Larger ISF assuming they are co-located. Include licensing strategy and approaches as necessary to ensure integration between storage and transportation elements. FY 2015 iteration will emphasize ISF licensing strategy. | 2015-07-15 |  | 2015-07-15 |  | 2015 | Complete | Strategy for Licensing a Consolidated Interim Used Fuel Storage Facility | Bruce Bevard | Bruce Bevard | OUO |  | FCRD-NFST-2015-000442
M3FT-15OR0907043 ULR. This document contains information of a preliminary nature and is not intended for release. It is subject to revision or correction and therefore does not represent a final report.​ | M3 | 1.02.09.07.04 | ORNL | FT-15OR090704 | ST: NEPA - ORNL | Bevard, Bruce | Carter, Joe | Technical Approach for ECR Preparation | Technical Approach for ECR Preparation | Support development of Technical Approach for ECR Preparation (SRNL M3-15SR0907033) | 2015-09-30 06:00 |  | 2015-09-30 | The Oak Ridge National Laboratory input was provided to the Savannah River National Laboratory team in new text and comments to existing draft documents. The SRS deliverable FCRD-NFST-2015-000806, Revision 0 provides a proposed approach for the development of the technical content for ECR. | 2015 | Complete | NSFT NEPA_ECR Technical Approach_M3_ORNL-SPR-2015-592 | ORNL | ORNL | None | NSFT NEPA_ECR Technical Approach_M3_ORNL-SPR-2015-592.pdf | FCRD-NFST-2015-000807 | NEPA; ECR; Environmental Considerations Report; National Environmental Policy Act;
M3FT-15OR09120212 ULR. Predecisional Draft. | M3 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Initial 5-yr Transportation System Project Plan | Initial 5-yr Transportation System Project Plan | Development of a initial resource-loaded 5-yr project plan (Gantt Chart) for development of a large-scale transportation system for SNF and HLW. | 2015-08-21 |  | 2015-08-21 |  | 2015 | Complete | Nuclear Fuels Storage and Transportation: Initial Five-Year Transportation System Project Plan | Bill Reich | Matt Feldman | None |  | FCRD-NFST-2015-000443 | Transportation, transportation planning, transportation system development
M3FT-15OR0912027 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Updated dose rate report on selected loaded transportation casks | Updated dose rate report on selected loaded transportation casks | This will be an update to the FY14 report to develop at least two additional transportation cask dose rate analysis models for UNF-ST&DARDS and document the results. | 2015-09-11 |  | 2015-09-11 | Completed the M3 milestone M3FT-15OR0912027-“ Updated dose rate report on selected loaded transportation casks”. This report documents the application of automated radiation source term calculations and dose rate analyses performed with UNF-ST&DARDS of as-loaded transportation packages. Specifically, this work expanded the number of transportation package configurations to include the following: (1) Maine Yankee site spent nuclear fuel (SNF) (60 canisters); (2) Rancho Seco site SNF (21 canisters); (3) Trojan site SNF (34 canisters); and (4) Connecticut Yankee site SNF (39 canisters). This report presents the main characteristics of the transportation package models and UNF-ST&DARDS dose rate results for the simulated as-loaded transportation packages. Dose rate calculations for as-loaded transportation packages were performed as a function of decay time in selected calendar years between 2014 and 2100 for both normal conditions of transport (NCT) and hypothetical accident conditions (HAC). The simulations of as-loaded transportation packages show that dose rate values associated with actual package loadings could be significantly smaller than the regulatory dose rates. Realistic dose rate values based on actual contents may be used to enable a better understanding of the implications to, and planning for, the public’s health and safety related to the large-scale transportation (thousands of cask shipments) of used nuclear fuel. | 2015 | Complete | FY2015 Updated Dose Rate Report for Selected Loaded Transportation Casks | Georgeta Radulescu | Matt Feldman | None | M3FT-15OR0912027 - Dose Rate on Selected Loaded Casks.pdf | FCRD-NFST-2015-000444
M3FT-15OR0912028 ULR. DRAFT. | M3 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Unit dose rate factor analysis comparison as applied through START | Unit dose rate factor analysis comparison as applied through START | This report will provide a comparison between using the unit dose factors as calculated based on bounding SAR specifications, versus using the more detailed canister specific values. | 2015-04-17 |  | 2015-04-17 |  | 2015 | Complete | Transportation Route Dose Analysis using Unit Dose Factors and START | Kevin Connolly | Kevin Connolly | None | M3FT-15OR0912028-with cover sheet.pdf | FCRD-NFST-2015-000445 | udf, start, routing, dose assessment, transportation
M3FT-15OR0913012 ULR. DRAFT. | M3 | 1.02.09.13.01 | ORNL | FT-15OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Task Order 17 Comparison Report | Task Order 17 Comparison Report | Provide a report that compares and contrasts the results from both of the awardees of Task Order 17. | 2015-05-15 |  | 2015-05-15 |  | 2015 | Complete | Comparison Report for the High-Burnup Spent Nuclear Fuel Transportation Cask Design Study | Alsaed, Halim | Matt Feldman | None |  | FCRD-NFST-2015-000446
M3FT-15OR0913015 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.13.01 | ORNL | FT-15OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Hardware Needs Report for De-Inventorying the Shutdown Sites, | Hardware Needs Report for De-Inventorying the Shutdown Sites, | Summary report on hardware needs analysis for shutdown sites. Report to be | 2015-07-17 | 2015-09-25 | 2015-09-29 | The report "Initial Shutdown Sites Transportation Hardware Needs Analysis and Methods for Procurement Alternatives Evaluation" evaluates transportation hardware needs and describes approaches for analyzing alternatives for removing spent fuel and high-level waste from the shutdown sites. A list of transportation casks which would be required for the de-inventory efforts, along with the ancillary equipment associated with each cask, is presented, along with preliminary cost and schedule estimates for the complete de-inventory of the nine oldest shutdown sites. Approaches and methods for decision-making related to the acquisition of hardware resources are also included in the report. | 2015 | Completed Late | Initial Shutdown Sites Transportation Hardware Needs Analysis and Methods for Procurement Alternatives Evaluation | Connolly, Kevin | Matt Feldman | None | Transp HW Needs Analysis_Final_R0.docx | FCRD-NFST-2015-000447 | transportation, hardware, hardware needs
M3FT-15PN09120311 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.12.03 | PNNL | FT-15PN091203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Revision of the Comparative Assessment of Removing Spent Nuclear Fuel from Shutdown Sites | Comparative Assessment of Removing Spent Nuclear Fuel from Shutdown Sites | Revise the Comparative Assessment of Removing Spent Nuclear Fuel from Shutdown Sites, incorporating comments from reviewers. | 2014-11-21 |  | 2014-11-21 03:00 |  | 2015 | Complete | Comparative Assessment and Ranking of Shutdown Sites Based on the Resources, Constraints, Time, & Costs Associated with Removing Spent Nuclear Fuel & GTCC Waste | Steven J Maheras | Steven J Maheras | None | FCRD-NFST-2015-000001_M3.pdf | FCRD-NFST-2015-000001
M3FT-15SR0902091 ULR. Preliminary Draft. | M3 | 1.02.09.02.09 | SRNL | FT-15SR090209 | Waste Management System Architecture Analysis - SRNL | Carter, Joe | Jarrell, Josh | Fuel Projection Tool | Commercial Fuel Forecast Tool | SRNL will update the next generation fuel forecast tool based on the new GC-859 data, complete V&V activities and document the results. | 2015-03-31 05:00 |  | 2015-03-31 |  | 2015 | Complete | Description and Validation of a Revised Tool for Projecting of U.S. Commercial Spent Nuclear Fuel Inventory | Dennis Vinson | Joe T. Carter | None | FCRD-NFST-2015-000534 - Description and Validation of a Revised Tool.pdf | FCRD-NFST-2015-000534 | Tool for Projecting US Commercial SNF
M3FT-15SR0907033 | M3 | 1.02.09.07.03 | SRNL | FT-15SR090703 | ST: NEPA - SRNL | Carter, Joe | Carter, Joe | Technical Approach for ECR Preparation | Technical Approach for ECR Preparation | Draft Technical Approach for ECR Preparation report | 2015-09-30 04:00 |  | 2015-09-30 | The purpose of this report is to provide a proposed approach for the development of the technical content for each of the sections identified in the draft ECR outline developed for the milestone M4FT-15AN0907012. | 2015 | Complete | Technical Approach for ECR Preparation | Robert Jones | Robert Jones | None | FCRD-NFST-2015-000806 Technical Approach for ECR.pdf QA Cover Sheet - Technical Approach for ECR Preparation.pdf | FCRD-NFST-2015-000806 | Technical Approach for ECR
M4FT-15AN0902013 ULR. PREDECISIONAL DRAFT | M4 | 1.02.09.02.01 | ANL | FT-15AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Jarrell, Josh | Revised Decision Roadmap | Used Nuclear Fuel Management Decision Roadmap | Revised decision road map reconciled with the Execution Strategy Analysis model | 2015-01-30 05:00 |  | 2015-01-30 01:00 |  | 2015 | Complete | Nuclear Fuel Storage and Transportation FY15 Decision Roadmap Update. | Michael Samsa | Michael Samsa | None |  | FCRD-NFST-2015-000553 | deceision support framework system roadmap rosd map execution strategy analysis
M4FT-15AN0902014 ULR. Predecisional Draft. | M4 | 1.02.09.02.01 | ANL | FT-15AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Jarrell, Josh | Pilot Decision Support Application: Appraisal of NFST Alternatives | Pilot Decision Support Application: Appraisal of NFST Alternatives | An appraisal of alternative courses of action for an important UNF system component or strategy by using decision-analytic techniques to gain insights into how well each alternative will meet multiple and conflicting objectives and from the perspectives of multiple stakeholders. | 2015-04-30 07:00 |  | 2015-04-29 01:00 |  | 2015 | Complete | Multi-Objective Evaluation of the Preliminary FY15 Canister Standardization Scenarios | Michael E. Samsa | Michael E. Samsa | None | Multi-Criteria Evaluation of Can Std Scenarios 2015-04-30.pdf | FCRD-NFST-2015-000554 | multi-objective, decision support, multi-criteria, canister standardization
M4FT-15AN0902015 ULR. Predecisional Draft. | M4 | 1.02.09.02.01 | ANL | FT-15AN090201 | Waste Management Decision Support Framework - ANL | Samsa, Michael | Jarrell, Josh | Decision Support Workhop | NFST Decision Support Workshop | Workshop on alternatives appraisal using decision analytic techniques and featuring the selected pilot application as a case example. | 2015-06-30 06:00 | 2015-08-04 02:00 | 2015-08-04 02:00 |  | 2015 | Completed Late | Multi-Objective Evaluation Workshop and Review of the FY15 Canister Standardization Scenarios | Michael Samsa | Michael Samsa | None |  | FCRD-NFST-2015-000555 | canister, standardization, decision support, multi-objective, evaluation, stakeholder
M4FT-15AN0902045 ULR. Draft. | M4 | 1.02.09.02.04 | ANL | FT-15AN090204 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | Transition Plan for Migration From TSL/TSM to NGSAM | Transition Plan for Migration From TSL/TSM to NGSAM | Transition Plan for Migration From TSL/TSM to NGSAM | 2015-03-31 05:00 |  | 2015-03-31 01:00 |  | 2015 | Complete | Transition Plan for Next-Generation Waste Management System Analysis Modeling Tool | St. Aubin, James | St. Aubin, James | None |  | FCRD-NFST-2015-000558 | NGSAM
M4FT-15AN0904011 | M4 | 1.02.09.04.01 | ANL | FT-15AN090401 | CX: Standardization and Integration - ANL | Fortner, Jeffrey | Howard, Rob | Define FY15 Standardization Scenarios | FY15 Standardization Scenarios | Define and document standardization scenarios that will be evaluated in FY15 as a draft section that will be included in M3FT-15OR0904025, Draft of FY15 Standardization Assessment Update. | 2014-11-28 06:00 |  | 2014-11-24 03:00 |  | 2015 | Complete | Fiscal Year 2015 Standardized Canister System Evaluation – Scenario Definitions | Mark Nutt | Mark Nutt | None | FY15_Standardization_Assessment_Scenarios.docx | FCRD-NFST-2015-000560 | Standardization
M4FT-15ID0911029 ULR. Predecisional Draft. | M4 | 1.02.09.11.02 | DOE-ID | FT-15ID091102 | TR: Institutional (North Wind) - ID | Helvey, Elizabeth | Feldman, Matt | Incorporate Industry Input into Routing Methodology Report | Incorporate Industry Input into Routing Methodology Report | Incorporate Industry Input into Routing Methodology Report | 2015-01-30 06:00 | 2015-09-23 02:00 | 2015-09-30 02:00 | Comments were received from industry on the Routing Methodology Report but not incorporated into the document. Had the comments been incorporated, it would have prevented on-going discussions with the state officials involved. | 2015 | Completed Late | Incorporate Industry Input into Routing Methodology Report |  |  | None |  | FCRD-NFST-2015-000566
M4FT-15OR0901024 | M4 | 1.02.09.01.02 | ORNL | FT-15OR090102 | CX: Project Management - ORNL | Howard, Rob | Howard, Rob | Update NFST Near Term Implementation Plan | NFST Near Term Implementation Plan | Update the NFST Near Term Implementation Plan to address customer comments | 2014-12-31 02:00 |  | 2014-12-31 |  | 2015 | Complete | Nuclear Fuels Storage and Transportation Planning Project Near Term Implementation Plan | Rob Howard | Rob Howard | None | NFST Near-Term Implementation Plan - 31Dec2014_Deliverable.pdf | FCRD-NFST-2015-000640 | NFST Implementation Plan
M4FT-15OR0902052 ULR. DRAFT. | M4 | 1.02.09.02.05 | ORNL | FT-15OR090205 | Waste Management System Analysis Tool Development and Maintenance - ORNL | van den Akker, Bret | Jarrell, Josh | JTOM Software Development | Completion of JTOM software application | Complete the design, development, and testing of JTOM transportation fleet logistics functionality into NGSAM; leveraging approaches and algorithms in the TSL-TOM transportation logistics simulation tool | 2015-03-31 08:00 |  | 2015-03-31 |  | 2015 | Complete | JTOM Programmer's Guide | Ingrid Busch | Ingrid Busch | None | JTOM Programmers Guide.pdf | FCRD-NFST-2015-000641
M4FT-15OR0902053 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M4 | 1.02.09.02.05 | ORNL | FT-15OR090205 | Waste Management System Analysis Tool Development and Maintenance - ORNL | van den Akker, Bret | Jarrell, Josh | NGSAM Dry Storage Loading Logic | NGSAM Dry Storage Loading Logic | Design and develop the following logic to be included in NGSAM Phase 2 – Prototype 2: Improved loading of dry storage canisters and casks [i.e., zone-loading per certificates of compliance] | 2015-06-19 01:00 |  | 2015-06-19 |  | 2015 | Complete | Dry Storage Loading Algorithm | Kaushik Banerjee | Kaushik Banerjee | OUO |  | FCRD-NFST-2015-000642 | Dry Storage Loading Logic
M4FT-15OR0902054 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M4 | 1.02.09.02.05 | ORNL | FT-15OR090205 | Waste Management System Analysis Tool Development and Maintenance - ORNL | van den Akker, Bret | Jarrell, Josh | NGSAM Transportation Overpack/Cask Radiation Exposure Limit Logic | NGSAM Transportation Overpack/Cask Radiation Exposure Limit Logic | Design and develop the following logic to be included in NGSAM Phase 2 – Prototype 2: determining whether loaded dry canisters/casks [actual loads or projected to be loaded] and bare fuel casks [projected to be loaded] meet 10CFR71 radiation exposure limits. | 2015-07-17 05:00 |  | 2015-07-17 |  | 2015 | Complete | NGSAM Transportation Overpack/Cask Radiation Exposure Limit Logic | Georgeta Radulescu | Georgeta Radulescu | OUO |  | FCRD-NFST-2015-000643 | Radiation, transportation, logic
M4FT-15OR09020710 ULR. Draft. | M4 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Review of past, current, and future system scenarios | Past, Current, and Future System Scenarios Report | This report will document the scenarios that have been analyzed to date (FY12, FY13, and FY14 System Architecture Reports as well as Standardization-related analyses), the scenarios that will be analyzed in FY15, and the potential scenarios for FY16 and beyond. | 2015-03-20 02:00 |  | 2015-03-20 |  | 2015 | Complete | Review of Past, Current and Future System Scenarios | Abiodun Adeniyi | Abiodun Adeniyi | None | Review of Past Current and Future Systems Scenarios_03202015_0.pdf | FCRD-NFST-2015-000644
M4FT-15OR0902072 ULR. Predecisional Draft. | M4 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Expand and refine process flow diagram/process node descriptions | Status Report on the Process Flow Diagrams and Process Node Descriptions Effort | Expand and refine process flow diagram/process node descriptions. This year's work will expand computational capabilities within the Process Flow Diagrams and will also provide input to the Standardization effort. | 2015-07-31 03:00 |  | 2015-07-31 |  | 2015 | Complete | Status Report on the Process Flow Diagrams and Process Node Descriptions Effort | Robby Joseph | Josh Jarrell | OUO |  | FCRD-NFST-2015-000645
M4FT-15OR0902073 | M4 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Howard, Rob | Worker Exposure Methodology and Parameters | Worker Exposure Methodology and Parameters for Incorporation in System Architecture Studies | Update document "Worker Exposure Methodology for Incorporation in System Architecture Studies" as needed. | 2015-05-29 01:00 |  | 2015-05-29 |  | 2015 | Complete | Worker Exposure Methodology for Incorporation in System Architecture Studies | Kaushik Banerjee | Josh Jarrell | None |  | FCRD-NFST-2015-000646
M4FT-15OR0902079 Same DMS number as for M2FT-15OR0902071, Rev 1 | M4 | 1.02.09.02.07 | ORNL | FT-15OR090207 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Howard, Rob | Draft ISF Cost-Benefit Analysis | Draft Interim Storage Facility Cost Benefit Analysis | Draft report detailing the ISF Cost-Benefit Analysis which will serve as input for the M2-milestone due in January. | 2014-11-21 03:00 |  | 2014-11-21 |  | 2015 | Complete | Implications of an Interim Storage Facility in the Waste Management System | Josh Jarrell | Josh Jarrell | None | M4FT-15OR0902079_ISF Cost Benefit Analysis_Rev8.docx | FCRD-NFST-2015-000648
M4FT-15OR0902101 ULR. Draft. | M4 | 1.02.09.02.10 | ORNL | FT-15OR090210 | Waste Management Functional and Operational Requirements - ORNL | Howard, Rob | Jarrell, Josh | Requirements Identification and Revision Based on TO 16 60% Design Review | Requirements Identification and Revision Based on Task Order 16 60% design review | Letter Report identifying new requirements, lower tier requirements, existing requirements needing revision based on the results of the 60% Design Review of Task Order 16 | 2015-03-31 01:00 | 2015-04-10 | 2015-03-23 |  | 2015 | Complete | Requirements Identification and Revision Based on TO16 60% Design Review | Bruce Bevard | Bruce Bevard | None | Requirements Identification and Revision Based on TO16 60% Design Review.docx | FCRD-NFST-2015-000649
M4FT-15OR0903011 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M4 | 1.02.09.03.01 | ORNL | FT-15OR090301 | Collaborative Document and Data Access System (CURIE) - ORNL | Joseph, Robby | Jarrell, Josh | Document UNF-ST&DARDS data integration and accessibility with CURIE | Document UNF-ST&DARDS data integration and accessibility with CURIE | This deliverable will document the current UNF data (specifically from the UNF-ST&DARDS Unified Database) available and accessible on CURIE. It will also provide a description of the available capabilities for users to access this data. | 2015-01-23 01:00 |  | 2015-01-23 |  | 2015 | Complete | Document UNF-ST&DARDS data integration and accessibility with CURIE | Robby Joseph | Robby Joseph | None | FCRD_NFST_2015_000650_Final.pdf | FCRD-NFST-2015-000650
M4FT-15OR0904024 | M4 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Revise Concept of Operations Report | Concept of Operations Revision | This deliverable will revise the concept of operations report to include the most recent information from the Task Order 16 work (specifically, diagrams and available images) as well as incorporate Task Order 14 repackaging information. | 2015-05-01 04:00 |  | 2015-05-01 |  | 2015 | Complete | Preliminary Spent Fuel Management System Concept of Operation | Riley Cumberland | Josh Jarrell | None |  | FCRD-NFST-2015-000653
M4FT-15OR0904026 URL. NFST Working Document: Review Required Prior to External Release or Reference | M4 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Revise Concept of Operations Report | Concept of Operations Revision | Revise the concept of operations report to include a fleet and cask maintenance facility and to incorporate information from the Task Order 18 and Task Order 21 reports. | 2015-10-23 |  |  | On Schedule | 2015 | 90 Day |  |  |  | None |  | FCRD-NFST-2015-000654
M4FT-15OR09050111 ULR. Predecisional Draft. | M4 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Depletion and Decay analyses capability | UNF-ST&DARDS Depletion and Decay analyses capability | Expand UNF-ST&DARDS depletion and decay analyses capability | 2015-01-30 02:00 |  | 2015-01-30 |  | 2015 | Complete | Fuel Assembly Characterization for GC 859 Incorporation into the Unified Database | J. B. Clarity | Scaglione, John | None | fuel_chacterization_final.pdf | FCRD-NFST-2015-000655
M4FT-15OR0905016 ULR. DRAFT | M4 | 1.02.09.05.01 | ORNL | FT-15OR090501 | CX: Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Containment Analyses Capability of UNF-ST&DARDS | Containment Analyses Capability of UNF-ST&DARDS | Development of UNF-ST&DARDS containment analysis capability | 2015-03-16 04:00 |  | 2015-03-16 |  | 2015 | Complete | Containment Analysis Capability of UNF-ST&DARDS | Georgeta Radulescu | Scaglione, John | None | FCRD-NFST-2015-000657.pdf | FCRD-NFST-2015-000657
M4FT-15OR0910023 ULR. PREDECISIONAL | M4 | 1.02.09.10.02 | ORNL | FT-15OR091002 | ST: Storage Design - ORNL | Bevard, Bruce | Carter, Joe | Document Results of TO 16 60% Design Review | Summary of Task Order 16 60% Design Review | Letter Report documenting the results of the TO 16 60 % Design Review. Emphasis will be placed on the lines of inquiry developed prior to the review. Letter report may include meeting minutes supplied by Tech Source. | 2015-01-30 |  | 2015-02-01 |  | 2015 | Completed Late | Summary of Task Order 16 60% Design Review | Bruce Bevard | Bruce Bevard | Predecisional |  | FCRD-NFST-2015-000659 | Task Order 16
M4FT-15OR0910024 ULR. Predecisional Draft. | M4 | 1.02.09.10.02 | ORNL | FT-15OR091002 | ST: Storage Design - ORNL | Bevard, Bruce | Carter, Joe | Document Results of Task Order 16 90% Design Review | Task Order 16 90% Design Review Letter Report | Letter Report documenting the results of the 90% Design Review for Task Order 16. Emphasis will be placed on the lines of inquiry developed prior to the review. The report may make use of meeting minutes provided by Tech Source. | 2015-05-29 |  | 2015-05-29 |  | 2015 | Complete | Summary of Task Order 16 (Generic Design Alternatives for Dry Storage of Used Nuclear Fuel) 90% Design Review | Bruce Bevard | ORNL | None |  | FCRD-NFST-2015-000660 | ISF; Pilot ISF; 90% Design Review; Task Order 16;
M4FT-15OR0910027 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.10.02 | ORNL | FT-15OR091002 | ST: Storage Design - ORNL | Bevard, Bruce | Carter, Joe | Cask and Fleet Maintenance Facilities Design Concept Studies | Cask and Fleet Maintenance Facilities Concepts Letter Report | Continue to develop Fleet Maintenance Facility Concepts and Cask Maintenance Facility Concepts and document in a letter report | 2015-05-29 |  | 2015-05-29 |  | 2015 | Complete | Fleet Maintenance Facility Conceptual Design and Cost Estimate and Cask Maintenance Facility Conceptual Design | Bruce Bevard | ORNL | None |  | FCRD-NFST-2015-000661 | Rail repair faciity; Fleet maintenance facility, Cask maintenance facility;
M4FT-15OR09120211 ULR. PREDECISIONAL | M4 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Report on Methodology and Results for Calculation of Generic Unit Risk Factors for START | Report on Methodology and Results for Calculation of Generic Unit Risk Factors for START | Development of a report detailing the methodology and results of the calculation of Unit Risk Factors for normal conditions of transportation for START. | 2015-01-30 |  | 2015-01-30 |  | 2015 | Complete | Unit Dose Factors for Incident-Free Spent Nuclear Fuel Transportation | Kevin Connolly | Kevin Connolly | None | M4FT-15OR09120211-with cover sheet.pdf | FCRD-NFST-2015-000662 | routing, dose assessment, udf
M4FT-15OR09120213 ULR. Predecisional Draft. | M4 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Draft SNF Transportation Incident Database | Draft SNF Transportation Incident Database | Development of a database that documents incidents related to the transport of SNF | 2015-06-30 |  | 2015-06-30 |  | 2015 | Complete | Past Incidents in Transporting Spent Nuclear Fuel and High Level Radioactive Waste | Kevin Connolly | Kevin Connolly | OUO |  | FCRD-NFST-2015-000663 | SNF, transportation, incident, accident, contamination, database, reporting
M4FT-15OR0912029 ULR. Predecisional | M4 | 1.02.09.12.02 | ORNL | FT-15OR091202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Document Progress on NAS Going the Distance Recommendations | Report Documenting Progress on NAS Going the Distance Recommendations | Review recommendations of the National Academy of Sciences’ report Going the Distance and document progress on meeting recommendations contained therein | 2014-12-19 |  | 2014-12-19 |  | 2015 | Complete | Implementing US National Academies Recommendations for SNF Transportation | Kevin Connolly | Kevin Connolly | None | M4FT-15OR0912029 - final.pdf | FCRD-NFST-2015-000664 | NAS, BRC, Strategy
M4FT-15PN0905022 | M4 | 1.02.09.05.02 | PNNL | FT-15PN090502 | CX: Characterization and Assessment - PNNL | Maheras, Steve | Jarrell, Josh | CHARMER Database and Documentation | Updated CHARMER Database and Documentation | Updated CHARMER database and documentation letter report. | 2015-09-16 |  | 2015-09-19 06:00 | This report is an M4 report that describes the CHARMER code algorithm in detail, and the models used to create the prerun library of temperature data. It also covers installing and running the CHARMER code. CHARMER was developed using the Python language to generate dry storage canisters (DSC) temperature profiles for various NUHOMS horizontal dry cask storage modules. The DSC temperature profiles generated by CHARMER are compatible with COBRA-SFS, and can be used as an input boundary set for COBRA-SFS. The CHARMER code uses select data from a pre-run library of results to set up boundary temperature conditions for a DSC within a storage module. The pre-run library contains a collection of calculated DSC boundary temperature distributions from simulations of several DSC configurations in a range of ambient temperatures and decay heat loads. With a user-specified ambient temperature and decay heat load for a selected canister and module geometry in the used fuel disposition library, CHARMER produces a compatible input boundary set for COBRA-SFS. | 2015 | Completed Late | CHARMER: A Python Based Program for Generating COBRA-SFS Boundary Condition | Steve Maheras | Steve Maheras | None | FCRD-NFST-2015-000703_M4_Charmer_signed.pdf | FCRD-NFST-2015-000703 | UNF-ST&DARDS, CHARMER, COBRA-SFS, thermal modeling, NUHOMS, horizontal dry storage casks, dry storage canisters
M4FT-15PN0912039 | M4 | 1.02.09.12.03 | PNNL | FT-15PN091203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Cask Transportability Report | Draft Cask Transportability Report | Draft cask transportability report. | 2015-08-04 03:00 |  | 2015-08-04 12:00 |  | 2015 | Complete | Draft Cask Transportability Report | Steve Maheras | Steve Maheras | None | FCRD-NFST-2015-000705_M4_signed.pdf | FCRD-NFST-2015-000705 | UNF-ST&DARDS, COBRA-SFS, thermal modeling, vacuum drying, dry storage casks, dry storage canisters
M4FT-15SN0902021 ULR. Draft. | M4 | 1.02.09.02.02 | SNL | FT-15SN090202 | Waste Management Decision Support Framework - SNL | Kalinina, Elena | Jarrell, Josh | Federal Policy Metrics Taxonomy | Federal Policy Metrics Taxonomy Report | Develop federal policy metrics taxonomy, including decision metrics, measures, and other relevant factors that have been applied in alternatives appraisal and decision support for previous nuclear waste disposal initiatives. | 2015-02-27 16:00 |  | 2015-02-27 02:00 |  | 2015 | Complete | Federal Policy Metrics Taxonomy | Elena A. Kalinina | Elena A. Kalinina | None | Federal Metrics Taxonomy 02-27-15.pdf | FCRD-NFST-2015-000718 | Decision analysis, decision objective, objective performance measure, hierarchical structure
M4FT-15SN0902022 Per Matt Brainard: Note: “Only the cover sheet of the document was uploaded. Report is being maintained with the author. It will be transmitted to the Document Management System when Official Use Only questions related to DOE directed markings are resolved.” DMS No. FCRD-NFST-2015-000719. Main Document Title: “Stakeholders Perspective Reference Metrics Taxonomy.” | M4 | 1.02.09.02.02 | SNL | FT-15SN090202 | Waste Management Decision Support Framework - SNL | Kalinina, Elena | Jarrell, Josh | Stakeholders Perspective Reference Metrics Taxonomy | Stakeholders Perspective Reference Metrics Taxonomy Report | Develop stakeholders metrics taxonomy, including decision metrics, measures, and other relevant factors based on the available public hearing documentation / testimony from prior nuclear waste disposal initiatives. | 2015-07-10 14:00 |  | 2015-07-10 02:00 |  | 2015 | Complete | Stakeholders Perspective Reference Metrics Taxonomy | Elena A. Kalinina | Elena A. Kalinina | None | Cover Sheet FCRD-NFST-2015-000719 Signed.pdf | FCRD-NFST-2015-000719 | Decision support framework, stakeholders values, hierarchical structures, decision objectives
M4FT-15SN0902084 ULR. DRAFT. Deliberative Process Pre-Decisional-- Privileged and Confidential FOIA exempt per Exemption 5 of the FO​ | M4 | 1.02.09.02.08 | SNL | FT-15SN090208 | Waste Management System Architecture Analysis - SNL | Kalinina, Elena | Jarrell, Josh | Shutdown Site Evaluation | Shutdown Site Evaluation | Integrate with shutdown site evaluations and concepts for Pilot ISF. | 2015-05-31 16:00 |  | 2015-05-29 02:00 |  | 2015 | Complete | Shutdown Reactor Site Evaluation | Elena Kalinina | Elena Kalinina | None | FCRD-NFST-2015-000722_05-29-15.pdf | FCRD-NFST-2015-000722 | shutdown reactors, de-inventorying schedule, transportation analysis, transportation costs, loaded-consist miles
M4FT-15SN0909012 | M4 | 1.02.09.09.01 | SNL | FT-15SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Howard, Rob | Conceptual themes for national survey on public perceptions of nuclear waste management | Conceptual Themes for Evaluating Public Perceptions in 2015n 2015 | report on conceptual themes that will guide development of the survey questionnaire on public perceptions of nuclear waste management with emphasis on transportation and interim storage | 2015-04-30 02:00 | 42185.0833 | 2015-06-30 02:00 |  | 2015 | Completed Late | Conceptual Development of Issues Pertaining to Public Views on the Storage and Transportation of Spent Nuclear Fuel | Rob P. Rechard | Rob P. Rechard | None |  | FCRD-NFST-2015-000724 | spent nuclear fuel storage, spent nuclear fuel transportation, public perference survey
M4FT-15SN0912061 ULR. DRAFT. | M4 | 1.02.09.12.06 | SNL | FT-15SN091206 | TR: Risk Factors - SNL | Kalinina, Elena | Feldman, Matt | Unit Risk Factors V&V | Unit Risk Factor V&V Rpr | Validation and verification of the unit risk factors. | 2015-03-31 12:00 |  | 2015-03-25 02:00 |  | 2015 | Complete | Unit Risk Factor Validation and Verification | Elena Kalinina | Elena Kalinina | None | FCRD-NFST-2015-000725_Rev0.pdf | FCRD-NFST-2015-000725
M4FT-15SR0902112 | M4 | 1.02.09.02.11 | SRNL | FT-15SR090211 | Waste Management Functional and Operational Requirements - SRNL | Carter, Joe | Jarrell, Josh | Functions and Requirements TBD/TBV Path Forward Matrix | Functions and Requirements TBD/TBV Path Forward Matrix | Document | 2015-02-28 01:00 |  | 2015-02-25 |  | 2015 | Complete | Functions and Performance Requirements | Carter, Joe | Carter, Joe | None | Functions and Performance Requirements.pdf | FCRD-NFST-2015-000741 | To Be Verified and To Be Determined.
M4FT-15SR0910033 | M4 | 1.02.09.10.03 | SRNL | FT-15SR091003 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | TO16 90% Design Review Lines of Inquiry | TO16 90% Review Loines of Inquiry | TO16 90% design review Lines of Inquiry | 2015-02-11 04:00 | 2015-02-28 | 2015-02-25 |  | 2015 | Completed Late | Lines of Inquiry, 90% Design Review | Jones, Robert | Jones, Robert | None |  | FCRD-NFST-2015-000745 | Lines of Inquiry, 90% Design Review
M5FT-15OR0904023 ULR. Predecisional Draft. | M5 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | None | Summarize TO14 system-specific information | Summarize TO14 system-specific information | This deliverable will be satisfied by preparing a summary of the differences between the TO14 information and past repackaging assumptions. This report will be rolled into the Savannah River Level 5 milestone report in the Systems Architecture Work Package due at the end of May. | 2015-01-16 04:00 |  | 2015-01-15 |  | 2015 | Complete | Task Order 14 Report Data Summary | Cumberland, Riley | Cumberland, Riley | None | TO-14_Review_Final.pdf | FCRD-NFST-2015-000751
M5FT-15OR0904028 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M5 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | None | Review and update the at-reactor system analysis data input | Review and update the at-reactor system analysis data input | This report will use information from Task orders 12, 17, 18, 21, and any other information sources to update the input data related to reactors for systems analysis, specifically with a focus on standardization. Document the bases for the revised data in a sections for incorporation in "Data Identification and Verification for Waste Management System Analyses" | 2015-05-29 02:00 |  | 2015-05-29 |  | 2015 | Complete | Review and Update of At-Reactor System Analysis Data Input | Cumberland, Riley | Josh Jarrell | None |  | FCRD-NFST-2015-000752
M5FT-15OR0904029 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M5 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | None | Review and update the cask system analysis data input | Review and update the cask system analysis data input | This report will use information from Task orders 12, 17, 18, 21, and any other information sources to update the input data related to cask systems for systems analysis, specifically with a focus on standardization. Document the bases for the revised data in a sections for incorporation in "Data Identification and Verification for Waste Management System Analyses" | 2015-05-29 02:00 |  | 2015-05-29 |  | 2015 | Complete | Review and Update of Cask System Data Input | Cumberland, Riley | Josh Jarrell | None |  | FCRD-NFST-2015-000753
M2FT-16AN090101011 | M2 | 1.02.09.01.01.01 | ANL | FT-16AN09010101 | CX: Project Management - ANL | Nutt, Mark | Jarrell, Josh | FY15 NFST Accomplishments Report | FY15 NFST Accomplishments Report | Report summarizing key FY2015 NFST accomplishments | 2015-12-18 05:00 |  | 2015-12-18 01:00 |  | 2016 | Complete | FY15 NFST Accomplishments Report | Nutt, Mark | Nutt, Mark | None | FY15 NFST Accomplishments (M2FT-16AN090101011).docx | FCRD-NFST-2016-000083 | NFST, Nuclear Fuel Storage and Transportation Planning Project, Implementation Plan
M2FT-16AN090102032 | M2 | 1.02.09.01.02.03 | ANL | FT-16AN09010203 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | Deployment of NGSAM, Version 2.1.1 software | Deployment of NGSAM Version 2.1.1 software | This release of NGSAM will include improved (1) at-reactor transportation cask thermal and radiation exposure algorithms, (2) initial logic to support at-ISF operations, and (3) key NGSAM feature requests identified in the Systems Architecture WP. | 2016-02-26 13:00 |  | 2016-02-26 02:00 |  | 2016 | Complete | Completion of NFST Planning Project Level 2 Milestone, “Deployment of NGSAM Version 2.1.1 Software” | St. Aubin, Jim | St. Aubin, Jim | None |  | FCRD-NFST-2016-000084 | Systems Analysis Model, NGSAM, SNL, logistics
M2FT-16AN090201011 M3FT-16OR090201024 and M4FT-16OR090201028 were not stand-alone documents; they were incorporated into M2FT-16AN090201011 | M2 | 1.02.09.02.01.01 | ANL | FT-16AN09020101 | CB: Siting Process - ANL | Saraeva, Natalia | Howard, Rob | Draft "What We’ve Heard” Document on Consent | Draft "What We’ve Heard” Document on Consent | A draft of the "What We've Heard" document following receipt of written information from the public and stakeholders and from regional meetings. | 2016-09-23 |  | 2016-08-22 |  | 2016 | Complete | NFST CBS Designing a Consent Based Siting Process: Summary of Public Input Draft Report | Saraeva, Natalia | Saraeva, Natalia | None | Draft Summary Report M2-8-22-2016.docx | FCRD-NFST-2016-000089 | consent-based siting, integrated waste management,waste management, transparency,
M2FT-16OR090102051 ULR. DRAFT. NFST Working Document: External Release or Reference Requires DOE-NE Approval. | M2 | 1.02.09.01.02.05 | ORNL | FT-16OR09010205 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Consolidated Interim Storage from an Integrated Systems Perspective | Consolidated Interim Storage from an Integrated Systems Perspective | Develop a report documenting consolidated interim storage from an Integrated systems perspective. | 2016-06-30 04:00 |  | 2016-06-30 |  | 2016 | Complete | Summary'of' Consolidated'Interim Storage'Advantages and Disadvantages from an Integrated Systems Perspective | Jarrell, Josh | Jarrell, Josh | None | 2016-06-30_ISF-Implications_M2_final.pdf | FCRD-NFST-2016-000086
M2FT-16OR090104011 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M2 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Standardization Assessment Report | Standardization Assessment Report | Deliver Final Standardization Assessment Report. This report will incorporate findings from FY14 and FY15 standardization evaluation reports as well as any potential scenarios and analysis that occurs in FY16 | 2016-05-30 04:00 |  | 2016-05-30 |  | 2016 | Complete | FY16 Standardized Canister System Evaluation | Jarrell, Josh | Jarrell, Josh | None | FY16_Standardization_Assess_M2_2016-05_30_final.pdf | FCRD-NFST-2016-000085
M2FT-16OR090402021 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M2 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Humbolt Bay Implementation Plan | Humbolt Bay Implementation Plan | Selected vendor will submit an Initial Site-Specific De-Inventory Implementation Plan for the Humboldt Bay site. | 2016-04-29 02:00 |  | 2016-04-29 |  | 2016 | Complete | Humboldt Bay De-Inventory Study | AREVA | Feldman, Matt | None | HUMBOLDT BAY REPORT (Rev. 1).pdf | FCRD-NFST-2016-000092 | Humboldt Bay, campaign, transportation, logistics, shutdown site
M2FT-16SN090201031 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ No SAND number on report. | M2 | 1.02.09.02.01.03 | SNL | FT-16SN09020103 | CB: Siting Process - SNL | Rechard, Rob | Howard, Rob | Insights from Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Insights from Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Report describing insights gained from surveys related to transportation and siting of nuclear waste facilities conducted in FY2016. | 2016-09-30 12:00 |  | 2016-09-29 02:00 | M2 document, Insights from public surveys related to consent-based siting and radioactive waste management in the US, delivered. Report discussed 4 topics in 4 self-contained chapters: (1) public view on the nuclear fuel cycle;(2) public awareness about nuclear issues and institutional trust; (3) public preferences on storage and disposal options; and (4) public preferences related to consent-based siting. | 2016 | Complete | Insights from Public Surveys Related to Consent-Based Siting and Radioactive Waste Management in the United States | Rechard, Rob | Rechard, Rob | None | EE16 Overview Analysis Report 09-29-16.pdf | FCRD-NFST-2016-000090 | consent-based siting; radioactive waste management; public preference survey
M3FT-16AN090102021 ULR. NFST Working Document: External Release or Reference Requires DOE-NE | M3 | 1.02.09.01.02.02 | ANL | FT-16AN09010202 | Execution Strategy Analysis - ANL | Saraeva, Natalia | Jarrell, Josh | FY16 Execution Strategy Analysis Tool Development and Application, Part I | FY16 Execution Strategy Analysis Tool Development and Application, Part I | Rev 3 of the M3 report FCRD-NFST-2015- 000352. Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Tool Development and Enhancements. The report will incorporate enhancements made to the ESA model and analysis performed between 9/1/15 and 2/29/16, including but not limited to update of the front end of the model, analysis of design alternatives. | 2016-02-29 05:00 |  | 2016-02-29 |  | 2016 | Complete | Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Tool Development and Enhancements | Nutt, Mark | Argonne National Laboratory | None | FY16 NFST ESA (M3FT-15AN090203).pdf | FCRD-NFST-2016-000448 | NFST, waste management, system analysis, execution strategy analysis, GoldSim, Monte Carlo, risks, uncertainties, constraints
M3FT-16AN090102022 | M3 | 1.02.09.01.02.02 | ANL | FT-16AN09010202 | Execution Strategy Analysis - ANL | Saraeva, Natalia | Jarrell, Josh | FY16 Execution Strategy Analysis Tool Development and Application, Part II | FY16 Execution Strategy Analysis Tool Development and Application, Part II | report will be the Rev 4 of the M3 report FCRD-NFST-2015- 000352. Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Tool Development and Enhancements. The report will incorporate enhancements made to the ESA model and analysis performed between 3/1/16 and 9/30/16, including but not limited to analysis of clearing shutdown sites. | 2016-09-30 05:00 |  | 2016-09-30 | Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Development of Version 2.0 of the ESA Tool | 2016 | Complete | Nuclear Fuel Storage and Transportation Execution Strategy Analysis: Development of Version 2.0 of the ESA Tool | Nutt, Mark | Saraeva, Natalia | None | M3FT-16AN090102022.pdf | FCRD-NFST-2016-000461 | NFST, ESA, Execution Strategy Analysis, waste management,
M3FT-16AN090102034 ULR Predecisional Draft. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.01.02.03 | ANL | FT-16AN09010203 | Waste Management System Analysis Tool Development and Maintenance - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM FY2016 Status Report | NGSAM FY2016 Status Report | Report on FY2016 NFST collaboration and completed NGSAM-related activities from all DOE labs involved. | 2016-09-30 12:00 |  | 2016-09-30 01:00 | NGSAM Accomplishments for FY 2016 | 2016 | Complete | FY2016 Next-Generation System Analysis Model (NGSAM) Status Report |  |  | None | NFST FY2016 Status M3FT Report - FINAL 29-SEP-2016.pdf | FCRD-NFST-2016-000463
M3FT-16AN090102042 ULR Predecisional Draft.​ This document contains preliminary information and must be reviewed by the originating facility before public release. | M3 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Fiscal Year 2016 Waste Managment System Architecture Analyses | Fiscal Year 2016 Waste Managment System Architecture Analyses | Report describing the system architecture analyses performed in FY 16. | 2016-09-30 11:00 |  | 2016-09-29 01:00 | Report completed | 2016 | Complete | Fiscal Year 2016 Waste Management System Architecture Analysis | Casey D. Trail | Casey D. Trail | None | 20160930-FY16WasteManagementSystemArchitectureAnalysis.pdf | FCRD-NFST-2016-000462 | Systems Architecture, Systems Analysis
M3FT-16AN090102043 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Systems Analysis Tool Transition and Benchmarking report | Systems Analysis Tool Transition and Benchmarking report | Report documenting the findings from the NGSAM benchmark analysis against legacy systems analysis tools. | 2016-03-31 13:00 |  | 2016-03-31 01:00 |  | 2016 | Complete | NGSAM Transition and Benchmarking Report | Casey D. Trail | Casey D. Trail | None | 20160331-FINAL_BechmarkReportM3v2.pdf | FCRD-NFST-2016-000449
M3FT-16AN090201012 | M3 | 1.02.09.02.01.01 | ANL | FT-16AN09020101 | CB: Siting Process - ANL | Saraeva, Natalia | Howard, Rob | Preliminary Draft What we've heard document on consent | Preliminary Draft What we've heard document on consent | preliminary draft "what we've heard document on consent developed as a result of public meetings and other interactions with stakeholders and public | 2016-08-15 |  | 2016-08-15 |  | 2016 | Complete | NFST CBS Designing a Consent Based Siting Process: Summary of Public Input Draft Report | Natalia Saraeva; | Natalia Saraeva | None | Draft Summary Report -combined-8-15-2016.docx | FCRD-NFST-2016-000466 | consent based siting process; consent; fairness; trust;
M3FT-16OR090104016 NFST Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Standardization Assessment Review and Path Forward Report | Standardization Assessment Review and Path Forward Report | High-level report which summarizes the three previous standardization evaluations, incorporates other considerations, and provides options for future activities related to standardization in the waste management system. | 2016-08-19 02:00 |  | 2016-08-19 |  | 2016 | Complete | Standardization in the Integrated Waste Management System: What We Have Learned and Potential Next Steps | Jarrell, Josh | Jarrell, Josh | None | 2016-08_Standardization-Path-Forward_final.pdf | FCRD-NFST-2016-000457
M3FT-16OR090105015 | M3 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | Automated fuel characteristics report generation through simplified interface | Automated CDB report generation through simplified interface | Enhancement of the Unified Database to include fuel characteristics information and automated report generation (PDF, HTML, LATEX) through simplified interface (e.g., UNF-ST&DARDS and CURIE) | 2016-06-24 02:00 |  | 2016-06-24 |  | 2016 | Complete | Characteristics of Potential Repository Waste | Peterson, Joshua | Scaglione, John | None | CharacteristicsReport_signed.pdf | FCRD-NFST-2016-000453 | Fuel characteristics report
M3FT-16OR090105016 | M3 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Criticality Model Development and Implementation | UNF-ST&DARDS Criticality Model Development and Implementation | Criticality model development, testing and implementation | 2016-07-29 02:00 |  | 2016-07-29 |  | 2016 | Complete |  | Clarity, Justin | Scaglione, John | None | CRITICALITY_REPORT_7_29_16_rev1_FINAL.pdf | FCRD-NFST-2016-000455 | UNF-ST&DARDS, criticality
M3FT-16OR090105017 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approva​l | M3 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Thermal Model Development and Implementation | UNF-ST&DARDS Thermal Model Development and Implementation | Thermal model development, testing and implementation | 2016-08-12 02:00 |  | 2016-08-12 |  | 2016 | Complete | UNF-ST&DARDS Thermal Model Development and Implementation | Kevin Robb | John Scaglione | None | UNF-ST&DARDS_Thermal_Update_2016.pdf | FCRD-NFST-2016-000456 | unf-st&dards, thermal, transient
M3FT-16OR090105018 URL. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | Jarrell, Josh | UNF-ST&DARDS Shielding Model Development and Implementation | UNF-ST&DARDS Shielding Model Development and Implementation | Shielding model development, testing and implementation for transportation casks | 2016-08-19 02:00 |  | 2016-06-29 |  | 2016 | Complete | UNF-ST&DARDS Shielding Model Development and Implementation for Fiscal Year 2016 | Georgeta Radulescu | John Scaglione | None | NFST-shielding-dev&impl-2016.pdf | FCRD-NFST-2016-000458 | UNF-ST&DARDS, shielding
M3FT-16OR090201023 Per Rob Howard: I could not find M3FT-13OR0902029; however, M3FT-16OR090201023 “Preliminary Siting Factors and Considerations v1_4-29-16_R2.pdf” is a revised and updated version of the same deliverable. OUO. Predecisional Draft. Deliberative Process Pre-Decisional Privileged and Confidentia​l | M3 | 1.02.09.02.01.02 | ORNL | FT-16OR09020102 | CB: Siting Process - ORNL | Howard, Rob | Howard, Rob | Draft Update of ISF Siting Considerations Document | ISF Siting Considerations | Preliminary Draft of the updated the ISF Siting Considerations Document | 2016-04-29 |  | 2016-04-29 |  | 2016 | Complete | Preliminary Site Factors and Considerations for Interim Used Fuel Storage Facilities | Randy Belles | Robert Howard | OUO |  | FCRD-NFST-2016-000464
M3FT-16OR090401052 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.04.01.05 | ORNL | FT-16OR09040105 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | Transportation Planning Framework Status Report | Transportation Planning Framework Status Report | Support development of position papers for eventual inclusion in the Transportation Planning Framework and provide status report | 2016-03-25 | 2016-04-22 | 2016-04-29 |  | 2016 | Completed Late | Transportation Planning Framework Status Report | Chuck Messick | Matt Feldman | None | Final Draft TPF Status Report.pdf | FCRD-NFST-2016-000471 | TPF, transportation, institutional
M3FT-16OR090401053 | M3 | 1.02.09.04.01.05 | ORNL | FT-16OR09040105 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | Routing Methodology Development Status Report | Routing Methodology Development Status Report | Support Routing Methodology Development and provide status report | 2016-07-29 |  | 2016-07-29 |  | 2016 | Complete | Draft Status Report on Development of Routing Methodology for SNF | Bailey, Melissa | Feldman, Matt | None | M3FT-16OR090401053.pdf | FCRD-NFST-2016-000476 | transportation, SRG, NTSF, routing, institutional
M3FT-16OR090402026 | M3 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | UNF ST&NDARDS Activities | Updated dose rate report on selected loaded transportation casks | Continue development of the UNF ST&NDARDS analysis tool | 2016-09-09 |  | 2016-09-02 | This report presents the characteristics of the transportation package models for dose rate calculations and UNF-ST&DARDS dose rate results for 214 HI-STAR 100 transportation packages containing SNF canisters in storage at 12 independent spent fuel storage installations. Dose rate calculations for transportation packages were performed for selected calendar years between 2020 and 2100, modelling an as-loaded configuration. The maximum normal conditions of transport (NCT) dose rate at 2 m from the lateral surface of the vehicle varies from approximately 2 to 11 mrem/h among the 214 transportation packages evaluated at 2020. Of the 214 transportation packages, 12 would exceed the regulatory dose rate limit of 10 mrem/h at 2 m from the lateral surface of the transportation vehicle under NCT. All 214 transportation packages are projected to comply with regulatory dose rate requirements in 2030 and thereafter. The maximum dose rate values vary according to the canister type, and they decrease with increasing decay time by approximately one order of magnitude over the time interval analyzed. The simulations of as-loaded transportation packages show that dose rate values associated with actual package loadings could be significantly smaller than the regulatory dose rates. | 2016 | Complete | FY2016 Dose Rate Report for Selected Loaded Transportation Casks | Radulescu, Georgeta | Feldman, Matt | None | M3FR-16OR090402026.pdf | FCRD-NFST-2016-000477 | transportation, operational, shielding, cask, dose rate
M3FT-16OR090402029 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M3 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Transportation System Project Planning | Transportation System Operational Flowchart Report | Transportation System Project Planning | 2016-03-25 |  | 2016-03-24 |  | 2016 | Complete | Transportation System Concept of Operations: High-Level Flow Diagrams | Bill Reich | Matt Feldman | None | M3FT-16OR090402029-Transportation System Project Planning.pdf | FCRD-NFST-2016-000472 | transportation, operations, flowcharts, process flow, diagrams, casks, railcars
M3FT-16OR090403021 | M3 | 1.02.09.04.03.02 | ORNL | FT-16OR09040302 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Rail Car Development | Railcar Design Report | Provide oversight and input into the development of cask and buffer railcar designs. | 2016-09-30 |  | 2016-09-23 | Level-3 Milestone M3FT-16OR090403021 “Rail Car Development” (work package FT-16OR09040302, TR: Hardware – ORNL, WBS # 1.02.09.04.03) is completed and submitted to PICs:NE. This status report for FY2016 documents the ongoing progress on the current Atlas railcar contract for the design, associated analysis, and prototype fabrication of railcars to transport spent nuclear fuel (SNF) and high-level radioactive waste (HLW). The current railcar design contract includes three phases: (1) Mobilization and Conceptual Design, (2) Preliminary Design, and (3) Prototype Fabrication and Delivery. This report also describes the future testing activities that will be required to obtain Association of American Railroads (AAR) conditional approval of the railcar designs. | 2016 | Complete | Atlas Railcar Design Project Status Report for FY2016 | Bill Reich | Matt Feldman | None | M3FT-16OR090403021-Railcar Development Report-Sept 23 2016.pdf | FCRD-NFST-2016-000479 | S-2043, railcar, cask railcar, buffer railcar
M3FT-16OR090403024 | M3 | 1.02.09.04.03.02 | ORNL | FT-16OR09040302 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Hardware Procurement Strategy | Draft Hardware Procurement Alternatives Report | Alternatives analysis on how to conduct large shipment campaigns | 2016-09-30 |  | 2016-09-29 | Level-3 Milestone M3FT-OR090403024 “DRAFT Hardware Procurement Strategy” (work package FT-16OR09040302, TR: Hardware – ORNL, WBS # 1.02.09.04.03) is completed and submitted to PICs:NE. This report presents an initial, preliminary AoA for transportation system hardware operations. This preliminary analysis provides guidance for a future definitive AoA to be developed once more information on the costs, schedule, and feasibility of transportation operations is available. | 2016 | Complete | NFST SNF Transportation System Hardware Operations: Preliminary Analysis of Alternatives | Scott Dam | Matt Feldman | None | M3FT-16OR090403024-DRAFT Hardware Procurement Strategy-Sept 29 2016.pdf | FCRD-NFST-2016-000480 | AOA, Hardware, Alternatives, Analysis of Alternatives
M3FT-16SN090201033 | M3 | 1.02.09.02.01.03 | SNL | FT-16SN09020103 | CB: Siting Process - SNL | Rechard, Rob | Howard, Rob | Draft Insights from Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Draft Insights on Public Preferences Related to Transportation and Siting of Nuclear Waste Facilities | In accordance with the NFST Guidelines document, this is a draft of the M2 | 2016-08-19 16:00 |  | 2016-08-19 02:00 |  | 2016 | Complete | Insight from Public Surveys Related to Consent-Based Siting and Radioactive Waste Management in the United States: An Overview of Findings from a 2016 Nationwide Survey | Rob P Rechard | Rob P Rechard | None | EE16 Overview Analysis Report without jazzed chapters 08-19-16 .pdf | FCRD-NFST-2016-000468 | Consent-Based Siting; Public Surveys, Radioactive Waste Management
M3FT-16SN090201034 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval. Sandia No. 475703​ | M3 | 1.02.09.02.01.03 | SNL | FT-16SN09020103 | CB: Siting Process - SNL | Rechard, Rob | Howard, Rob | Develop Disposal Systems Siting Considerations Document | Disposal System Siting Considerations | The preliminary siting considerations for disposal facilities will cover the following: site size needs (expected to be variable based on MTU capacity and waste forms considered), geologic media, geologic and other hazards, environmental factors, socioeconomic factors, and transportation. The geologic, environmental, and socioeconomic considerations are not all inclusive. | 2016-06-30 12:00 |  | 2016-06-30 02:00 |  | 2016 | Complete | Preliminary Technical Considerations for Siting a Geologic Repository for Spent Nuclear Fuel and High-Level Radioactive Waste | Rob P. Rechard | Rob P. Rechard | None | Siting Considerations for Geologic Repository 06-30-16.pdf | FCRD-NFST-2016-000465 | Consent-Based Siting; Siting Geologic Repository
M3FT-16SR090105031 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M3 | 1.02.09.01.05.03 | SRNL | FT-16SR09010503 | Characterization and Assessment - SRNL | Carter, Joe | Jarrell, Josh | NFST Planning Project Inventory Report, Rev. 4 | NFST Planning Project Inventory Report, Rev. 4 | SRNL will update the NFST Inventory projections report. | 2016-06-30 02:00 |  | 2016-06-30 |  | 2016 | Complete | Commercial Spent Nuclear Fuel and High-Level Radioactive Waste Inventory Report | Dennis Vinson | Dennis Vinson | None | FCRD-NFST-2013-000263 Rev. 4 - NFST Inventory Rev 4.pdf QA Cover Sheet - NFST Planning Project Inventory Report Rev 4.pdf | FCRD-NFST-2016-000454 | Commercial spent fuel
M3FT-16SR090303031 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.02.09.03.03.03 | SRNL | FT-16SR09030303 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | Revision 3 of the Functions and Requirements Report | Revision 3 of the Functions and Requirements | Revision of the the Waste Management Systems Functions and Requirements Document | 2016-06-30 05:00 |  | 2016-06-29 |  | 2016 | Complete | Nuclear Fuels Storage and Transportation Requirement Document | Doug Melton | Doug Melton | None | FCRD-NFST-2013-000330 Functions & Requirements Doc_Rev 3-Final.pdf QA Cover Sheet - Revision 3 of the Functions and Requirement Report.pdf | FCRD-NFST-2016-000470 | Functions and Requirement
M4FT-16AN090102011 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M4 | 1.02.09.01.02.01 | ANL | FT-16AN09010201 | Multi-Objective Evaluation Framework - ANL | Samsa, Michael | Jarrell, Josh | Multi-Objective Evaluation of Alternative Acceptance Strategies | Multi-Objective Evaluation of Alternative Acceptance Strategies | Application of the Multi-Objective Evaluation Framework to evaluate updated alternative allocation strategies from multiple priority perspectives | 2016-02-29 08:00 |  | 2016-02-29 02:00 |  | 2016 | Complete | Multi-Objective Evaluation of the FY15 Alternative Allocation Architectures | Michael E Samsa | Michael E Samsa | None | Multi-Objective Evaluation of FY15 Alt Allocation Scenarios 2016-02-29 Draft Rev 0.pdf | FCRD-NFST-2016-000644 | multi-objective; evaluation; allocation; OFF; standard contract; ISF;
M4FT-16AN090102045 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | NGSAM Features Update for Systems Analysis | NGSAM Features Update for Systems Analysis | Report documenting modifications to NGSAM based upon systems analysts feedback and feature requests provided in milestone M5FT-16AN0102044. In addition to listing improvements to NGSAM, this report will also discuss those feature requests not completed. Where possible, those feature requests that had not been completed by the time of the report will have a justification as to why they were not completed as well as how those remaining issues fit into the remaining development plan for NGSAM. | 2016-02-29 08:00 |  | 2016-02-26 01:00 |  | 2016 | Complete | NGSAM Features Update for Systems Analysis | Casey D. Trail | Casey D. Trail | None | 20160222-NgsamUpdateM4.pdf | FCRD-NFST-2016-000645 | NGSAM, Systems analysis
M4FT-16AN090102046 | M4 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Facility Modeling and Visualization | Wate Management Facility Modeling and Visualization | A summary report including the results and status of the facility modeling and 3D visualization effort. | 2016-09-01 07:00 | 42619.0417 | 2016-09-06 01:00 | Report satisfying milestone M4FT-16AN090102046, and available on CURIE at http://curie.ornl.gov/content/facility-modeling-and-visualization-snf-repackaging-concepts. | 2016 | Completed Late | Facility Modeling and Visualization of SNF Repackaging Concepts | Park, Young | Casey D. Trail | None | FacilityModelingVisualization_FINAL.pdf | FCRD-NFST-2016-000652
M4FT-16OR090103012 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.01.03.01 | ORNL | FT-16OR09010301 | Collaborative Document and Data Access System (CURIE) - ORNL | Joseph, Robby | Jarrell, Josh | Update CURIE User Manual | Update CURIE User Manual | Update the CURIE user manual | 2016-08-31 02:00 |  | 2016-08-12 |  | 2016 | Complete | CURIE User Manual Rev. 2 |  |  | None | CURIE_Manual_2016_Final.pdf | FCRD-NFST-2016-000651
M4FT-16OR090104012 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Define FY16 Scenarios | Define FY16 Scenarios | Define all FY16 Scenarios that will be analyzed. | 2015-11-06 04:00 |  | 2015-11-06 |  | 2016 | Complete | Scenario Descriptions for the Final Standardized Canister System Evaluation | Robby Joseph | Josh Jarrell | None | FY16_Standardization_Final_Evaluation_Scenarios_Final.pdf | FCRD-NFST-2016-000006
M4FT-16OR090104013 ULR. NFST Working Document: Review Required Prior to External Release or Reference | M4 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Update Concept of Operations | Update Concept of Operations | Update NFST concept of operations report based on latest task orders and NFST R&D efforts. | 2016-07-31 04:00 |  | 2016-07-29 |  | 2016 | Complete | Preliminary Spent Nuclear Fuel Management System Concept of Operations | Riley Cumberland | Josh Jarrell | None | PB1600585_Cumberland_PrelimSNF-14.pdf | FCRD-NFST-2016-000650
M4FT-16OR090104019 | M4 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | Develop Dry Repackaging Facility Concepts | Develop Dry Repackaging Facility Concepts | Develop Repackaging Facility Concepts with dry handling and transfer of SNF. | 2016-01-29 02:00 | 42490 | 2016-04-29 |  | 2016 | Completed Late | Spent Nuclear Fuel Dry Packaging Facility Design Concept, Throughput Analysis, and Costing | Bret van den Akker | Joshua Jarrel | None | Spent Nuclear Fuel Dry Packaging Facility Design Concept Throughput Analysis and Costing.pdf | FCRD-NFST-2016-000642
M4FT-16OR090302021 | M4 | 1.02.09.03.02.02 | ORNL | FT-16OR09030202 | ST: NEPA - ORNL | Bevard, Bruce | Carter, Joe | ORNL Input to Environmental Considerations Document | ORNL Input to Environmental Considerations Document | work with the the NEPA team to develop a comprehensive data call and environmental considerations document. | 2016-04-21 17:00 |  | 2016-04-21 |  | 2016 | Complete | M4FT-16OR090302021-ORNL Input to Environmental Considerations Document | ORNL | Greg Zimmerman, | None | M4FT-16OR090302021-ORNL Input to Environmental Considerations Document.pdf | FCRD-NFST-2016-000661 | NEPA, Environmental Considerations Report, Consolidated Interim Storage, Spent Nuclear Fuel
M4FT-16OR090403022 | M4 | 1.02.09.04.03.02 | ORNL | FT-16OR09040302 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Draft Railcar Development Progress Report | Draft Railcar Progress Report | Draft report documenting progress on cask and buffer railcar development effort | 2016-08-19 |  | 2016-08-19 |  | 2016 | Complete | DRAFT Atlas Railcar Design Project Status Report for FY2016 | Bill Reich | Matt Feldman | None | M4FT-16OR090403022-Railcar Development Report-Aug 19 2016.pdf | FCRD-NFST-2016-000673 | railcar, S-2043, Atlas
M4FT-16OR090403025 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.04.03.02 | ORNL | FT-16OR09040302 | TR: Hardware - ORNL | Connolly, Kevin | Feldman, Matt | Refinement of Hardware Acquisition Assumptions and Data | REport on Hardware Acquisition Assumptions and Data | Report detailing methodologies and assumptions to be used moving forward in the development of hardware procurement strategies. | 2016-05-27 |  | 2016-05-27 |  | 2016 | Complete | Analysis Methodologies and Data Needs for Hardware Acquisition Strategy Development | Kevin Connolly | Matt Feldman | None | M4FT-16OR090403025.pdf | FCRD-NFST-2016-000670 | transportation, hardware, methods, analysis, computational tools, data, procurement, acquisition, cask, railcar
M4FT-16OR090403026 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval​ | M4 | 1.02.09.04.03.02 | ORNL | FT-16OR09040302 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Document Railcar and Cask Fleet Operations and Maintenance Activities | Railcar and Cask Fleet Operations and Maintenance Activities | Report identifying railcar and cask fleet operations and maintenance activities. | 2016-01-29 |  | 2016-01-29 |  | 2016 | Complete | Railcar and Transportation Cask Maintenance and Operations Activities | Kevin Connolly | Matt Feldman | None | M4FT-16OR090403026-Railcar and Transportation Cask Maintenance and Operations Activities | FCRD-NFST-2016-000666 | Maintenance, Operations, Railcar, Transportation, casks
M4FT-16PN090103021 | M4 | 1.02.09.01.03.02 | PNNL | FT-16PN09010302 | Shutdown Reactor SNF Data Capture and Preservation - PNNL | Maheras, Steve | Jarrell, Josh | SNF Film Capture Considerations Report | SNF Film Capture Considerations Report | Submit a report discussing possible approaches and considerations such as benefits, costs, quality, time requirements, and other factors related to film capture, including conversion to digital and preservation. | 2016-04-15 02:00 |  | 2016-04-14 06:00 |  | 2016 | Complete | SPENT NUCLEAR FUEL INSPECTION VIDEO DATA CAPTURE: PILOT PLAN SAN ONOFRE NUCLEAR GENERATING STATION | Steve Maheras | Steve Maheras | None | FCRD-NFST-2016-000647_M4.pdf | FCRD-NFST-2016-000647 | Data preservation, fuel inspection, San Onofre, data capture
M4FT-16PN090302032 ULR. NFST Working Document: External Release Requires DOE-NE Approval​ | M4 | 1.02.09.03.02.03 | PNNL | FT-16PN09030203 | ST: NEPA - PNNL | Maheras, Steve | Carter, Joe | ECR Transportation and Transportation Infrastructure Sections | ECR Transportation and Transportation Infrastructure | Develop transportation and transportation infrastructure sections of the ECR. | 2016-04-29 |  | 2016-04-29 12:00 |  | 2016 | Complete | Environmental Considerations Report - Appendix C Transportation | Steve Maheras | Steve Maheras | None | FCRD-NFST-2016-000662_M4_signed.pdf | FCRD-NFST-2016-000662 | NEPA, ISF, EIS, transportation, ECR, environmental considerations report
M4FT-16PN0904020315 | M4 | 1.02.09.04.02.03 | PNNL | FT-16PN09040203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Shutdown Sites Report | Draft Shutdown Sites Report | Submit draft shutdown sites report. | 2016-07-01 |  | 2016-07-01 06:00 |  | 2016 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Steve Maheras | Steve Maheras | None | FCRD-NFST-2016-000671_M4_signed.pdf | FCRD-NFST-2016-000671 | Shutdown sites, SNF, UNF, GTCC, transportation, logistics, near site transportation infrastructure, transportation infrastructure
M4FT-16PN0904020316 | M4 | 1.02.09.04.02.03 | PNNL | FT-16PN09040203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | White Paper on Role of Transportation in Consent-Based Siting | Role of Transportation in Consent-Based Siting White Paper | Submit white paper on role of transportation in consent-based siting. | 2015-12-11 04:00 |  | 2015-12-11 06:00 |  | 2016 | Complete | Role of Transportation in Consent-Based Siting | Steve Maheras | Steve Maheras | None | Transportation and CBS White Paper_2015-12-11.pdf | FCRD-NFST-2016-000665 | Consent-based siting, transportation, consultative planning process
M4FT-16SN090104022 Rev 0 is Unlimited. Rev. 1 is ULR per CURIE. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE. | M4 | 1.02.09.01.04.02 | SNL | FT-16SN09010402 | Standardization and Integration - SNL | Hardin, Ernest | Jarrell, Josh | Develop "multipack" disposal concepts | Multi-pack Concepts for Spent Fuel Disposal | Develop one or more disposal concepts for “multi-pack” disposal, in which small, sealed canisters of spent fuel (e.g., four 4-PWR canisters) are grouped in a larger overpack for disposal. Develop concepts for: 1) an open-mode repository, and 2) a salt repository. | 2015-12-04 06:00 | 2015-12-17 02:00 | 2015-12-23 02:00 |  | 2016 | Completed Late | Multi-Pack Disposal Concepts for Spent Fuel | Ernest Hardin | Ernest Hardin | None | Multi-pack-disposal-concepts_for-SNF 23Dec15 final.pdf | FCRD-NFST-2016-000640 | spent fuel; disposal concept; can-in-canister; STAD canister
M4FT-16SN090201036 ULR. NFST Working Document External Release or Reference Requires DOE-NE Approval | M4 | 1.02.09.02.01.03 | SNL | FT-16SN09020103 | CB: Siting Process - SNL | Rechard, Rob | Howard, Rob | Support DOE Regional Meetings and Outreach Engagements | Status report on monitoring media related to DOE regional meetings | Provide technical support, as requested, to DOE regional meetings and outreach engagements. Support may take the form of "open houses" and poster sessions at public meetings. | 2016-05-31 04:00 | 2016-09-30 02:00 | 2016-09-30 02:00 | This report presents that status of monitoring multiple streams of nuclear narratives related to consent-based siting. In FY16, most work was spent developing tools to evaluate Twitter social media traffic. A 3 step process was used: all Twitter traffic from January through June 30, 2016, (1) filtered for relevant and irrelevant content; (2) tweets containing the word “nuclear” and related terms; (3) tweets related to consent-based siting. Between January and June 30, 2016, a total of 431 Twitter messages made reference to consent-based siting (Figure 3). This was less than 0.01% of all nuclear energy/waste tweets. On average, there were 3 tweets/day about consent based siting , with peak days of up to 40 tweets. These peak days, however, did not coincide with the timing of the regional meetings, which indicates that while people were talking about consent based siting and nuclear waste management, the frequency of those messages was not substantially influenced by the meetings. In fact, the peak number of tweets during this period were related to the proposed field test examining the feasibility of drilling large diameter boreholes 5 km deep for the disposal of some types of radioactive waste. Of the 431 tweets, the majority were announcing the DOE regional meeting, not commenting on the content of the meeting. | 2016 | Completed Late | Status of Monitoring Multiple Streams of Media Data Related to Consent-Based Siting and Radioactive Waste Management in the United States | Rob P Rechard | Rob P Rechard | None | Status of Media Monitoring 09-30-16.pdf | FCRD-NFST-2016-000031 | twiter analysis, 2016 regional meetings on consent-based siting,
M4FT-16SN090202041 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M4 | 1.02.09.02.02.04 | SNL | FT-16SN09020204 | CB: Communications Products - SNL | Rechard, Rob | Howard, Rob | Support Communications Product Development | Status report on support to DOE regional meetings | Provide technical support and input to communications product development as requested. | 2016-09-30 22:00 |  | 2016-09-30 06:00 | This report presents observations on the public discussion about how to conduct a consent based process for locating future radioactive waste management facilities. The public discussion occurred during 8 one-day, regional meetings the US Department of Energy (DOE) held throughout the US in 2016 in Chicago during March, in Atlanta and Sacramento during April, Denver during May, Boston and Tempe during June, and Boise and Minnesota during July. These observations are compared to findings from nationwide surveys, administered since 2006, that measure preferences of United States (US) residents concerning the environment and energy sources. In general (1)discussion about consent-based siting closely tied to the general topic of nuclear energy; (2) substantial participation by organized interest groups who had view different from the general public; (3)Lack of trust in DOE was brought up often, which differed from general public; (4) Expert panels and citizen group discussions provided wide viewpoints and use of these components could have role in consent-based siting; and (5) Participants were engaged and committed in small groups, demonstrating willingness to participate in citizen deliberative panels. | 2016 | Complete | Observations on DOE Regional Meetings Related to Consent-Based Siting of Radioactive Waste Facilities in the United States | Rob P Rechard | Rob P Rechard | None | Observations on DOE Regional Meetings 09-30-16.pdf | FCRD-NFST-2016-000032 | consent-based siting; public preferences;
M4FT-16SR090302042 | M4 | 1.02.09.03.02.04 | SRNL | FT-16SR09030204 | ST: NEPA - SRNL | Carter, Joe | Carter, Joe | Draft Environmental Considerations Report - Storage Input | Environmental Consideration Report Storage Design Input | Provide Storage Design input to Environmental Considerations Report. | 2016-04-29 05:00 |  | 2016-04-26 |  | 2016 | Complete | Draft Environmental Considerations Report - Storage Input | Robert Jones | Robert Jones | None | FCRD-NFST-2016-000663 - Draft ECR Storage Input.pdf QA Cover Sheet - Jones - ECR Storage Input.pdf | FCRD-NFST-2016-000663 | ECR, Storage
M4FT-16SR090303035 ULR. Predecisional Draft. | M4 | 1.02.09.03.03.03 | SRNL | FT-16SR09030303 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | Packaging Facility Design Concept Development | Packaging for Disposal Design Concepts | Provide packaging for disposal design concepts | 2016-02-29 02:00 | 2016-03-05 | 2016-03-05 |  | 2016 | Completed Late | Spent Nuclear Fuel Packaging Facility - Pool Concept and Cost Estimate | Severynse, Tom | Tom Severynse | None | SNF Packaging Facility - Pool Concept and Cost Estimate Rev 0.pdf | FCRD-NFST-2016-000660 | Spent Nuclear Fuel
M4FT-16SR090303036 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval | M4 | 1.02.09.03.03.03 | SRNL | FT-16SR09030303 | ST: Storage Design - SRNL | Carter, Joe | Carter, Joe | Repository Concept Estimates | STAD disposal concepts | Develop 2 additional cost estimates for STAD canister disposal in an open ventilated and salt repository concepts | 2016-01-22 02:00 |  | 2016-01-22 |  | 2016 | Complete | Multi-Pack Disposal Cost Estimates | Tom Severynse | Tom Severynse | None | Email - Closure Document M4FT-16SR090303036 - Multi-Pack Disposal C.pdf Multi-Pack Disposal Cost Estimates (Rev 0)-M4FT-16SR090303036.pdf QA Cover - M4FT-16SR090303036.pdf | FCRD-NFST-2016-000659 | Multi-Pack Cost Estimates
M5FT-16AN090102044 ULR. NFST Working Document: External Release or Reference Requires | M5 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | None | NGSAM Feature Requests | NGSAM Feature Requests | As the transition of NGSAM begins, systems analysts will naturally identify a number of desired features for the tool. This report will provide a list of feature requests, and a brief assessment of the feasibility (considering time and complexity) of implementing these requests. The assessment of feature requests will be provided through engagement with the NGSAM team. The kickoff for this portion of the systems architecture effort will be a meeting early in FY16 (mid October) to provide systems analysts in depth instruction on using NGSAM. | 2015-11-06 10:00 |  | 2015-11-06 01:00 |  | 2016 | Complete | Feature Requests for NGSAM | Casey D. Trail | Casey D. Trail | None | 20151106-M5_Milestone-FeatureRequestsForNgsam.docx | FCRD-NFST-2016-000008 | NGSAM, systems analysis
M5FT-16OR090102057 | M5 | 1.02.09.01.02.05 | ORNL | FT-16OR09010205 | Waste Management System Architecture Analysis - ORNL | Jarrell, Josh | None | Document repository cost estimates are in the Unified Database | Document repository cost estimates are in the Unified Database | Document repository cost estimates are in the Unified Database | 2016-01-29 02:00 |  | 2016-01-29 |  | 2016 | Complete | Document repository cost estimates are in the Unified Database | van den Akker, Bret | Josh Jarrell | None |  | FCRD-NFST-2016-000705
M5FT-16OR090102059 ULR. NFST Working Document: External Release or Reference Requires DOE-NE Approval ​ | M5 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | None | Document NGSAM-requested data availability | Document NGSAM-requested data availability | Based on NGSAM requests, document additional data collected or identified to be collected to support future system analyses. | 2016-04-15 |  | 2016-04-14 |  | 2016 | Complete | NGSAM-Requested Data Availability | Robby Joseph | Joshua Jarrell | None | NGSAM_Requested_Data_Availability_Rev7.pdf | FCRD-NFST-2016-000711
M5FT-16OR090104014 ULR. This is a draft document has not yet been approved for public release and is not to be shared with others outside this private CURIE community without prior authorization from DOE.​ | M5 | 1.02.09.01.02.04 | ANL | FT-16AN09010204 | Waste Management System Architecture Analysis - ANL | Trail, Casey | None | Create NFST Glossary | Create NFST Glossary | Report to update NFST glossary report (originally in FY15 Systems Architecture Report Appendix) and make it a stand-alone report. | 2015-12-11 04:00 |  | 2015-12-11 |  | 2016 | Complete | NFST Glossary | Josh Jarrell | Josh Jarrell | None | 2015-12-11_NFST-Glossary_M5FT16OR090104014_rev8.docx | FCRD-NFST-2016-000703
M5FT-16OR0901050112 | M5 | 1.02.09.01.05.01 | ORNL | FT-16OR09010501 | Characterization and Assessment - ORNL | Scaglione, John | None | Dry run generation of cask inventory report from the unified database | Draft cask inventory report generated from UNF-ST&DARDS | This milestone will generate the cask inventory report and identify gaps in data that need to be filled in to support the ability to dynamically generate a cask inventory report from the unified database at anytime. | 2016-03-31 04:00 | 2016-05-13 | 2016-05-31 |  | 2016 | Completed Late | Dry Cask Inventory Assessment | Cumberland, Riley | Scaglione, John | None |  | FCRD-NFST-2016-000710
M5FT-16SN090102073 | M5 | 1.02.09.01.03.01 | ORNL | FT-16OR09010301 | Collaborative Document and Data Access System (CURIE) - ORNL | Joseph, Robby | None | NGSAM Benchmark | NGSAM Benchmark | NGSAM benchmark | 2016-02-29 08:00 | 42432.0833 | 2016-03-03 02:00 |  | 2016 | Completed Late | SHUTDOWN REACTOR SITES TEST IN SUPPORT OF NGSAM BENCHMARK | Elena A. Kalinina | Elena A. Kalinina | None |  | FCRD-NFST-2016-000707 | Waste management; system architecture; logistics model; transportation operations model; benchmark test; shutdown reactors
M2SF-17AN020101012 | M2 | 1.08.02.01.01.01 | ANL | SF-17AN02010101 | Siting Process Design - ANL (CLOSED) | Saraeva, Natalia | Howard, Rob | Draft Consent Based Siting Process for Nuclear Waste Management Facilities | Draft Consent Based Siting Process for Nuclear Waste Management Facilities | Draft Siting Process for Discussion with Stakeholders and Interested Communities. | 2016-12-15 |  | 2016-12-15 |  | 2017 | Complete | Draft Consent Based Siting Process for Nuclear Waste Management Facilities | Reim, Mike | Saraeva, Natalia | None | Draft Consent-Based Siting Process and Siting Considerations FINAL no formatting 12-15-16.docx | SFWD-IWM-2017-000019 | consent based siting, nuclear waste management, siting guidelines
M2SF-17OR020301011 | M2 | 1.08.02.03.01.01 | ORNL | SF-17OR02030101 | Transportation: Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | NWPA Section 180(c) Program Development | NWPA Section 180(c) Program Development | Recommendations for revising the 2008 FRN Draft Section 180(c) Policy. | 2017-08-31 |  | 2017-08-31 |  | 2017 | Complete | Recommendations for Revising the 2008 Federal Register Notice Draft Section 180(c) Policy | Helvey, Elizabeth | Feldman, Matt | None | M2SF-17OR020301011.pdf | SFWD-IWM-2017-000021 | transportation, engagement, nwpa section 180(c)
M2SF-17OR020301012 ULR Predecisional Draft SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M2 | 1.08.02.03.01.01 | ORNL | SF-17OR02030101 | Transportation: Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | Evaluation of Funding Formula and Shipment Scenario Modeling | Evaluation of Funding Formula and Shipment Scenario Modeling | Develop various shipping scenarios and evaluate how the funding formula is impacted by them. | 2017-03-17 |  | 2017-03-17 |  | 2017 | Complete | Evaluation of 2008 Proposed Section 180(c) Funding Formula Using IWM Modeling Tools | Connolly, Kevin | Feldman, Matt | None | M2SF-17OR020301012.pdf | SFWD-IWM-2017-000022 | transportation, nwpa, training grants, section 180(c), stakeholders, engagement, funding
M2SF-17OR020303021 | M2 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Transportation Hardware Alternatives Analysis | Transportation Hardware Alternatives Analysis | Initial alternatives analysis on how to operate (lease vs buy vs contract for, etc) the transportation system. | 2017-08-18 |  | 2017-08-18 |  | 2017 | Complete | SNF Transportation System Hardware Operations: Analysis of Alternatives | Dam, Scott | Feldman, Matt | None | M2SF-17OR020303021-Transportation Hardware AoA-Sept 29 2017-R1.pdf | SFWD-IWM-2017-000177
M3SF-17AN020101014 | M3 | 1.08.02.01.01.01 | ANL | SF-17AN02010101 | Siting Process Design - ANL (CLOSED) | Saraeva, Natalia | Howard, Rob | Draft Consent Based Siting Process for Nuclear Waste Management Facilities | Preliminary Draft Consent Based Siting Process for Nuclear Waste Management Facilities | M3 Draft Consent Based Siting Process for Nuclear Waste Management Facilities for internal discussion and review. | 2016-11-15 |  | 2016-11-15 |  | 2017 | Complete | Consent-Based Siting Process Design Document | Natalia Saraeva, | Natalia Saraeva | None | CBS Design Doc Draft 11-12-2016.docx | SFWD-IWM-2017-000048 | consent based siting, integrated nuclear waste management
M3SF-17AN020401011 ULR Predecisional Draft SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.08.02.04.01.01 | ANL | SF-17AN02040101 | IWM Project Management - ANL | Nutt, Mark | Jarrell, Josh | FY16 NFST Accomplishments Report | FY16 NFST Accomplishments Report | Nuclear Fuel Storage and Transportation Planning Project accomplishments for FY16 | 2016-11-30 03:00 | 2016-12-05 01:00 | 2016-12-05 01:00 |  | 2017 | Completed Late | FY2016 NFST Accomplishments | William Nutt | William Nutt | None | FY16 NFST Accomplishments (M3SF-17AN020401011).docx | SFWD-IWM-2017-000064 | NFST, Accomplishments, Fiscal Year 2016, FY16
M3SF-17AN020403011 | M3 | 1.08.02.04.03.01 | ANL | SF-17AN02040301 | MOEF Application - ANL | Samsa, Michael | Jarrell, Josh | Deliver Integrated Assessment of ISF Deployment Scenarios Report | Integrated Assessment of ISF Deployment Scenarios Report (Final) | This report will document an integrated assessment of ISF deployment scenarios using MOEF, ESA, and NGSAM or TSL-CALVIN tools. | 2017-09-29 10:00 |  | 2017-09-29 01:00 | This report satisfies the Level-3 milestone entitled “Integrated Assessment of ISF Deployment Scenarios,” M3SF-17AN020403011, work package SF-17AN02040301, work breakdown structure No. 1.08.02.04.03. | 2017 | Complete | FY2017 Integrated Assessment of Alternative ISF Deployment Scenarios | Samsa, Michael | Samsa, Michael | None | FY2017 Integrated Assessment (Final) 2017-09-30.pdf | SFWD-IWM-2017-000026 | integraed assessment, private isf, ESA, NGSAM, MOEF
M3SF-17AN020403042 ULR Predecisional Draft. SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.08.02.04.03.04 | ANL | SF-17AN02040304 | ESA Development and Application - ANL | Saraeva, Natalia | Jarrell, Josh | Deliver an enhanced ESA toolkit-Draft Report | Deliver an enhanced ESA toolkit - Draft Report | This deliverable will have a description of updated ESA toolkit. The updates will be made between 10/1/16 to 8/30/17. the toolkit will provide additional capabilities such as shutdown-site infrastructure. The user manual will be included. This report will be submitted as level 3 milestone. | 2017-09-29 04:00 |  | 2017-09-18 | Integrate Waste Management Program Execution Strategy Analysis: Development of Version 2.1 of the ESA Tool | 2017 | Complete | Integrated Waste Management Program Execution Strategy Analysis: Development of Version 2.1 of the ESA Tool | Stoll, Ralph | Natalia Saraeva | None | ESA FY17 M3 Report Draft 9-17-2017.pdf | SFWD-IWM-2017-000067 | integrated waste managment system; waste management, system analysis, execution strategy analysis, GoldSim, Monte Carlo, risks, uncertainties, constraints
M3SF-17AN020403085 | M3 | 1.08.02.04.03.08 | ANL | SF-17AN02040308 | NGSAM Development and Application - ANL | St. Aubin, Jim | Jarrell, Josh | NGSAM FY2017 Status Report | NGSAM FY2017 Status Report | Report of NGSAM-related accomplishments and activities supported by numerous DOE labs | 2017-09-29 07:00 |  | 2017-09-29 03:00 | This report summarizes all NGSAM-related FY 2017 activities and milestones | 2017 | Complete | FY2017 Next-Generation System Analysis Model (NGSAM) Status Report | ANL | St Aubin, Jim | None | SFWD IWM M3FT FY2017 NGSAM Status Report - #2 FINAL 29-Sep-2017.pdf | SFWD-IWM-2017-000068 | NGSAM, Status, IWM
M3SF-17AN020403101 ULR Predecisional Draft | M3 | 1.08.02.04.03.10 | ANL | SF-17AN02040310 | System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | Fiscal Year 2017 Systems Architecture Analyses Report | Fiscal Year 2017 Waste Management System Architecture Analyses | Report of the analysis conducted to evaluate an integrated approach to the waste management system. This report incorporates the latest information provided through other program activities to update and augment strategies and approaches for managing SNF throughout the waste management system. | 2017-09-30 08:00 |  | 2017-09-29 01:00 | This report fulfills the Level 3 Milestone M3SF-17AN020403101 in the Waste Management System Architecture Analysis work package SF-17AN02040310. | 2017 | Complete | Fiscal Year 2017 Waste Management System Architecture Analyses | Casey D. Trail | W. Mark Nutt | None | FY17WasteManagementSystemArchitectureAnalysis_Final.pdf | SFWD-IWM-2017-000069
M3SF-17AN020403101 ULR. Predecisional Draft. Same DMS # as for M4SF-17OR020403273, which I can't find in Matt Brainard's PICS/NE spreadsheet. | M4 | curie | ORNL | SF-17OR02040327 | System Deployment Analysis - ORNL | Howard, Rob | Howard, Rob | Preliminary Hypothetical Community Impact Analysis | Preliminary Hypothetical Community Impact Analysis | Develop a preliminary Community Impact Analysis illustrating how an interim storage facility might impact a hypothetical host community. A nuclear waste management facility will carry with it a number of impacts that are carried by the host community and state. These impacts will vary significantly depending on a variety of factors, such as type of facility (ISF vs repository), the facility scope and design, geographic location, and phases of operation (i.e. construction, operation and decommissioning). | 2017-08-04 |  | 2017-08-04 |  | 2017 | Complete | Monetized and Non-Monetized Impacts of an ISF on a Hypothetical Host Community | Robby Joseph | Rob Howard | OUO |  | SFWD-IWM-2017-000209
M3SF-17ID020201071 | M3 | 1.08.02.02.01.07 | DOE-ID | SF-17ID02020107 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Ford, Brayton | Carter, Joe | Kickoff Meeting | Kickoff Meeting Briefing | Kickoff Meeting | 2017-02-01 |  | 2017-02-01 |  | 2017 | Complete | Pilot Interim Storage of Spent Nuclear Fuel Generic Design and Topical Safety Analysis Kick-Off Meeting | J. Clemmens, | CBI | None | CSF TSAR Kick-Off Meeting- CBI.pptx | SFWD-IWM-2017-000228
M3SF-17ID020301041 | M3 | 1.08.02.03.01.04 | DOE-ID | SF-17ID02030104 | Transportation: Intergovernmental and External Engagement - DOE-ID (North Wind) | Helvey, Elizabeth | Feldman, Matt | Recommendations for Revising the 2008 FRN Draft Section 180(c) Policy | Recommendations for Revising the 2008 FRN Draft Section 180(c) Policy | Write a paper recommending changes to the language in the 2008 FRN Draft Section 180(c) Policy. Any recommended changes will reflect the knowledge gained from the Section 180(c) Policy Implementation Exercise, other interactions with stakeholders, and policy and operational updates since the 2008 FRN was published. | 2017-06-30 08:00 |  | 2017-07-01 02:00 |  | 2017 | Completed Late | Recommendations for Revising the 2008 FRN Draft Section 180(c) Policy |  |  | None | Policy Language Updates_Final.docx | SFWD-IWM-2017-000060
M3SF-17ID020302071 | M3 | 1.08.02.03.02.07 | DOE-ID | SF-17ID02030207 | Transportation: Operational - DOE-ID (North Wind) | Helvey, Elizabeth | Feldman, Matt | Identify Path to Developing a Public Version of START | Identify Path to Developing a Public Version of START | Investigate whether a public version of START can be developed and how different audiences might use it. Develop a paper explaining what features would be available, what audiences could learn from it, and how that helps the public evaluate their level of trust and confidence in the transportation program. | 2017-08-11 08:00 |  | 2017-08-11 02:00 |  | 2017 | Complete | Identify Path to Developing a Public Version of START | Abkowitz,Mark |  | None | M3SF-17ID020302071 START_v2.pdf | SFWD-IWM-2017-000062 | START, Routing, route selection methodology, transportation,
M3SF-17OR020301016 | M3 | 1.08.02.03.01.01 | ORNL | SF-17OR02030101 | Transportation: Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | Draft Evaluation of Funding Formula and Shipment Scenario Modeling | Draft Evaluation of Funding Formula and Shipment Scenario Modeling | Develop draft various shipping scenarios and evaluate how the funding formula is impacted by them. | 2017-01-27 |  | 2017-01-27 |  | 2017 | Complete | Draft Evaluation of 2008 Proposed Section 180(c) Funding Formula Using IWM Modeling Tools | Kevin Connolly | Matt Feldman | None | M3SF-17OR020301016.pdf | SFWD-IWM-2017-000059 | transportation, engagement, NWPA, Section 180(c), stakeholders, funding
M3SF-17OR0203020211 | M3 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Document Hierarchy Report | Document Hierarchy Report | Report detailing the proposed hierarchy of documents for development of the transportation system. | 2017-01-20 |  | 2017-01-20 |  | 2017 | Complete | IWM Transportation System Document Hierarchy | Kevin Connolly | Kevin Connolly | None | M3SF-17OR0203020211.pdf | SFWD-IWM-2017-000179 | transportation, operational, management, procedures, planning, structure, documents, engagement, framework
M3SF-17OR0203020216 | M3 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Revise Connecticut Yankee Initial Site Specific De-Inventory Report | Connecticut Yankee Initial Site-Specific De-Inventory Report, Revision 1 | Revise the Connecticut Yankee Initial Site Specific De-Inventory Report to include Multi-Attribute Utility Analysis of possible transport modes and routes and otherwise upgrade the report to the level of the subsequent De-Inventory reports (Humboldt Bay, Maine Yankee, and Trojan). | 2017-05-26 |  | 2017-05-23 |  | 2017 | Complete | Initial Site-Specific Deinventory Report for Connecticut Yankee | AREVA | Feldman, Matt | None | CY Deinventory Report Rev 2 (Final).pdf | SFWD-IWM-2017-000180 | Connecticut Yankee, Haddam Neck, campaign, transportation, logisitcs, shutdown site, MUA
M3SF-17OR0203020217 | M3 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Revise Big Rock Point Initial Site Specific De-Inventory Report | Big Rock Point Initial Site-Specific De-Inventory Report, Revision 1 | Revise the Big Rock Point Yankee Initial Site Specific De-Inventory Report to include Multi-Attribute Utility Analysis of possible transport modes and routes and otherwise upgrade the report to the level of the subsequent De-Inventory reports (Humboldt Bay, Maine Yankee, and Trojan). | 2017-05-26 |  | 2017-05-23 |  | 2017 | Complete | Initial Site-Specific De-Inventory Report for Big Rock Point | AREVA | Feldman, Matt | None | BRP Deinventory Report Rev. 2 (Final).pdf | SFWD-IWM-2017-000181 | Big Rock Point, campaign, transportation, logisitcs, shutdown site, MUA
M3SF-17OR0203020219 | M3 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Transportation System Functional Decomposition | Transportation System Concept of Operations Functional Decomposition | Updated concept of operations report | 2017-06-30 | 2017-07-31 | 2017-07-31 |  | 2017 | Completed Late | Transportation System Concept of Operations: Process Flowcharts | Anderson, Kimberly | Connolly, Kevin | None | CONOPS rev 20_alb.docx | SFWD-IWM-2017-000207 | transportation, operational, concept of operations, flowcharts, process flow
M3SF-17OR020303022 | M3 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Draft Transportation Hardware Alternatives Analysis | Draft Transportation Hardware Alternatives Analysis | Initial alternatives analysis on how to operate (lease vs buy vs contract for) the transportation system. | 2017-06-16 |  | 2017-06-16 |  | 2017 | Complete | SNF Transportation System Hardware Operations: Draft Analysis of Alternatives | Scott Dam | Bill Reich | None | M3SF-17OR020303022-DRAFT Transportation Hardware Operations AoA-June 16 2017.pdf | SFWD-IWM-2017-000185 | Atlas Railcar, AoA
M3SF-17OR020303023 | M3 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Prototype SNF Transportation Railcar Design | ATLAS Railcar Design Project Status Report | Support development of S-2043 compliant cask and buffer railcars. | 2017-09-30 |  | 2017-09-29 | The milestone report was completed on schedule. | 2017 | Complete | Atlas Railcar Design Project Status Report for FY2017 | Bill Reich | Bill Reich | None | M3SF-17OR020303023-Atlas Railcar Design Project Status Report-Sept 29 2017-R3.pdf | SFWD-IWM-2017-000186
M3SF-17OR020303025 | M3 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Establish Transportation Assets for Pilot ISF | Preliminary Transportation Needs Assessment report | Develop preliminary report detailing the assets that will be necessary to procure to de-inventory sites for pilot ISF operations | 2017-09-08 |  | 2017-09-08 | M3 milestone report completed on time. | 2017 | Complete | Establish Transportation Assets for an Interim Storage Facility | Bill Reich, | Matt Feldman | None | M3SF-17OR020303025-Establish Transportation Assets-Sept 8 2017-FINAL.pdf | SFWD-IWM-2017-000187
M3SF-17OR020501024 | M3 | 1.08.02.05.01.02 | ORNL | SF-17OR02050102 | Systematic Studies Involving Canisters- ORNL | Scaglione, John | Nutt, Mark | Analysis of Different Options for a Postulated Nonconformance in a Dry Storage System | Analysis of Different Options for a Postulated Nonconformance in a Dry Storage System | Summary report of various options and alternatives evalauted for addressing a nonconforming dry storage systems in cluding a. Regulatory Impact (first of a kind, prior experience, grading low-medium-high) b. Operational Impact (safety, security, staffing, on-going operations, constraints) c. Dose (low-medium-high) d. Cost (low-medium-high) e. Schedule (duration, time sequence) f. Technology Readiness Level (TRL) | 2017-09-30 |  | 2017-09-27 | M3 Milestone on options to address nonconforming canisters completed ahead of schedule | 2017 | Complete | Assessment of Options for Nonconforming Dry Storage Systems | Chatzidakis, Stylianos | Scaglione, John | None | PB1701111_Chatzidakis-Dry-rr-vsc_alb_alb.pdf | SFWD-IWM-2017-000215 | nonconformance, repair, mitigation, remediation
M3SF-17PN020302038 | M3 | 1.08.02.03.02.03 | PNNL | SF-17PN02030203 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Revised Shutdown Sites Evaluation | Draft Revised Shutdown Sites Report | Draft Revised Shutdown Sites Report | 2017-06-30 |  | 2017-06-28 06:00 |  | 2017 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Steve Maheras | Steve Maheras | None | SFWD-IWM-2017-000061_096_red_signed.pdf | SFWD-IWM-2017-000061 | shutdown sites, SNF, UNF, GTCC, transportation, logistics, near site transportation infrastructure, transportation infrastructure
M3SF-17SN020403303 | M3 | 1.08.02.04.03.30 | SNL | SF-17SN02040330 | System Deployment Analysis - SNL | Rechard, Rob | Jarrell, Josh | Insights from Surveys Related to Radioactive Waste Transportation and Nuclear Waste Facilities | Insights from Nationwide Surveys Related to US Nuclear Facilities | Report describing insights gained from surveys related to nuclear waste facilities conducted in FY2017. Results will be weighted analyses of OU-owned data to be collected through a nationwide survey implemented in Spring/Summer 2017. Weighted analyses will permit analysis of trends by assuring that the demographic characteristics of the sample match those of the most recent US Census estimates. Neither survey question design nor data collection will be a part of this activity. | 2017-09-29 16:00 |  | 2017-09-28 02:00 | Report submitted on the analysis of data from the nationwide survey conducted by University of Oklahoma in 2017 that is pertinent to IWM Project. | 2017 | Complete | Public Views about Radioactive Waste Management in the United States: An Overview of Findings from a 2017 Nationwide Survey | Rob P. Rechard | Rob P. Rechard | None | EE17 Overview Analysis Report Complete 09-28-17.pdf | SFWD-IWM-2017-000251
M4SF-17AN020403102 ULR Predecisional Draft SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M4 | 1.08.02.04.03.10 | ANL | SF-17AN02040310 | System Architecture Analysis - ANL | Trail, Casey | Jarrell, Josh | NGSAM Transition Status Update report | NGSAM Transition Status Update | Report documenting the progress of the transition from legacy systems analysis tools to NGSAM. This report will focus on the latest improvements to the NGSAM modeling software, specifically revisions to the modeling of reactor sites, and the improvements to modeling of the ISF. This is a follow-up to a similar report delivered in FY16 that focused on the improved logic of modeling the reactor sites and their interaction with the waste management system. | 2017-03-01 06:00 |  | 2017-03-01 02:00 |  | 2017 | Complete | NGSAM Transition Status Update | Casey D. Trail | Casey D. Trail | None | 20170301-Benchmarking_Report_rFinal.pdf | SFWD-IWM-2017-000070
M4SF-17AN020403252 ULR Predecisional Draft SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M4 | 1.08.02.04.03.25 | ANL | SF-17AN02040325 | System Deployment Analysis - ANL | Saraeva, Natalia | Jarrell, Josh | Nuclear Waste Fund Background | Nuclear Waste Background | This activity will result in a paper that describes the history and mechanics of the Nuclear Waste Fund including the original intent of the Fund and subsequent legislative and administrative actions that caused the change in the way Fund operates now | 2017-06-30 | 2017-07-31 | 2017-07-25 |  | 2017 | Completed Late | Financing Nuclear Waste Disposal | Thomas Cotton | Natalia Saraeva | None | M4SF-17AN020403252 Financing Nuclear Waste Disposal.pdf | SFWD-IWM-2017-000220 | nuclear waste; spent nuclear fuel; nuclear waste fund; nuclear waste fee
M4SF-17OR020301014 ULR. CURIE predecisional draft. Additional workshop documentation is available in CURIE. | M4 | 1.08.02.03.01.01 | ORNL | SF-17OR02030101 | Transportation: Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | Routing Workshop Summary Report | Routing Workshop Summary Report | Issue a summary report on the routing workshop held in FY17. | 2017-09-29 |  | 2017-09-29 | Level 4 milestone M4SF-17OR020301014, “Routing Workshop Summary Report,” (work package SF-17OR02030101, Transportation: Intergovernmental and External Engagement – ORNL, WBS #1.08.02.03.01) was completed. The deliverable is a report entitled “Routing Workshop Meeting Summary: DOE NTSF SNF Rail/Routing Ad Hoc Working Group.” | 2017 | Complete | Routing Workshop Meeting Summary: DOE NTSF SNF Rail/Routing Ad Hoc Working Group | Elizabeth Helvey | Matt Feldman | None | M4SF-17OR020301014 - routing workshop summary.docx | SFWD-IWM-2017-000058
M4SF-17OR0203020212 | M4 | 1.08.02.03.02.02 | ORNL | SF-17OR02030202 | Transportation: Operational - ORNL | Connolly, Kevin | Feldman, Matt | Draft Document Hierarchy Report | Draft Document Hierarchy Report | Draft report detailing the proposed hierarchy of documents for development of the transportation system. | 2016-11-18 |  | 2016-11-16 |  | 2017 | Complete | Draft IWM Transportation System Document Hierarchy | Kevin Connolly | Kevin Connolly | None | M4SF-17OR0203020212.pdf | SFWD-IWM-2017-000188 | transportation, operational, structure, framework, documents, planning, engagement, plans, procedures
M4SF-17OR020303024 | M4 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Draft Atlas Railcar Design Project Status Report | Draft Atlas Railcar Design Project Status Report | Draft Report on the project status of development of S-2043 compliant cask and buffer railcars. | 2017-08-18 |  | 2017-08-18 |  | 2017 | Complete | DRAFT Atlas Railcar Design Project Status Report for FY2017 | Bill Reich, | Matt Feldman | None | M4SF-17OR020303024-Draft Atlas Railcar Design Project Status Report-Aug 18 2017-R3.pdf | SFWD-IWM-2017-000191
M4SF-17OR020303026 | M4 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Draft Preliminary Needs Assessment | Draft Preliminary Needs Assessment | Develop draft preliminary report detailing the assets that will be necessary to procure to de-inventory sites for pilot ISF operations. | 2017-07-07 |  | 2017-07-07 |  | 2017 | Complete | DRAFT: Establish Transportation Assets for an Interim Storage Facility | Bill Reich | Bill Reich | None | M4SF-17OR020303026-Draft Preliminary Needs Assessment-July 7 2017-FINAL.pdf | SFWD-IWM-2017-000192 | Transportation Assets
M4SF-17OR020303027 | M4 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Operating Scenarios for Asset Determination Report | Operating Scenarios for Asset Determination Report | Determine the operating scenarios that will be considered for the determination of transportation assets. | 2017-02-24 |  | 2017-02-24 |  | 2017 | Complete | Operating Scenarios for Transportation Assets Determination | Bill Reich | Matt Feldman | None | M4SF-17OR020303027-Operating Scenarios for Asset Determination-Feb 24 2017-FINAL.pdf | SFWD-IWM-2017-000193 | Transportation,modeling scenarios
M4SF-17OR020303028 | M4 | 1.08.02.03.03.02 | ORNL | SF-17OR02030302 | Transportation: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Develop Draft Sources Sought Notice for Industry Participation AOA Process | Draft Sources Sought Notice for Industry Participation AOA Process | Develop a draft sources sought notice for industry participation in AOA Process for hardware needs to be reviewed by federal sponsors. | 2016-11-18 |  | 2016-11-18 |  | 2017 | Complete | Draft Request for Expression of Interest for Nuclear Spent Fuel Transportation Equipment and Services | Dam, Scott | Matt Feldman | None | EOI NFST Transportation Services DRAFT 11-18-16.docx | SFWD-IWM-2017-000194 | Request for Expression of Interest, REI, railcar, procurement
M4SF-17OR020403113 ULR Predecisional Draft | M4 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Howard, Rob | Howard, Rob | NGSAM Data Needs Report - Progress and New Requests | NGSAM Data Needs Report - Progress and New Requests | Report on NGSAM's data needs including status on the progress of needs already identified as well as documenting additional needs. | 2017-09-22 |  | 2017-09-22 | The Next Generation System Analysis Model (NGSAM) is being developed to model the Integrated Waste Management System to support planning studies [1]. NGSAM uses analyst input and supporting data to model the storage and transportation of spent nuclear fuel (SNF) from its origin at nuclear reactors to its ultimate destination of an underground repository. The dataset supporting NGSAM is under constant development. This report documents the efforts to improve the dataset in Fiscal Year 2017 and presents a list of potential improvements that can be made to the dataset supporting NGSAM | 2017 | Complete | NGSAM Data Needs Report – Progress and New Requests | Riley Cumberland | Riley Cumberland | OUO |  | SFWD-IWM-2017-000149 | SNF Systems Analysis
M4SF-17OR020403117 | M4 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Jarrell, Josh | Jarrell, Josh | Provide Additional NGSAM Feature Requests to NGSAM PoC | NGSAM Feature Requests | This report will document additional analyst-requested features based on testing of the most recent NGSAM release. | 2016-12-09 |  | 2016-12-09 |  | 2017 | Complete | NGSAM Feature Requests | Robert Joseph III | Josh Jarrell | None | PB1601098_Joseph_NGSAM_Final.pdf | SFWD-IWM-2017-000150
M4SF-17OR020501023 | M4 | 1.08.02.05.01.02 | ORNL | SF-17OR02050102 | Systematic Studies Involving Canisters- ORNL | Scaglione, John | Nutt, Mark | Report addressing Repair, Rework, and Repackaging options for nonconforming canister/cask | Functions and Operational Requirements for Mobile Facility | Functions and operational requirements document for a mobile examination and repair facility (MERF) to support identification of options for dealing with DPCs that are not transportable. These requirements will be refined and developed in more detail, as the conceptual design evolves. | 2017-07-31 |  | 2017-02-01 |  | 2017 | Complete | N/A - due to BCP | Chatzidakis, Stylianos | Scaglione, John | None |  | SFWD-IWM-2017-000210
M4SF-17PN020403062 | M4 | 1.08.02.04.03.06 | PNNL | SF-17PN02040306 | ESA Development and Application - PNNL | Maheras, Steve | Jarrell, Josh | Shutdown Reactor Site Transportation Infrastructure Analysis Part I | Shutdown Reactor Site Transportation Infrastructure Analysis Part I | A) Generic basic success-precedence diagrams of major milestone, activities necessary to establish the infrastructure needed to begin accepting spent nuclear fuel canisters at a shutdown site. B) Development of a generic set of risks that could impact establishment of the transportation infrastructure. | 2016-12-31 |  | 2016-12-20 06:00 |  | 2017 | Complete | Shutdown Reactor Site Transportation Infrastructure Analysis- I | Steve Maheras | Steve Maheras | None | M4SF-17PN020403062_Shutdown Site Risk Register and Base Inputs_2016-12-20.xlsx M4SF-17PN020403062_SPDs_r1_2016-12-08.pdf M4SF-17PN020403062_SPDs_r1_2016-12-08.vsdx M4SF-17PN020403062_Summary of Site Deinventory Milestones_2016-12-20.docx | SFWD-IWM-2017-000144 | Shutdown sites, near site transportation infrastructure, transportation infrastructure, success-precedence diagram, SPD, execution strategy analysis, de-inventory
M4SF-17PN020403063 | M4 | 1.08.02.04.03.06 | PNNL | SF-17PN02040306 | ESA Development and Application - PNNL | Maheras, Steve | Jarrell, Josh | Shutdown Reactor Site Transportation Infrastructure Analysis Part II | Shutdown Reactor Site Transportation Infrastructure Analysis Part II | A) Development of site-specific success-precedence diagrams of major milestones and activities necessary to establish the infrastructure needed to begin accepting spent nuclear fuel canisters at each shutdown site (using the generic diagrams from Part I). B) Identification of activity costs, duration and major risks for each shutdown site. | 2017-03-31 |  | 2017-03-31 03:00 |  | 2017 | Complete | Excel file - NFST Execution Strategy Model for Shutdown Sites | Steve Maheras | Steve Maheras | None | M4SF-17PN020403063_Shutdown_Reactor_Site_Infrastructure_Analysis_Part_2.xlsx | SFWD-IWM-2017-000145 | Shutdown sites, near site transportation infrastructure, transportation infrastructure, success-precedence diagram, SPD, execution strategy analysis, ESA, de-inventory, base input data, risk register
M4SF-17SN020101046 | M4 | 1.08.02.01.01.04 | SNL | SF-17SN02010104 | Siting Process Design - SNL (CLOSED) | Rechard, Rob | Howard, Rob | Conceptual design for an CBS process data instrument | Conceptual Issues Pertaining to Public Views on Consent Based Siting for Facilities of an Integrated Waste Management System | Create the conceptual design for an data instrument that will focus on the transportation to, and site selection process for, storage and disposal of spent nuclear fuel. Components of the conceptual design will be informed by discussions among the OU Team, Sandia project manager, and waste management program personnel from DOE. A workshop meeting, to be held in Norman, OK, in March 2017 will provide the final conceptual input for this Task. The conceptual design will also include continued evaluation of data from past surveys on the “non-market value” of on-site and interim storage facilities. Neither question design nor data collection will be a part of the conceptual design process. | 2017-04-28 10:00 | 2017-05-08 02:00 | 2017-05-01 02:00 |  | 2017 | Completed Late | Conceptual Development for Evaluating Public Beliefs and Preferences Regarding Programs and Facilities for Nuclear Waste Management | Rob P Rechard | Rob P Rechard | None | EE17 Conceptual Design Report 4-28-17.pdf | SFWD-IWM-2017-000122
M4SF-17SN020101048 Per Matt Brainard: Note: This milestone was also submitted under M4SF-17SN020403301 with Josh Jarrell (ORNL) as control account manager. | M4 | 1.08.02.01.01.04 | SNL | SF-17SN02010104 | Siting Process Design - SNL (CLOSED) | Rechard, Rob | Howard, Rob | Analysis of text-based historical information on public concerns and preferences. | Analysis of Public Concerns and Preferences at Hearings on DOE Nuclear Facilities | Gather, code, and analyze public input (4 sets of public hearings, to the extent practicable, spanning the period from the 1980s to the 2010s) to identify both consistencies and changes in public concerns and preferences over time. OU will provide a summary and technical report describing the analytical findings and methods used. | 2017-07-31 08:00 | 2017-08-11 02:00 | 2017-08-11 02:00 |  | 2017 | Completed Late | Interest and Advice on Spent Nuclear Fuel Management Expressed in Federal Hearings over Four Decades | Rob P. Rechard | Rob P. Rechard | None | EE17 Analysis of Congressional Hearings 08-01-17.pdf | SFWD-IWM-2017-000123 | spent nuclear fuel; congressional hearings on spent nuclear fuel
M4SF-17SN020201034 | M4 | 1.08.02.02.01.03 | SNL | SF-17SN02020103 | Storage Design Concepts - SNL | Durbin, Sam | Carter, Joe | Preliminary security evaluation of a vault-style storage system for ISF applications | Preliminary security evaluation of a vault-style storage system for ISF applications | Classified Sandia Letter Report | 2017-03-31 04:00 |  | 2017-03-29 02:00 |  | 2017 | Complete | Security Assessment of Vault-Style Buildings for Spent Nuclear Fuel Storage at Interim Storage Facilities (U) | Durbin, Samuel | Durbin, Samuel | None |  | SFWD-IWM-2017-000128 | vault; interim storage; security; sabotage; dry storage; spent nuclear fuel
M4SF-17SN020403301 Per Matt Brainard: Note: This milestone was also submitted under M4SF-17SN020101048. | M4 | 1.08.02.04.03.30 | SNL | SF-17SN02040330 | System Deployment Analysis - SNL | Rechard, Rob | Jarrell, Josh | Analysis of text-based historical information on public concerns and preferences | Analysis of text-based historical information on public concerns and preferences | Gather, code, and analyze public input (4 sets of public hearings, to the extent practicable, spanning the period from the 1980s to the 2010s) to identify both consistencies and changes in public concerns and preferences over time. OU will provide a summary and technical report describing the analytical findings and methods used. | 2017-07-31 20:00 | 2017-08-11 02:00 | 2017-08-11 02:00 |  | 2017 | Completed Late | Interest and Advice on Spent Nuclear Fuel Management Expressed in Federal Hearings over Four Decades | Rob P Rechard | Rob P Rechard | None | EE17 Analysis of Congressional Hearings 08-01-17.pdf | SFWD-IWM-2017-000244 | spent nuclear fuel; congressional hearings on spent nuclear fuel, text analysis
M4SF-17SN020403302 | M4 | 1.08.02.04.03.30 | SNL | SF-17SN02040330 | System Deployment Analysis - SNL | Rechard, Rob | Jarrell, Josh | Preliminary Findings from 2017 Nationwide Survey of US Residents | Preliminary Findings from 2017 Nationwide Survey of US Residents on Nuclear Facilities | A presentation with slides will be prepared on the preliminary results from the 2017 Energy and Environment Survey. The presentation will be used to inform other team members such that they can anticipate the final findings that will be documented in September. | 2017-07-31 18:00 | 2017-08-14 02:00 | 2017-08-14 02:00 |  | 2017 | Completed Late | Status of 2017 Energy and Environment Survey and Social Media Analysis Related to Radioactive Waste Management in US | Rob P. Rechard | Rob P. Rechard | None | Status of EE17 Survey and Media Monitoring 08-08-17.pdf | SFWD-IWM-2017-000219 | national preferrence survey, Twitter message analysis, radioactive waste management
M5SF-17AN020403044 | M5 | 1.08.02.04.03.09 | ORNL | SF-17OR02040309 | NGSAM Development and Application - ORNL | Jarrell, Josh | None | Document ESA capabilities related to integration assessment of ISF deployment | ESA capabilities related to integration assessment of ISF deployment | Document ESA capabilities related to integration assessment of ISF deployment | 2017-02-17 01:00 |  | 2017-03-01 |  | 2017 | Completed Late | Capability of the Execution Strategy Analysis (ESA) Tool to Evaluate Integrated Assessment of ISF Deployment Alternative Scenarios | Mark Nutt, | Mark Nutt, | None | ESA Capabilities Evalation - Scenario for Assmt of ISF Deploy Alts 2017-03-01 (Draft).docx | SFWD-IWM-2017-000168 | ESA, integrated waste managment
M5SF-17AN020403089 ULR Predecisional Draft SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M5 | 1.08.02.04.03.04 | ANL | SF-17AN02040304 | ESA Development and Application - ANL | Saraeva, Natalia | None | NGSAM Preparation for Integrated Assessment of ISF Deployment Scenarios | NGSAM Preparation for Integrated Assessment of ISF Deployment Scenarios | This short report will document NGSAM preparation for the larger Integrated Assessment of ISF Deployment Scenarios, which were documented in a Level 5 Deliverable from ANL’s MOEF WP with a due date of November 18th (M5SF-17AN020403014). It will identify if NGSAM can perform the requested scenarios and if not will identify the path forward to ensure it has those capabilities in the future. | 2016-12-16 05:00 |  | 2016-12-16 01:00 |  | 2017 | Complete | NGSAM Preparation for Integrated Assessment of ISF Deployment Scenarios | Jim St. Aubin | ANL | None | NGSAM M5 Milestone Report 2016-12-13 FINAL-3.pdf | SFWD-IWM-2017-000169 | NGSAM, System Architecture, MOEF
M5SF-17ID020301044 Summary Report, Rev. 1: M4SF-17OR020301014, SFWD-IWM-2017-000058-R1 Additional documentation of workshop is in CURIE | M5 | 1.08.02.05.01.03 | DOE-ID | SF-17ID02050103 | Simultaneous Welding Task (Task Order 2) | Ford, Brayton | None | Conduct a Routing Workshop and Draft a Summary Report | Conduct a Routing Workshop and Write a Draft Summary Report | Develop materials for, provide states and tribes technical assistance in, conduct a transportation routing workshop, and write a draft report summarizing lessons learned. | 2017-08-31 04:00 | 2017-09-13 02:00 | 2017-09-12 02:00 | This document summarizes the discussion that occurred at the August 24-25, 2017 Rail/Routing Ad Hoc Working Group Rail Routing Workshop in Colorado Springs, Colorado. | 2017 | Completed Late | Meeting Summary for the Rail/Routing Ad Hoc Working Group Routing Workshop |  |  | None | Mtg Summary_R_R AHWG Workshop_Aug_24_25_2017.docx | SFWD-IWM-2017-000129
M5SF-17OR020403115 | M5 | 1.08.02.04.03.08 | ANL | SF-17AN02040308 | NGSAM Development and Application - ANL | St. Aubin, Jim | None | Canister and Overpack Site Assignments and Loading Maps | Canister and Overpack Site Assignments and Loading Maps | Report outlining the cask list and loading maps for those canisters and overpacks to be contained in the UDB. This includes information indicating what data elements are already part of the UDB and which still need to be added to the database. Additionally, this report should include sufficient information to identify which canister systems and overpacks should be assigned to each reactor site in waste management system analysis tools, as well as identify which systems should be used in place of any that may be unavailable in the UDB. | 2017-01-21 |  | 2017-01-20 |  | 2017 | Complete | Development of Canister and Overpack Site Assignments and Thermal Limit Maps | Riley Cumberland | Josh Jarrell | None | Development of Canister and Overpack Site Assignments and Loading Maps M5SF-17OR020403115 copy.pdf | SFWD-IWM-2017-000171
M5SF-17OR020403116 | M5 | 1.08.02.04.03.01 | ANL | SF-17AN02040301 | MOEF Application - ANL | Samsa, Michael | None | Cost Information for NGSAM Implementation Report | Cost Information for NGSAM Implementation Report | report outlining the cost information to be used in the implementation of NGSAM. This report should be very brief, but should include cost information to at least the level of fidelity of legacy system analysis tools. Finally, this report should highlight any inconsistencies in the current implementation of cost calculation from what is planned as a final implementation in NGSAM. | 2016-12-16 |  | 2016-12-15 |  | 2017 | Complete | Cost Information for NGSAM Implementation | Riley Cumberland | Josh Jarrell | None | M5SF-17OR020403116 Cost Information for NGSAM Implementation.pdf | SFWD-IWM-2017-000172
M5SF-17OR020501027 | M5 | 1.08.02.04.03.11 | ORNL | SF-17OR02040311 | System Architecture Analysis - ORNL | Jarrell, Josh | None | Shielding weight evaluations to support design concept for a generic salt repository that accepts 21 PWR waste packages | Shielding weight evaluations to support design concept for a generic salt repository that accepts 21 PWR waste packages | Perfrom shielding weight evalautions to support development of a detailed design concept for a generic salt repository that accepts 21 PWR canisters as the canister portion of the waste package. This concept will need to include operations necessary to emplace the waste packages (e.g., ramps, hoists [11], etc.) as well as the waste package materials and thicknesses. SNL-led, ORNL-support | 2017-06-30 |  | 2017-06-30 |  | 2017 | Complete | Mass evaluation of supplemental waste package shielding | Cumberland | Scaglione | None |  | SFWD-IWM-2017-000249
M3SF-18BM020303053 | M3 | 1.08.02.03.03.05 | BMPC | SF-18BM02030305 | Transportation: Hardware - BMPC (Naval Reactors) | Schwab, Patrick | Feldman, Matt | Agreement with NNPP for acquisition of one REV | Memorandum of Agreement with NNPP | Agreement with NNPP and transfer funds from NE to NNPP. | 2018-06-30 |  | 2018-06-13 |  | 2018 | Complete | AGREEMENTS AND PROJECT PLAN FOR RAIL ESCORT VEHICLE PROCUREMENT | Jointly written by NE and NNPP. | NE and NNPP | None | DOENE_REV_Agreements_issued.pdf |  | Atlas Railcar, Rail Escort Vehicle,
M2SF-18OR020102011 Contains M4SF-18OR020102014 as input. | M2 | 1.08.02.01.02.01 | ORNL | SF-18OR02010201 | Private Initiative Implementation Plan - ORNL | Howard, Rob | Howard, Rob | DRAFT Private Initiative Implementation Plan | Draft Private Initiative Implementation Plan | DRAFT Private Initiative Implementation Plan | 2018-06-15 |  | 2018-06-15 |  | 2018 | Complete | Draft Private Initiative Plan | Howard, Rob | Howard, Rob | OUO
M2SF-18OR020103011 | M2 | 1.08.02.01.03.01 | ORNL | SF-18OR02010301 | Government-Owned, Contractor Operated Implementation Plan - ORNL | Feldman, Matt | Feldman, Matt | DRAFT Government-Owned, Contractor Operated Implementation Plan | Draft Government-Owned, Contractor Operated Implementation Plan | DRAFT Government-Owned, Contractor Operated Implementation Plan | 2018-05-16 |  | 2018-05-16 |  | 2018 | Complete | Government-Owned, Contractor-Operated (GOCO) Integrated Waste Management Plan – Predecisional Draft | Feldman, Matt | Feldman, Matt | None | M2SF-18OR020103011_GOCO-IWM Plan_Predecisional Draft Final.pdf |  | GOCO, Government-owned, Contractor-operated, CISF Plan, Implementation Plan
M2SF-18SR020101021 | M2 | 1.08.02.01.01.02 | SRNL | SF-18SR02010102 | Bases for Potential Acquisition of SNF Storage and Transportation Capabilities - SRNL | Carter, Joe | Carter, Joe | DRAFT Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | DRAFT Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | DRAFT Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | 2018-08-15 |  | 2018-06-29 |  | 2018 | Complete | Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | Carter, Joe | Carter, Joe | None | M2SF-18SR020101021 - Bases for Potential Acquisition - Final DRAFT 6-29-18.pdf QA Cover - M2SF-18SR020101021 - Bases for Potential Acquisition.pdf |  | Potential Acquisition
M3SF-18AN020107011 ULR. Predecisional Draft. | M3 | 1.08.02.01.07.01 | ANL | SF-18AN02010701 | Contract Issues and Approach Report - ANL | Nutt, Mark | Nutt, Mark | DRAFT Contract Issues and Approaches | DRAFT Contract Issues and Approaches | DRAFT Contract Issues and Approaches | 2018-02-28 |  | 2018-02-28 02:00 |  | 2018 | Complete | Contract Issues, Options, and Approaches –Draft V.0 | William Nutt | William Nutt | None | Contracting Issues Options and Approaches Report M3SF-18AN020107011 Draft V0.pdf |  | ISF, CISF, Consolidated Interim Storage, Acquisition
M3SF-18ID020201041 Supersedes M3SF-17ID020201075 Per Matt Brainard: Narrative: “90% Design Review Presentation to the Review Team was completed on 12/14/2017.” Deliverable Title: “Pilot ISF Design Report (Section 4.2.1), TSAR (Section 4.2.2)” – Note this does not match the file uploaded to PICS:NE. Main Document Title: “Pilot Interim Storage of Spent Fuel, Generic Design and Topical Safety Analysis Report, 90% Generic Design/TSAR Review”. Approval comment: “The 90% Generic Design Report and TSAR contract deliverables were received in December as scheduled. Comments on both products are developed and will be transmitted to DOE in January.” | M3 | 1.08.02.02.01.04 | DOE-ID | SF-18ID02020104 | Pilot Interim Storage of Spent Nuclear Fuel: Generic Design and Topical Safety Analysis Report (TSAR) - DOE-ID | Reeves, Steve | Carter, Joe | 90 Percent Project Review | Pilot ISF Design Report (Section 4.2.1), TSAR (Section 4.2.2) | 90 Percent Project Review | 2017-12-14 |  | 2017-12-14 |  | 2018 | Complete | Pilot Interim Storage of Spent Fuel, Generic Design and Topical Safety Analysis Report, 90% Generic Design/TSAR Review |  |  | None | Agenda- 90 Percent Generic Design TSAR Review.docx
M3SF-18ID020408031 Supersedes M3SF-17ID020501031. Per Matt Brainard: “The subject milestone, Complete Task Order 2 (TO2) Phase 1: Prototype Ready for Testing, was successfully completed by Atkins on 10/25/2017 with the End-of-Phase 1 Progress Review Meeting held at DOE Headquarters. Confirmation of the prototype being ready for testing was documented in the attached letter sent to Jack Wheeler by Ivan Thomas, Atkins TO2 Task Manager, prior to the meeting.” | M3 | 1.08.02.04.08.03 | DOE-ID | SF-18ID02040803 | Simultaneous Welding Task (Task Order 2) - DOE-ID (COMPLETE) | Wheeler, Jack | Howard, Rob | Complete TO2 Phase 1: Prototype Ready for Testing | Complete TO2 Phase 1: Prototype Ready for Testing | Complete TO2 Phase 1: Prototype Ready for Testing | 2017-10-31 |  | 2017-10-25 |  | 2018 | Complete | A&AS CONTRACT NUMBER DE-NE0008493 – TASK ORDER 2 – SIMULTANEOUS WELDING OF MULTIPLE STAD CANISTERS – TO #DE-DT0012826 - CONFIRMATION THAT WELDING SYSTEM PROTOTYPE HAS BEEN COMPLETED AND IS READY FOR PHASE 2 TESTING | Atkins | Atkins | None | LT-5155689-GE-0002 - Atkins Task Order 2 Phase 1 Completion Letter - 10.pdf
M3SF-18ID020408032 Supersedes M3SF-17ID020501032. Per Matt Brainard: M3SF-18ID020408032: Complete TO2 Phase 2: Testing and Evaluation” and completed on 2/23/2018 under the follow on FY18 work package. Deliverable attached. Narrative: “Atkins submitted Rev. 0 of the Test & Evaluation (T&E) Report on testing conducted under Phase 2 of DOE Task Order No. 2. This submittal satisfactorily addressed DOE-NE comments provided on the preliminary release of this deliverable.” Deliverable Title: “Phase 2 Testing and Evaluation Report”. Main Document Title: “Task Order 2, Simultaneous Welding of Multiple Standardized Transportation, Aging, and Disposal (STAD) Canisters, Test and Evaluation Report”. Notes: “The main document has been posted to the private side of the CURIE website (https://curie.ornl.gov) while it is going through the HQ review process. Upon successful completion, the document will be moved to the public side of CURIE.” | M3 | 1.08.02.04.08.03 | DOE-ID | SF-18ID02040803 | Simultaneous Welding Task (Task Order 2) - DOE-ID (COMPLETE) | Wheeler, Jack | Howard, Rob | Complete TO2 Phase 2: Testing and Evaluation | Phase 2 Testing and Evaluation Report | Complete TO2 Phase 2: Testing and Evaluation | 2018-03-12 |  | 2018-02-23 |  | 2018 | Complete | Task Order 2, Simultaneous Welding of Multiple Standardized Transportation, Aging, and Disposal (STAD) Canisters, Test and Evaluation Report | Christine Gorschboth | Ivan Thomas | None |  |  | welding, SNF, STAD, canister
M3SF-18OR020104031 ULR., SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.08.02.01.04.03 | ORNL | SF-18OR02010403 | Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis - ORNL | Joseph, Robby | Howard, Rob | DRAFT Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis | DRAFT Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis | DRAFT Interim Storage and Associated Transportation System Functions, Attributes, and Options Analysis | 2018-02-28 |  | 2018-02-28 |  | 2018 | Complete | Draft Interim Storage and Associated Transportation System Functions and Attributes Options Analysis Document |  |  | None | FAOA M3SF-18OR020104031_FCT-reviewerpage.pdf
M3SF-18OR020303023 File name and document show M3SF-18OR020303021-Atlas Railcar Design Project Status Report-Sept 30 2018-FINAL.pdf | M3 | 1.08.02.03.03.02 | ORNL | SF-18OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Design Project Status Report for FY2018 | Atlas Railcar Design Project Status Report for FY2018 |  | 2018-09-30 |  | 2018-09-26 | Milestone report completed on schedule. | 2018 | Complete | Atlas Railcar Design Project Status Report for FY2018 | Bill Reich | Matt Feldman | None | M3SF-18OR020303021-Atlas Railcar Design Project Status Report-Sept 30 2018-FINAL.pdf |  | Atlas Railcar
M3SF-18OR020408011 | M3 | 1.08.02.04.08.01 | ORNL | SF-18OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | RD&D multi-year plan | MERF development and demonstration plan | 2. Development of a 5-year research, development, and demonstration plan that culminates in a design, build, and field test of the mobile examination and remediation facility (MERF) on a dry storage system. The workplan should emphasize: • Developing requirements, defining assumptions, selecting equipment, materials and sources, determining testing needs, and providing acceptance criteria • Identify potential host sites for cold testing • Assess regulatory challenges that would need to be addressed and potential path forward • Identify key programmatic milestones | 2018-06-29 |  | 2018-06-29 |  | 2018 | Complete | MERF Development and Demonstration Plan | Chatzidakis, Stylianos | Scaglione, John | None | MERF RDD plan_v12_20180703_ED_vsc-vkv-vsc-vsc-bbb-jms-rlh-vsc-alb-vsc.pdf
M3SF-18OR020408013 | M3 | 1.08.02.04.08.01 | ORNL | SF-18OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Multi-option downstream impact assessment deep dive | Impact assessment comparison of different options for addressing non-conforming dry storage systems | • There are several options to address nonconforming DSSs: use-as-is, overpack, repair, rework, and replacement. This activity will be focused on evaluating downstream impacts, enhancement/establishment of key metrics for each option and documenting an impact assessment for the different options. Document will discuss advantages and disadvantages, technical maturity, typical timing for technology maturation, and a cost comparison for the different options. This activity will be focused on extending the M3 deliverable to incorporate a cost comparison and timing execution, as well as identification of key parameters to support systems analysis modeling | 2018-09-28 |  | 2018-09-28 | Previous work identified and qualitatively evaluated options for addressing potential future deficiencies associated with DSSs. Further, efforts have been initiated to develop and demonstrate a Mobile Examination and Remediation Fixture (MERF) with functions and capabilities for onsite remediation of nonconforming canisters/casks. The present study aims to extend previous work by quantitatively evaluating two downstream impact metrics, cost and schedule, for previously identified resolution options that could address a postulated defect in a welded steel canister or bolted lid metal cask. Cost and schedule deviations above baseline are calculated for each of the identified options. | 2018 | Complete | System-Wide Impacts of Resolution Options for a Non-Comforming Dry Storage System | Chatzidakis, Stylianos | Scaglione, John | None | M3SF-18OR02040813 MERF Downstream Deep Dive.pdf
M3SF-18OR020408014 | M3 | 1.08.02.04.08.01 | ORNL | SF-18OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Functions and Requirements and Concept of Operations for MERF | MERF Functions and Requirements and Concept of Operations | Develop a concept of operations for the MERF that includes interface with ISFSI and canister array, development of equipment and component specifications, safety assessment against design basis events, operational procedures, and deployment methodology for different scenarios, e.g., vertical vs. horizontal DSS. Initial focus will be on repairing existing weld, and secondary focus is to support repackaging | 2018-09-30 |  | 2018-09-30 | Milestone report completed that lays out functions and requirements and a concept of operations for a Mobile Examination and Remediation Fixture (MERF) capable of onsite remediation of nonconforming canisters/casks. The purpose of this report is to describe the key systems and operations of a MERF on a DSS. The MERF concept, as summarized in this report, addresses the functions and requirements, operational procedures, and deployment methodology of examination- and repair-related systems needed to remotely perform remediation operations on existing DSSs to support continued storage or offsite transportation. The main MERF function would be to perform onsite remediation of identified nonconformances related to the confinement boundary of vertical or horizontal DSSs. To achieve this, a MERF concept has been developed that describes a mobile (i.e., transportable), multi-purpose fixture, remotely operated and computer controlled with semi-automated equipment to allow trained operators to safely perform remediation activities while keeping worker radiation dose as low as reasonably achievable (ALARA). Once a condition has been identified that prevents a welded stainless-steel canister or bolted-lid metal cask from being transportable or suitable for continued storage, the MERF would be available to perform remediation activities to correct the nonconformance and enable offsite transportation or continued storage. | 2018 | Complete | Functions and Requirements and Concept of Operations for MERF | Chatzidakis, Stylianos | Scaglione, John | None | PB1800858_Chatzidakis_MERF-final.pdf
M3SF-18PN020106032 ULR. PREDECISIONAL DRAFT. | M3 | 1.08.02.01.06.03 | PNNL | SF-18PN02010603 | Legislative, Legal and Regulatory, Orders - Issues and Strategies - PNNL | Maheras, Steve | Maheras, Steve | Draft LLROIS Report | Draft LLROIS Report | Draft M3 LLROIS Report | 2018-02-28 |  | 2018-02-28 06:00 |  | 2018 | Complete | Integrated Waste Management Legislative, Legal, Regulatory, Orders – Issues and Strategy Draft Report | Steve Maheras | Steve Maheras | None | LLROIS_M3SF-18PN020106032.pdf |  | LLROIS, legislation, funding, indemnification, Standard Contract, NEPA, legal issues, regulatory issues, DOE Orders, intergovernmental and external engagement issues
M3SF-18SN020201052 | M3 | 1.08.02.02.01.05 | SNL | SF-18SN02020105 | Storage Design - SNL | Durbin, Sam | Carter, Joe | Uncertainty Analysis of a Security-Related Source Term from Spent Nuclear Fuel in Underground Storage | Uncertainty Analysis of a Security-Related Source Term from Spent Nuclear Fuel in Underground Storage | Classified SAND Report | 2017-11-30 04:00 |  | 2017-11-29 02:00 |  | 2018 | Complete | Uncertainty Analysis of a Spent Nuclear Fuel Release from Dry Storage during a Security-Related Scenario | Samuel Durbin | SNL | None |  |  | spent nuclear fuel; dry storage; sabotage; source term
M3SF-18SR020105031 ULR Predecisional Draft. SFWD Working Document: External Release or Reference Requires DOE-NE Approval | M3 | 1.08.02.01.05.03 | SRNL | SF-18SR02010503 | Reference Concept - SRNL | Carter, Joe | Carter, Joe | DRAFT IWM Reference Concept | Reference Concept Report | DRAFT IWM Reference Concept | 2018-04-05 |  | 2018-03-09 |  | 2018 | Complete | Reference Concepts for Interim Storage | Carter, Joe | Carter, Joe | None | M3SF-18SR020105031 - Reference Concept.pdf |  | Reference Concepts
M4SF-18AN020107013 | M4 | 1.08.02.01.07.01 | ANL | SF-18AN02010701 | Contract Issues and Approach Report - ANL | Nutt, Mark | Nutt, Mark | DRAFT Contract Issues and Approaches Annotated Outline | DRAFT Contract Issues and Approaches Annotated Outline | DRAFT Contract Issues and Approaches Annotated Outline | 2017-11-15 |  | 2017-11-15 01:00 |  | 2018 | Complete | DRAFT Contract Issues and Approaches Annotated Outline | William Nutt | William Nutt | None | Contracting Issues Options and Approaches Report _Annotated Outline_20171108.docx
M4SF-18ID020301042 Per Matt Brainard: Notes: “Some members of the Tribal Radioactive Materials Transportation Committee requested DOE directly contact them to request information. Calls were made to the Prairie Island Indian Community, the Shoshone-Bannock Tribes, and the Consolidated Group of Tribes and Organizations (CGTO). All feedback generally supported the information contained in historical comment documents DOE found from the 1990s and early 2000s, with some additional comments/context provided.” | M4 | 1.08.02.03.01.04 | DOE-ID | SF-18ID02030104 | Transportation: Intergovernmental and External Engagement - DOE-ID (SRGs and Tribes) | Bickford, Erica | Feldman, Matt | Request for Information Item #1: Historical comments on waste program privatization | Information Request #1 | Request for SRGs/Tribes to provide copies of past comments submitted in response to proposal to privatize aspects of the waste program. Specifically comments from mid-1990s and early 2000s. | 2018-02-28 |  | 2018-01-19 |  | 2018 | Complete | Responses to Request for Information Item #1: Historical comments on waste program privatization | Bickford, Erica | Bickford, Erica | None | CSGMW_InformationRequest_Response1.pdf DOE-IWM Information Request #1 (SSEB).pdf NCSL_InformationRequest_Response1.pdf Northeast Task Force Response to DOE Information Request #1 Jan 5 2018.pdf WIEB Response to DOE Info Request no.1.pdf |  | State Regional Groups, stakeholders, Tribes
M4SF-18ID020301043 Per Matt Brainard: Notes: “All five Cooperative Agreement recipients submitted a response to DOE's information request. Two groups - CSG-MW and TRMTC (via NCSL) - indicated that they would defer substantive completion of this task until FY19, when they would include it as a "Targeted Task" under their FY19 Cooperative Agreement renewal. The three other groups provided substantive responses for their regions.” | M4 | 1.08.02.03.01.04 | DOE-ID | SF-18ID02030104 | Transportation: Intergovernmental and External Engagement - DOE-ID (SRGs and Tribes) | Bickford, Erica | Feldman, Matt | Request for Information Item #2: SocioEconomic Considerations for SNF removal | Information Request Item #2 | Request for SRGs to coordinate information from their regions relating to social and economic considerations for removing fuel from sites. | 2018-07-31 |  | 2018-05-31 |  | 2018 | Complete | Responses to Request for Information Item #2: Non-technical (socioeconomic) Considerations for Removing SNF from Shutdown Sites | Bickford, Erica | Bickford, Erica | None | CSG_ERC - DOE INformation Request #2.pdf CSGMW_InformationRequest_Response2.pdf SSEB_DOE-IWM Information Request #2.pdf TRMTC Response to DOE Info Request 2.pdf WIEB Response to DOE Info Request no.2.pdf |  | State Regional Groups, stakeholders, Tribes
M4SF-18ID020301044 | M4 | 1.08.02.03.01.04 | DOE-ID | SF-18ID02030104 | Transportation: Intergovernmental and External Engagement - DOE-ID (SRGs and Tribes) | Bickford, Erica | Feldman, Matt | Request for Information Item #3: HRCQ Transportation Statues/Requirements | Information Request Item #3 | Request for states (and Tribes where applicable) to submit information on their requirements/practices/procedures for inspecting and escorting HRCQ shipments through their jurisdictions, handling of armed security with shipments, fee structures, etc. | 2018-09-30 |  | 2018-09-28 | All entities provided at least a minimal response to this information request. SSEB submitted the most comprehensive data covering 15 states in its region. CSG-MW submitted comprehensive data for 9 of its states, and limited data for 3 others. CSG-ERC submitted information on 4 states, and indicated it has more information but DOE email servers were blocking email attachments. Efforts to obtain the information are still in progress. WIEB submitted thorough information on state regulations for 10 states in its region. NCSL provided information on only 2 Tribes (out of ~15 involved in TRMTC). A consolidated file of the information provided by September 28th, 2018 is attached. | 2018 | Complete | Info. Request 3 Responses |  |  | None | Info. Request 3 Responses_9.28.2018.xlsx
M4SF-18ID0203030410 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 4: Long Lead Material Receipt & Inspection Complete (driven by Monitoring System Installation) | Long Lead Material Receipt & Inspection Report | CLIN 3 Event 4: Long Lead Material Receipt & Inspection Complete (driven by Monitoring System Installation) | 2019-02-21 |  | 2018-08-10 |  | 2018 | Complete | Submission of Long-Lead Material Report, CLIN 3 Event 4 | Orano Federal Services | Orano Federal Services | None | FS-18-0193 LL Material Report.docx FS-18-0193 LL Matl Property Report.xlsx FS-18-0193 LL Matl PTI Files.pdf |  | Atlas Railcar long-lead-time materials
M4SF-18ID020303042 Supersedes M3SF-17ID0203030510 Per Matt Brainard: Narrative: “AAR approved the Atlas and buffer railcar preliminary designs. These two letters transmit these approvals to DOE's contractor, Kasgro Rail.” Deliverable Title: “AAR Notice to Proceed”. Main Document Title: “AAR Notices to Proceed, Atlas Cask and Buffer Railcars”. | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 2 Event 5: AAR Notice to Proceed | AAR Notice to Proceed | CLIN 2 Event 5: AAR Notice to Proceed | 2018-02-02 |  | 2018-02-02 |  | 2018 | Complete | AAR Notices to Proceed, Atlas Cask and Buffer Railcars | Association of American Railroads | Schwab | None | 209.240 Kasgro HLRM Atlas Car Initial Design Approval.pdf 209.240 Kasgro HLRM Buffer Car Initial Design Approval.pdf |  | Railcar designs, cask car, buffer car, Atlas, AAR
M4SF-18ID020303045 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 2: Receipt Inspection of Fabrication Material Complete | Receipt Inspection of Fabrication Material | CLIN 3 Event 2: Receipt Inspection of Fabrication Material Complete | 2018-09-24 | 2018-08-24 | 2018-08-10 |  | 2018 | Complete | Submission of Fabrication Material Report, CLIN 3 Event 2 | Orano | Orano | None | FS-18-0192 Fab Material Report.docx FS-18-0192 Fab Matl Property Report.xlsx FS-18-0192 Fab PTI Files.pdf |  | Atlas Railcar fabrication materials
M4SF-18ID020303047 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 5: Wheel Sets Receipt & Inspection Complete | Wheel Sets Receipt & Inspection Report | CLIN 3 Event 5: Wheel Sets Receipt & Inspection Complete | 2018-10-28 |  | 2018-04-03 |  | 2018 | Complete | Wheel Set Inspection Document Package | Orano | Schwab | None | FS-18-0080 Accepted Wheelset Documents.docx FS-18-0080 Kasgro Rail - DTF 013.pdf |  | Atlas, railcar, wheel sets,
M4SF-18ID020408033 Supersedes M4SF-17ID020501034. Per Matt Brainard: Narrative: “A Simultaneous Welding Test of Four Small STAD Canister Mock-ups for DOE was conducted on December 19-20, 2018 at Liburdi Dimetrics facility in Mooresville, NC. The testing was witnessed by representatives from DOE and ORNL.” | M4 | 1.08.02.04.08.03 | DOE-ID | SF-18ID02040803 | Simultaneous Welding Task (Task Order 2) - DOE-ID (COMPLETE) | Wheeler, Jack | Howard, Rob | Conduct Simultaneous Welding Test for DOE | Conduct Simultaneous Welding Test for DOE | Conduct Simultaneous Welding Test for DOE | 2017-12-20 |  | 2017-12-20 |  | 2018 | Complete | Task Order 2 - Simultaneous Welding of Multiple STAD Canisters, Atkins Monthly Status for December 2017 |  |  | None | Atkins Task Order 2 - December 2017 Status Report - FINAL - 1_4_18.pdf
M4SF-18OR020103013 | M4 | 1.08.02.01.03.01 | ORNL | SF-18OR02010301 | Government-Owned, Contractor Operated Implementation Plan - ORNL | Feldman, Matt | Feldman, Matt | Annotated Outline for Draft Government-Owned, Contractor Operated Implementation Plan | Annotated Outline for Draft Government-Owned, Contractor Operated Implementation Plan | Submit an annotated outline for he Draft Government-Owned, Contractor Operated Implementation Plan. | 2017-12-06 |  | 2017-12-06 |  | 2018 | Complete | Government-Owned, Contractor Operated (GOCO) Plan Annotated Outline | Matt Feldman | Matt Feldman | None | M4SF-18OR020103013 - GOCO Annotated Outline.pdf |  | GoCo, Implementation Plan, Outline
M4SF-18OR020303022 | M4 | 1.08.02.03.03.02 | ORNL | SF-18OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Draft Atlas Railcar Design Project Status Report for FY2018 | Draft Atlas Railcar Design Project Status Report for FY2018 |  | 2018-08-17 |  | 2018-08-17 |  | 2018 | Complete | Draft Atlas Railcar Design Project Status Report for FY2018 | Bill Reich | Matt Feldman | None | M4SF-18OR020303022-Draft Atlas Railcar Design Project Status Report-Aug 10 2018-R0-signed.pdf |  | Atlas Railcar Annual Report
M4SF-18OR020408012 | M4 | 1.08.02.04.08.01 | ORNL | SF-18OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Literature review of past repairs on existing dry storage systems | Past experience in repairing dry storage systems | 1. Perform literature review of previous work and past experience in addressing nonconforming dry storage systems (DSSs) and equipment including past experience at: • Surry ISFSI, Peach Bottom ISFSI, Susquehanna ISFSI, other nuclear reactor sites, and international experience • Evaluate existing technology available for performing repairs remotely • Identify limitations and constraints with using existing technology (e.g., height cask handling machine can lift transfer cask) • Identify gas monitoring devices and results from existing repairs • Identify repair inspection technologies used to confirm repair | 2018-02-28 |  | 2018-02-28 |  | 2018 | Complete | Past Experience in Repairing Dry Storage Systems | Chatzidakis, Stylianos | Scaglione, John | None | PB1800099_Chatzidakis_DryStorage-rr-ds_kj_lwv_vsc_rlh_bbb_vsc_JMS_vsc.pdf |  | remediation, mitigation, repair
M4SF-18OR020408016 | M4 | 1.08.02.04.08.01 | ORNL | SF-18OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Summary report on repair technologies and demonstration | Summary of weld repair demonstration small-scale tests and inspection results | Summary report on existing testing and demonstration activities conducted to date | 2018-09-21 |  | 2018-09-21 | Milestone report completed describing the development of weld repair qualification and demonstration procedures for dry storage canister systems. The weld repair qualification and demonstration, as summarized in this report, address the laboratory qualification and demonstration of repair-related capabilities needed to remotely perform remediation operations on a nonconforming welded stainless steel canister. Once a condition has been identified that prevents a welded stainless steel canister or bolted-lid metal cask from being transportable or suitable for continued storage, the Mobile Examination and Remediation Fixture (MERF) would be available to perform remediation activities to correct the nonconformance and enable offsite transportation or continued storage. | 2018 | Complete | Weld Repair Qualification and Demonstration | Chatzidakis, Stylianos | Scaglione, John | None | PB1800935_Chatzidakis_Weld-rr-vsc-drg-vsc-alb-vsc.pdf
M4SF-18PN020106033 | M4 | 1.08.02.01.06.03 | PNNL | SF-18PN02010603 | Legislative, Legal and Regulatory, Orders - Issues and Strategies - PNNL | Maheras, Steve | Maheras, Steve | Annotated Outline for Draft LLROIS Report | Annotated Outline for LLROIS Report | Develop annotade outline for LLROIS report. | 2017-11-15 |  | 2017-11-15 03:00 |  | 2018 | Complete | Integrated Waste Management Legislative, Legal, Regulatory, Orders – Issues and Strategy Report Annotated Outline | Steve Maheras | Steve Maheras | None | LLROIS_Annotated_Outline_20171108_r1_signed.pdf |  | LLROIS, legislation, funding, Standard Contract, NEPA, legal issues, regulatory issues, DOE Orders, intergovernmental and external engagement issues
M4SF-18PN020302055 | M4 | 1.08.02.03.02.05 | PNNL | SF-18PN02030205 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | CHARMER Database Update | CHARMER Database Update | Update CHARMER database. | 2018-09-21 |  | 2018-09-11 03:00 | This report describes the COBRA-SFS model developed for the NUHOMS® 32PT DSC, which will serve as a basis for templates applicable to specific sites, utilizing the UNF-ST&DARDS tool. The CHARMER database provides canister surface boundary temperatures for the COBRA-SFS model in a specific horizontal storage environment. This model enables application of the UNF-ST&DARDS tool to seven existing spent fuel storage sites, identified based on data as of 2017. Current information indicates that there are at least 84 32PT DSCs storing 2,688 fuel assemblies at these sites. WE 14x14 fuel is represented in the COBRA-SFS model, since this is the fuel type reported in storage at all but one of the sites utilizing 32PT DSCs. The model also includes the three different basket configurations available for the 32PT DSC, based on number and arrangement of neutron poison plates within the basket cells. | 2018 | Complete | COBRA-SFS Model Template for 32PT Canister with PWR Fuel | Steve Maheras | Steve Maheras | None | 32PT-DSC_COBRA-SFS_Model_PNNL-28243_signed.pdf |  | Thermal Template, 32PT, PWR, NUHOMS, dry storage canister
M4SF-18PN020404022 | M4 | 1.08.02.04.04.02 | PNNL | SF-18PN02040402 | Data Capture and Preservation - PNNL | Maheras, Steve | Howard, Rob | Detailed San Onofre Videotape Archiving Plan and Procedures | Detailed San Onofre Videotape Archiving Plan and Procedures | Develop detailed plan and procedures for archiving San Onofre fuel inspection videotapes. | 2018-07-13 |  | 2018-07-12 06:00 |  | 2018 | Complete | Spent Nuclear Fuel Inspection Video Data Capture: Summarized Conversion Procedure | Steve Maheras | Steve Maheras | None | M4SF-18PN020404022.pdf |  | Shutdown sites, SNF, San Onofre, SONGS, fuel inspection, videotape, videotape conversion
M4SF-18SR020101022 | M4 | 1.08.02.01.01.02 | SRNL | SF-18SR02010102 | Bases for Potential Acquisition of SNF Storage and Transportation Capabilities - SRNL | Carter, Joe | Carter, Joe | Annotated Outline | Annotated outline for the draft Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | provide and annotated outline for the Draft Bases for Potential Acquisition of SNF Storage and Transportation Capabilities | 2018-01-24 | 2018-02-28 | 2018-02-28 |  | 2018 | Completed Late | Bases for Potential Acquisition of SNF Storage and Transportation Capabilities Annotated Outline | Joe Carter | Joe Carter | None | M4SF-18SR020101022 - Bases for Potential Acquisition of SNF S&T Capabilities Annotated Outline.pdf |  | Potential Acquisition
M4SF-18SR020105032 | M4 | 1.08.02.01.05.03 | SRNL | SF-18SR02010503 | Reference Concept - SRNL | Carter, Joe | Carter, Joe | Annotated Outline | Reference Concept Annotated Outline | Provide an annotated outline for the reference Concept report | 2017-11-15 |  | 2017-11-15 |  | 2018 | Complete | Referemce Concept for Interim Storage Annotated Outline | Robert Jones | Robert Jones | None | M4SF-18SR020105032 -Reference Concept - Annotated Outline 20171108.pdf |  | Reference Concept
M5SF-18AN020402023 | M5 | 1.08.02.04.02.05 | INL | SF-18IN02040205 | System Architecture Analysis - INL | Jarrell, Josh | None | NGSAM 3-Year Plan | FY2018 Next-Generation System Analysis Model (NGSAM) 3-Year Plan | NGSAM 3-year plan with FY2018 funded releases 1 and 2 that include identified High, Medium, and Low enhancements | 2018-06-15 |  | 2018-07-01 01:00 |  | 2018 | Completed Late | FY2018 Next-Generation System Analysis Model (NGSAM) 3-Year Plan | James St. Aubin | James St. Aubin | None | NGSAM 3-Year Plan - 15-June-2018 - FINAL.pdf |  | NGSAM, 3-year plan, IWM
M5SF-18IN020402052 | M5 | 1.08.02.04.02.02 | ANL | SF-18AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | None | Review previous 4 years of system architecture work for potential inclusion in FY18 system architecture report | Review previous IWM system evaluations | Review previous systems architecture and standardization evaluation reports to establish specific scenarios to evaluate as part of the FY18 systems architecture report. | 2018-06-01 |  | 2018-05-30 02:00 |  | 2018 | Complete | Review of past systems architecture reports and suggestion for new evaluations | Josh Jarrell | Josh Jarrell | None
M3SF-19ID020302012 | M3 | 1.08.02.03.02.01 | DOE-ID | SF-19ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Revised START Requirements Document | Revised START Requirements Document | Revise the START Requirements Document including detailed documentation of the comprehensive configuration control methodology and plan under which START is developed and maintained. | 2019-03-22 |  |  | I spoke with Mark Abkowitz on Monday, March 11 and he confirmed he is on schedule to meet all current milestones. | 2019 | 90 Day |  |  |  | None
M3SF-19OR020402061 | M3 | 1.08.02.04.02.06 | ORNL | SF-19OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | System Architecture/NGSAM Results Summary | FY18 System Architecture Report | Report of the analysis conducted to evaluate an integrated approach to the waste management system. This report incorporates the latest information provided through other program activities to update and augment strategies and approaches for managing SNF throughout the waste management system. | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | System Architecture/NGSAM Results Summary |  |  | None | PB1900115_Joseph_NGSAM_Final.docx
M3SF-19SR020201029 | M3 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility Concept | Canister Inspection and Remediation Facility Concept | Canister Inspection and Remediation Facility Concept | 2019-05-31 |  |  | on schedule | 2019 | On Schedule |  |  |  | None
M3SF-19SR020405022 Supersedes M3SF-18SR020405023. | M3 | 1.08.02.04.05.02 | SRNL | SF-19SR02040502 | Commercial SNF Characterization - SRNL | Carter, Joe | Howard, Rob | Inventory Report rev 6 | Inventory Report Rev 6 | Inventory Report rev 6 | 2019-03-31 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M4SF-19AN020402014 | M4 | 1.08.02.04.02.01 | ANL | SF-19AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | Integrated Waste Management Facility Configuration Evaluation: Draft Annotated Outline | Integrated Waste Management Facility Configuration Evaluation: Draft Annotated Outline | Annotated outline for L-2 Integrated Waste Management Facility Configuration Evaluation | 2018-10-31 |  | 2018-10-31 |  | 2019 | Complete | Integrated Waste Management Facility Configuration Evaluation: Draft Annotated Outline | Natalia Saraeva | Saraeva, Natalia | None | M4SF-18AN020402015.pdf |  | waste management, integrated waste management
M4SF-19IN020402052 | M4 | 1.08.02.04.02.05 | INL | SF-19IN02040205 | System Architecture Analysis - INL | Jarrell, Josh | Howard, Rob | Evaluation of at-reactor spent fuel management costs | Report on at-reactor spent fuel management costs | Report on annual at-reactor costs due to spent fuel storage | 2019-04-05 |  | 2019-04-05 | On Schedule | 2019 | 90 Day | Reevaluation of Post- Shutdown, At-Reactor Costs | Gordon Petersen | Gordon Petersen | None | At Reactor Cost Evaluation Final.pdf
M4SF-19OR020303025 | M4 | 1.08.02.03.03.02 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Security Services for Atlas Railcar Demonstration Run | Security Services for Atlas Railcar Demonstration Run | Prepare final security services plan for the Atlas railcar consist demonstration run. | 2019-06-07 |  | 2019-06-07 | Completed report on Atlas railcar security services for the demonstration run. | 2019 | Complete | Security Services for Atlas Railcar Demonstration Run | William J. Reich | Matthew R. Feldman | None | M4SF-19OR020303025-Security Services for Atlas Railcar Demonstration Run-June 7 2019-FINAL-R1.pdf |  | Atlas railcar security
M4SF-19PN020404023 | M4 | 1.08.02.04.04.02 | PNNL | SF-19PN02040402 | Data Capture and Preservation - PNNL | Maheras, Steve | Howard, Rob | Briefing on Capture of Videos at a Commercial Nuclear Power Plant | Briefing on Capture of Videos at a Commercial Nuclear Power Plant | Briefing on Capture of Videos at a Commercial Nuclear Power Plant. | 2019-09-13 |  | 2019-08-20 | This milestone describes the process used to archive the San Onofre fuel inspection videotapes, provides examples of captured content, describes issues associated with the S-VHS format of the videotapes, describes other issues associated with archiving process, and makes recommendations for future archiving of videotapes. Please note that the attached presentation has not been cleared by San Onofre for public release. | 2019 | Complete | Spent Nuclear Fuel Inspection Video Data Capture at SONGS | Pavlo Ivanusa | Steve Maheras | None | SNF Inspection Video Data Capture_without videos_201908150837_signed.pdf |  | Shutdown sites, knowledge management, videotapes, San Onofre
M4SF-19SR020201024 | M4 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Initial Test Plan for Phase 1 Testing | Initial Test Plan for Phase 1 Testing | initial Test Plan | 2018-10-31 |  | 2018-10-31 |  | 2019 | Complete | Canister Acceptance Testing Following Transportation - Plase 1 Test Plan | Melton, Douglas | Melton, Douglas | None | M4SF-18SR020201024 - Appendix E Cover Sheet.pdf M4SF-18SR020201024 - Canister Acceptance Testing Following Transportaton - Phase 1 Test Plan.pdf |  | Test Plan
M4SF-19SR020402081 | M4 | 1.08.02.04.02.08 | SRNL | SF-19SR02040208 | System Architecture Analysis - SRNL | Carter, Joe | Howard, Rob | Review draft TSAR and GDR for cost info | Documentation (e-mail) of task completion | Review draft TSAR and GDR for cost info and other data that should be added to UDB and produce inputs in a format provided by ORNL staff- | 2018-10-15 |  | 2018-10-15 |  | 2019 | Complete | Cost Estimates for an Unbackfilled, Open Repository in Shale Geologic Medium | Severynse, Tom | Severynse, Tom | None | M4SF-19SR020402081 - Cost Estimates for Unbackfilled.pdf M4SF-19SR020402081 - Reference Concept Cost Basis.pdf M4SF-19SR020402081 -Appendix E Cover Sheet.pdf |  | Cost Estimate
M4SF-19SR020405025 | M4 | 1.08.02.04.05.02 | SRNL | SF-19SR02040502 | Commercial SNF Characterization - SRNL | Carter, Joe | Howard, Rob | Data Needs and Assessment update | Inventory Update for UDB | Update the Commercial SNF and Government materials requiring disposition for incorpation in the UDB based on Rev 6 of the Inventory Report. | 2019-06-14 |  | 2019-06-12 | Excel file contains Inventory Report Rev 6 data for incorporation into the UDB. | 2019 | Complete | ORNL Projection (St_Dev-6.11.19).GCOutput | Joe Carter | Joe Carter | None | ORNL Projection (St_Dev-6.11.19).GCOutput.xls |  | Commercial SNF Data
M5SF-19AN0204020210 | M5 | 1.08.02.04.02.06 | ORNL | SF-19OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | None | NGSAM Verfication Plan | NGSAM Verification Plan | High level plan with test cases from system analysts. | 2019-05-31 |  | 2019-05-31 | Completed the NGSAM Verification Plan (M5SF-19AN0204020210). On May 31, distributed this milestone report to the IWM NTD (Mark Nutt), Deputy NTD (Rob Howard), and System Architecture System Analyst work package manager (Robby Joseph)for their review and feedback. | 2019 | Complete | Next-Generation System Analysis Model (NGSAM) 2019 Verification Plan | James St. Aubin | James St. Aubin | None | SFWD IWM M5FT NGSAM Verification Plan - 31-May-2019.pdf |  | NGSAM, V&V, verification
M5SF-19ID020404032 | M5 | 1.08.02.03.03.02 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | None | Progress Report on Knowledge Capture and Preservation | Progress Report on Knowledge Capture and Preservation | Write a report that describes the work accomplished since June 1, 2018. The document should include the information captured, the research methods used, and suggest potential next steps and any difficulties encountered in the research. | 2019-02-28 |  | 2019-02-02 | Milestone completed on 2/2/2019. | 2019 | Complete | KNOWLEDGE CAPTURE AND PRESERVATION PROJECT DRAFT PROGRESS REPORT – DECEMBER 2018 | Rodman, Lauren | North Wind | None | Knowledge Capture - Final Report Outline 11.28.18.docx
M5SF-19IN020409014 | M5 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | None | Literature review of past neutrons absorbers | Literature review of past neutrons absorbers | Literature review of past reports related to selection of neutrons absorbers for the standardized canister. | 2018-11-30 |  | 2018-11-30 02:00 | Completion of deliverable M5SF-19IN020409014 entitled “Literature Review of Past Neutron Absorbers.” | 2019 | Complete | Neutron Absorber Considerations for the DOE Standardized Canister | Petersen, Gordon | Petersen, Gordon | None | Neutron Absorber Considerations for the DOE Standardized Canister_Final.pdf
M5SF-19OR020303024 | M5 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | None | DRAFT Security Services for Atlas Railcar Demonstration Run | DRAFT Security Services for Atlas Railcar Demonstration Run | Prepare draft security services plan for the Atlas railcar consist demonstration run. | 2019-04-26 |  | 2019-04-26 | M5 draft milestone report on security services for Atlas railcar demonstration run. | 2019 | Complete | DRAFT Security Services for Atlas Railcar Demonstration Run | William J. Reich | Matthew R. Feldman | None | M5SF-19OR020303024-Apr 26 2019-R1-signed.pdf |  | Atlas Railcar, Security, Demonstration Run
M5SF-19PN0203020413 | M5 | 1.08.02.04.01.01 | ORNL | SF-19OR02040101 | Project Management - ORNL | Howard, Rob | None | Cultural Resource Summary Table (11.3) | Cultural Resource Summary Table | Create a summary management table identifying Cultural Resource concerns. | 2019-05-31 |  | 2019-05-30 | This document presents the methods used to summarize, rank, and identify cultural resource related data needs that are described in the “Cultural Resources Summary and Data Gathering Needs” Microsoft Excel spreadsheet (also attached), for sixteen shutdown nuclear power plant sites and nine nuclear power plant sites that have announced the intent to shutdown at the time this summary was prepared (collectively referred to as the “Sites”). The purpose of these documents is to support the U.S. Department of Energy Office of Nuclear Energy (DOE-NE) Integrated Waste Management Program, future transportation planning and environmental compliance activities by providing DOE-NE and American Indian stakeholders with a summary of cultural resource-related information, a list of cultural resource-related data gaps, and a list of corresponding cultural resource-related information needs for each Site. In addition, the Sites are ranked as having a high, moderate, or low need for additional cultural resources information such that DOE-NE and American Indian stakeholders can readily understand which of the Sites may require more time and effort to adequately consider cultural resources during planning activities, particularly if there is a federal and/or state permitting nexus that requires cultural resources and stakeholder consultation be addressed prior to any on-site alterations necessary to support future transportation needs. | 2019 | Complete | Cultural Resource Data Needs at Shutdown and Announced Shutdown Sites | Steve Maheras | Steve Maheras | None | M5SF-19PN0203020413_signed.pdf |  | shutdown sites, announced shutdown sites, cultural resources
M2SF-19AN020402013 Draft report shows M2SF-19OR020402061 Per Matt Brainard: Integrated Waste Management Facility Configuration Evaluation, originally planned for FY19 completion on 2/28/2019. Superseded by FY19 milestone M2SF-19AN020402013 - Integrated Waste Management Facility Configuration Evaluation, attached. Note that the ORNL M2 Deliverable (M2SF-19OR020402061) appears to be satisfying the ANL M2 Milestone (M2SF-19AN020402013). | M2 | 1.08.02.04.02.01 | ANL | SF-19AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | Integrated Waste Management Facility Configuration Evaluation | Integrated Waste Management Facility Configuration Evaluation Report | Integrated Waste Management Facility Configuration Evaluation Report | 2019-02-28 |  | 2019-02-28 | Led by ANL, this report was delivered on time and is a result of a very collaborative effort of multiple labs and contractors. | 2019 | Complete | Integrated Waste Management Facility Configuration Evaluation Report | Saraeva, Natalia | Saraeva, Natalia | None | M2SF-19OR020402061-WM Facility Configuration Systems Operations Evaluations-final draft.pdf |  | system analysis, integrated waste management system
M3SF-19AN020402012 Supersedes M3SF-18AN020402013. | M3 | 1.08.02.04.02.01 | ANL | SF-19AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | ESA Input to Facility Configuration Analysis | ESA Development Report | Draft chapters describing the ESA model and analysis for input to the Facility Configuration Analysis | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | ESA Input to Facility Configuration Analysis | Natalia Saraeva, | Natalia Saraeva | None | M3SF-19AN020402012 ESA Input to Facility Configuration -final.pdf |  | spent nuclear fuel, system analysis
M3SF-19AN020402023 Supersedes M3SF-18AN020402025. | M3 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | NGSAM Current and Future Capabilities | NGSAM FY2018 Status Report | Report of NGSAM-related accomplishments and activities supported by numerous DOE labs | 2019-01-31 |  | 2019-01-31 02:00 |  | 2019 | Complete | FY2019 Next-Generation System Analysis Model (NGSAM) Current and Future Capabilities | James St. Aubin | James St. Aubin | None | SFWD IWM M3FT FY2019 NGSAM Current and Future Capabilites Report - 2Two 31-Jan-2019.pdf |  | NGSAM, Capabilities, operational, functional
M3SF-19OR0203020310 Supersedes M3SF-18OR0203020411 | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report | Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report | Report on analysis of various options for acceptance queues from pick-up of spent nuclear fuel from commercial nuclear power plants. | 2019-02-22 |  | 2019-02-22 | The main thrust of this project has been the analysis of various options for acceptance queues for pick-up of spent nuclear fuel from commercial nuclear power plants. The report uses the recently acquired transportation cost data to look at overall system costs for various methodologies for determining the order in which SNF is picked up from all commercial reactor sites (macro queue). The report also details options for removal order of SNF specifically from currently shutdown sites (micro queue). | 2019 | Complete | Commercial Nuclear Power Plant De-Inventory Queue Analysis Draft Report | Matt Feldman | Matt Feldman | None | M3SF-19OR0203020310-Transportation Queue Draft Study_final_signed.pdf |  | Transportation, Queue, De-Inventory
M3SF-19OR020405014 Supersedes M3SF-18OR020405015. | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS thermal report | Update UNF-ST&DARDS thermal report | The deliverable includes development of new thermal model(s)(storage, transfer), and integration of new thermal model(s) into UNF-ST&DARDS. Under this deliverable, any PNNL developed thermal models will also be incorporated into UNF-ST&DARDS. Canister surface temperature will be included as a parameter of interest with peak cladding temperature, and cask surface temperature. | 2019-05-31 |  |  | On Schedule | 2019 | On Schedule |  |  |  | None
M3SF-19OR020405015. Supersedes M3SF-18OR020405016. | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | validation of UNF-ST&DARDS as-loaded analysis methodology | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | 2019-02-28 |  | 2019-02-28 | This report provides a summary of work performed in the first phase of the effort to enable detailed modeling using the Used Nuclear Fuel – Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). | 2019 | Complete | Phase I Validation of As-Loaded Calculations Using Detailed Fuel and Operational Data with UNF-ST&DARDS | Justin Clarity | Kaushik Banerjee | None | PB1900249_Clarity_ValidAsLoad_TO_PM_II_FINAL_PDmarkingsremoved.pdf
M3SF-19OR020405016 Supersedes M3SF-18OR020405017. | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS shielding report | UNF-ST&DARDS shielding analysis capability | The deliverable includes development of new shielding model(s) (transport), and integration of new shielding model(s) into UNF-ST&DARDS. Under this deliverable, on-the-fly dose analysis methodology may be integrated into UNF-ST&DARDS if Shift Monte Carlo code is ready with complete hybrid variance reduction capability. | 2019-06-28 |  |  | On Schedule | 2019 | On Schedule |  |  |  | None
M4SF-19OR020302039 | M4 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Incident-Case Dose Factors Methodology Development Report | Transportation Incident-Case Dose Factors Methodology Development Report | Initial report on development of methodology for incident-case dose factors for SNF transport that could be integrated into the START tool. | 2019-02-08 |  | 2019-02-08 | This report presents an initial investigation into the development of a methodology for the evaluation of radiation dose from hypothetical transportation incidents involving spent nuclear fuel (SNF). It describes the need for such a method and documents a series of transportation incident scenarios for which dose evaluation may be necessary or expected in advance of future transportation campaigns for SNF. | 2019 | Complete | Spent Nuclear Fuel Transportation Incident Dose Evaluation Methodology: Initial Investigation | Kevin Connolly | Matt Feldman | None | M4SF-OR020302039-Transportation Incident-Case Dose Factors_Final.pdf |  | Transportation, Accident, Incident, Dose Factors
M4SF-19OR020303022 | M4 | 1.08.02.03.03.02 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Interface Control Document | Atlas Railcar Interface Control Document | The Interface Control Document identifies, manages and controls the transportation system interactions between the railcar transportation equipment and external activities including vendor-supplied SNF transportation casks and cradles. | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | Atlas High-Level Radioactive Material Transportation Railcar and Spent Fuel Cask Interface Control Document | Bill Reich, | Matthew Feldman | None | M4SF-19OR020303022-Interface Control Document-Jan 31 2019-FINAL.docx M4SF-19OR020303022-Interface Control Document-Jan 31 2019-FINAL.pdf |  | Atlas, Railcar, Interface Control
M4SF-19PN020302044 | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | COBRA-SFS Code Modernization | Update of COBRA-SFS. | Modernize COBRA-SFS. | 2019-01-25 |  | 2019-01-25 09:00 |  | 2019 | Complete | COBRA-SFS: A Thermal-Hydraulic Analysis Code for Spent Fuel Storage and Transportation Casks | Steve Maheras | Steve Maheras | None | M4SF-19PN020302044_COBRA-SFS_V5.0_Users_Manual_Final_Signed.pdf |  | COBRA-SFS, UNF-ST&DARDS, thermal analysis, dry storage system, transportation cask, transfer cask
M5SF-19OR020401014 | M5 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | None | Initial Information Security Assessment Report | Assessment of Information Security Considerations for Use of UNF-ST&DARDS by NRC-Regulated Users: | Provide assessment results and recommendations based on Case 1 (assumes use of UNF-ST&DARDS Version 4.0). | 2019-01-31 |  | 2019-01-31 |  | 2019 | Complete | Initial Information Security Assessment for use of UNF-ST&DARDS by NRC-Regulated Users | William Reich |  | None | M5SF-19OR020401014-Initial Information Security Assessment Report-Jan 31 2019-R3 (002).docx |  | Information Security
M5SF-19OR020408012 | M5 | 1.08.02.04.03.02 | SNL | SF-19SN02040302 | Standardization and Integration - SNL | Hardin, Ernest | None | Finalize design of the MERF versatile remediation arm | MERF versatile arm design | This activity will push the MERF versatile remediation module design forward. The final design will include drawings, equipment specs, motors, adaptors, etc. in adequate detail to allow for construction and testing. | 2019-05-31 |  | 2019-05-31 | The purpose of this report is to describe the Versatile Remediation Module (VRM) main design features and component specifications. Once developed, this module will be used to promote development and demonstration of commercial remediation tools using ASME-qualified procedures to the extent practical. Before use to possibly remediate a DPC, all equipment must undergo rigorous testing in an environment that is as close to realistic as possible. | 2019 | Complete | Versatile Remediation Module Design and Specifications | Chatzidakis | Scaglione | None | Chatzidakis_M5SF-19OR020408012_Versatile Remediation Module_v1_20190531.pdf |  | Remediation, Mitigation
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | M3 Milestone report for the design concept for canister inspection and remediation facility at an ISF | 2019-08-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 | 1.08.02.02.01.02 | SRNL | SF-19SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | M3 Milestone report for the design concept for canister inspection and remediation facility at an ISF | 2019-08-30 |  |  |  | 2019 | On Schedule |  |  |  | None
M2SF-19SR020201022- Superseded by M2SF-20SR020201022 | M2 |  | SRNL | [7 empty] | due 11/30/2019 |  |  |  | 2019 |  |  |  |  | M2SF-18SR020201023 - Canister Inspection and Remediation Facility – Report, Originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M2SF-19SR020201022 - Canister Inspection and Remediation Facility – Report, which isn’t due until FY20 on 11/30/2019. No Deliverable to provide as of yet.
M3SF-19AN020402027 | M3 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | NGSAM 2019 Verification Report | NGSAM Verification Report | Report of NGSAM-related accomplishments and activities supported by numerous DOE labs | 2019-09-27 |  | 2019-09-27 | Completed and distributed the NGSAM 2019 Verification Report to IWM management and system analyst. | 2019 | Complete | Next-Generation System Analysis Model (NGSAM) FY2019 Verification Report | Jim St. Aubin, Brian Craig, Lucas Vander Wal | Jim St. Aubin | None | SFWD IWM M3FT NGSAM Verification Report - 2019-SEP-27.pdf |  | NGSAM, V&V, verification
M3SF-19AN020402029 | M3 | 1.08.02.04.02.02 | ANL | SF-19AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | NGSAM Methods Manual | NGSAM Methods Manual | Describe NGSAM functionalities and capabilities of the software under development and maintenance | 2019-09-06 |  | 2019-09-06 | This report, for the Department of Energy (DOE) Spent Fuel and Waste Disposition (SFWD), Office of Integrated Waste Management (IWM), provides users (IWM system analysts and decision makers) with detailed methods logic for the Next-Generation System Analysis Model (NGSAM) tool. This NGSAM Methods Manual supports the ongoing DOE-NE verification and validation (V&V) directives. Method details provided in this initial report pertain to NGSAM 2.3.6.0 tool that was released on June 21, 2019. Annual revisions to this report will be completed as new or revised methods are added to each new NGSAM release. | 2019 | Complete | Next-Generation System Analysis Model (NGSAM) Methods Manual | Chuck Olson, Lucas Vander Wal, Evan VanderZee, Brian Craig, Kathy Lee Simunich and Jim St. Aubin | Jim St. Aubin | None | SFWD IWM M3FT NGSAM Methods Manual - Final 2019-Sep-06.docx |  | NGSAM system analysts, methods
M3SF-19OR020302035 Per Matt Brainard: Supersedes M3SF-18ORD20302045. Due 8/23/2019 in the FY 19 follow-on work package. | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #7 | Site Specific De-Inventory Report #7 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-08-23 |  | 2019-08-21 | The M3SF-19OR020302035 deliverable, a report titled "Initial Site-Specific De-Inventory Report for Crystal River" was prepared by Orano Federal Services LLC under subcontract to ORNL. It provides an investigation of the organizations and operations necessary to remove all spent nuclear fuel (SNF) and greater than Class C low level radioactive waste (GTCC) from the shutdown Crystal River nuclear power plant site. It begins by describing the site characteristics, including the material to be shipped and the near-site transportation infrastructure. It then describes many potential transportation scenario options for removing the SNF and GTCC and uses a multi-attribute utility analysis (MUA) to determine the contractor’s preferred transportation scenario (modes and route) for delivering all of the site’s SNF and GTCC to a railroad. A concept of operations is described for the preferred scenario, along with a discussion on security planning, a budget, and a schedule. It should be noted that the MUA only includes attributes strictly related to logistics and should not be considered a final decision by DOE on such SNF will be removed. | 2019 | Complete | Initial Site-Specific De-Inventory Report for Crystal River, Rev 0 | Orano, LLC | Matt Feldman | None | Initial Site-Specific De-Inventory Report for Crystal River_Rev0_signed.pdf |  | Crystal River, campaign, transportation, logisitcs, shutdown site, MUA
M3SF-19OR0203020352 | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Incident Knowledge Base Rev. 0 | Transportation Incident Knowledge Base Rev. 0 Report | Report detailing development of Transportation Incident Knowledge Base Rev. 0. | 2019-08-30 |  | 2019-08-30 | Level 3 milestone M3SF-19OR0203020352, “Transportation Incident Knowledge Base Rev. 0,” (work package SF-19OR02030203, Transportation: Operational – ORNL, WBS #1.08.02.03.02) was completed and submitted on time. The deliverable is a report entitled “A Radioactive Material Transportation Incident Knowledge Base.” This report documents the search for incidents involving radioactive materials, including SNF and HLW, during shipments. This work included searching US Department of Transportation records for radioactive materials incidents since the discontinuation of a past radioactive materials transportation incident database in 2004. In addition, it includes photographs of a historical transportation accident provided by a stakeholder from North Dakota who responded to the accident and subsequent cleanup; he has given us permission to share them. | 2019 | Complete | A Radioactive Material Transportation Incident Knowledge Base | Kevin Connolly | Matt Feldman | None | M3SF-19OR0203020352_Transportation Incident Knowledge Base Rev 0.pdf |  | transportation, risk assessment, history, statistics, shipments, SNF, HLW
M3SF-19OR020302036 Per Matt Brainard: Supersedes M3SF-18OR020302046. Due 8/23/2019 in the FY19 follow-on work package. | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #8 | Site Specific De-Inventory Report #8 | Report detailing the logistics and costs and schedule of full de-inventory of a shutdown commercial nuclear power plant. | 2019-03-31 | 2019-07-19 | 2019-08-23 | The deliverable, a report titled "Initial Site-Specific De-Inventory Report for Rancho Seco" was prepared by Orano Federal Services LLC under subcontract to ORNL. It provides an investigation of the organizations and operations necessary to remove all spent nuclear fuel (SNF) and greater than Class C low level radioactive waste (GTCC) from the shutdown Rancho Seco nuclear power plant site. It begins by describing the site characteristics, including the material to be shipped and the near-site transportation infrastructure. It then describes many potential transportation scenario options for removing the SNF and GTCC and uses a multi-attribute utility analysis (MUA) to determine the contractor’s preferred transportation scenario (modes and route) for delivering all of the site’s SNF and GTCC to a railroad. A concept of operations is described for the preferred scenario, along with a discussion on security planning, a budget, and a schedule. It should be noted that the MUA only includes attributes strictly related to logistics and should not be considered a final decision by DOE on such SNF will be removed. | 2019 | Complete | Initial Site-Specific De-Inventory Report for Rancho Seco Rev 0 | Orano Federal Services, LLC | Matt Feldman | None | Initial Site-Specific De-Inventory Report for Rancho Seco_Rev0_signed.pdf |  | Rancho Seco, campaign, transportation, logisitcs, shutdown site, MUA
M3SF-19OR0203020361 | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Incident Dose Prediction Methodology Report | Transportation Incident Dose Prediction Methodology Report | Report on the development and implementation of a methodology for incident-case dose factors. | 2019-06-28 |  | 2019-06-28 | Level 3 milestone M3SF-19OR0203020361, “Transportation Incident Dose Prediction Methodology Report,” (work package SF-19OR02030203, Transportation: Operational – ORNL, WBS #1.08.02.03.02) was completed. The deliverable is a report entitled “Spent Nuclear Fuel Transportation Incident Dose Evaluation Methodology: Sample Calculations.” This report presents sample calculations for the evaluation of radiation dose from hypothetical transportation accidents involving SNF. It uses two established computational codes, Radiological Assessment System for Consequence Analysis (RASCAL) and HotSpot, to calculate radiation dose from a hypothetical accident in which radioactive material is released from a transportation cask during shipment. Both HotSpot and RASCAL were developed for rapid assessment of doses due to radiological emergencies. There are advantages and disadvantages associated with the use of both codes, and these were identified during this preliminary model comparison study. The radionuclide data for these calculations were provided by the Used Nuclear Fuel - Storage, Transportation & Disposal Analysis Resource and Data Systems (UNF-ST&DARDS) computational tool. | 2019 | Complete | Spent Nuclear Fuel Transportation Incident Dose Evaluation Methodology: Sample Calculations | Kevin Connolly | Matt Feldman | None | M3SF-19OR0203020361.pdf |  | transportation, dose, accident, RASCAL, HotSpot, UNF-ST&DARDS, operational, risk analysis
M3SF-19OR020402064 | M3 | 1.08.02.04.02.06 | ORNL | SF-19OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | FY19 System Analysis Report | FY19 System Architecture Report | Specific analyses planned for FY19 to be led out of this area include Standardized Canister Scenario Studies including examining the effects of timing for deployment, comparing costs relative to non-standardized approaches, and evaluating IWMS performance for such scenarios. | 2019-09-13 |  | 2019-09-13 | Completed the M3 milestone M3SF-19OR020402064, entitled “FY19 System Analysis Report” in the work package SF-19OR02040206, entitled “System Architecture Analysis - ORNL.” This document describes system analyses that was completed in the second half of FY19. | 2019 | Complete | FY19 System Analysis Report |  |  | None | PB1901063_Joseph_SAR_Rev2.pdf
M3SF-19OR020405019 | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | A report outlining a plan and requirements for a topical report supporting as-loaded analysis | A plan describing a topical report for as-loaded analysis | Report documenting the plan for a topical report supporting as-loaded analysis methodology | 2019-07-19 |  | 2019-07-19 | This document outlines the purpose and scope of a proposed topical report (TR) on as-loaded safety analysis methodology, identifies the NRC’s rationale for agreeing to review a TR, including the prioritization of the review, and the process for developing, submitting and supporting the NRC review of this TR including preliminary cost estimate. | 2019 | Complete | Requirements for a Topical Report on As-loaded Spent Nuclear Fuel Analysis Methodology | Brian Gutherman | Kaushik Banerjee | None | TopicalReportFramework_ver5.pdf
M4SF-19AN020402032 | M4 | 1.08.02.04.02.03 | ANL | SF-19AN02040203 | System Architecture Analysis - ANL | Saraeva, Natalia | Howard, Rob | Integrated systems status report | Integrated systems status report | This report will provide an update from related M2 report (currently under ESA) on integration of IWMS system analysis tools | 2019-09-27 |  | 2019-09-27 | status report | 2019 | Complete | Integrated System Analysis Status Report | Saraeva, Natalia | Saraeva, Natalia | None | M4SF-19AN020402032.pdf
M4SF-19IN020409013 | M4 | 1.08.02.04.09.01 | INL | SF-19IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Initial storage configuration alternative study | Initial storage configuration alternative study |  | 2019-09-30 |  | 2019-09-30 | Deliverable completed on time and delivered via email. | 2019 | Complete | Initial DOE SNF Standardized Canister Storage Configuration Alternatives Study | Daniel Thomas | Daniel Thomas | None | INL-19-55841_Initial-DOE-Canister-Storage-Study_Draft-rev0.pdf
M4SF-19OR0203020350 | M4 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | UNF ST&DARDS Transportation Cask Template Development Report | UNF ST&DARDS Transportation Cask Template Development Report | Provide a detailed report of the development of 3 Transportation Cask Templates for use with UNF ST&DARDS. | 2019-09-13 |  | 2019-09-13 | This report presents models developed for the Used Nuclear Fuel-Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS) shielding analyses of as-loaded transportation packages. New models were developed for four canisters: (1) Nuclear Horizontal Modular Storage 61BT dry shielded canister (NUHOMS® 61BT DSC), (2) multi-purpose canister (MPC)-37, (3) Holtec’s MPC 89, and (4) MPC-68M. New models were also developed for the transportation overpacks designated for these canisters—the NUHOMS® MP197 and the HI-STAR 190. | 2019 | Complete | FY 2019 UNF-ST&DARDS Transportation Cask Template Development Report | Georgeta Radulescu | Matt Feldman | None | M4SF-19OR0203020350.pdf |  | Transportation, cask, canister, MP197, Hi-Star 190
M4SF-19OR020303026 | M4 | 1.08.02.03.03.02 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Draft Atlas Railcar Project Annual Status Report | Draft Atlas Railcar Project Annual Status Report | Draft report on the project status of development of S-2043 compliant cask, buffer, and escort railcars. | 2019-08-16 |  | 2019-08-16 | This report describes progress made on the Atlas Railcar Project during fiscal year 2019. | 2019 | Complete | DRAFT Atlas Railcar Design Project Status Report for FY 2019 | Bill Reich | Matt Feldman | None | M4SF-19OR020303026-Draft Atlas Railcar Project Status Report-Aug 16 2019-R1.pdf |  | Atlas railcar
M4SF-19OR020408017 | M4 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | Howard, Rob | Mock-up canister design report attributes for use in future remediation demonstration activities | Design and construction of mock-up canister for remediation demonstration | This report wil document the design and capabilities of the mock-up caniser features, sensors and instrumentation to support future remediation technology demonstration activities. | 2019-07-31 |  | 2019-07-31 | This report describes the design and specifications of the Versatile Remediation Module (VRM) and Mock-up Canister for use in future remediation demonstration activities. Currently, the design and specifications of the VRM have been finalized and main components have been purchased and are being assembled. A control system architecture has been developed and main control components have been selected and a full-scale mock-up canister has been designed and is under fabrication. It is expected that testing of the VRM will begin as planned next September-October 2019. | 2019 | Complete | Versatile Remediation Module and Mock-up Canister Design and Specifications | Stylianos Chatzidakis | John Scaglione | None | M4SF-19OR020408017_Versatile Remediation Module and Mock-up Canister Design and Specifications.pdf |  | Remediation, MERF, mockup canister
M4SF-19PN0203020414 | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Reference Archive and Database (11.4) | Reference Archive and Database | Create a reference archive and reference database for environmental reviews. | 2019-09-30 |  | 2019-09-14 | Pacific Northwest National Laboratory (PNNL) staff created the Cultural Resources Reference Archive and Database to gather documents cited in a cultural resources summary document being completed for select nuclear power plant sites, which will be delivered as the M3 milestone M3SF-19PN0203020412. Staff entered reference documents into a Microsoft SharePoint library for access, retrieval, and storage. The database, together with a bibliography builder application developed by PNNL, provides the means to efficiently generate bibliographies for authors, allowing accuracy and consistency in citation development and providing time savings. The milestone consists of a report, a Microsoft EXCEL spreadsheet specifying database files and their metadata, and noncopyrighted copies of those files. The noncopyrighted files are being sent separately on a DVD. | 2019 | Complete | Cultural Resources Reference Archive and Database | Joanne Duncan | Steve Maheras | None | M4SF-19PN0203020414_signed.pdf |  | cultural resources, database, nuclear power plant sites
M4SF-19PN0203020415 | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Cultural Resource GIS Database (11.5) | Cultural Resource GIS Database | Create Cultural Resource database for shutdown sites. | 2019-09-30 |  | 2019-09-14 | This report summarizes development of Geographic Information System (GIS) datasets addressing 17 nuclear power plant (NPP) sites. The sites include: • Big Rock Point (Michigan) • Connecticut Yankee (Connecticut) • Crystal River (Florida) • Humboldt Bay (California) • Fort Calhoun (Nebraska) • Fort Saint Vrain (Colorado) • Indian Point (New York) • La Crosse (Wisconsin) • Maine Yankee (Maine) • Oyster Creek (New Jersey) • Pilgrim (Massachusetts) • Rancho Seco (California) • San Onofre (California) • Trojan (Oregon) • Vermont Yankee (Vermont) • Yankee Rowe (Massachusetts) • Zion (Illinois) GIS data on these sites have been assembled for various subjects of planning interest, including transportation infrastructure, cultural resources, sensitive ecological resources, environmental justice, Native American tribal resources, and site-specific features including property ownership and local heavy haul transportation resources, etc. The associated kmz files were submitted through PNNL’s file transfer utility. | 2019 | Complete | GIS Documentation for 17 Nuclear Power Plant Sites | Dave Anderson | Steve Maheras | None | M4SF-19PN0203020415_signed.pdf |  | GIS, nuclear power plant sites, kmz
M4SF-19PN0203020418 | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #1 | Thermal Template #1 | Develop thermal template #1. | 2019-08-30 |  | 2019-08-29 | This report describes the COBRA-SFS model developed for the Holtec International® HI-STAR-190 transportation cask housing a multi-purpose canister (MPC)-37 which will serve as the primary site-specific storage and transportation modeling template utilizing the UNF-ST&DARDS tool. The template provides the capability to model the thermal behavior of the HI-STAR 190 when subjected to transportation conditions. The Westinghouse 17 x 17 OFA fuel assembly is the prototypic fuel assembly in this model because it is thermally representative of most fuel designs the MPC-37 is expected to contain. The HI-STAR 190 transportation cask is capable of housing either the MPC-37 or MPC-89, however, separate templates must be constructed to model the separate configurations. | 2019 | Complete | COBRA-SFS Model of HI-STAR 190 MPC-37 for UNF-ST&DARDS | Brian Hom | Steve Maheras | None | M4SF-19PN0203020418_signed.pdf |  | thermal templates, HI-STAR 190, MPC-37, COBRA-SFS
M4SF-19PN0203020419 | M4 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #2 | Thermal Template #2 | Thermal template #2. | 2019-08-30 |  | 2019-08-29 | This report describes the COBRA-SFS model developed for the Holtec International® HI-STAR-190 transportation cask with the MPC-89 canister, which will serve as the primary site-specific transportation modeling template utilizing the UNF-ST&DARDS tool. The template provides the capability to model the thermal behavior of the HI-STAR 190 when subjected to transportation conditions. The GE 14 10x10 fuel assembly is the prototypical fuel assembly in this model as it is thermally representative of the fuel assemblies to be transported in this system. The HI-STAR 190 transportation cask is capable of housing either the MPC-37 or MPC-89, however, separate templates must be constructed to model the separate configurations. This template enables important analysis capabilities for sites at which HI-STAR 190 transportation casks are currently or expected to be in use. | 2019 | Complete | COBRA-SFS Model of the HI-STAR 190 MPC-89 for UNF-ST&DARDS | Brian Hom | Steve Maheras | None | M4SF-19PN0203020419_signed.pdf |  | thermal templates, HI-STAR 190, MPC-89, COBRA-SFS
M4SF-19SN020302062- OUO | M4 | 1.08.02.03.02.06 | SNL | SF-19SN02030206 | Transportation: Operational - SNL | Kalinina, Elena | Feldman, Matt | Transportation Sabotage Analysis Recommendations | Transportation Sabotage Analysis Recommendations | The Transportation Sabotage Analysis Recommendations report will document the review of the transportation sabotage analysis performed for the Yucca Mountain EIS and will contain recommendations on if there is a need to update the YM transportation sabotage analysis and if so a project plan (including costs), and also an unclassified summary of the review and recommendations will be provided for upload to PICSNE. | 2019-06-14 | 2019-11-18 |  | On schedule | 2019 | On Schedule |  |  |  | OUO
M4SF-19SN020402071 | M4 | 1.08.02.04.02.07 | SNL | SF-19SN02040207 | NGSAM Development and Application - SNL | Kalinina, Elena | Howard, Rob | V&V on JTOM and Transportation of NGSAM | NGSAM V&V Report | V&V on JTOM and Transportation of NGSAM | 2019-07-22 |  | 2019-07-22 | M4 deliverable | 2019 | Delayed | NGSAM Verification and Validation | Elena Kalinina | Elena Kalinina | None | NGSAM_V&V Final 07-22-19.pdf |  | Verification and validation, transportation, spent nuclear fuel, system analysis tool
M5SF-19PN0203020410 | M5 | 1.08.02.04.04.03 | DOE-ID | SF-19ID02040403 | Knowledge Capture and Preservation - DOE-ID (North Wind) | Helvey, Elizabeth | None | Environmental Reviews for Shutdown Sites (11.1) | Environmental Reviews for Shutdown Sites | Prepare summaries for additional resource areas such as EJ, eco/terrestrial/, ESA Section 7, hydrology, etc. to highlight potential issues. | 2019-09-30 |  | 2019-08-30 | This document presents information related to potential permitting requirements for dredging that may be needed to support possible barge transport of SNF from one nuclear power plant site, the Oyster Creek Nuclear Generating Station (OCNGS) located in New Jersey. This report does not recommend the design of a dredging project, nor does it imply that the utility, plant facility operator, or DOE has expressed the intention to pursue a particular permitting scenario. Rather, the report outlines the potential options for pursuing dredging permits should they be required in the future. The research methodology used is described in Section 2 and includes contacting the U.S. Army Corps of Engineers (USACE), New Jersey Department of Environmental Protection (NJDEP), and New Jersey Department of Transportation (NJDOT) regarding dredging permits and related authorizations and requirements. Additionally, a May 2019 site visit to OCNGS was conducted to assess on-site conditions. Information gathered during the site visit supplemented research efforts and was included in the analysis. Following Section 2 the report describes OCNGS and the surrounding water bodies (Section 3.1), as well as potential permitting scenarios based on applicant type (Section 3.2). Permits and authorizations from USACE, NJDEP, and NJDOT that would likely be needed to support dredging at OCNGS are listed and discussed in Section 3.3. This section includes an analysis of the potential permitting costs and timeframes for acquiring the necessary permits. The projected timeline for acquiring permits and authorizations is about one year. This timeframe is contingent upon input from permitting agencies during project planning as well as on the permit applicant’s provision of complete project design information, from initial hydrography through disposition of dredged materials, in permit application materials. | 2019 | Complete | Dredging Permit Requirements for the Oyster Creek Nuclear Power Plant Site | James Becker | Steve Maheras | None | M5SF-19PN0203020410_signed.pdf |  | Oyster Creek, dredging, barge, near-site transportation infrastructure
M5SF-19SN020403023 | M5 | 1.08.02.04.08.01 | ORNL | SF-19OR02040801 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites - ORNL | Scaglione, John | None | Technical Memo on Neutron Absorber Materials | Technical Memo on Neutron Absorber Materials for Multiple Disposal Environments | Produce a technical memo (M5 deliverable) documenting scoping activities to identify alternative absorber materials and engage vendors. | 2019-08-15 |  | 2019-08-15 | Discussed with the team on 8/12. Cover sheet to be uploaded separately when signed. | 2019 | Complete | Technical Memo on Neutron Absorber Materials | Hardin, Ernest | Hardin, Ernest | None | Neutron absorber lit search M5 deliverable final.pdf
M3SF-18AN020402013 Per Matt Brainard: ESA Input to Facility Configuration Analysis - Originally planned for FY19 completion on 1/31/2019. Superseded by FY19 milestone M3SF-19AN020402012 - ESA Input to Facility Configuration Analysis, completed on 1/31/2019. | M3 | 1.08.02.04.02.01 | ANL | SF-18AN02040201 | ESA Development and Application - ANL | Saraeva, Natalia | Howard, Rob | ESA Input to Facility Configuration Analysis | ESA Development Report | Draft chapters describing the ESA model and analysis for input to the Facility Configuration Analysis | 2019-01-31 |  | 2019-01-31 | ESA Input to Facility Configuration Analysis deliverable completed and submitted on time | 2019 | Complete | ESA Input to Facility Configuration Analysis | Natalia Saraeva, Ralph Stoll, ALan Keizur | Natalia Saraeva | None | M3SF-19AN020402012 ESA Input to Facility Configuration -final.pdf |  | spent nuclear fuel, system analysis
M3SF-19OR020405016 | M3 | 1.08.02.04.05 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS shielding report | UNF-ST&DARDS shielding analysis capability | This report presents the shielding models developed and implemented in UNF-ST&DARDS during fiscal year (FY) 2019. Models were developed for the NUHOMS® MP197 transportation system, which includes the NUHOMS® MP197 packaging and the NUHOMS® dry shielded canisters (DSCs) 61BT. The FY 2019 shielding model templates facilitate UNF-ST&DARDS dose rate analyses of transportation packages containing boiling water reactor spent nuclear fuel (SNF) currently stored in NUHOMS® horizontal modules at 7 independent spent fuel storage installations (ISFSIs), provided canister loading maps are available for those installations. | 2019-06-28 |  | 2019-06-28 | This report presents the shielding models developed and implemented in UNF-ST&DARDS during fiscal year (FY) 2019. | 2019 | Complete | UNF-ST&DARDS Shielding Model Development and Implementation for Fiscal Year 2019 | Georgeta Radulescu | Kaushik Banerjee | None | PB1900711_Radulescu_unf-Rev6.pdf
M3SF-19OR0203020354 | M3 | 1.08.02.03.02 | ORNL | SF-19OR02030203 | SF-19OR02030203 | Feldman, Matt | Feldman, Matt | Accelerated Transportation Study Report | Accelerated Transportation Report | Report | 2019-09-27 |  | 2019-09-27 | This report evaluates methodologies for accelerating the development of a large-scale transportation system to move spent nuclear fuel (SNF) from commercial nuclear reactor sites to an as-yet undefined destination. | 2019 | Complete | Methodologies for Accelerating the Development of a Transportation System | Feldman, Matt | Feldman, Matt | None | M3SF-19OR0203020354_R0_Final.pdf |  | Transportation, accelerated, Spent Nuclear Fuel, SNF Transport
M3SF-19OR020201012 | M3 | 1.08.02.02.01 | ORNL | SF-19OR02020101 | IWM Facilities Concepts - ORNL | Bevard, Bruce | Carter, Joe | Identify data needs and experimental approaches to support handling SNF in air | Experiments and testing necessary to support efficient canister handling and fuel handling operations | Document describes some of the work previously done to understand the effects of SNF in air at temperature; describes existing gaps in knowledge for having fuel in air for long duration; outlines an experimental test plan to close these gaps. | 2019-09-30 |  | 2019-10-01 | The document was provided to SRNL for review and comment. It outlines the gaps in knowledge concerning SNF in air (at temperature) and proposed testing to close those gaps | 2019 | Complete | Oxidation of Spent Fuel During Fuel Handling Accidents Test Plan | Dr Jason Harp | Bruce Bevard | None | Oxidation of Spent Fuel During Fuel Handling Accidents Test Plan.pdf |  | fuel in air; SNF; oxidation of fuel
M3SF-19PN0203020412 | M3 | 1.08.02.03.02 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Continue Cultural Resource Reviews (11.2) | Final Report on Cultural Resource Reviews | Report | 2019-09-30 |  | 2019-09-23 | This report presents cultural resources-related information for 25 nuclear power plant sites (NPP) sites and identifies American Indian tribes that may have historical, cultural and/or geographical ties to those sites or that may be potentially impacted by future transportation activities. The report includes a section for each of the 25 NPPs, each of which describes the NPP location, when it began and ceased operations, and the status of the decommissioning process. American Indian tribes that may have historic and cultural and/or geographic ties to the NPP are also identified, as is their engagement on any established community engagement panels or citizen’s advisory boards associated with decommissioning activities. For each NPP, five key cultural resources related data points are summarized: (1) cultural resources field work completed before and after construction, (2) any cultural resources identified, (3) indication of whether a cultural resources protection plan is, or has been, in place, (4) a summary of prior consultation and/or engagement with the SHPO and American Indian tribes, and (5) an overview of any cultural resources issues or concerns that emerged as a result of those interactions. Finally, relevant cultural resources information retrieved from each of the documents identified by the online literature review is presented. | 2019 | Compete | Cultural Resource Summaries for Twenty-Five Nuclear Power Plant Sites | Ellen Kennedy | Steve Maheras | None | M3SF-19PN0203020412_signed.pdf |  | cultural resources, nuclear power plant sites, American Indian tribes
M3SF-19OR020303027 | M3 | 1.08.02.03.03 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Project Annual Status Report | Final Atlas Railcar Project Annual Status Report | This annual status report for FY 2019 documents the completion of the first Atlas railcar contract for the design, associated analysis, and prototype fabrication of railcars to transport SNF and HLW. This railcar design contract included Phase 1—Mobilization and Conceptual Design, Phase 2—Preliminary Design, and Phase 3—Prototype Fabrication and Delivery. This report goes on to describe the second Atlas railcar contract, which includes Phase 4—Single-Car Testing, and Phase 5—Multiple-Car Testing. | 2019-09-30 |  | 2019-09-25 | Report was completed on schedule. | 2019 | Complete | Atlas Railcar Design Project Status Report for FY2019 | Bill Reich | Matt Feldman | None | M3SF-19OR020303027-Atlas Railcar Project Status Report-Sept 30 2019-FINAL.pdf |  | Atlas railcars
M3SF-19OR0204050158 | M3 | 1.08.02.04.05 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Revision of Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology | validation of UNF-ST&DARDS as-loaded analysis methodology | This report summarizes the work performed to enable detailed modeling using the Used Nuclear Fuel – Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). The ultimate goal of this project is to be able to validate and determine the level of conservatism in the current modeling methods and assumptions in the as-loaded safety analysis methodology using detailed operational data from a small number of sites. This report describes the modeling methods currently used within UNF-ST&DARDS and the justification for those methods. Discussion is also provided regarding the plants from which detailed operational data are available. The types of calculations are outlined for boiling water reactor (BWR) and pressurized water reactor (PWR) fuel, and initial calculations are presented for a limited number of fuel assemblies. A Limited detailed data from Swedish PWRs and BWRs is also included in this as-loaded analysis methodology validation effort. | 2019-09-30 |  | 2019-09-30 | This report summarizes the work performed to enable detailed modeling using the Used Nuclear Fuel – Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). | 2019 | Complete | Validation of As-Loaded Calculations Using Detailed Fuel and Operational Data with UNF-ST&DARDS | Justin Clarity | Kaushik Banerjee | None | PB1901182_Clarity_ValidAsLoad_Final.pdf |  | UNF-ST&DARDS, as-loaded analysis, validation
M4SF-19PN020301022 | M4 | 1.08.02.03.01 | PNNL | SF-19PN02030102 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Reciprocal Rail Inspection Protocol Annotated Outline | Annotated Outline for Draft Rail Inspection Protocol | report | 2019-05-22 |  | 2019-05-22 | This outline is the first step in the development of a rail safety inspection protocol that allows for communicating inspection results to other states along a transportation corridor, decreasing the number or level of detail for inspections at State borders and setting up the opportunity for inspection reciprocity. | 2019 | Complete | Reciprocal Rail Safety Inspection Protocol Annotated Outline | Steve Maheras | Steve Maheras | None | M4SF-19PN020301022 Annotated Outline_2019-05-23_signed.pdf |  | Rail inspection, protocol
M4SF-19OR030102062 | M4 | 1.08.03.01.02 | ORNL | SF-19OR03010206 | Quality Assurance - ORNL | Vance, Mark | Brainard, Matt | ORNL SFWD QA POC Surveillance | FY2019 Suveillance of the ORNL NTRD QA program | Entitled Assessment of the Quality Program for Activities Sponsored by the Department of Energy Office of Nuclear Energy’s Spent Fuel and Waste Disposition Program Conducted at the Oak Ridge National Laboratory,this report provides the results of an assessment of the implementation and effectiveness of the Oak Ridge National Laboratory (ORNL) quality assurance (QA) program as it applies to technical tasks described in research and development (R&D) work packages and associated milestone deliverables funded by the Department of Energy Office of Nuclear Energy’s (DOE-NE) Spent Fuel and Waste Disposition (SFWD) Program conducted at the Oak Ridge National Laboratory | 2019-05-30 |  | 2019-05-30 | This report provides the results of an assessment of the implementation and effectiveness of the Oak Ridge National Laboratory (ORNL) quality assurance (QA) program as it applies to technical tasks described in research and development (R&D) work packages and associated milestone deliverables funded by the Department of Energy Office of Nuclear Energy’s (DOENE) Spent Fuel and Waste Disposition (SFWD) Program conducted at the Oak Ridge National Laboratory. | 2019 | Complete | Assessment of the Quality Program for Activities Sponsored by the Department of Energy Office of Nuclear Energy’s Spent Fuel and Waste Disposition Program Conducted at the Oak Ridge National Laboratory | Mark C. Vance | Mark C. Vance | None | SF&WDAssessmentReportMayl2019Final.pdf |  | Quality assurance, assessment
M4SF-19IN020402054 | M4 | 1.08.02.04.02 | INL | SF-19IN02040205 | System Architecture Analysis - INL | Jarrell, Josh | Howard, Rob | Provide NGSAM Updates to Software Developers | Provide NGSAM Updates to Software Developers | This report proposes updates to software developers at Argonne National Lab (ANL) for the Next-Generation System Analysis Model (NGSAM) tool. This is part of a broader proposal which verifies the NGSAM tool’s ability to model different options and allocation strategies for spent nuclear fuel (SNF) at Department of Energy (DOE) owned facilities. This document builds on the previous document Waste Management System Analysis Simulation Tool Requirements which describes NGSAM tool requirements. NGSAM currently provides limited capabilities for DOE SNF. This document requests a number of capabilities be added to more adequately model DOE SNF and identifies different scenarios for testing the capabilities of DOE SNF utilizing NGSAM. The scenarios are prioritized in two different tiers. The first tier is necessary to perform NGSAM system analysis for DOE-owned SNF. The second tier is necessary to analyze more in-depth system strategies that involve commercial fuel or degradation of existing facilities. | 2019-06-10 |  | 2019-06-10 | Deliverable completed on time | 2019 | Complete | Proposed NGSAM Updates for Expansion of DOE-Owned SNF Capabilities | Gordon Petersen | Gordon Petersen | None | NGSAM Updates for Expansion of DOE-Owned SNF_Final[1].pdf
M4SF-19OR020402066 | M4 | 1.08.02.04.02 | ORNL | SF-19OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | Scenarios and Assumptions for FY19 System Analysis Report | Scenarios and Assumptions for the FY19 System Analysis Report |  | 2019-06-28 |  | 2019-06-26 | Completed the M4 milestone M4SF-19OR020402066, entitled “Scenarios and Assumptions for the FY19 System Analysis Report” in the work package SF-19OR02040206, entitled “System Architecture Analysis - ORNL.” This document describes various scenarios and key assumptions necessary to complete the planned FY19 system analysis. This M4 serves as input to the M3 due September 13, 2019 entitled ‘FY19 System Analysis Report,” which we are actively working on. | 2019 | Complete | Scenarios and Assumptions for the FY19 System Analysis Report |  |  |  | M4_Draft Scenarios and Assumptions_Final.docx
M4SF-19OR020402065 | M4 | 1.08.02.04.02 | ORNL | SF-19OR02040206 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | System Architecture Data Report | System Architecture Data Report |  | 2019-08-30 |  | 2019-08-30 | Completed M4 milestone entitled 'Systems Architecture Data Report.' The purpose of this document is to provide documentation of the underlying assumptions made for Integrated Waste Management (IWM) systems analysis work in fiscal year 2019. This document describes the relevant data inputs for a typical NGSAM analysis. It builds upon appendices in the IWM Facility Configuration Systems Operations Evaluations published early in 2019. | 2019 | Complete | An Overview of Data Supporting Integrated Waste Management System Architecture Analysis |  |  | None | DataManual 20190830.pdf
M4SF-19IN020402055 | M4 | 1.08.02.04.02 | INL | SF-19IN02040205 | System Architecture Analysis - INL | Jarrell, Josh | Howard, Rob | Data Collection: SNF/HLW, Storage & Packaging, Legal/ROD/EIS Requirements, Facility Throughput | Data Collection: SNF/HLW, Storage & Packaging, Legal/ROD/EIS Requirements, Facility Throughput | This email serves as completion of the deliverable M4SF-19IN020402055 to collect Department of Energy (DOE) spent nuclear fuel (SNF), DOE high-level waste (HLW), and DOE facility data. It focuses on Hanford, Savannah River Site (SRS), Idaho National Laboratory (INL), Fort St. Vrain, and West Valley. It also generally describes SNF from non-DOE domestic and foreign research reactors. Existing and future canister capacity and throughputs are documented for the different sites. The legal requirements and records of decisions are also documented. The data will be used to analyze the SNF management system using the Next-Generation System Analysis Model (NGSAM). This is part of a broader proposal, which verifies the NGSAM tool’s ability to model different options and allocation strategies for SNF at DOE-owned facilities. Because the Appendix is OUO, the full appendix is not attached. The Appendix contains the SNF descriptions, facility data, canister/container data, and a current configuration of DOE SNF storage at the various sites. | 2019-09-23 |  | 2019-09-23 | Deliverable completed on time via email | 2019 | Complete | Documenting Data and Assumptions for DOE SNF and HLW | Gordon Petersen | Gordon Petersen | None | INL-EXT-19-55527_Documenting-Data-Assumptions-DOE-SNF-and-HLW_Draft-Rev0.pdf
M4SF-19PN020301023 | M4 | 1.08.02.03.01 | PNNL | SF-19PN02030102 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Draft Reciprocal Rail Inspection Protocol | Draft Reciprocal Rail Inspection Protocol | presentation | 2019-09-27 |  | 2019-09-23 | This deliverable consists of a presentation given at the August 21, 2019 Transportation Core Group meeting that describes the objectives of developing a reciprocal railcar safety inspection protocol; the existing railcar inspection regime; past efforts to develop an inspection protocol; Association of American Railroad (AAR) Standard S-2043 monitored parameters; provides a simplified concept of operations, destination site activities, and origin site activities; documentation of inspections; and provides an overview of near-term next steps in the development of the protocol. The primary emphasis of Intergovernmental and External Engagement activities is on the revised Federal Railroad Administration Safety Compliance Oversight Plan; continued work on the protocol will take place after the development of the revised Safety Compliance Oversight Plan. | 2019 | Complete | Development of a Proposed Reciprocal Railcar Safety Inspection Protocol | Steve Maheras | Steve Maheras | None | M4SF-19PN020301023_signed.pdf |  | railcar inspection, protocol, S-2043
M4SF-19OR020301012 | M4 | 1.08.02.03.01 | ORNL | SF-19OR02030101 | Intergovernmental and External Engagement - ORNL | Feldman, Matt | Feldman, Matt | Core Group Meeting | Core Group Meeting | Email | 2019-09-30 |  | 2019-08-21 | A Transportation Core Group Meeting was held August 21, 2019 in Washington D.C. The Transportation Core Group includes key representatives from the State Regional Groups and the National Counsel of State Governments and their Tribal Radioactive Material Transportation Committee. This meeting focused on various transportation issues including current status of participants' respective committees, discussion of planned IWM activities for the year ahead, and rail inspection activities currently underway. | 2019 | Complete | Completion of Milestone M4SF-19OR020301012 Core Group Meeting | Matt Feldman | Matt Feldman | None | M4SF-19OR020301012 Core Group Meeting.pdf |  | Core Group, transportation, states, Tribes
M4SF-19PN020402111 | M4 | 1.08.02.04.02 | PNNL | SF-19PN02040211 | System Architecture Analysis - PNNL | Nutt, Mark | Howard, Rob | DCSS Demonstration Program Plan | WESF DCSS Demonstration Program Plan | This technical report describes a unique opportunity for the U.S. Department of Energy (DOE) to partner with CH2M Hill Plateau Remediation Company (CHPRC) on the Management of Cesium and Strontium Capsules (MCSC) Project at Hanford to perform technology development activities related to nuclear material dry canister storage systems. Extended long-term storage of spent nuclear fuel (SNF) is a significant area of concern for DOE, with phenomena such as stress corrosion cracking highlighting the need to understand the aging process in dry storage canister systems. The MCSC Project’s cask storage systems (CSS) incorporate a stainless steel transportable storage canister (TSC) that is a close analog to a dual-purpose SNF canister and is well suited for technology development related to SNF extended storage. Regardless of DOE investment, the MCSC project is planning to fabricate an extra CSS unit, including an empty TSC, to be used as a training tool in the beginning stages of the project and later as an early warning detector for stress corrosion cracking or any other material degradation phenomenon that could threaten canister integrity. This extra TSC is called the lead canister, and it is a key component in the aging management plan for the Hanford Maintenance and Storage Facility. The unique aspect of this opportunity is that the MCSC project is open to collaborating with DOE on technology development activities that use the lead canister, as long as the lead canister’s function as an early warning detector is not compromised. This report describes proposed technology development activities that use the lead canister to develop practical solutions to addressing stress corrosion cracking, mitigation and repair of cracks in steel canisters, nondestructive evaluation technologies, particle deposition model validation, and other important issues that affect the extended dry storage of nuclear material, especially SNF. The scope of work proposed in this report is divided into two categories: a set of core development activities that form a minimum level of effort necessary to take advantage of the lead canister opportunity, and a selection of additional technology development activities that are made possible by this collaboration. | 2019-09-30 |  | 2019-09-30 | This technical report describes a unique opportunity for the U.S. Department of Energy (DOE) to partner with CH2M Hill Plateau Remediation Company (CHPRC) on the Management of Cesium and Strontium Capsules (MCSC) Project at Hanford to perform technology development activities related to nuclear material dry canister storage systems. Extended long-term storage of spent nuclear fuel (SNF) is a significant area of concern for DOE, with phenomena such as stress corrosion cracking highlighting the need to understand the aging process in dry storage canister systems. | 2019 | Complete | Lead Canister Initiative Proposal | Nicholas A. Klymyshyn, Eric J. Berglin, Jim A. Fort, Sarah Suffield, Philip J. Jensen, Ryan M. Meyer, John P. Lareau, Kenneth A. Ross | Nicholas A. Klymyshyn | None | Lead Canister Initiative Proposal_distribution.pdf
M5SF-19IN020403043 | M5 | 1.08.02.04.03 | INL | SF-19IN02040304 | Standardization and Integration - INL | Jarrell, Josh | None | Overview report of available absorber samples and equipment | Overview report of available absorber samples and equipment | This report satisfies the level 5 deliverable, M5SF-19IN020403043, entitled “Overview Report of available absorber samples and equipment.” We hope this report will provide enough detail on INL’s samples, equipment, and facilities to support ORNL’s level 4 deliverable due at the end of July. We have a number of borated stainless steel samples, advanced neutron absorber samples, and other material samples as well as a suite of corrosion testing equipment that we believe could be leveraged for future material corrosion testing in a range of environments. | 2019-06-22 |  | 2019-06-27 | Deliverable completed on schedule | 2019 | Complete | Report on Capabilities to Revive Neutron Absorbing Alloy Corrosion Testing | Tedd Lister | Tedd Lister | None | Materials and Capabilities INL Neutron Absorbers Testing_clean.docx
M5SF-19PN020301024 | M5 | 1.08.02.03.01 | PNNL | SF-19PN02030102 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | None | Transportation Core Group Meeting Summary | Transportation Core Group Meeting Summary | report | 2019-09-23 |  | 2019-09-17 | This document presents a meeting summary for the DOE Office of Nuclear Energy (DOE-NE) Transportation Core Group Meeting, held in Washington, DC on August 21, 2019. This meeting is typically held once or twice a year between DOE and state and tribal representatives and provides a forum for updates to be provided among stakeholders as well as an opportunity for information exchange. | 2019 | Complete | DOE-NE Transportation Core Group Meeting Summary | Lauren Rodman | Steve Maheras | None | M5SF-19PN020301024_Transportation Core Group Summary_signed.pdf |  | Core Group, State Regional Groups, Transportation
M3SF-19OR020201012 | M3 | 1.08.02.02.01.01 | ORNL | SF-19OR02020101 | IWM Facilities Concepts - ORNL | Bevard, Bruce | Carter, Joe | Identify data needs and experimental approaches to support handling SNF in air | Experiments and testing necessary to support efficient canister handling and fuel handling operations | Identify experiments and testing necessary to support efficient canister handling and fuel handling operations. FY2019 is focused on identifying data needs and experimental approaches to support handling fuel in air. | 2019-09-30 | 2019-10-31 | 2019-10-01 | The document was provided to SRNL for review and comment. It outlines the gaps in knowledge concerning SNF in air (at temperature) and proposed testing to close those gaps | 2019 | Complete | Oxidation of Spent Fuel During Fuel Handling Accidents Test Plan | Dr Jason Harp | Bruce Bevard | None | Oxidation of Spent Fuel During Fuel Handling Accidents Test Plan.pdf |  | fuel in air; SNF; oxidation of fuel
M3SF-19OR0203020354 | M3 | 1.08.02.03.02.03 | ORNL | SF-19OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Accelerated Transportation Study Report | Accelerated Transportation Report | Develop a report that detail a process through which transportation activities could be accelerated tot he extent possible. | 2019-09-27 |  | 2019-09-27 | This report evaluates methodologies for accelerating the development of a large-scale transportation system to move spent nuclear fuel (SNF) from commercial nuclear reactor sites to an as-yet undefined destination. | 2019 | Complete | Methodologies for Accelerating the Development of a Transportation System | Matt Feldman | Matt Feldman | None | M3SF-19OR0203020354_R0_Final.pdf |  | Transportation; accelerated; Spent Nuclear Fuel; SNF Transport
M3SF-19OR020303027 | M3 | 1.08.02.03.03.02 | ORNL | SF-19OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Project Annual Status Report | Final Atlas Railcar Project Annual Status Report | Final report on the project status of development of S-2043 compliant cask, buffer, and escort railcars. | 2019-09-30 |  | 2019-09-25 | Report was completed on schedule. | 2019 | Complete | Atlas Railcar Design Project Status Report for FY2019 | Bill Reich | Matt Feldman | None | M3SF-19OR020303027-Atlas Railcar Project Status Report-Sept 30 2019-FINAL.pdf |  | Atlas railcars
M3SF-19OR0204050158 | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Revision of Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology | validation of UNF-ST&DARDS as-loaded analysis methodology | Revision of the report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data with additional analyses. | 2019-09-30 |  | 2019-09-30 | This report summarizes the work performed to enable detailed modeling using the Used Nuclear Fuel – Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). | 2019 | Complete | Validation of As-Loaded Calculations Using Detailed Fuel and Operational Data with UNF-ST&DARDS | Justin Clarity | Kaushik Banerjee | None | PB1901182_Clarity_ValidAsLoad_Final.pdf |  | UNF-ST&DARDS; as-loaded analysis; validation
M3SF-19OR0204050160 | M3 | 1.08.02.04.05.01 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Update UNF-ST&DARDS criticality report | UNF-ST&DARDS criticality analysis capability | The deliverable includes development of new criticality model(s)(storage, transport), and integration of new criticality model(s) into UNF-ST&DARDS | 2019-09-20 |  | 2019-09-20 | This report documents UNF-ST&DARDS criticality analysis templates. | 2019 | Complete | Criticality Process, Modeling and Status for UNF-ST&DARDS | Justin Clarity | Kaushik Banerjee | None | PB1901109_Clarity_Criticality_Final.pdf |  | UNF-ST&DARDS; criticality
M3SF-19PN0203020412 | M3 | 1.08.02.03.02.04 | PNNL | SF-19PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Continue Cultural Resource Reviews -- Final (11.2) | Final Report on Cultural Resource Reviews | Prepare summaries of known cultural resources, status of Section 106 consultation, and potential issues. | 2019-09-30 |  | 2019-09-23 | This report presents cultural resources-related information for 25 nuclear power plant sites (NPP) sites and identifies American Indian tribes that may have historical, cultural and/or geographical ties to those sites or that may be potentially impacted by future transportation activities. The report includes a section for each of the 25 NPPs, each of which describes the NPP location, when it began and ceased operations, and the status of the decommissioning process. American Indian tribes that may have historic and cultural and/or geographic ties to the NPP are also identified, as is their engagement on any established community engagement panels or citizen’s advisory boards associated with decommissioning activities. For each NPP, five key cultural resources related data points are summarized: (1) cultural resources field work completed before and after construction, (2) any cultural resources identified, (3) indication of whether a cultural resources protection plan is, or has been, in place, (4) a summary of prior consultation and/or engagement with the SHPO and American Indian tribes, and (5) an overview of any cultural resources issues or concerns that emerged as a result of those interactions. Finally, relevant cultural resources information retrieved from each of the documents identified by the online literature review is presented. | 2019 | Complete | Cultural Resource Summaries for Twenty-Five Nuclear Power Plant Sites | Ellen Kennedy | Steve Maheras | None | M3SF-19PN0203020412_signed.pdf |  | cultural resources; nuclear power plant sites; American Indian tribes
M4SF-19PN020408051- Superceed by: M4SF-20PN020408041 | M4 | 1.08.02.04.08 | PNNL | SF-20PN02040804 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites (MERF) - PNNL | Nutt, Mark | Howard, Rob | Friction Stir Weld Repair Demonstration Status | Friction Stir Weld Repair Demonstration Status | This report provides a preliminary analysis and limited experimentation to develop preliminary specifications for implementing FSP capability into a Mobile Examination and Remediation Repair Facility (MERF). Friction stir welding (FSW) and FSP should be considered for use in new fabrication of canisters and repair of existing canisters with the overpack removed. Low heat input and grain refinement associated with low-temperature FSP result in material with improved mechanical properties and equivalent generalized corrosion performance relative to base metal. | 2019-11-29 |  | 2019-11-27 | This report provides a preliminary analysis and limited experimentation to develop preliminary specifications for implementing FSP capability into a Mobile Examination and Remediation Repair Facility (MERF). Friction stir welding (FSW) and FSP should be considered for use in new fabrication of canisters and repair of existing canisters with the overpack removed. Low heat input and grain refinement associated with low-temperature FSP result in material with improved mechanical properties and equivalent generalized corrosion performance relative to base metal. | 2020 | Complete | Friction Stir Processing for a Mobile Examination and Remediation Repair Facility | Ken Ross | Ken Ross | None | Friction Stir Processing for a MERF (M4SF-20PN020408041).pdf
M2SF-20SR020201022 | M2 | 1.08.02.02.01 | SRNL | SF-20SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Inspection and Remediation Facility - Report | Canister inspection and Remediation Facility Design Concept | Please find attached, the Inspection and Remediation Facility for Dry Storage Canisters: Preliminary Concept Report which fulfills the Level 2 milestone M2SF-20SR020201022 within work package SF-20SR02020102. | 2019-11-30 |  | 2019-11-26 | The report lays out a concept for an Inspection & Remediation Facility (I&RF) for SNF canisters within an Interim Storage Facility ISF)/Monitored Retrievable Storage (MRS) or a Geologic Repository Complex. The I&RF would have the functions and capabilities to perform onsite inspection and remediation of aging Dry Storage Canisters (DSCs). This report outlines facility requirements needed to receive a cask from storage, perform inspection and remediation activities, and return a cask to storage. Inspection and remediation operations include: remove a DSC from its cask, re-orient the DSC, transfer the DSC into a shielded structure, remotely inspect the DSC through Nondestructive Examination (NDE) methods, remotely repair, perform overpacking operations, and repackage a DSC into its cask, as necessary. | 2020 | Complete | Closure Document Inspection and Remediation Facility for Dry Storage Canisters Preliminary Concept Report | Joe Carter | Joe Carter | None | Closure Document IRF for Dry Storage Canisters Preliminary Concept Report.pdf |  | Inspection and Remediation
M2SF-20SN020801015 | M2 | 1.08.02.08.01 | SNL | SF-20SN02080101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Complete data/content copy from Legacy Mgt to Cloud | Document status of content upload to Cloud storage. |  | 2019-12-20 |  | 2019-12-17 | Milestone completed on 12/17/2019. Final documentation is lagging due to the WPM having to go out on family medical leave. It will be provided as soon as it becomes available and passes SNL export control. | 2020 | Complete | M2 Data Copy Artifact |  |  | None | 1_20191217_NWM_DataCopyStatus.docx
M3SF-20OR0203020310 | M3 | 1.08.02.03.02 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Commercial Nuclear Power Plant De-Inventory Queue Analysis Report | Commercial Nuclear Power Plant De-Inventory Queue Analysis Report | Report | 2019-10-25 |  | 2019-10-25 | This work analyzed various options for acceptance queues for pickup of spent nuclear fuel (SNF) from commercial nuclear power plants. | 2020 | Complete | Commercial Nuclear Power Plant Deinventory Queue Analysis Report | Robby Joseph | Matt Feldman | None | M3SF-19OR0203020357_Rev0.pdf |  | Transportation, Queue, De-Inventory
M3SF-20SR020201026 | M3 | 1.08.02.02.01 | SRNL | SF-20SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Canister Leak Check Testing Status Report | Canister Leak Check Status Report | This report satisfies Milestone M3SF-20SR020201026-Canister Leak Check Status Report that was due on 11/15/19. | 2019-11-15 |  | 2019-11-15 | The report describes the status of canister leak testing activities being conducted at the Savannah River National Laboratory. Recent activities have included contracting with outside vendors (APTIM, Holtec) to provide ASME Boiler and Pressure Vessel (Section VIII) code compliant design for a mock canister and vacuum chamber required to conduct the leak testing program. This design has progressed through the 90% design review and comments have been provided concurrently with this status report (November 15, 2019). The design contract deliverables are due on November 30, 2019. | 2020 | Complete | Canister Leak Check Status Report | Joe Carter/George Rawls | Joe Carter/George Rawls | None | Closure Docment - M3SF-20SR020201026 Canister Leak Check Status Report.pdf |  | Canister Leak Check
M3SF-20OR0203020311 | M3 | 1.08.02.03.02 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #9 | Site Specific De-Inventory Report #9 | Report | 2019-11-15 |  | 2019-11-15 | The M3SF-20OR0203020311deliverable, a report titled "Initial Site-Specific De-Inventory Report for La Crosse" was prepared by Orano Federal Services LLC under subcontract to ORNL. It provides an investigation of the organizations and operations necessary to remove all spent nuclear fuel (SNF) and greater than Class C low level radioactive waste (GTCC) from the shutdown La Crosse nuclear power plant site. It begins by describing the site characteristics, including the material to be shipped and the near-site transportation infrastructure. It then describes many potential transportation scenario options for removing the SNF and GTCC and uses a multi-attribute utility analysis (MUA) to determine the contractor’s preferred transportation scenario (modes and route) for delivering all of the site’s SNF and GTCC to a railroad. A concept of operations is described for the preferred scenario, along with a discussion on security planning, a budget, and a schedule. It should be noted that the MUA only includes attributes strictly related to logistics and should not be considered a final decision by DOE on how such SNF will be removed. | 2020 | Complete | Initial Site-Specific De-Inventory Report for La Crosse | Orano, LLC | Matt Feldman | None | Initial Site-Specific De-Inventory Report for La Crosse.pdf |  | La Crosse, campaign, transportation, logistics, shutdown site, MUA
M3SF-20OR0203020312 | M3 | 1.08.02.03.02 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #10 | Site Specific De-Inventory Report #10 | Report | 2019-11-15 |  | 2019-11-15 | The M3SF-20OR0203020312 deliverable, a report titled "Initial Site-Specific De-Inventory Report for Zion" was prepared by Orano Federal Services LLC under subcontract to ORNL. It provides an investigation of the organizations and operations necessary to remove all spent nuclear fuel (SNF) and greater than Class C low level radioactive waste (GTCC) from the shutdown Zion nuclear power plant site. It begins by describing the site characteristics, including the material to be shipped and the near-site transportation infrastructure. It then describes many potential transportation scenario options for removing the SNF and GTCC and uses a multi-attribute utility analysis (MUA) to determine the contractor’s preferred transportation scenario (modes and route) for delivering all of the site’s SNF and GTCC to a railroad. A concept of operations is described for the preferred scenario, along with a discussion on security planning, a budget, and a schedule. It should be noted that the MUA only includes attributes strictly related to logistics and should not be considered a final decision by DOE on how such SNF will be removed. | 2020 | Complete | Initial Site-Specific De-Inventory Report for Zion | Orano, LLC | Matt Feldman | None | Initial Site-Specific De-Inventory Report for Zion.pdf |  | Zion, campaign, transportation, logistics, shutdown site, MUA
M3SF-20OR0203020313 | M3 | 1.08.02.03.02 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site Specific De-Inventory Report #11 | Site Specific De-Inventory Report #11 | Report | 2019-11-15 |  | 2019-11-15 | The M3SF-20OR0203020313 deliverable, a report titled "Initial Site-Specific De-Inventory Report for Yankee Rowe" was prepared by Orano Federal Services LLC under subcontract to ORNL. It provides an investigation of the organizations and operations necessary to remove all spent nuclear fuel (SNF) and greater than Class C low level radioactive waste (GTCC) from the shutdown Yankee Rowe nuclear power plant site. It begins by describing the site characteristics, including the material to be shipped and the near-site transportation infrastructure. It then describes many potential transportation scenario options for removing the SNF and GTCC and uses a multi-attribute utility analysis (MUA) to determine the contractor’s preferred transportation scenario (modes and route) for delivering all of the site’s SNF and GTCC to a railroad. A concept of operations is described for the preferred scenario, along with a discussion on security planning, a budget, and a schedule. It should be noted that the MUA only includes attributes strictly related to logistics and should not be considered a final decision by DOE on how such SNF will be removed. | 2020 | Complete | Initial Site-Specific De-Inventory Report for Yankee Rowe | Orano, LLC | Matt Feldman | None | Initial Site Specific De-Inventory Report for Yankee Rowe.pdf |  | Yankee Rowe, campaign, transportation, logistics, shutdown site, MUA
M3SF-20SR020201027 | M3 | 1.08.02.02.01 | SRNL | SF-20SR02020102 | IWM Facilities Concepts - SRNL | Carter, Joe | Carter, Joe | Repackaging Facility Concepts | Repackaging Facility Concept | The attached report “A Packaging Facility for Transferring Spent Nuclear Fuel from Storage to Disposal Canisters” documenting work performed to fulfill the Level 3 milestone M3SF-20SR020201027 within work package SF-20SR02020102. | 2020-11-30 |  | 2020-11-20 | This report lays out a conceptual facility design for transferring Spent Nuclear Fuel (SNF) from Dual Purpose Canisters (DPC) and Bare Fuel Casks (BFC) to disposal canisters for further processing and disposal at a repository. The report outlines design facility requirements needed to receive casks from either on-site storage, for the case in which the facility would be constructed at an Interim Storage Facility (ISF) / Monitored Retrievable Storage (MRS) or from a transportation cask, for the case in which the facility is co-located with a repository, transfer the canister or cask into a Shielded Structure, remotely open the canister or cask, transfer the fuel to a new canister designed for repository disposal, dry, inert and weld closed the disposal canister. The report has been produced in two volumes. Volume 1 contains background information including the technical basis used in developing the concept. Volume 2 describes the concept. | 2020 | Complete | A Packaging Facility For Transferring Spent Nuclear Fuel From Storage To Disposal Canister Volume 1 and 2 | Joe T. Carter | Joe T. Carter | None | Closure Document Packaging Concept Report Volume 2.pdf Closure Document Repackaging Concept Report Volume 1.pdf |  | Packaging Facility for Transferring SNF
M3SF-20IN020409012 | M3 | 1.08.02.04.09.01 | INL | SF-20IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Develop 3D models of CPP-603 | Develop 3D models of CPP-603 | Have LIDAR measurements made of the areas of the CPP-603 facility where DOE Standard Canisters are to be loaded and handled, the areas equipment for the loading and handling is brought in and used, and areas I&C (power supply, video, etc.) for the equipment operations are needed. These measurements and existing legacy drawings will be used to develop 3D models which will support fabrication and installation of equipment, and operations. | 2020-01-30 |  | 2020-01-30 06:00 | Memo/letter issued on time fulfills deliverable completion criteria. | 2020 | Complete | A memo/letter describing the 3D model deliverable. | Daniel Thomas | Daniel Thomas | None | 01302020 Letter - Deliverable M3SF-20IN020409012-Develop 3D Model of CPP-603.pdf
M3SF-20IN020409013 | M3 | 1.08.02.04.09.01 | INL | SF-20IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Finalize DOE Standard Canister and basket design for Peach Bottom fuel elements | Finalize DOE Standard Canister and basket design for Peach Bottom fuel elements | Perform criticality and possibly geochemistry analysis to determine fuel element capacity (10 or 12) and need for neutron absorbers in the basket. Finalize the drawings based on analyses. | 2020-05-28 | 2020-07-20 10:00 | 2020-07-20 06:00 | Email "Completion of Deliverable "M3SF-20IN020409013 - Finalize DOE Standard Canister and Basket Design for Peach Bottom Fuel Elements"" with a PDF file attachment of the final design report, including the drawings as Appendix, was sent to control account manager and federal program manager on July 20, 2020. | 2020 | Completed Late | DOE Standard Canister Basket for Peach Bottom Unit 1 Core 2 Fuel | Samual Trost | Daniel Thomas | None | INL EXT-20-59094 DOE Standard Canister Basket for Peach Bottom Unit 1 Core 2 Fuel (002).pdf |  | DOE Standard Canister, Basket, Peach Bottom
M3SF-20ID020403051 | M3 | 1.08.02.04.03.05 | DOE-ID | SF-20ID02040305 | Standardization and Integration - DOE-ID (Task Order 8 - Aptim) | Wheeler, Jack | Howard, Rob | Complete Final Study Report for Task Order 8 (Aptim) | Final Study Report(s) for Task Order 8 (Aptim) | Complete Final Study Report(s) for Task Order 8 | 2020-05-29 |  | 2020-04-16 | APTIM-Holtec Team completed a Study of a Transportation, Aging, and Disposal (TAD) Canister Loading Demonstration Project | 2020 | Complete | Study of a Transportation, Aging, and Disposal (TAD) Canister Loading Demonstration Project (by Holtec in support of APTIM) | Holtec International (supporting APTIM) | Richard Berry (APTIM) | None | HI-2200173.pdf
M3SF-20ID020403061 | M3 | 1.08.02.04.03.06 | DOE-ID | SF-20ID02040306 | Standardization and Integration - DOE-ID (Task Order 8 - Orano) | Wheeler, Jack | Howard, Rob | Complete final study report for Task Order 8 (Orano) | Final Study Report for Task Order 8 (Orano) | Complete final study report for Task Order 8 (Orano) | 2020-05-29 |  | 2020-05-15 | Orano Team completed a Study of a Transportation, Aging, and Disposal (TAD) Canister Loading Demonstration Project | 2020 | Complete | Study of a Transportation, Aging, and Disposal (TAD) Canister Loading Demonstration Project - Orano | Orano Federal Services | Sven Bader (Orano) | None | IDIQ TO 8 Report (Orano TAD Demo) Rev.0 (Final without Attachment B)_Nonproprietary.pdf
M3SF-20SR020405023 | M3 | 1.08.02.04.05.02 | SRNL | SF-20SR02040502 | Commercial SNF Characterization - SRNL | Carter, Joe | Howard, Rob | Inventory Report Rev 7 | Spent Nuclear Fuel and High-Level Waste Inventory Report Rev 7 | Updated Report | 2020-06-30 |  | 2020-05-29 | Completed early | 2020 | Complete | Spent Nuclear Fuel and High-Level Radioactive Waste Inventory Report, Rev 7c | Joe Carter | Joe Carter | None | 2020 State by State Dashboard May 2020 final.pdf SNF and HLW Inventory Rev 7c (FCRD-NFST-2013-000273) May 2020 final.pdf
M3SF-20OR0203020318 | M3 | 1.08.02.03.02.03 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Transportation Risk Assessment - Incident Case with Release | Transportation Risk Assessment - Incident Case with Release | Report detailing analytical technique to be used to calculate dose impact of incident case with release. | 2020-07-31 |  | 2020-07-31 | IWM is developing a methodology to estimate the potential radiological impacts from a hypothetical transportation accident involving spent nuclear fuel (SNF). Results from this methodology could be used to inform environmental assessments, as well as safety and security planning. | 2020 | Complete | Transportation Risk Assessment - Incident Case with Release | Kevin Connelly | Kevin Connelly | None | M3SF-20OR0203020318.pdf |  | radiological release; transportation accident; Spent nuclear fuel (SNF); Evnironmental impacts; radiological safety;Risk assessment;
M3SF-20SN020801012 | M3 | 1.08.02.08.01.01 | SNL | SF-20SN02080101 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Continue To Develop/Implement/Test Legacy Application Functions in FY20 | Document status of deployment of Legacy Application functionality into Cloud. | Continue To Develop/Implement/Test Legacy Application Functions in FY20 | 2020-09-17 |  | 2020-09-17 02:00 | The FY20 Dev/Implementation work on the Legacy Applications has been completed. This is an ongoing effort that will be completed in FY21. | 2020 | Complete | FY20 NWM Legacy Application Status | Cynthia Huber |  | None | NWM_FY20-Q4-PICS Application Status Update.docx
M3SF-20AN020402027 | M3 | 1.08.02.04.02.02 | ANL | SF-20AN02040202 | NGSAM Development and Application - ANL | Craig, Brian | Howard, Rob | Revise NGSAM Verification Report | NGSAM Verification Report | Revise FY2019 NGSAM Verification Report | 2020-09-29 |  | 2020-09-29 02:00 | NGSAM Verification Report was revised to include the latest development work in FY19 and FY20. The report was delivered to NTD and DOE on 9/29 via email. | 2020 | Complete | Next-Generation System Analysis Model (NGSAM) Verification Report | Argonne National Laboratory | Brian Craig | None | SFWD IWM M3FT NGSAM Verification Report_final.pdf
M3SF-20PN0203020412 | M3 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Nuclear Power Plant Site Infrastructure Report | Nuclear Power Plant Site Infrastructure Report | Revision of the nuclear power plant site infrastructure report. | 2020-09-30 |  | 2020-09-28 03:00 | This report provides evaluations of the nuclear power plant (NPP) site infrastructure and near-site transportation infrastructure for removing spent nuclear fuel from 16 NPP sites. The material to be removed from the NPP sites includes both the spent nuclear fuel (SNF) and the greater-than-Class C low-level radioactive waste (GTCC waste) that is stored, or will be stored, at the sites. This report is a continuation of the work previously published in a series of reports entitled “Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites” (Maheras et al. 2017). The updated report title reflects the expansion of the site evaluations to include operating NPP sites. | 2020 | Complete | Nuclear Power Plant Infrastructure Evaluations for Removal of Spent Nuclear Fuel | Steve Maheras | Steve Maheras | None | M3SF-20PN0203020412 20200928.pdf |  | nuclear power plant site evaluations, near-site transportation infrastructure, spent nuclear fuel (SNF)
M3SF-20OR020303026 | M3 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Design Project Status Report for FY2020 | Atlas Railcar Design Project Status Report for FY2020 | Prepare Atlas Railcar Design Project Status Report for FY2020 that describes accomplishments for this FY. | 2020-09-30 |  | 2020-09-30 | Annual status report for the Atlas Railcar Design Project. | 2020 | Complete | Atlas Railcar Design Project Status Report for FY 2020 | William J. Reich | William J. Reich | None | M3SF-20OR020303026-Atlas Railcar Project Status Report-Sept 30 2020-R2.pdf |  | Atlas railcar
M3SF-20OR020405015 | M3 | 1.08.02.04.05.01 | ORNL | SF-20OR02040501 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | Status report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | validation of UNF-ST&DARDS as-loaded analysis methodology | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | 2020-09-30 |  | 2020-09-30 | This report summarizes the work performed to enable detailed modeling using the Used Nuclear Fuel – Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS). | 2020 | Complete | Validation of the UNF-ST&DARDS As-Loaded Calculation Methodology | Justin Clarity | Kaushik Banerjee | None | Detailed_Validation_to_Final.pdf |  | UNF-ST&DARDS, validation
M4SF-20PN0203020410 | M4 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #4 | Thermal Template #4 | Thermal template #4. | 2019-11-29 |  | 2019-11-27 06:00 | A thermal-fluids model of the NUHOMS® -MP197HB transport cask was developed using COBRA-SFS to add to the repertoire of model templates available for use in UNF-ST&DARDS. The template provides the capability to model the thermal behavior of the NUHOMS-MP197HB transport cask when subjected to transportation conditions. The ABB ANF 8x8 fuel assembly was chosen as the prototypic fuel assembly for this model because it is thermally representative of the fuel assemblies to be transported in this system. The NUHOMS-MP197HB transport cask is capable of housing canisters other than the NUHOMS-61BT-Dry Shielded Canister (DSC) but separate templates must be constructed to model the separate configurations. This template enables important analysis capabilities for sites at which NUHOMS-MP197HB transport casks are currently or expected to be in use. | 2020 | Complete | COBRA-SFS Model of the NUHOMS-MP197HB for UNF-ST&DARDS | Christopher Grant | Steve Maheras | None | M4SF-20PN0203020410 Thermal 4_signed.pdf |  | Thermal template, UNF-ST&DARDS, COBRA-SFS, MP197HB, transportation cask
M4SF-20PN020302049 | M4 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Thermal Template #3 | Thermal Template #3 | Thermal template #3. | 2019-11-29 |  | 2019-11-27 06:00 | This report describes the COBRA-SFS models of the HI-TRAC VW transfer cask loaded with the Multi-Purpose Canister (MPC)-37 and MPC-89 storage and transportation canisters. These models were developed to be templates for the UNF-ST&DARDS tool. The templates provide the capability to model the thermal performance of the HI-TRAC VW transfer cask system. The MPC-37 is modeled with Westinghouse 17x17 OFA pressurized water reactor (PWR) assemblies and the MPC-89 is modeled with GE14 10x10 boiling water reactor (BWR) assemblies. These assembly types are used for testing because they are representative of the assemblies being loaded into the HI-TRAC VW transfer cask system. These template models significantly increase the ability of UNF-ST&DARDS to model loading and transfer of spent fuel assemblies. This capability is critical because the initial temperatures of spent fuel have a significant impact on the condition of the cladding when it is transported. | 2020 | Complete | COBRA-SFS Model of the HI-TRAC VW for UNF-ST&DARDS | Ben Jensen | Steve Maheras | None | M4SF-20PN020302049 Thermal 3_signed.pdf |  | Thermal template, UNF-ST&DARDS, COBRA-SFS, HI-TRAC, transfer cask, MPC-37, MPC-89
M4SF-20OR020403012 | M4 | 1.08.02.04.03.01 | ORNL | SF-20OR02040301 | Standardization and Integration - ORNL | Howard, Rob | Howard, Rob | Draft Description Document for Development and Testing on a Range of Potential Neutron Absorber Materials for use in Triple Purpose SNF canisters: | Neutron Absorber Evaluation Plan | Draft Neutron Absorber Material Evaluation Description document should include: A. A range of post-closure chemical environments /service conditions. This should include chemical conditions in anoxic and oxidizing environments as well as account for chemical evolution associated with water contacting steel waste package materials, spent nuclear fuel, and spent nuclear fuel assembly components. B. A range of materials to be considered for evaluation and corrosion testing. C. Identification and discussion of available existing mechanical, degradation, and failure data available D. Identification and consideration of advanced manufacturing approaches for neutron absorber material production | 2019-11-29 |  | 2019-11-26 | ” Among other things, the Neutron Absorber Evaluation Plan includes: • A range of post-closure chemical environments/service conditions, including chemical conditions in anoxic and oxidizing environments, accounting for chemical evolution associated with water contacting steel waste package materials, SNF, and SNF assembly components • A range of materials to be considered for evaluation and corrosion testing • A range of options for how to carry out neutron absorber evaluation and testing. The plan was developed as a collaboration between ORNL, INL, SNL, and contractor staff. | 2020 | Complete | Neutron Absorber Evaluation Plan | Robert Howard | Robert Howard | None | NAM Eval Plan_26Nov2019.pdf
M4SF-20PN020408041 | M4 | 1.08.02.04.08.04 | PNNL | SF-20PN02040804 | Non-Transportable Canister/Cask Fuel Removal from Commercial Sites (MERF) - PNNL | Nutt, Mark | Howard, Rob | Friction Stir Weld Repair Demonstration Status | Friction Stir Weld Repair Demonstration Status | Friction Stir Weld Repair Demonstration Status | 2019-11-29 |  | 2019-11-27 18:00 | This report provides a preliminary analysis and limited experimentation to develop preliminary specifications for implementing FSP capability into a Mobile Examination and Remediation Repair Facility (MERF). Friction stir welding (FSW) and FSP should be considered for use in new fabrication of canisters and repair of existing canisters with the overpack removed. Low heat input and grain refinement associated with low-temperature FSP result in material with improved mechanical properties and equivalent generalized corrosion performance relative to base metal. | 2020 | Complete | Friction Stir Processing for a Mobile Examination and Remediation Repair Facility | Ken Ross | Ken Ross | None | Friction Stir Processing for a MERF (M4SF-20PN020408041).pdf
M4SF-20ID020302013 | M4 | 1.08.02.03.02.01 | DOE-ID | SF-20ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Revised START User’s Manual | Revised Start User’s Manual | Revise the START User’s Manual to reflect the current functions and capabilities of the START tool. | 2019-12-13 | 2020-02-29 02:00 | 2020-02-14 02:00 | Completed as planned on revised finish date of February 14. | 2020 | Completed Late | START Version 3.2 User Manual |  |  | None | START Version 3.2 User Manual - Feb 14 2020 Draft.pdf
M4SF-20OR0203020316 | M4 | 1.08.02.03.02.03 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Feldman, Matt | Feldman, Matt | Transportation Risk Assessment Functions and Requirements Document | Transportation Risk Assessment Functions and Requirements Report | Report detailing the functions and requirements for programmatic transportation dose risk assessment | 2020-01-17 |  | 2020-01-17 | Level 4 milestone M4SF-20OR0203020316, “Transportation Risk Assessment Functions and Requirements Document,” (work package SF-20OR02030203, Transportation: Operational – ORNL, WBS #1.08.02.03.02) was completed. The deliverable is a report entitled “Transportation Radiological Risk Assessment Methodology Functions and Requirements.” This report presents the functions and requirements of a methodology to estimate the radiological impacts of transportation accidents involving SNF that can be used by IWM and other users to develop an EIS. | 2020 | Complete | ransportation Radiological Risk Assessment Methodology Functions and Requirements | Kevin Connolly | Matt Feldman | None | M4SF-20OR0203020316.pdf |  | Transportation, Accident, Incident, Dose Factors
M4SF-20AN020402028 | M4 | 1.08.02.04.02.02 | ANL | SF-20AN02040202 | NGSAM Development and Application - ANL | St. Aubin, Jim | Howard, Rob | Revise NGSAM Software Guide and Training Manual | NGSAM Software Guide and Training Manual | Revise NGSAM Software Guide and Training Manual | 2020-03-20 |  | 2020-03-20 03:00 | The purpose of this “user guide” documentation is to assist the system analysts in understanding and navigating the NGSAM 2.3.7.0 tool (both operationally & functionality). | 2020 | Complete | Next-Generation System Analysis Model (NGSAM) Software Guide and Training Manual | Lucas Vander Wal | Jim St. Aubin | None | NGSAM_UserGuide NGSAM 2020-March-24 FINAL2.docx NGSAM_UserGuide NGSAM 2020-March-24 FINAL2.pdf |  | NGSAM, Traininig, User Guide
M4SF-20PN0203020419 | M4 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Oyster Creek and Pilgrim Site Infrastructure Report Sections | Oyster Creek and Pilgrim Site Infrastructure Report Sections | Site infrastructure report sections for Oyster Creek and Pilgrim. | 2020-04-24 |  | 2020-04-24 03:00 | The U.S. Department of Energy Office of Integrated Waste Management (DOE-IWM) conducted evaluations of removing spent nuclear fuel from the Oyster Creek and Pilgrim nuclear power plant sites. The Oyster Creek site infrastructure evaluation took place May 13-17, 2019. The site is located in Lacey Township in eastern New Jersey adjacent to Barnegat Bay, approximately 9 miles south of Toms River, New Jersey, 60 miles south of Newark, New Jersey, 35 miles north of Atlantic City, New Jersey, and 50 miles east of Philadelphia, Pennsylvania. The Oyster Creek site was found to have two transportation mode options, onsite barge access and offsite rail access. Dredging of the Oyster Creek state and federal channels, the Intracoastal Waterway, and the Barnegat Bay Inlet federal channel could potentially be required to ship spent nuclear fuel from the Oyster Creek site by barge. Use of offsite rail would require heavy haul truck transport to a location where transportation casks could be transloaded to railcars. Three potential offsite heavy haul truck to rail transload locations were evaluated in Lakehurst and Freehold, New Jersey and the Conrail Railyard in Morrisville, Pennsylvania, which would require moving spent nuclear fuel 30 to 70 miles by heavy haul truck. The Pilgrim site evaluation took place on November 4-8, 2019. The Pilgrim site is located on the western shore of Cape Cod Bay in the Town of Plymouth, Massachusetts, about 38 miles southeast of Boston and 44 miles east of Providence, Rhode Island. The Pilgrim site was found to have two transportation mode options for the removal of spent nuclear fuel, offsite rail access and onsite barge access. Two offsite heavy haul truck to rail transload locations were evaluated, one in Middleborough, Massachusetts, about 23-30 miles from the Pilgrim site, and a second location in Middleborough about 24-28 miles from the Pilgrim site. A passenger railroad terminates in Plymouth, Massachusetts, about 7 miles from the Pilgrim site; however, this location is not suitable for freight rail involving large spent nuclear fuel transportation casks. There is also an onsite barge facility located on the Pilgrim site that was used during construction and would require refurbishment to be used. | 2020 | Complete | Oyster Creek and Pilgrim Nuclear Power Plant Site Infrastructure Evaluations | Steve Maheras | Steve Maheras | None | M4SF-20PN0203020419 20200430_signed.pdf |  | nuclear power plant, site infrastructure evaluations, Pilgrim, Oyster Creek, spent nuclear fuel
M4SF-20OR0203020317 | M4 | 1.08.02.03.02.03 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Transportation Risk Assessment - Incident Case no Release, loss of shielding | Transportation Risk Assessment - Incident Case no Release, loss of Shielding Report | Report detailing analytical technique to be used to calculate dose impact of incident case with no release but with loss of shielding. | 2020-04-30 | 2020-05-29 | 2020-04-30 | This report presents new templates for generating shielding calculation input files within the Used Nuclear Fuel Storage, Transportation & Disposal Analysis Resource and Data System (UNF-ST&DARDS) computational toolset. New templates were created to model several loss of shielding scenarios described in NUREG-2125, Spent Fuel Transportation Risk Assessment (NRC 2014). These templates may be used to perform shielding calculations of as-loaded transportation casks in accidents at varying impact speeds and cask positions, and they may be used to analyze the effects of loss of lead shielding on the cask’s external dose rate. | 2020 | Complete | Transportation Risk Assessment - Incident Case no Release, loss of Shielding Report | Kevin Connelly | Kevin Connelly | None | M4SF-20OR0203020317.pdf |  | Transportation; loss of shielding; accident scenario;Used Nuclear Fuel Storage, Transportation & Disposal Analysis Resource and Data System; UNF-ST&DARDS;;
M4SF-20PN020303034 | M4 | 1.08.02.03.03.03 | PNNL | SF-20PN02030303 | Transportation: Hardware - PNNL | Maheras, Steve | Feldman, Matt | Railcar Testing Report | Analysis of Atlas Railcar Testing | Railcar testing report. | 2020-06-12 |  | 2020-06-12 03:00 | A significant problem was identified during the dynamic testing of the Atlas railcar. Under certain speed, loading, and wheel conditions, the railcar was hunting. Hunting is a lateral instability in which the wheelsets rapidly move from side-to-side because of high lateral forces not sufficiently countered by the damping effects of the overall design. The purpose of this report is to provide path-forward recommendations to identify the root cause of the problem and to successfully resolve it based on an in-depth review of the hunting-related dynamic testing work performed to date on the Atlas railcar, an analysis of the work processes used to perform the testing to date, and careful consideration of possible options that can be used to ensure mission success moving forward. | 2020 | Complete | Atlas Railcar Hunting Testing Review | Matt Feldman | Steve Maheras | None | M4SF-20PN020303034-Final_Signed.pdf |  | hunting, Atlas railcar, railcar, railcar testing
M4SF-20OR020402054 | M4 | 1.08.02.04.02.05 | ORNL | SF-20OR02040205 | System Architecture Analysis - ORNL | Joseph, Robby | Howard, Rob | System sensitivity study on potential MRS Capacities | System sensitivity study of MRS capacity | System sensitivity study on potential MRS Capacities | 2020-06-30 |  | 2020-06-30 | Completed the M4 milestone M4SF-20OR020402054, entitled “System sensitivity study on potential ISF capacities” in the work package SF-19OR02040206, entitled “System Architecture Analysis - ORNL [Oak Ridge National Laboratory].” This document describes an exploration of the implications of various potential interim storage facility (ISF) capacities. Note that in PICS-NE, MRS is listed instead of ISF due to previous guidance. ISF is used in the milestone report based on the latest guidance. | 2020 | Complete | Sensitivity Study on Potential ISF Capacities |  |  | None | PB2000699_Joseph_ISF-Cap_Rev3.docx
M4SF-20PN020301023 | M4 | 1.08.02.03.01.02 | PNNL | SF-20PN02030102 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Draft Final Reciprocal Railcar Safety Inspection Protocol | Draft Final Reciprocal Railcar Safety Inspection Protocol | Draft Final Reciprocal Railcar Safety Inspection Protocol | 2020-08-28 | 2020-09-30 06:00 | 2020-09-17 03:00 | Inspection reports for inspections conducted by the Federal Railroad Administration (FRA), States, and rail carriers are generally not shared and are often viewed as confidential or proprietary. The lack of sharing of the inspection reports with States or Tribes along transportation routes presents a significant obstacle to inspection reciprocity. This Draft Final Railcar Safety Inspection Protocol is being developed in coordination with DOE’s National Transportation Stakeholders Forum’s Spent Nuclear Fuel Rail/Routing Ad Hoc Working Group. The Draft Inspection Protocol could be considered for adoption by DOE for future DOE rail shipments of SNF to promote inspection reciprocity among States and Tribes along transportation routes. In order to promote reciprocity, the Draft Inspection Protocol consists of two components. The first component of the Draft Inspection Protocol consists of inspections to be performed at origin sites, which include nuclear power plant sites, transload locations, and ports. These inspections would be verified, observed, or conducted by a DOE contractor, and the resulting inspection reports would be distributed to States and Tribes along a transportation route used for DOE rail shipments of SNF, potentially through DOE’s Transportation Tracking and Communication System (TRANSCOM). The second component of the Draft Inspection Protocol consists of providing appropriate State and Tribal personnel along transportation routes access to the data feeds from the safety monitoring system required by Association of American Railroads (AAR) Standard S-2043. Determining which personnel would have access to railcar data feeds will likely be part of security protocols for DOE shipments that have yet to be developed. The inspections outlined in this Draft Inspection Protocol are not meant to replace regulatory inspections conducted by the FRA, States, or the rail carriers. Rather, the inspections outlined in this Draft Inspection Protocol and access to the AAR Standard S-2043 data feeds are extra-regulatory and specifically structured to promote inspection reciprocity along DOE rail transportation routes. | 2020 | Completed Late | Draft Final Reciprocal Railcar Safety Inspection Protocol | Steve Maheras | Steve Maheras | None | M4SF-20PN020301023 signed.pdf |  | railcar safety inspection protocol, locomotive inspection, freight car inspection, hazardous materials inspection, motive power and equipment inspection
M4SF-20IN020402043 | M4 | 1.08.02.04.02.04 | INL | SF-20IN02040204 | System Architecture Analysis - INL | Petersen, Gordon | Howard, Rob | System Analysis Support Testing for latest NGSAM Release | Documenting and Testing DOE SNF and HLW in NGSAM | Testing of DOE SNF and HLW inclusion into NGSAM. A report will be generated with the testing results. | 2020-09-18 |  | 2020-09-18 04:00 | This report satisfies the M4 milestone M4SF-9IN020404043, entitled “System analysis support testing for latest NGSAM [Next Generation System Analysis Model] release” in the work package SF-9IN02040404 entitled “System Architecture Analysis – INL [Idaho National Laboratory].” This report describes the capabilities and testing of NGSAM for non-commercial spent nuclear fuel (SNF) and high-level waste (HLW). | 2020 | Complete | Testing Capabilities of Non-Commercial SNF in NGSAM | Gordon Petersen | Gordon Petersen | None | M4SF-9IN020404043 Testing Capabilities of Non-Commercial SNF in NGSAM.docx |  | non-commercial SNF, NGSAM
M4SF-20OR0203020319 | M4 | 1.08.02.03.02.03 | ORNL | SF-20OR02030203 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Maximumly Exposed Individual Scenario (MEIS) Development | Transportation Risk Assessment - Maximumly Exposed Individual Scenario (MEIS) Report | Report detailing analytical technique to be used to calculate dose impact from the maximumly exposed individual scenario (MEIS). | 2020-09-25 |  | 2020-09-25 | This report presents scenarios in which an individual might receive a radiation dose larger than doses received by others during an SNF transportation campaign. | 2020 | Complete | Transportation Radiological Risk Assessment Scenario: Maximally Exposed Individuals | Kevin Connelly | Kevin Connelly | None | M4SF-20OR0203020319.pdf |  | Radiation Dose; maximally exposed individuals; SNF transportation;radiological risks; hypothetical transportation accidents,
M4SF-20PN0203020417 | M4 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | START Verification and Validation Report | START Verification and Validation Report | Produce verification and validation report for START based on current user manual. | 2020-09-30 |  | 2020-09-25 03:00 | The Stakeholder Tool for Assessing Radioactive Transport (START) is a web-based, decision-support tool developed for evaluating routing options and other aspects of transporting spent nuclear fuel and radioactive waste from nuclear power plant and DOE sites to interim storage or disposal sites. This report is a status report which presents progress made in FY20 to Verify and Validate (V&V) START. The V&V of the buffer population and distance reported in START was achieved by utilizing a custom workflow developed in QGIS. QGIS was chosen because it is fully independent of START. Over 200 test cases were run, and good agreement was seen between START and the V&V test cases in QGIS. In all cases, the percent difference was less than +/- 5%, and the majority of cases were below +/- 1%. These cases were also duplicated in ArcMap, which is Environmental Systems Research Institute’s (ESRI) GIS desktop application. ArcMap was only used to verify the methodology for population calculations because START uses ESRI’s GIS web services in their application logic which invokes the same underlying program logic used in ArcMap for its processing. The ArcMap results also show good agreement; however, they cannot be considered independent of START. In addition to the V&V cases, several custom scripts and workflows were developed which automate the V&V process. This allows for future V&V testing to be easily implemented. Finally, a collaborative V&V process was developed between the PNNL team and the START development team. This process greatly enriched the V&V and lead to improvements in START. | 2020 | Complete | START Verification and Validation: Status Update | Philip Jensen | Steve Maheras | None | M4SF-20PN0203020417_signed.pdf |  | START, rail routing, truck routing, barge routing, Stakeholder Tool for Assessing Radioactive Transport, transportation routing, verification and validation
M4SF-20PN020402092 | M4 | 1.08.02.04.02.09 | PNNL | SF-20PN02040209 | System Architecture Analysis - PNNL | Nutt, Mark | Howard, Rob | Intermodal Transportation Enhancements for NGSAM | Intermodal Transportation Enhancements for NGSAM | Report that describes the improved representations of intermodal (heavy haul truck and barge to rail) transfers to more realistically model intermodal and transload-related asset activity within IWM system analysis modeling. | 2020-09-30 |  | 2020-09-28 03:00 | The U.S. Department of Energy (DOE) Office of Integrated Waste Management has sponsored development of the Next Generation Systems Analysis Model (NGSAM), an agent-based simulation software tool, to support system analysts and decision-makers in evaluating integrated waste management system architectures and scenarios, including spent nuclear fuel (SNF) transportation operations. This work was undertaken to be a constructive review of the NGSAM transportation capability with the goals of producing both insight into system behavior and identifying model improvements. | 2020 | Complete | Intermodal Transportation Enhancements for NGSAM | Dan Sullivan | Dan Sullivan | None | Intermodal Transportation Enhancements for NGSAM (Sep 2020)_SJM.pdf
M5SF-20PN0203020416 | M5 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve |  | START Verification and Validation Plan | START Verification and Validation Plan | Initiate verification and validation of START by producing verification and validation plan. | 2019-11-15 |  | 2019-11-14 06:00 | The Stakeholder Tool for Assessing Radioactive Transport (START) is a web-based, decision-support tool developed for evaluating routing options and other aspects of transporting radioactive waste from nuclear power plant sites. This document provides information about how START will be verified and validated (V&V). This is an initial planning document; the actual V&V of the START tool will be completed during fiscal year 2020, after which a detailed report about the START V&V will be issued. | 2020 | Complete | Verification and Validation Plan for the Stakeholder Tool for Assessing Radioactive Transport (START) | Philip Jensen | Steve Maheras | None | M5SF-20PN0203020416_signed.pdf |  | START, routing, nuclear power plant sites, rail, barge, truck, verification, validation, V&V
M5SF-20ID020302014 | M5 | 1.08.02.03.02.01 | DOE-ID | SF-20ID02030201 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan |  | Technical Information Appendix to START User’s Manual | Technical Information Appendix to START User’s Manual | Add an appendix to the START User’s Manual to include “Technical Information” capturing methodologies for accident rates, normalizing daytime and nighttime populations, how weighted routing criteria is performed, derivation of vehicle speeds, etc. | 2020-02-14 |  | 2020-02-14 02:00 | Completed on schedule on February 14. | 2020 | Complete | START 3.2 User Manual Technical Appendix |  |  | None | START 3.2 User Manual_Tech Appendix.docx
M5SF-20OR020303023 | M5 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill |  | Atlas Railcar Demonstration Run Planning Letter Report #1 | Atlas Railcar Demonstration Run Planning Letter Report #1 | Provide brief letter report update on progress with demonstration run preparations. | 2020-02-14 |  | 2020-02-14 | This letter report provides an update on the planning and preparation for the Atlas railcar demonstration run that will occur near the end of Phase 5 of the Atlas railcar project. | 2020 | Complete | Atlas Railcar Demonstration Run Planning Letter Report #1 | Bill Reich | Bill Reich | None | M5SF-20OR020303023-Atlas Railcar Letter Report #1-Feb 14 2020-R0.pdf |  | Atlas Railcar, security
M5SF-20PN0203020414 | M5 | 1.08.02.03.02.04 | PNNL | SF-20PN02030204 | Transportation: Operational - PNNL | Maheras, Steve |  | Master List of Nuclear Power Plant Site Evaluation and Interaction Questions | Master List of Nuclear Power Plant Site Evaluation and Interactions Questions | Master List of Nuclear Power Plant Site Evaluation and Interactions Questions | 2020-03-13 |  | 2020-03-01 06:00 | The U.S. Department of Energy Office of Integrated Waste Management (DOE-IWM) is planning for future large-scale transport of commercial spent nuclear fuel (SNF) and high-level radioactive waste (HLW) to eventual disposal and/or storage facilities. As part of its planning efforts, DOE-IWM conducts e valuations of removing SNF from nuclear power plant (NPP) sites. These NPP site infrastructure evaluations (“site visits”), are a pivotal piece in DOE-IWM’s planning for eventual disposal and/or storage of SNF. This report discusses the broader organization of the NPP site infrastructure project, including its objectives, scope, and key roles and responsibilities. The report also outlines the NPP site visit process by describing the planning efforts undertaken to prepare for site visits, the steps involved prior to, during, and after a site visit, and provides examples of key guidance documents that can be used during NPP site visits. Finally, the report includes a master list of site visit questions that have been developed as an aid for data gathering during site visits. These site visit questions are designed to be sent to NPP sites prior to a site visit, as well as to be discussed during data collection on the ground. The questions focus on evaluating infrastructure and conditions at NPP sites and form a catalog of questions that can be utilized and adapted for future site visits. A key aim of the site visit questions is that they can be tailored to the unique conditions and experience at various NPP sites. | 2020 | Complete | Nuclear Power Plant Site Infrastructure Evaluations Guidance Document | Lauren Rodman | Steve Maheras | None | Nuclear Power Plant Site Infrastructure Evaluations Guidance Document_Final_signed.pdf |  | nuclear power plant, site infrastructure evaluations, site evaluation questions
M5SF-20PN020301022 | M5 | 1.08.02.03.01.02 | PNNL | SF-20PN02030102 | Intergovernmental and External Engagement - PNNL | Maheras, Steve |  | Draft Reciprocal Railcar Safety Inspection Protocol | Draft Reciprocal Railcar Safety Inspection Protocol | Develop Draft Reciprocal Railcar Safety Inspection Protocol. | 2020-03-27 |  | 2020-03-24 06:00 | Inspection reports for inspections conducted by the Federal Railroad Administration (FRA), states, and railroads are generally not shared and are often viewed as confidential or proprietary. In addition, the U.S. Department of Energy (DOE) cannot compel the FRA, states, or railroads to share inspection reports with states and Tribes along transportation routes. These restrictions do not allow for the sharing of inspection reports with states or Tribes along transportation routes, presenting a significant obstacle to inspection reciprocity. The draft reciprocal railcar safety inspection protocol is being developed in conjunction with the National Transportation Stakeholders Forum Spent Nuclear Fuel Rail/Routing Ad Hoc Working Group. The purpose of the draft reciprocal railcar safety inspection protocol is to present an inspection protocol for trains carrying spent nuclear fuel (SNF) that promotes inspection reciprocity. The protocol consists of two components. The first component of the protocol are inspections performed at origin sites, which include nuclear power plant sites, transload locations, and ports. These inspections would be verified, observed, or conducted by an independent contractor and the resulting inspection reports would be distributed to states and Tribes along a transportation route, potentially through the Transportation Tracking and Communication System (TRANSCOM). The second component of the protocol is providing states and Tribes along transportation routes access to the data feeds from system safety monitoring system required by Association of American Railroads (AAR) Standard S-2043. The inspections outlined in this protocol are not meant to replace inspections conducted by the FRA, states, or the railroads. Rather, the inspections outlined in this protocol and access to the AAR Standard S-2043 data feeds are extra-regulatory and specifically structured to promote inspection reciprocity along transportation routes. | 2020 | Complete | Draft Reciprocal Railcar Safety Inspection Protocol | Steve Maheras | Steve Maheras | None | M5SF-20PN020301022 signed.pdf |  | railcar safety inspection protocol, locomotive inspection, freight car inspection, hazardous materials inspection, motive power and equipment inspection
M5SF-20OR020303024 | M5 | 1.08.02.03.03.02 | ORNL | SF-20OR02030302 | Transportation: Hardware - ORNL | Reich, Bill |  | Atlas Railcar Demonstration Run Planning Letter Report #2 | Atlas Railcar Demonstration Run Planning Letter Report #2 | Provide brief letter report update on progress with demonstration run preparations. | 2020-06-30 |  | 2020-06-30 | Report provides an update on the planning and preparation for the Atlas railcar demonstration run that is scheduled near the end of Phase 5. | 2020 | Complete | Atlas Railcar Demonstration Run Planning Letter Report #2 | William J. Reich | William J. Reich | None | M5SF-20OR020303024-Atlas Railcar Letter Report no 2-June 30 2020-R1.docx |  | Atlas Railcar Demonstration Run
M5SF-20OR020303028- Superseded by M5SF-21OR020303052 | M5 | 1.08.02.03.03 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill |  | Letter Report on Organizational Coordination, Agreements, and Planning | Letter Report on Organizational Coordination, Agreements, and Planning | This report describes the organizational coordination, agreements, and planning that must be performed to document the mission need, project charter, alternative selection, mission requirements, and stakeholders for the integrated security and safety monitoring system (ISSMS) project. | 2020-10-30 |  | 2020-10-30 | 2020-10-30 | 2020 | Complete | Letter Report on Organizational Coordination, Agreements, and Planning | William J Reich | William J Reich | None | M5SF-20OR020303028-Organizational Coordination-Oct 30 2020-FINAL.pdf
M4SF-20OR020402055- Superseded by M4SF-21OR020402101 | M4 | 1.08.02.04.02 | ORNL | SF-21OR02040210 | Waste Management System Architecture - NGSAM Model Development and V&V - ORNL | Joseph, Robby | Howard, Rob | Report Summarizing NGSAM Testing | Report Summarizing NGSAM Testing |  | 2021-01-29 |  |  | The attached document satisfies the M4 milestone M4SF-21OR020402102, entitled “Report Summarizing NGSAM Testing” in the work package SF-21OR02040210, entitled “Waste Management System Architecture- NGSAM Model Development and V&V- ORNL.” This document describes the Next-Generation System Analysis Model (NGSAM) testing work completed recently. | 2020 | 90 Day | Report Summarizing NGSAM Testing |  |  | None | PB2100028_Joseph_NGSAM_Final.pdf
M3SF-21PN020302079 | M3 | 1.08.02.03.02.07 | PNNL | SF-21PN02030207 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Draft Accelerated Transportation Project Plan | Draft Accelerated Transportation Project Plan | Develop Draft Accelerated Transportation Project Plan. | 2020-10-30 |  | 2020-11-02 03:00 |  | 2021 | Completed Late | Draft Baseline and Accelerated Transportation Project Plans | Matt Feldman | Steve Maheras | None | M3SF-21PN020302079_final_signed.pdf | transportation system project plan; accelerated plan; baseline plan
M4SF-21ID020301032 | M4 | 1.08.02.03.01.03 | DOE-ID | SF-21ID02030103 | Intergovernmental and External Engagement - DOE-ID (CSG - ERC) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | CSG-ERC Quarterly Reports | CSG-ERC submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-15 | 2020-11-30 | 2020-11-19 | FY20 Quarterly (4) reports submitted to DOE-NE by CSG-ERC, including member survey | 2021 | Completed Late | CSG ERC FY20 Quarterly Reports | CSG ERC | CSG ERC | None | DE-NE0008603 CSG-ERC Quarterly Progress Reports FY20.pdf
M4SF-21ID020301042 | M4 | 1.08.02.03.01.04 | DOE-ID | SF-21ID02030104 | Intergovernmental and External Engagement - DOE-ID (CSG - Midwest) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | CSG-MW Quarterly Reports | CSG-MW submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-15 | 2020-11-30 | 2020-11-18 |  | 2021 | Completed Late | CSG Midwest FY20 Quarterly Reports | CSG Midwest | CSG Midwest | None | DE-NE0008604 CSG-MW Quarterly Progress Reports FY20.pdf
M4SF-21ID020301052 | M4 | 1.08.02.03.01.05 | DOE-ID | SF-21ID02030105 | Intergovernmental and External Engagement - DOE-ID (SSEB) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | SSEB Quarterly Reports | SSEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-15 |  | 2020-11-10 |  | 2021 | Complete | SSEB FY20 Quarterly Reports | SSEB | SSEB | None | DE-NE0008605 SSEB Quarterly Progress Reports FY20.pdf | SSEB, cooperative agreement
M4SF-21ID020301062 | M4 | 1.08.02.03.01.06 | DOE-ID | SF-21ID02030106 | Intergovernmental and External Engagement - DOE-ID (WIEB) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | WIEB Quarterly Reports | WIEB submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-15 |  | 2020-11-10 |  | 2021 | Complete | WIEB FY20 Quarterly Reports | WIEB | WIEB | None | DE-NE0008601 WIEB Quarterly Progress Reports FY20.pdf | WIEB, cooperative agreement,
M4SF-21ID020301072 | M4 | 1.08.02.03.01.07 | DOE-ID | SF-21ID02030107 | Intergovernmental and External Engagement - DOE-ID (NCSL) | Bickford, Erica | Feldman, Matt | Quarterly Reports Oct. 2019 - Sept. 2020 | NCSL Quarterly Reports | NCSL submits quarterly reports on activities and accomplishments under the cooperative agreement. This milestone will compile all quarterly reports submitted between Oct. 2019 - Sept. 2020 into one M4 milestone due end of October 2020. | 2020-11-15 |  | 2020-11-10 |  | 2021 | Complete | NCSL FY20 Quarterly Reports | NCSL | NCSL | None | DE-NE0008586 NCSL Quarterly Progress Reports FY20.pdf
M5SF-21IN020402072 | M5 | 1.08.02.04.02.07 | INL | SF-21IN02040207 | Update Used Fuel Inventory Categorization Report - INL | Orrell, Stanley |  | Complete review of previous reports | Complete review of previous reports | INL will organize a review of the previous Categorization Report, identifying required text revisions, new/revised data needs, etc. for INL and other labs to provide new input. | 2020-12-18 |  | 2020-12-18 02:00 | Annoted outline as shared with the team. | 2021 | Complete |  | Stanley Orrell, Raymond Fanning | Stanley Orrell, Raymond Fanning | None | Annotated Outline-121520 REVISED FOR M5 Milestone.pdf |  | SNF Inventory, Categorization
M4SF-21OR020303053 | M4 | 1.08.02.03.03.05 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | ISSMS Project Plan | SSMS Project Plan | Prepare a detailed project plan to include system requirements, interface requirements, and coordination between all design organizations. Will include a detailed Microsoft Project plan for the three project phases. | 2020-12-31 |  | 2020-12-31 | The ISSMS Project Management Plan was completed. | 2021 | Complete | Integrated Security & Safety Monitoring System Project Management Plan | Bill Reich | Bill Reich | None | M4SF-21OR020303053-ISSMS Project Plan-Dec 31 2020-R10.docx M4SF-21OR020303053-ISSMS Project Plan-Dec 31 2020-R6.docx |  | ISSMS, Atlas railcar, project plan
M5SF-21PN020303065 | M5 | 1.08.02.03.03.06 | PNNL | SF-21PN02030306 | Transportation: Hardware - PNNL | Maheras, Steve |  | Draft Demonstration Run Plan | Draft Demonstration Run Plan | Develop a draft demonstration run plan. | 2020-12-31 | 2021-01-31 03:00 | 2021-01-26 06:00 | The purpose of this report is to help lay the groundwork for the Demonstration Run (DR) portion of the Atlas Railcar project. This report considers and makes recommendations for three subjects related to the DR for the Atlas, buffer railcars and the Rail Escort Vehicle (REV) as follows: (1) route determination, (2) personnel in the REV, and (3) stakeholder outreach during the DR. | 2021 | Completed Late | Draft Demonstration Run Oath Forward Report | Matt Feldman | Steve Maheras | None | M5SF-21PN020303065 Demo Run Draft Report_Final_signed.pdf |  | Atlas railcar; demonstration run; buffer railcar; rail escort vehicle; REV; START; rail routing
M4SF-21OR020302062 | M4 | 1.08.02.03.02.06 | ORNL | SF-21OR02030206 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Plan for integrating Transportation Risk Assessment dose factors with START (February 2021) | Plan for integrating Transportation Risk Assessment dose factors with START | This will be a report detailing how the transportation risk assessment dose factors developed in 2015 and 2020 for incident-free SNF transportation, accident conditions, and dose to the maximally exposed individuals, can be implemented with the START GIS tool. This ORNL-led milestone will include contributions from the START team at Northwind. | 2021-02-26 |  | 2021-02-26 | This report provides information on program development of a methodology to estimate the potential radiological impacts from incident-free transportation of spent nuclear fuel (SNF) and hypothetical transportation accidents involving SNF. | 2021 | Complete | Transportation Radiological Risk Assessment: Plan for Integration of Dose Factors with START | Kevin Connelly | Kevin Connelly | None | M4 - Dose Factors in START - 4a.docx |  | Transportation, START, Dose Factors, Risk Assessment; Spent Nuclear Fuel, Stakeholder Tool for Assessing Radioactive Transportation; incident-free transportation
M3SF-21PN020401052 | M3 | 1.08.02.04.01.05 | PNNL | SF-21PN02040105 | COBRA-SFS Code Development - PNNL | Richmond, David | Howard, Rob | COBRA-SFS Version 6.0 and Users Manual | COBRA-SFS Version 6.0 and Revised Users Manual | Release of COBRA-SFS Version 6.0 and the revised Users Manual | 2021-02-28 |  | 2021-02-25 03:00 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on February 25,2021. | 2021 | Complete | COBRA-SFS: A Thermal Hydraulic Analysis Code for Spent Fuel Storage and Transportation Casks | David J. Richmond | David J. Richmond | None | COBRA_SFS_Manual_V6.0_M3SF-21PN020401052.pdf |  | thermal hydraulic analysis code, spent fuel storage and transportaiton
M3SF-21OR020401016 | M3 | 1.08.02.04.01.01 | ORNL | SF-21OR02040101 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Joseph, Robby | Implement on-the-fly dose analysis methodology in UNF-ST&DARDS | UNF-ST&DARDS on-the-fly dose analysis capability | Implement on-the-fly methodology for as-loaded shielding analysis. This analysis approach will allow quick shielding analysis of a given system by changing loading maps. Initial implementation will include two systems (e.g., HI-STAR 190 + MPC 37 and MPC 89) with the goal to quickly add additional systems in the future. | 2021-03-26 |  | 2021-03-26 | The on-the-fly dose report documents the development of python libraries for the MPC-37 in the HI-STORM FW cask. These libraries can be used to perform dose estimates for casks without having to perform problem dependent radiation transport calculations, saving substantial computational time. | 2021 | Complete | Demonstration of the On-the-Fly Shielding Analysis Method | Georgeta Radulescu | Kaushik Banerjee | None | PB2100368_Radulescu_on-the-fly_REV02_pics.pdf |  | HI-STORM; Dose; On-the-fly
M4SF-21OR020302065 | M4 | 1.08.02.03.02.06 | ORNL | SF-21OR02030206 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Type B Package Incident History | Type B Package Incident History | This milestone report will document past transportation accidents and incidents involving Type B packages of radioactive materials and may include other shipments of interest relevant to the deinventory of nuclear power plants, such as incidents involving large components to and from nuclear power plant sites. | 2021-03-26 |  | 2021-03-26 | The goal of this activity is to create and maintain a centralized complete record of incidents involving the transportation of radioactive materials in Type B quantities within the United States. | 2021 | Complete | A Database of Transportation Incidents Involving Type B Packages | Kevin Connelly | Kevin Connelly | None | M4SF-21OR020302065.pdf |  | Type B package; spent nuclear fuel transport; radioactive materials transport; High level waste (HLW) transport
M3SF-21OR020402105 | M3 | 1.08.02.04.02.10 | ORNL | SF-21OR02040210 | Waste Management System Architecture - NGSAM Model Development and V&V - ORNL | Joseph, Robby | Joseph, Robby | Updated Waste Management System Analysis Simulation Tool Requirements | Updated Waste Management System Analysis Simulation Tool Requirements | Updated Waste Management System Analysis Simulation Tool Requirements | 2021-03-30 |  | 2021-03-30 | M3 milestone M3SF-21OR020402105, entitled “Updated Waste Management System Analysis Simulation Tool Requirements” completed. The requirements document describes the ultimate end-state desired capabilities for NGSAM. The initial requirements added in this update for advanced reactor fuels, reprocessing, treatment, and conditioning are preliminary and high-level in this report, and it is planned that more specific requirements will be provided to the NGSAM team by analysts in the future. This requirements document also adds many specific requirements for modeling DOE-managed waste. | 2021 | Complete | Updated NGSAM Requirements Document |  |  | None | PB2100369_Joseph_WM_Rev1.pdf
M5SF-21IN020201073 | M5 | 1.08.02.02.01.07 | INL | SF-21IN02020107 | Canister SCC Mitigation - INL | Thomas, Dan |  | Draft Functional Requirements for FSW and Cold Spray Equipment | Draft Functional Requirements for DOE Standard Canister FSW Closure and Cold Spray Coating Equipment | Working draft internal report with information on the functional requirements (design envelop, use case, functional specifications, operating limitations, etc.) for FSW and Cold Spray equipment that could be used on DOE Standard Canister in the Fuel Handling Cave of the CPP-603 facility at INTEC. | 2021-03-31 |  | 2021-03-31 | Delivered via email to WP manager. | 2021 | Complete | Friction Stir Welding, Friction Stir Processing, and Cold-Spray Surface Coating Equipment for DOE SNF Packaging Demonstration | Thomas, Daniel Albert | Jarrell, Joshua J | None | FOR-619-0A Draft Functiona Requirement FSW-FSP-CSC Equipment for DOE SNF Packaging Demonstration.pdf
M4SF-21PN020301118 | M4 | 1.08.02.03.01.11 | PNNL | SF-21PN02030111 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Revised Railcar Safety Inspection Protocol | Revised Railcar Safety Inspection Protocol | Prepare revised railcar safety inspection protocol in response to R/R AHWG comments. | 2021-04-30 |  | 2021-04-30 | Inspection reports for inspections conducted by the Federal Railroad Administration (FRA), States, and rail carriers are generally not shared with other States or Tribes, and are often viewed as confidential or proprietary. The lack of sharing of the inspection reports with States or Tribes along transportation routes presents a significant obstacle to inspection reciprocity. This Revised Draft Railcar Safety Inspection Protocol is being developed in coordination with DOE’s National Transportation Stakeholders Forum’s Spent Nuclear Fuel Rail/Routing Ad Hoc Working Group. The Draft Inspection Protocol could be considered for adoption by DOE for future DOE rail shipments of SNF to promote inspection reciprocity among States and Tribes along transportation routes. In order to promote reciprocity, the Draft Inspection Protocol consists of two parts. The first part of the Draft Inspection Protocol consists of inspections to be performed at origin sites, which include nuclear power plant sites, transload locations, and ports. These inspections would be verified, observed, or conducted by a DOE contractor, and the resulting inspection reports would be distributed to States and Tribes along a transportation route used for DOE rail shipments of SNF, potentially through DOE’s Transportation Tracking and Communication System (TRANSCOM). The second part of the Draft Inspection Protocol consists of providing appropriate State and Tribal personnel along transportation routes access to the data feeds from the safety monitoring system required by Association of American Railroads (AAR) Standard S-2043. Determining which personnel would have access to railcar data feeds will likely be part of security protocols for DOE shipments that have yet to be developed. The inspections outlined in this Draft Inspection Protocol are not meant to replace regulatory inspections conducted by the FRA, States, or the rail carriers. Rather, the inspections outlined in this Draft Inspection Protocol and access to the AAR Standard S-2043 data feeds are extra-regulatory and specifically structured to promote inspection reciprocity along DOE rail transportation routes. | 2021 | 90 Day | Revised Draft Railcar Safety Inspection Protocol | Steven Maheras | Steven Maheras | None | M4SF-21PN020301118 20210430_signed.pdf |  | railcar safety inspection protocol; locomotive inspection; freight car inspection; hazardous materials inspection; motive power and equipment inspection
M5SF-21PN020201102 | M5 | 1.08.02.02.01.10 | PNNL | SF-21PN02020110 | Canister SCC Mitigation - PNNL | Howard, Rob |  | Canister SCC Mitigation: Friction Stir Welding and Cold Spray Mid-Year Status | Canister SCC Mitigation: Friction Stir Welding and Cold Spray Mid-Year Status | Status email on progress of R&D for friction stir welding and cold spray techniques for DOE Standard Canister weld SCC mitigation/coating. | 2021-04-30 |  | 2021-04-30 | this work covers evaluation of Friction Stir Welding (FSW) and cold spray coatings as approaches to mitigate potential stress corrosion cracking of spent nuclear fuel storage canisters. | 2021 | 90 Day |  | Ken Ross | Rob Howard | None | PNNL milestone M5SF-21PN020201102 .pdf
M4SF-21IN020402062 | M4 | 1.08.02.04.02.06 | INL | SF-21IN02040206 | Waste Management System Architecture - NGSAM Model Development and V&V - INL | Petersen, Gordon | Howard, Rob | Fy21 NGSAM Model Development and V&V Non-Commercial Report | FY21 NGSAM Model Development V&V Report: Non-Commercial | NGSAM Model Develop and V&V: Non-Commercial | 2021-05-28 |  | 2021-05-28 | Completed the M4 Milestone M4SF-21IN020402062, “Fy21 NGSAM Model Development and V&V Non-Commercial Report,” in the work package SF-21IN02040206, “Waste Management System Architecture- NGSAM Model Development and V&V- INL.” | 2021 | 90 Day | NGSAM Validation and Verification Report: Non-Commercial | Gordon Petersen | Gordon Petersen | None | M4SF-21IN020402062 Fy21 NGSAM Model Development and V&V Non-Commercial Report.docx |  | non-commercial SNF; NGSAM; System Analysis
M5SF-21OR020402123 | M5 | 1.08.02.04.02.12 | ORNL | SF-21OR02040212 | Advanced Fuel Cycle Waste Form Management and Planning - ORNL | Joseph, Robby |  | Requirements for System Level Modeling | Requirements for System Level Modeling | Requirements for System Level Modeling | 2021-05-31 |  | 2021-05-28 | Completed the M5 Milestone entitled ‘Requirements for System Level Modeling' on May 28. | 2021 | Complete | Requirements for System Level Modeling |  |  | None | Spent Fuel Management M5_Rev3.docx
M5SF-21PN020301113 | M5 | 1.08.02.03.01.11 | PNNL | SF-21PN02030111 | Intergovernmental and External Engagement - PNNL | Maheras, Steve |  | Draft 180(c) Summary Report | Draft 180(c) Summary Report | Prepare Draft 180(c) Summary Report | 2021-06-11 |  | 2021-06-10 | This report summarizes activities conducted between 1983 and 2017 by DOE and various DOE-supported working groups to examine implementation of Section 180(c) of the Nuclear Waste Policy Act (NWPA). Objectives of this report include documenting and tracking Section 180(c) implementation issues and their resolution, identifying pivotal work products, summarizing outstanding issues, and providing an overview of legislative proposals that may affect implementation of Section 180(c). After a brief description of Section 180(c) of the NWPA and the main phases of engagement between DOE and DOE-supported working groups in Sections 2 and 3, this report outlines the major activities, issues addressed, and documents produced by the working groups in Section 4 and then provides a brief status of outstanding issues in Section 5. This report concludes with an analysis of proposed legislative actions related to Section 180(c). | 2021 | Complete | Section 180(c) Ad Hoc Working Group Summary Report | Lauren Rodman | Steve Maheras | None | M5SF-21PN020301113_Final_signed.pdf |  | Nuclear Waste Policy Act; NWPA; Section 180(c); training; funding and technical assistance; States; Tribes
M5SF-21OR020303058 | M5 | 1.08.02.03.03.05 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill |  | ISSMS Status Report | ISSMS Status Report | ISSMS status report on phase 2 progress with developing the prototype system design and initial procurement of hardware to support fabrication of prototype system. | 2021-06-18 |  | 2021-06-18 | ISSMS Project Management Plan Rev. 1 | 2021 | Complete | Integrated Security and Safety Monitoring System Project Management Plan Rev. 1 | Bill Reich | Bill Reich | None | M5SF-21OR020303058-ISSMS Status Report-PMP Rev 1-June 18 2021-R6.docx |  | ISSMS; PMP; Atlas railcar
M4SF-21PN020201111 | M4 | 1.08.02.02.01.11 | PNNL | SF-21PN02020111 | Hanford Lead Canister - PNNL | Howard, Rob | Carter, Joe | Hanford Lead Canister Progress Report | Hanford Lead Canister Progress Report | Progress report documenting status of canister heater control system programing and thermal modeling to date. | 2021-06-30 |  | 2021-06-30 | This report describes the progress made on the Hanford Lead Canister (HLC) project through approximately May of 2021. The HLC is a unique collaborative opportunity for conducting research and development (R&D) related to stainless-steel canisters that contain nuclear material in dry storage. | 2021 | Complete | Hanford Lead Canister 2021 Status Report | Nick Klymyshyn | Rob Howard | None | OneDrive_1_7-13-2021.zip
M4SF-21PN020301116 | M4 | 1.08.02.03.01.11 | PNNL | SF-21PN02030111 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Stakeholder Interface Tool Proposal | Proposal for Stakeholder Interface Tools | Develop stakeholder interface tool proposal. | 2021-06-30 |  | 2021-06-30 | The U.S. Department of Energy Office of Integrated Waste Management (DOE-IWM) is planning for future large-scale transport of commercial spent nuclear fuel (SNF) and high-level radioactive waste (HLW) to eventual disposal and/or storage facilities. As part of these activities, DOE-IWM is exploring options for development of stakeholder engagement tools with the objectives of promoting informed public acceptance of a SNF national transportation plan (NTP) and ultimately an integrated waste management (IWM) solution in the United States. This document presents proposed stakeholder engagement tools that DOE-IWM may employ to meet these objectives. | 2021 | Complete | A Proposal for Improving Communications with Stakeholders to Advance a Spent Nuclear Fuel Transportation Plan in the United States | RL Kreuzer | Steve Maheras | None | M4SF-21PN020301116-Draft_Prop_Stakeholder_Engagement-20210630_signed.pdf |  | stakeholder engagement; stakeholder tools; proposal; transportation; communications; spent nuclear fuel (SNF)
M4SF-21PN0203020710 | M4 | 1.08.02.03.02.07 | PNNL | SF-21PN02030207 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Morris Site Evaluation Report | Updated Nuclear Power Plant Infrastructure Evaluation Report | Develop stand-alone Morris site evaluation report. | 2021-06-30 |  | 2021-06-29 | The U.S. Department of Energy Office of Integrated Waste Management (DOE-IWM) conducted an evaluation of removing spent nuclear fuel from the GE-Hitachi Morris Operation Independent Spent Fuel Storage Installation (Morris site). The virtual site evaluation took place June 24, 2020 and included a drone survey of the near-site transportation infrastructure. While the Morris site is a spent fuel storage facility, there are no reactors on the site. The site is owned and operated by GE-Hitachi Corporation located in Grundy County, about 7.5 miles (12 km) east-northeast of the small town of Morris, Illinois, and about 48 miles (77 km) southwest of Chicago. The Des Plaines River and the Kankakee River join to form the Illinois River about 1.2 miles (2 km) northeast of the Morris site. The Morris site has two transportation mode options available: barge access from Dresden Nuclear Power Plant barge area on the Illinois River and rail access from the Illinois River Subdivision rail line to the Dresden rail spur and then to the Morris rail spur. These transportation modes are available; however, refurbishment will be required, particularly in the case of the Morris rail spur, which has been cut-off from the site due to it being paved over at East Collins Road. Vegetation will need to be cleared, and the state of the tracks and rail bed will need to be confirmed. Paved and unpaved roads that would be used to facilitate barge shipments appears to be in good order. In the future, on-site inspection of the drone survey routes is recommended to confirm and enhance the drone survey findings because inspections of rails, track hardware, railroad ties, roadway pavement, vegetation/overgrowth, overhead surveys for wires and utilities along with other details cannot be determined with a great degree of accuracy from aerial photography. Roads that would be used to facilitate barge transport via heavy-haul trucks appear level and also appear to provide adequate clearance, however; this would have to be confirmed. It is also recommended that the barge area be surveyed to confirm substructure conditions at the barge area for items such as wood pilings, wood planking, seawalls, seawall tie backs, seawall hardware etc. The waterway directly adjacent to the barge area could require a marine survey to confirm adequate draft is available for a barge to dock. Siltation that may have occurred over the years in this area which may require dredging. | 2021 | Complete | Morris Operation Independent Spent Fuel Storage Installation Virtual Site Infrastructure Evaluation | Steve Maheras | Steve Maheras | None | M4SF-21PN0203020710 - Morris Virtual Site Evaluation 20210629_signed.pdf |  | Morris; site evaluation; drone survey; virtual; near-site transportation infrastructure; spent nuclear fuel (SNF)
M4SF-21AN020402021 | M4 | 1.08.02.04.02.02 | ANL | SF-21AN02040202 | Waste Management System Architecture - NGSAM Model Development and V&V - ANL | Feng, Bo | Joseph, Robby | Identification of Generic Activities/Milestones for Deploying Advanced Reactor SNF Management Facilities, | Generic Activities/Milestones for Deploying Advanced Reactor SNF Management Facilities, | Identify generic activities and milestones for deploying Advanced Reactor SNF Management Facilities. This may include a generic milestone dictionary and logic diagrams linking generic activities and milestones. | 2021-06-30 |  | 2021-06-29 | Submitted M4 milestone report titled, "Generic Activities and Milestones for Deploying Advanced Reactor Spent Fuel Management Facilities". Based on previous experience with LWR SNF and incorporating new considerations for advanced reactor fuel types, this report proposes a generic set of facilities necessary to manage any type of SNF and a generic set of high-level milestones and activities required for the deployment of these facilities. | 2021 | Complete | Generic Activities and Milestones for Deploying Advanced Reactor Spent Fuel Management Facilities | Milos Atz | Bo Feng | None | M4-Milestones for SF Facilities - ANL 2021.pdf
M4SF-21OR020402104 | M4 | 1.08.02.04.02.10 | ORNL | SF-21OR02040210 | Waste Management System Architecture - NGSAM Model Development and V&V - ORNL | Joseph, Robby | Joseph, Robby | Data and Information Needs for Advanced Reactor SNF Simulation | Data and Information Needs for Advanced Reactor SNF Simulation | Identify data and information needed for the integrated system level analysis of advanced reactor SNF. | 2021-06-30 |  | 2021-06-30 | Completed the M4 milestone M4SF-21OR020402104, entitled “Data and Information Needs for Advanced Reactor SNF Simulation.” The purpose of this document (attached to this email) is to provide a preliminary identification of data and information needed for the integrated system level analysis of advanced reactor wastes. The Next Generation System Analysis Model (NGSAM) requirements document was recently updated to add the initial requirements for reprocessing, treatment, and conditioning of advanced reactor fuels. These initial requirements are preliminary and are described at a high level: analysts will provide more specific requirements to the NGSAM team in the future. Likewise, analysts will provide more specific data as they become available and will refine data needs as model development proceeds. | 2021 | Complete | Data and Information Needs for Advanced Reactor SNF Simulation |  |  | None | PB2100784_Joseph_DataInfo_Rev2.pdf
M2FT-13ID0911032 Found doc in CURIE - couldn't find on Matt's list. Lac | M2 | None | DOE-ID | None | None | None | None | None | None | None | [7 empty] | North Wind Services, LLC | None |  |  | None
M3FT-13PN0912023 Final report shows M2FT-13PN0912022 | M3 | 1.02.09.12.02 | PNNL | FT-13PN091202 | TR Operational - Shutdown Sites - PNNL | Maheras, Steve | Wagner, John | Plan for removing stranded fuel from shutdown sites - Prepare L2 DRAFT report | Stranded Sites De-inventorying DRAFT Report | This activity requires interaction between ORNL, PNNL, SNL, and SRNL. All laboratories shall contribute to the DRAFT report. | 2013-08-30 10:00 |  | 2013-08-28 09:00 |  | 2013 | Complete |  | Steven Maheras | Steven Maheras | None | FCRD-NFST-2013-000238_M3.pdf FCRD-NFST-2013-000238_M3_Cover_Sheet.pdf | FCRD-NFST-2013-000238
M3FT-13SN0905013 | M3 | 1.02.09.05.01 | SNL | FT-13SN090501 | CX Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Wagner, John | Preliminary Draft of Analysis of Public and State Preferences Related to Consent Based Siting of Radioactive Waste Management Facilities for Storage and Disposal | Analysis of Public and State Preferences Related to Consent Based Siting of Radioactive Waste Management Facilities for Storage and Disposal preliminary draft for M2FT-13SN0905011 | Preliminary Draft of Analysis of Public and State Preferences Related to Consent Based Siting of Radioactive Waste Management Facilities for Storage and Disposal | 2013-01-03 04:00 |  | 2013-01-03 02:00 |  | 2013 | Complete |  | Rechard, Rob | Rechard, Rob | None | Public Preferences Related to Consent Based Siting 2012 M3 Report.docx | FCRD-NFST-2013-000076
M3FT-13SN0905025 same as M3FT-12SN0814105 | M3 | 1.02.09.05.02 | SNL | FT-13SN090502 | Siting Experience Database - SNL | Price, Laura | Wagner, John | Provide a report describing the archive, its content, and its use | US Nuclear Facility Siting Experience Archive | Produce a report describing the archive, its content, and how it is used. The report will include a short synopsis of each facility for which documentation has been obtained and a summary of the siting information identified in the data base. | 41362.3333 |  | 41362.125 |  | 2013 | Complete |  | Price, Laura | Price, Laura | None | Siting _Experience_Database_Final_Report_Rev01_w_cover_sheet.pdf | FCRD-NFST-2013-000109
M3FT-13SN0912052 | M3 | 1.02.09.12.05 | SNL | FT-13SN091205 | RADTRAN Capability Development and Maintenance - SNL | Weiner, Ruth | Feldman, Matt | Verification Document and User Guide for the Occupational Dose Model | Verification of RADTRAN 6.1; RADCAT User Guide Rev. 2. | Amended user guide and documentation | 2013-09-13 02:00 |  | 2013-10-01 04:00 | The milestone is complete | 2013 | 90 Day |  | Weiner, Ruth | Weiner, Ruth | None | RadCat 6.0 User Guide Rev 2.pdf | FCRD-NFST-2013-000320
M3FT-13SR0908051 | M3 | 1.02.09.08.05 | SRNL | FT-13SR090805 | Technical Support for Storage Design Concepts Evaluation - SRNL | Smith, Pat | Wagner, John | Complete a Pilot Project Conceptual Plan | Complete a Pilot Project Conceptual Plan | Complete a Pilot Project Conceptual Plan and signoff on document. | 2013-03-29 |  | 2013-03-28 |  | 2013 | Complete |  | Carter, Joe | Carter, Joe | None | NFST Design Concepts 3-28-13 Final.pdf |  | Project Concept
M2FT-14OR0904022 | M2 | 1.02.09.04.02 | ORNL | FT-14OR090402 | Standardization Assessment - ORNL | Jarrell, Josh | Nutt, Mark | Complete Preliminary Standardization Assessment | Complete Preliminary Standardization Assessment | Complete preliminary quantitative evaluation of transitioning to standardized canisters. This preliminary assessment is intended to document the status of the assessment, including preliminary findings, but is expected to be limited in terms of the completeness of the assessment due to time allowed to complete it and the available systems analysis capabilities and accuracy of require data. | 2014-08-29 06:00 |  | 2014-08-29 |  | 2014 | Complete | Initial Standardized Canister System Evaluation | Jarrell, Josh | Jarrell, Josh | None | Preliminary_Standardization_Assessment_M2_2014-08-29_final_new_format.pdf | FCRD-NFST-2014-000084
M2FT-14SN0909011 | M2 | 1.02.09.09.01 | SNL | FT-14SN090901 | Perspectives on Nuclear Waste Management - SNL | Rechard, Rob | Nutt, Mark | Insights from Public Perference Surveys Related to Transportation and Siting of Nuclear Waste Facilities | Insights on Conducting Consent-Based Siting of Radioactive Waste Management Facilities | Updated Report Providing Insights from Public Preference Surveys Related to Transportation and Siting of Nuclear Waste Facilities | 2014-09-30 22:00 |  | 2014-09-30 02:00 | Report on insight from public preference surveys related transportation and siting of nuclear waste facilities completed | 2014 | Complete | Insights on Conducting Consent-Based Siting of Radioactive Waste Management Facilities: Evidence from a Nationwide Survey of US Residents | Jenkins-Smith, Hank | Rechard, Rob | None | EE Survey Analysis Summary 10-29-14.docx | FCRD-NFST-2014-000087 | Public Preference Survey, Consent-Based Siting, Consolidated Interim Storage, Radioactive Waste Management
M3FT-14SN0912048 | M3 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Weiner, Ruth | Feldman, Matt | Complete RADTRAN Technical Manual | RADTRAN Technical Manual | Complete the RADTRAN Technical Manual | 2013-12-04 10:00 | 2013-12-18 02:00 | 2013-12-23 02:00 |  | 2014 | Completed Late | RADTRAN 6 Technical Manual |  |  | None | RT6MANUAL_2013.docx | FCRD-NFST-2014-000376 | RADTRAN, risk, transportation
M3FT-14SR0905022 | M3 | 1.02.09.05.02 | SRNL | FT-14SR090502 | Characterization and Assessment - SRNL | Smith, Pat | Nutt, Mark | NFST Inventory Report Revision 1 | NFST Inventory Report Revision 1 | Report sumbitted to the NTD and NFST Director. | 2014-03-31 |  | 2014-03-31 |  | 2014 | Complete | Nuclear Fuels Storage and Transportation Planning Project Inventory Basis, Revision 1 | Carter, Joe | Carter, Joe | OUO |  | FCRD-NFST-2013-000263 | NFST Inventory Report
M4FT-14SN0902071 | M4 | 1.02.09.02.07 | SNL | FT-14SN090207 | Waste Management System Architecture Analysis - SNL | Kalinina, Elena | Nutt, Mark | TSL V&V | TSL V&V Report | V&V of modifications to TSL | 2014-07-31 03:00 | 2014-09-30 04:00 | 2014-09-30 02:00 | TSL-CALVIn verification and validation report. | 2014 | Completed Late | TSL-CALVIN Software Verification and Validation | Elena Kalinina | Elena Kalinina | None |  | FCRD-NFST-2014-000533 | software verification and validation
M4FT-14SN0904032 | M4 | 1.02.09.04.03 | SNL | FT-14SN090403 | Standardization Assessment - SNL | Hardin, Ernest | Nutt, Mark | Materials for Consideration in Standardized Canister Design Activities | Letter report: Materials for Consideration in Standardized Canister Design Activities | Establish postclosure functional and operational requirements for key materials, and narrow the range of candidate materials that can potentially meet these requirements, for application across a range of disposal environments. Provide a review of pertinent literature data on material corrosion. Identify key uncertainties and data needs for use in planning follow-on activities. Describe in broad terms a future laboratory testing program for candidate materials that could address data needs and reduction of uncertainty. | 2014-09-19 02:00 | 2014-10-03 02:00 | 2014-10-03 06:00 | Deliverable completed in accordance with forecasted delay due to competing staff assignments. | 2014 | Expected Late | Materials for Consideration in Standardized Canister Design Activities | Charles Bryan | Charles Bryan | None | Standardized canister materials report Final.pdf
M4FT-14SN0912046 | M3 | 1.02.09.12.04 | SNL | FT-14SN091204 | TR: Operational - SNL | Durbin, Sam | Feldman, Matt | Final Report on Assessment of a Severe Accident Full-scale Rail Cask Test | Final Report: Severe Accident Full-scale Rail Cask Test Assessment | This final report will provide recommendations for moving forward with planning for a severe accident full-scale rail cask test. | 2014-09-19 12:00 |  | 2014-09-18 02:00 | Submittal of deliverable. | 2014 | Complete | Full-Scale Accident Testing in Supoort of Spent Nuclear Fuel Transportation | Durbin, Sam | Sorenson, Ken | None | Full-Scale Testing Supporting Transportation PPS 11-04-14.pdf | FCRD-NFST-2014-000375
M2FT-15OR0904022 | M2 | 1.02.09.04.02 | ORNL | FT-15OR090402 | CX: Standardization and Integration - ORNL | Jarrell, Josh | Jarrell, Josh | STAD Performance Specification Requirements Rationale | STAD Performance Specification Requirements Rationale | Develop and document technical rationale and bases for the requirements in the current version of the Performance Specification for Small and Medium Standardized Transportation, Aging, and Disposal Canister Systems FCRD-NFST-2014-000579 | 2015-04-30 03:00 |  | 2015-04-30 |  | 2015 | Complete | Rationale for the Performance Specification for Standardized Transportation, Aging, and Disposal Canister Systems | Howard, Rob | Howard, Rob | None | STAD Perf Spec Rationale_FINAL.pdf | FCRD-NFST-2015-000106
M2FT-15OR0913016 | M2 | 1.02.09.13.01 | ORNL | FT-15OR091301 | TR: Hardware - ORNL | Feldman, Matt | Feldman, Matt | Railcar Design Report | Railcar Design Report | Report that details the conceptual design(s) of the cask and buffer cars, how to load and attach the rail casks to the cask car, and ROM cost and schedule estimates. | 2015-09-30 02:00 |  | 2015-09-23 | This report documents progress on the contract for development of railcars to transport high level radioactive material (HLRM). Because the design contract was only recently awarded, this report focuses primarily on the significant effort expended to prepare for and award the design contract. As described in this report, a significant effort was expended over 18 months (March 2014 to August 2015) to prepare a combined sources sought notice and request for information, an acquisition plan, a pre-solicitation notice, and a request for proposals that resulted in DOE awarding a contract on August 21, 2015 for the design, associated analysis, and prototype fabrication of cask and buffer railcars. | 2015 | Complete | ATLAS Railcar Design Project Status Report | Reich, Bill | Feldman, Matt | None | M2FT-15OR0913016-Railcar Design Report-Final.pdf | FCRD-NFST-2015-000799 | transportation, railcar, cask railcar, hardware
M3FT-15PN0912038 | M3 | 1.02.09.12.03 | PNNL | FT-15PN091203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Revised Final Shutdown Sites Report | Revised Final Shutdown Sites Report | Revised shutdown sites final report. | 2015-09-18 03:00 |  | 2015-09-18 06:00 | This report is a M3 final report. Changes from Revision 2 (October 2014) of the report include adding the recently shut down Vermont Yankee site to the report; updating of Google Earth imagery; incorporating revisions to transportation certificates of compliance; revising the estimated number of canisters stored at the Crystal River and San Onofre sites; and adding information obtained from site visits to Kewaunee, Crystal River, and San Onofre. | 2015 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Steve Maheras | Steve Maheras | None | FCRD-NFST-2015-000498_M3_096_red_signed.pdf | FCRD-NFST-2015-000498 | Used nuclear fuel, shutdown sites, spent fuel inventory, on-site infrastructure, near-site transportation infrastructure
M3FT-15SR0905032 | M3 | 1.02.09.05.03 | SRNL | FT-15SR090503 | CX: Characterization and Assessment - SRNL | Carter, Joe | Jarrell, Josh | Cask Inventory Assessment | Dry Storage Cask Inventory Assessment, Rev 1 | SRNL will update the NFST Cask Inventory Report based upon the the most recent NFST inventory report including the new GC-859 | 2015-08-31 03:00 |  | 2015-08-26 |  | 2015 | Complete | Dry Storage Cask Inventory Assessment, Revision 1 | Robert Jones | Robert Jones | None | FCRD-NFST-2014-000602 Dry Storage Cask Inventory Assessment DRAFT Rev 1 - Final.pdf QA Cover Sheet - Dry Storage Cask Inventory Assessment.pdf | FCRD-NFST-2015-000537 | Dry Storage Cask Inventory
M3FT-15SR0906023 | M3 | 1.02.09.06.02 | SRNL | FT-15SR090602 | Regulatory - SRNL | Carter, Joe | Carter, Joe | Storage Cask License Review | Storage Cask License Review | Review Storage Cask licenses to summarize license conditions and parameters for their use at an ISF | 2015-03-31 03:00 | 2015-04-30 | 2015-04-30 |  | 2015 | Completed Late | Summary of Design Criteria for Dry Cask Storage of Shutdown Commercial Plant Fuel | Brian Gutherman | Brian Gutherman | None | Storage Cask License Review Summary of Design Criteria for Dry Cask Storage.pdf | FCRD-NFST-2015-000538 | Storage Cask License
M4FT-15SN0902083 | M4 | 1.02.09.02.08 | SNL | FT-15SN090208 | Waste Management System Architecture Analysis - SNL | Kalinina, Elena | Jarrell, Josh | TSL Validation and Verification | Validation and Verification Report | Continue the validation and verification of the TSL-CALVIN starting from the draft V&V report from FY14. Perform validation and verification of TSL-TOM. | 2015-04-01 14:00 | 2015-09-28 02:00 | 2015-09-30 02:00 | V&V evaluated the latest revisions of Calvin and Tom released at the end of August 2015. | 2015 | Completed Late | TSL-Calvin and TSL-TOM Software Validation and Verification | Elena Kalinina | Elena Kalinina | None |  | FCRD-NFST-2015-000721 | Software validation and verification, transportation and storage logistics model, thermal emplacement limit, interim storage, geologic repository. waste package
M4FT-15SN0904033 | M4 | 1.02.09.04.03 | SNL | FT-15SN090403 | CX: Standardization and Integration - SNL | Hardin, Ernest | Howard, Rob | Draft Geologic Disposal Requirements Basis for STAD Specification | Letter Report on Geologic Disposal Requirements Basis for STAD Specification | Develop technical requirements bases information for STAD canister performance specifications related to geologic disposal. | 2015-03-20 17:00 |  | 2015-03-25 02:00 |  | 2015 | Completed Late | Draft Geologic Disposal Requirements Basis for STAD Specification | Ilgen,Anastasia | Hardin,Ernest | None | FCRD-NFST-2013-000723 Geologic disposal draft requirements basis (Final).pdf | FCRD-NFST-2015-000723 | radioactive waste; storage; transportation; disposal; canister; requirements
M2FT-16OR090401051 | M2 | 1.02.09.04.01.05 | ORNL | FT-16OR09040105 | TR: Institutional - ORNL | Feldman, Matt | Feldman, Matt | 180(c) Implementation Exercise Final Report | 180(c) Implementation Exercise Final Report | Report that details the 180(c) Policy Implementation Exercise, including feedback obtained and proposed path forward to develop final Section 180(c) policy statement. | 2016-08-30 02:00 |  | 2016-08-26 |  | 2016 | Complete | Section 180(c) Exercise Final Report | Helvey, Elizabeth | Feldman, Matt | None | M2FT-16OR090401051.pdf | FCRD-NFST-2016-000094 | NWPA, transportation, institutional, policy, exercise, 180(c), Section 180(c)
M2FT-16OR090402022 | M2 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site 4 Implementation Plan | Site 4 Implementation Plan | Selected vendor will submit an Initial Site-Specific De-Inventory Implementation Plan for a site TBD. | 2016-09-30 |  | 2016-09-30 | Level 2 milestone M2FT-16OR090402022, Site 4 Implementation Plan (work package FT-16OR09040202 TR: Operational – ORNL, WBS #1.02.09.04.02) was completed and uploaded to PICs:NE. This report provides a detailed overview of the process necessary to de-inventory spent fuel and GTCC from the Maine Yankee site. The report includes discussion of site information, transportation route analysis, participating entities, multi-attribute utility analysis, concept of operations for the recommended approach, budget and spending plan of the recommended approach, safety and security plan procedures, emergency response and preparedness, and recommended next steps. The report was developed by AREVA Federal Services under contract to Oak Ridge National Laboratory. | 2016 | Complete | Maine Yankee De-Inventory Study, RPT-3016127-000 | AREVA | Feldman, Matt | None | MY combined files-signed.pdf | FCRD-NFST-2016-000095 | De-Inventory, Maine Yankee, MUA, MY
M2FT-16OR090402023 Rev 0 is ULR Rev 2 is Public | M2 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Site 5 Implementation Plan | Site 5 Implementation Plan | Selected vendor will submit an Initial Site-Specific De-Inventory Implementation Plan for a site TBD. | 2016-09-30 |  | 2016-09-30 | Level 2 milestone M2FT-16OR090402023 Site 5 Implementation Plan (work package FT-16OR09040202 TR: Operational – ORNL, WBS #1.02.09.04.02) was completed and uploaded to PICs:NE. This report provides a detailed overview of the process necessary to de-inventory spent fuel and GTCC from the Trojan site. The report includes discussion of site information, transportation route analysis, participating entities, multi-attribute utility analysis, concept of operations for the recommended approach, budget and spending plan of the recommended approach, safety and security plan procedures, emergency response and preparedness, and recommended next steps. The report was developed by AREVA Federal Services under contract to Oak Ridge National Laboratory. | 2016 | Complete | Trojan De-Inventory Study | AREVA | Feldman, Matt | None | Trojan combined files-signed.pdf | FCRD-NFST-2016-000096 | De-Inventory, Trojan, MUA
M3FT-16OR090402028 | M3 | 1.02.09.04.02.02 | ORNL | FT-16OR09040202 | TR: Operational - ORNL | Feldman, Matt | Feldman, Matt | Safety Record of SNF Shipments | Report on the Safety of Past SNF Shipments | Report documenting the safety record of SNF Shipments to date | 2016-06-24 |  | 2016-06-24 |  | 2016 | Complete | A Historical Review of the Safe Transport of Spent Nuclear Fuel | Kevin Connolly | Matt Feldman | None | M3FT-16OR090402028.pdf | FCRD-NFST-2016-000474 | transportation, risk assessment, history, statistics, shipments, SNF, HLW
M3FT-16PN0904020314 | M3 | 1.02.09.04.02.03 | PNNL | FT-16PN09040203 | TR: Operational - PNNL | Maheras, Steve | Feldman, Matt | Shutdown Sites Activities and Final Shutdown Sites Report | Final Shutdown Sites Report | Continue to develop knowledge base related to shutdown sites to allow for the eventual removal of used fuel and GTCC from these sites. Submit final shutdown sites report. | 2016-09-23 04:00 |  | 2016-09-21 06:00 | This report is an M3 report that updates the FY2015 Shutdown Sites Report. Changes from Revision 3 (September 2015) of the shutdown sites report include incorporating spent nuclear fuel data from the GC-859 database; updating of Google Earth imagery; incorporating revisions to transportation certificates of compliance; adding information obtained from site visits to the Pacific Sun Railroad and Camp Pendleton, California; adding rail assessments for Kewaunee, Crystal River, and San Onofre to Appendix B; and adding information obtained from the site visit to Vermont Yankee. It should be noted that SNF data from Vermont Yankee has not been received yet, so these data have not been revised. | 2016 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Steve Maheras | Steve Maheras | None | FCRD-NFST-2016-000478_M3_signed.pdf | FCRD-NFST-2016-000478 | Shutdown sites, SNF, UNF, GTCC, transportation, logistics, near site transportation infrastructure, transportation infrastructure
M3FT-16SR090105032 | M3 | 1.02.09.01.05.03 | SRNL | FT-16SR09010503 | Characterization and Assessment - SRNL | Carter, Joe | Jarrell, Josh | Cask Inventory Assessment | Dry Storage Cask Inventory Assessment, Rev. 3 | SRNL will update the NFST Cask Inventory Report based upon the most recent NFST Inventory report. | 2016-08-31 02:00 |  | 2016-08-22 |  | 2016 | Complete | Dry Storage Cask Inventory Assessment | Robert H. Jones, | Robert H. Jones | None | FCRD-NFST-2014-000602 Rev. 2 Dry Storage Cask Inventory Assessment.pdf QA Cover Sheet - FCRD-NFST-2014-000602 Rev. 2 Dry Storage Cask Inventory Assessment.pdf | FCRD-NFST-2016-000459 | Dry Storage Cask
M5FT-16OR090105013 | M5 | 1.02.09.01.04.01 | ORNL | FT-16OR09010401 | Standardization and Integration - ORNL | Jarrell, Josh | None | Integrated UNF-ST&DARDS users and developers manual | Integrated UNF-ST&DARDS users and developers manual | Development of integrated UNF-ST&DARDS users and developers manual with version control and available in various format including HTML, PDF, and LATEX | 2016-03-18 02:00 |  | 2016-03-18 |  | 2016 | Complete | UNF-ST&DARDS Documentation | Kaushik Banerjee | Scaglione, John | None | UNF-STDARDS.pdf | FCRD-NFST-2016-000708 | UNF-ST&DARDS, manual
M2SF-17AN020101011 M2SF-17OR020101021 was uploaded to Deliverable Form M2SF-17AN020101011. | M2 | 1.08.02.01.01.01 | ANL | SF-17AN02010101 | Siting Process Design - ANL (CLOSED) | Saraeva, Natalia | Howard, Rob | Finalize “Designing a Consent Based Siting Process: Summary of Public Input” document" | Designing a Consent Based Siting Process: Summary of Public Input” document (M2) | Update “Designing a Consent Based Siting Process: Summary of Public Input” document based on comments received during 45 day public review period. | 2016-12-15 |  | 2016-12-15 |  | 2017 | Complete | DESIGNING A CONSENT-BASED SITING PROCESS: SUMMARY OF PUBLIC INPUT REPORT. Final Draft | Reim, Mike | Saraeva, Natalia | None | Summary of Public Input Report FINAL no formatting 12-15-16.docx | SFWD-IWM-2017-000018 | consent based siting, nuclear waste management, trust, fairness, opennes
M2SF-17AN020403081 includes M4FT-15AN0902046 | M2 | 1.08.02.04.03.08 | ANL | SF-17AN02040308 | NGSAM Development and Application - ANL | St. Aubin, Jim | Jarrell, Josh | Deploy NGSAM Version 2.2.2.0 | Deploy NGSAM Version 2.2.2.0 | This deliverable will be satisfied by the delivery of NGSAM Version 2.2.2.0 tool to the sponsor. The new NGSAM version will provide additional capabilities such as improved ISF logic as well as thermal blending and repackaging capabilities. | 2017-05-16 11:00 |  | 2017-05-16 06:00 |  | 2017 | Complete | Deploy/Release of NGSAM Version 2.2.2.0 software with supporting documentation |  |  | None | NGSAM 2.2.2.0 Letter to Melissa 16-May-2017 with signature.pdf NGSAM Version 2.2.2.0 Release Notes 15May2017.docx NGSAM_UserGuide NGSAM 2.2.1.0 27Apr17.docx | SFWD-IWM-2017-000028
M2SF-17PN020302031 | M2 | 1.08.02.03.02.03 | PNNL | SF-17PN02030203 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | Revised Shutdown Sites Evaluation | Revised Shutdown Sites Evaluation | Continue to develop knowledge base related to shutdown sites to allow for the eventual removal of spent nuclear fuel and GTCC from these sites. Submit revised shutdown sites report. | 2017-08-18 |  | 2017-08-17 03:00 |  | 2017 | Complete | Preliminary Evaluation of Removing Used Nuclear Fuel from Shutdown Sites | Maheras, Steve | Maheras, Steve | None | SFWD-IWM-2017-000024 M2.pdf | SFWD-IWM-2017-000024 | Shutdown sites, SNF, UNF, GTCC, transportation, logistics, near site transportation infrastructure, transportation infrastructure
M4SF-17SN020501052 | M4 | 1.08.02.05.01.05 | SNL | SF-17SN02050105 | Systematic Studies Involving Canisters - SNL | Hardin, Ernest | Nutt, Mark | Report: Generic Salt Repository Concept for CSNF in 21-PWR Size Canisters | Generic Salt Repository Concept for CSNF in 21-PWR Size Canisters | Develop a detailed design concept for a generic salt repository that accepts 21-PWR canisters as the canister portion of the waste package. Include major facilities and operations necessary to emplace the waste packages (e.g., ramps, hoists, shielding, etc.) as well as the waste package materials and thicknesses. | 2017-09-29 04:00 |  | 2017-09-28 02:00 | The report describes waste packaging, surface facilities, repository layout, and construction sequence, with analysis of thermal management, shielding requirements, postclosure criticality, inadvertent human intrusion, waste package longevity, salt creep, mechanical loading of overpacks by salt creep, logistics of CSNF cooling, shaft hoist design, and ROM cost. | 2017 | Complete | Generic Salt Repository Concept for CSNF in 21-PWR Size Canisters | Hardin, Ernest | Hardin, Ernest | None | SFWD-IWM-2017-000246 R2 Salt 21-PWR CSNF Repository final.pdf | SFWD-IWM-2017-000246 | geologic disposal; salt repository; spent nuclear fuel
M3SF-18ID0203030414 | M3 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) | CLIN Completion Letter: CLIN 2 | CLIN 3 Event Final: Completion of CLIN 3 (Phase 3) | 2019-05-20 |  |  |  | 2018 | On Schedule |  |  |  | None
M3SF-18IN020409014 | M3 | 1.08.02.04.09.01 | INL | SF-18IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Multi-year Project Plan | Multi-year Project Plan | Report to lay out multi-year (nominally 3 year) plan for what is required to prepared DOE-managed fuel for transportation. Information in this report will include objective, scope, system concept, and multi-year goals of this activity. Specific out-year deliverables include: (1) evaluate the DOE standard canister for applicability to the current complex needs for storage, transportation, and disposal, (2) evaluate the facilities needed to move DOE-managed spent fuel into the DOE standard canister, (3) determine the most appropriate storage configuration for spent fuel, and (4) develop a transportation application to the NRC to allow spent fuel to be packaged in a truly road-ready configuration. | 2018-09-30 |  | 2018-09-27 02:00 | Deliverable provided via email to DOE. | 2018 | Complete | Multi-Year Plan to Prepare DOE-Managed Spent Fuel for Transportation | Josh Jarrell | Josh Jarrell | None | 2018-09_Standard-Canister-Path-Forward_final.pdf
M4SF-18ID020303043 Supersedes M4SF-17ID0203030511 Per Matt Brainard: Narrative: “Atlas Phase 2 Final Report. This completes the preliminary designs of the Atlas and Buffer railcars. It includes detailed drawings, calculations, and modeling results. These designs will be fabricated and tested. The designs will be modified only as much as necessary to pass the testing program.” | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 2 Event 5: Phase 2 Report including Conceptual Design Information for Simulated Cradle & Cask Test Loads | Phase 2 Report including Conceptual Design Information for Simulated Cradle & Cask Test Loads | CLIN 2 Event 5: Phase 2 Report including Conceptual Design Information for Simulated Cradle & Cask Test Loads | 2018-03-20 |  | 2018-03-07 |  | 2018 | Complete | Atlas Phase 2 Final Report | Orano | Schwab | None | FS-18-0051 ATLAS RAILCAR Phase 2 Final Report Rev 1.pdf |  | Railcar design, cask car, buffer car, Atlas
M4SF-18ID020303044 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 1: Material Procurement Complete | Material Procurement Report | CLIN 3 Event 1: Material Procurement Complete | 2018-02-28 |  | 2018-01-02 |  | 2018 | Complete | Submission of Completed Kasgro Purchase Orders | Mark Denton | Pat Schwab | None | AFS-17-0211R1 Submission of Completed Kasgro POs.docx |  | Railcar, Atlas, cask car, buffer car
M4SF-18ID020303046 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 3: Railcar Fabrication Mobilization & Setup Complete | Railcar Fabrication Mobilization & Setup | CLIN 3 Event 3: Railcar Fabrication Mobilization & Setup Complete | 2018-02-28 |  | 2018-01-02 |  | 2018 | Complete | Submission of Completed Atlas Project FCRR Checklist | Mark Denton | Pat Schwab | None | AFS-17-0193 FCRR Checklist.pdf |  | railcar, Atlas, buffer car, cask car
M4SF-18ID020303048 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-18ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 2 Event 4: Railcar Document Package and Fabrication Estimate Complete | CLIN 2 Event 4: Railcar Document Package and Fabrication Estimate | CLIN 2 Event 4: Railcar Document Package and Fabrication Estimate Complete | 2018-03-20 |  | 2018-03-07 |  | 2018 | Complete | Atlas Cask and Buffer Railcars Preliminary Design Packages | Orano (formerly Areva) Fed Services | Schwab | None | AFS-18-0027 Atlas Project CLIN 2 Event 4 Revised Submittal.pdf CALC-3018954-001.pdf |  | Railcar design, cask car, buffer car, Atlas
M4SF-19ID020303045 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-19ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 8: Prototype Railcars Delivered | Prototype Railcars Delivery Receipt | CLIN 3 Event 8: Prototype Railcars Delivered | 2019-04-20 | 2019-05-15 | 2019-05-19 | The Phase 3 Final Report was received and approved on May 19, 2019. | 2019 | Complete | Atlas Railcar Phase 3 Final Report |  |  | None | FS-19-0116 Phase 3 Report Rev 0.pdf
M3SF-19IN020409015 | M3 | 1.08.02.04.09.01 | INL | SF-19IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Evaluation of neutron absorbers for ATR fuel in the DOE standardized canister | Evaluation of neutron absorbers in the DOE standardized canister | Report documenting comparison of neutron absorbers for the standardized canister. | 2019-04-19 |  |  | On Schedule | 2019 | 90 Day |  |  |  | None
M4SF-19ID020303044 | M4 | 1.08.02.03.03.04 | DOE-ID | SF-19ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 7: Prototype Railcars Accepted | Prototype Railcars Accepted Report | CLIN 3 Event 7: Prototype Railcars Accepted | 2019-03-29 | 2019-04-30 | 2019-04-24 | Railcars have finished fabrication and they are en route to the test site. | 2019 | 90 Day | Delivery of Atlas and Buffer Railcars |  |  | None | FS-19-0110 Delivery of Atlas and Buffer Railcars.pdf
M4SF-19OR020403012 | M4 | 1.08.02.04.03.01 | ORNL | SF-19OR02040301 | Standardization and Integration - ORNL | Howard, Rob | Howard, Rob | Near-term Generic Large STAD Canister Concept Study Report | STAD Canister System Concept Status Report | This report documents the results of the study as outlined in the scope of work | 2019-04-26 | 2019-06-28 | 2019-06-27 | This study considers a near-term, large-capacity (21–pressurized water reactor [PWR] or 44–boiling water reactor [BWR] assemblies) generic standardized transportation, aging, and disposal (STAD) canister concept for commercial spent nuclear fuel (CSNF). A generic STAD canister would have the potential to support disposal of CSNF in various geologic media and could also potentially support CSNF storage at a generic consolidated interim storage facility. | 2019 | Complete | TAD+ Canister Concept Study Report, Rev. A (DRAFT) | James Blink | Rob Howard | None | TAD+_Canister Concept-RevA(draft)-Final_27Jun2019.pdf |  | Standardization, STAD, TAD
M4SF-19IN020409012 Supersedes M3SF-18IN020409016. | M4 | 1.08.02.04.09.01 | INL | SF-19IN02040901 | DOE Managed SNF for Transport - INL | Jarrell, Josh | Jarrell, Josh | Evaluation of CPP-603 for handling, loading, and drying ATR fuel in a standardized canister | Evaluation of CPP-603 for handling, loading, and drying ATR fuel in a standardized canister | The evaluation looks at the equipment and operations necessary to load United States Department of Energy (DOE)-owned Spent Nuclear Fuel (SNF) into DOE SNF Standardized Canisters in the CPP-603 Irradiated Fuel Storage Facility (IFSF) in the Idaho Nuclear Technology and Engineering Center (INTEC) area at Idaho National Laboratory (INL). Two types of fuels are looked at in the evaluation: Advanced Test Reactor (ATR) fuel (uranium-aluminide fuel with aluminum cladding) and Peach Bottom fuel (thorium-uranium carbide fuel in a graphite matrix). The ATR fuel ready for loading would come from fuel storage canisters in the CPP-603 facility, while the Peach Bottom fuel ready for loading could come from either fuel storage canisters in the CPP-603 facility and or containers in the CPP-749 Underground Fuel Storage Facility (UFSF) – Generation I Vaults. The evaluations describe the facility, the fuel types, the DOE SNF Standardized Canisters, and existing equipment; lists the needed loading operations; reviews facility features and equipment to perform the operations; and then lists the decisions, analyses, designs, demonstrations, and modifications that will be needed to perform the loading of DOE-owned SNF into DOE SNF Standardized Canisters in the CPP-603 IFSF. | 2019-09-02 |  | 2019-08-29 | Completed on schedule | 2019 | Complete | Preliminary Evaluation of Loading DOE Standardized Canisters in the CPP-603 Irradiated Fuel Storage Facility | Dan Thomas | Dan Thomas | None | INL-19-55389.pdf
M3SF-19OR0204050160 | M3 | 1.08.02.04.05 | ORNL | SF-19OR02040501 | Commercial SNF Characterization - ORNL | Clarity, Justin | Banerjee, Kaushik | Update UNF-ST&DARDS criticality report | UNF-ST&DARDS criticality analysis capability | This revision updates or adds three items: (1) and update to Table 22 in Section 5, which documents the status of the sites that have been analyzed, (2) addition of the Appendices sections A.13 and A.14 to document the CSAS6 models of the NUHOMS® 61BT/BTH-DSC and NUHOMS® 32PTH/PTH1 DSC canisters, and (3) an update to the query provided in Appendix B to extract results. The query has been updated to accommodate the more recent updates to the UDB table names. | 2019-09-20 |  | 2019-09-20 | This report documents UNF-ST&DARDS criticality analysis templates. | 2019 | Complete | Criticality Process, Modeling and Status for UNF-ST&DARDS | Justin Clarity | Kaushik Banerjee | None | PB1901109_Clarity_Criticality_Final.pdf |  | UNF-ST&DARDS, criticality
M4SF-19ID020303045 | M4 | 1.08.02.03.03 | DOE- Idaho Operations Office | SF-19ID02030304 | Transportation: Hardware - DOE-ID | Schwab, Patrick | Feldman, Matt | CLIN 3 Event 8: Prototype Railcars Delivered | Prototype Railcars Delivery Receipt | Atlas Railcar Phase 3 Final Report | 2019-04-20 | 2019-05-15 | 2019-05-19 | The Phase 3 Final Report was received and approved on May 19, 2019. | 2019 | Complete | Atlas Railcar Phase 3 Final Report |  |  | None | FS-19-0116 Phase 3 Report Rev 0.pdf
M2SF-20OR0204050113 Superseded by- M2SF-21OR020401017- No report. Software release. | M2 | 1.08.02.04.01 | ORNL | SF-21OR02040101 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Howard, Rob | UNF-ST&DARDS 4.1 Release | UNF-ST&DARDS 4.1 Release |  | 2020-12-18 |  |  | Version 4.1 of UNF-ST&DARDS has been released. | 2021 | In Progress |  |  |  | None
M3SF-20OR020405045 | M3 | 1.08.02.04.05.04 | ORNL | SF-20OR02040504 | Web-application for GC-859 Data - ORNL | Banerjee, Kaushik | Howard, Rob | Phase II demonstration of the web-app | Phase II demonstration of the web-app | Phase II demonstration of the web-app | 2021-09-30 |  |  |  | 2020 | On Schedule |  |  |  | None
M4SF-21ID020302043 | M4 | 1.08.02.03.02.04 | DOE-ID | SF-21ID02030204 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Updated START User’s Manual | Updated Start User’s Manual | Update the START User’s Manual to reflect the current functions and capabilities of the START tool. | 2021-03-31 | 2021-09-30 |  | On schedule to meet 3/31/21 finish date. | 2021 | 90 Day |  |  |  | None
M4SF-21PN020303066 | M4 | 1.08.02.03.03.06 | PNNL | SF-21PN02030306 | Transportation: Hardware - PNNL | Maheras, Steve | Feldman, Matt | Final Demonstration Run Plan | Final Demonstration Run Plan | Develop a final demonstration run plan. | 2021-03-31 | 2021-08-31 | 2021-08-27 | The purpose of this report is to help lay the groundwork for the Demonstration Run (DR) portion of the Atlas Railcar Project and will demonstrate that a complete Atlas railcar train (Atlas railcars, buffer railcars, and rail escort vehicle) can function properly under real-world conditions on the US railroad network. The recommendation is to use a route from the Transportation Technology Center in Pueblo, CO to the Savannah River Site to the Transportation Technology Center in Pueblo, CO. It is also recommended that the rail escort vehicle be crewed by a mix of Transportation Technology Center personnel and DOE federal and contractor employees, and that stakeholder involvement be limited to pre-DR discussion of the route and schedule, allowing interested individuals to track the progress of the DR in real time, real-time social media posts from DOE during the DR, and post-DR briefings regarding the DR and the results. | 2021 | Complete | Atlas Railcar Demonstration Run Planning Document | Matt Feldman | Steven Maheras | None | M4SF-21PN020303066 Demonstration Run Planning Document_Final.pdf |  | Atlas railcar, buffer railcar, rail escort vehicle, REV, demonstration run, run plan
M5SF-21PN020303064 | M5 | 1.08.02.03.03.06 | PNNL | SF-21PN02030306 | Transportation: Hardware - PNNL | Maheras, Steve |  | Atlas Railcar Suspension Pad Testing Report | Atlas Railcar Suspension Pad Testing Report | Report documenting the non-destructive and mechanical properties testing of the Atlas railcar suspension pads. | 2021-03-31 | 2021-08-31 |  | potentially delayed to 5/15(60% complete) | 2021 | 90 Day |  |  |  | None
M3SF-21OR020302066 | M3 | 1.08.02.03.02.06 | ORNL | SF-21OR02030206 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Updated Revision of Shipment History | Updated Revision of Shipment History | This milestone will be an update to the Historical Review of the Safe Transport of Spent Nuclear Fuel” published in 2016. The new revision will keep the document current using up-to-date shipment numbers from public sources. | 2021-07-30 |  | 2021-07-30 | This report contains a review of publicly available information on SNF transportation worldwide. Estimates were developed to ascertain the number of fuel assemblies, the number of tons of SNF shipped, and the number of shipments made between 1962 and 2021 worldwide. | 2021 | Complete | A Historical Review of the Safe Transport of Spent Nuclear Fuel | Kevin Connelly | Kevin Connelly | None | Shipment history rev 2 - 2.docx |  | SNF; Spent Nuclear Fuel; Used Fuel; UNF; fuel assemblies; shipping SNF
M3SF-21SR020401062 | M3 | 1.08.02.04.01.06 | SRNL | SF-21SR02040106 | Commercial SNF Characterization - SRNL | Carter, Joe | Howard, Rob | Spent Nuclear Fuel and Reprocessing Waste Inventory Rev 8 | Spent Nuclear Fuel and Reprocessing Waste Inventory Rev 8 | Spent Nuclear Fuel and Reprocessing Waste Inventory Rev 8 | 2021-07-30 |  | 2021-07-29 | The report provides information on the inventory of spent fuel and high level radioactive waste in the United States located at Nuclear Power Plants and away-from Reactor Independent Spent Fuel Storage Installations (ISFSI) as well as SNF and reprocessing waste located at DOE sites and other government locations. Actual or estimated quantitive values for current inventories are provided along with inventory forecasts derived from examining different future nuclear power generation scenarios. The inventory incorporates the recently issued GC-859 utility survey data through December 2017. | 2021 | Complete | Spent Nuclear Fuel and Reprocessing Waste Inventory | Shan Peters | Joe Carter | None | SNF and Rep Waste Inventory (FCRD-NFST-2013-000263) Rev 8d.pdf
M5SF-21IN020201074 | M5 | 1.08.02.02.01.07 | INL | SF-21IN02020107 | Canister SCC Mitigation - INL | Thomas, Dan |  | Draft Application Configuration Description for DOE Standard Canister FSW Closure and Cold Spray Coating Equipment | Draft Application Configuration Description for DOE Standard Canister FSW Closure and Cold Spray Coating Equipment | Working draft internal report with information on the updated application configuration description for FSW and Cold Spray equipment that could be used on DOE Standard Canister in the Fuel Handling Cave of the CPP-603 facility at INTEC. | 2021-07-30 |  | 2021-07-29 | Document submitted by due date. | 2021 | Complete | Application Configuration Description for SCC Protection of DOE Standard Canisters | Daniel A. Thomas | Josh J. Jarrell | None | INL-EXT-21-63650-0A.pdf
M4SF-21OR020402103 | M4 | 1.08.02.04.02.10 | ORNL | SF-21OR02040210 | Waste Management System Architecture - NGSAM Model Development and V&V - ORNL | Joseph, Robby | Joseph, Robby | FY21 NGSAM Model Development and V&V Report | FY21 NGSAM Model Development and V&V Report | NGSAM Model Develop and V&V | 2021-08-06 |  | 2021-08-06 | Completed the M4 milestone M4SF-21OR020402104, entitled “FY21 NGSAM Model Development and V&V,” in the work package SF-21OR02040210, entitled “Waste Management System Architecture- NGSAM Model Development and V&V- ORNL.” This document describes the testing of the Next-Generation System Analysis Model (NGSAM) that was recently completed. | 2021 | Complete | FY21 NGSAM Model Development and V&V |  |  | None | PB2100991_Joseph_NGSAM_Rev3.pdf
M5SF-21PN020201112- Delayed until FY22 | M5 | 1.08.02.02.01.11 | PNNL | SF-21PN02020111 | Hanford Lead Canister - PNNL | Howard, Rob |  | Heater Control System Programming | Heater Control Systems Programming Status Email | Write the code to fully programs the heater control system for the short term (FY2022) and long term (FY2026) test phases | 2021-08-13 |  | 2021-08-31 | Status report for HLC heater programming task | 2021 | Delayed |  | Robert Howard | Robert Howard | None
M5SF-21IN020301132 | M5 | 1.08.02.03.01.13 | INL | SF-21IN02030113 | Intergovernmental and External Engagement - INL | Carlsen, Brett |  | Prepare Transportation Communication Program Proposal | Prepare Transportation Communication Program Proposal | Prepare Transportation Communication Program Proposal | 2021-08-13 |  | 2021-08-12 | Proposal submitted to Matt Feldman w/ email dated 8/12/21 | 2021 | Complete | Nuclear Transport Communications Proposal |  |  | None | Transport Com Proposal - R0.pdf
M4SF-21PN020402131 | M4 | 1.08.02.04.02.13 | PNNL | SF-21PN02040213 | Waste Management System Architecture - NGSAM Model Development and V&V - PNNL | Nutt, Mark | Joseph, Robby | Improved Intermodal Transfer Operations Model | Improved Intermodal Transfer Operations Model | Develop improved representation of intermodal transfer operations. This includes development of intermodal transfer concepts of operations, quantification of process step duration, identification of equipment needed, and estimates of unit costs. Develop a revised approach for simulating intermodal operations for future incorporation into NGSAM/JTOM. | 2021-08-16 |  | 2021-08-17 | This report incorporates externally generated transportation data within current system analysis tools, Next Generation System Analysis Model (NGSAM) and Java-coded Transportation Operations Model (JTOM), through refinements to input tables and modeling methods. Proposed baseline parameter refinements to specific input tables were developed that provide a sound technical basis that better informs follow-on transportation modeling and analysis using the tools. | 2021 | Complete | Spent Nuclear Fuel Transportation: Baselining Intermodal Operations Metrics | Daniel Sullivan | Mark Nutt | None | Transload Operations Planning (draft M4SF-21PN020402131).docx
M4SF-21IN020402073 | M4 | 1.08.02.04.02.07 | INL | SF-21IN02040207 | Update Used Fuel Inventory Categorization Report - INL | Orrell, Stanley | Joseph, Robby | Develop Revised Categorization Report Draft for DOE | Develop Revised Categorization Report Draft for DOE | Take new inputs and revised narratives, and compile into a draft ready for DOE review. Includes one internal draft review cycle by report participants. | 2022-01-14 |  |  |  | 2021 | On Schedule |  |  |  | None
M3SF-21PN020201101- Converted into FY22 per Rob Howard | M3 | 1.08.02.02.01.10 | PNNL | SF-21PN02020110 | Canister SCC Mitigation - PNNL | Howard, Rob | Carter, Joe | Canister SCC Mitigation: Friction Stir Welding and Cold Spray FY2022 Status Report | Canister SCC Mitigation: Friction Stir Welding and Cold Spray FY2022 Status Report | A final report will include: 1) limited laboratory test data, 2) applicability analysis of FSW and Cold Spray to DOE SNF Packaging Demonstration and 3) recommendations for future work. | 2021-08-31 | 2021-10-29 |  | This deliverable is on track. | 2021 | Complete |  |  |  | None
M3SF-21OR0204010111 | M3 | 1.08.02.04.01.01 | ORNL | SF-21OR02040101 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Joseph, Robby | Revise thermal template development report | UNF-ST&DARDS Thermal Template Development Status | Investigate Moose based thermal analysis capability within UNF-ST&DARDS and revise the thermal template development report with one additional template (subject to availability of drawings). | 2021-08-31 | 2021-08-31 |  | The thermal analysis report documented two items 1.) It developed a COBRA-SFS model for the HI-STAR 100 with the MPC-32 loaded in it and 2.) it investigated the use of the use of the Pronghorn code for use in thermal analysis calculations within UNF-ST&DARDS. | 2021 | Complete | Thermal Model Development of HI-STAR 100 with MPC-32 and Feasibility Study for Integration of Pronghorn Code in UNF-ST&DARDS | Nicholas Kucinski | Justin Clarity | None | M3SF-21OR0204010111_final.pdf |  | HI-STAR; Thermal; COBRA
M4SF-21PN020401102 | M4 | 1.08.02.04.01.10 | PNNL | SF-21PN02040110 | UNF Standards Testing and Support - PNNL | Howard, Rob | Joseph, Robby | UNF-ST&DARDS Gap Analysis and Recommendations for Product Enhancements | UNF-ST&DARDS Gap Analysis and Recommendations for Product Enhancements | Under this milestone a gap analysis for UNF-ST&DARDS will be performed. The gap analysis will attempt to identify missing analysis features, missing analysis templates, and missing data for holistic analysis of the US spent nuclear fuel. The milestone will also identify recommendations for product enhancements and additional validation efforts for possible consideration in FY2022 IPL | 2021-08-31 |  | 2021-08-31 | This report (1) discusses various features of the Used Nuclear Fuel Storage, Transportation and Disposal Analysis Resource and Data System (UNF-ST&DARDS); (2) identifies feature-specific shortcomings/issues/gaps; (3) recommends various steps to enhance UNF-ST&DARDS overall infrastructure, applications, and long-term maintenance; and (4) identifies new features that can be developed within UNF-ST&DARDS. | 2021 | Complete | UNF-ST&DARDS: Recommendations for Product Enhancements | Kaushik Banerjee | Kaushik Banerjee | None | unf_stad_status_Rev3.pdf
M4SF-21PN020402152 | M4 | 1.08.02.04.02.15 | PNNL | SF-21PN02040215 | Advanced Fuel Cycle Waste Form Management and Planning - PNNL | Nutt, Mark | Joseph, Robby | Accident Tolerant Fuel | Incorporation of ATF Into the Back-End of the Fuel Cucle | Report identifying areas that could potentially be impacts and pointing out future work that would need to happen to incorporate ATF into the back-end | 2021-08-31 |  | 2021-08-31 | This is a scoping evaluation that identifies the potential impacts on storage and transportation of low- enriched uranium (LEU) and high assay low-enriched uranium (HALEU) accident tolerant fuel (ATF), with the latter having burnups greater than 62 GWD/MTU and enrichment greater than 5 wt%. This scoping evaluation includes (1) discussion of various ATF designs, (2) limited estimated ATF characteristics, (3) overall dry storage and transportation licensing impact, and (4) ATF impact on dry storage/transportation system design and operation from thermal, structural, shielding, and criticality perspectives. | 2021 | Complete | Incorporation of Accident Tolerant Fuel into the Back End of the Fuel Cycle | Kaushik Banerjee, Philip Jensen, Nicholas Klymyshyn, David Richmond, Antonio Rigato, Justin Clarity, Nicholas Kucinski, Paul Miller, Peter Stefanovic, Gordon Peterson | Mark Nutt | None | ATF_Back_End_FC_Final-(M4SF-21PN020402152).pdf
M4SF-21PN020301114 | M4 | 1.08.02.03.01.11 | PNNL | SF-21PN02030111 | Intergovernmental and External Engagement - PNNL | Maheras, Steve | Feldman, Matt | Final 180(c) Summary Report | Final 180(c) Summary Report | Final 180(c) Summary Report | 2021-09-10 |  | 2021-09-09 | This report summarizes activities conducted between 1983 and 2017 by DOE and various DOE-supported working groups to examine implementation of Section 180(c) of the Nuclear Waste Policy Act (NWPA). Objectives of this report include documenting and tracking Section 180(c) issues and their resolution, identifying pivotal work products, summarizing outstanding issues, and providing an overview of legislative proposals that may affect implementation of Section 180(c) policy. After a brief introduction to Section 180(c) of the NWPA, the report provides a chronological summary of the major issues addressed and products produced by the working groups. The report concludes with an analysis of proposed legislative actions related to Section 180(c) policy and a brief discussion of potential next steps regarding Section 180(c) activities. | 2021 | Complete | US Department of Energy Engagement with the States and Tribes on Section 180(c) of the Nuclear Waste Policy Act | Lauren Rodman | Steve Maheras | None | M4SF-21PN020301114.pdf |  | Nuclear Waste Policy Act; NWPA; Section 180©; training; funding and technical assistance; States; Tribes
M3SF-21SN020501022 | M3 | 1.08.02.05.01.02 | SNL | SF-21SN02050102 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Complete dev, test, implementation, and documentation of Legacy app functionality in the NWM Cloud environments. | Complete final Legacy Application status report and documentation. |  | 2021-09-23 | 2021-11-30 |  |  | 2021 | On Schedule |  |  |  | None
M4SF-21SN020501024 | M4 | 1.08.02.05.01.02 | SNL | SF-21SN02050102 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Productionize NWM DevOps/Cloud environment monitoring capabilities. | Sample report showing monthly review of cloud services usage and cost. | Implement automated processes and reporting regarding Cloud environment health, growth, costing, usage trends, and formal monitoring of changes with IT leadership. | 2021-09-23 |  | 2021-09-10 | NWM DevOps capabilities are productionized and were used to place NWM Legacy Applications in production status. | 2021 | Complete | NWM Cloud Status Update FY21Q4 |  |  | None | 1633569520790-NWM-FY21-Q4-PICS-Update.docx
M4SF-21SN020501025- Same report as M4SF-21SN020501024 | M4 | 1.08.02.05.01.02 | SNL | SF-21SN02050102 | Cloud-Based IT System for a Generic Nuclear Waste Management Program - SNL | Huber, Cynthia | Huber, Cynthia | Continue on-going NWM ATO security control implementations and assessments. | Semi-Annual & Annual ATO Review Reports | Complete security control implementations and assessments. Provide to DOE-CIO semi-annual and annual reports of progress. | 2021-09-23 |  | 2021-09-23 | Completed required FY21 ATO assessments. | 2021 | Complete | NWM Cloud Status Update - FY21Q4 |  |  | None | 1633569520790-NWM-FY21-Q4-PICS-Update.docx
M3SF-21OR020201091 | M3 | 1.08.02.02.01.09 | ORNL | SF-21OR02020109 | Standardization and Integration - ORNL | Banerjee, Kaushik | Carter, Joe | Development of advanced manufacturing techniques for SNF dry storage and transportation components | Development of advanced manufacturing techniques for SNF dry storage and transportation components | Status report describing development status of advanced manufacturing techniques (additive manufacturing/3D printing) of SNF dry storage and transportation components and ancillary equipment. | 2021-09-30 |  | 2021-09-30 | Milestone report complete and emailed to Jack Wheeler, Joe Carter and Rob Howard. | 2021 | Complete | Additive Manufacturing of Used Fuel Canisters Phase 1 | Wei Tang, Dominic Giuliano, Oscar Martinez | Oscar Martinez | None | M3SF-20OR02020109 Milestone Report Additive Manufacturing_FINAL.pdf |  | 3D printing; additive manufacturing
M3SF-21OR020303056 | M3 | 1.08.02.03.03.05 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | Atlas Railcar Design Project Status Report for FY2021 | Atlas Railcar Design Project Status Report for FY2021 | Prepare Atlas Railcar Design Project Status Report for FY2020 that describes accomplishments for this FY. | 2021-09-30 |  | 2021-09-30 | Milestone report completed on time. | 2021 | Complete | Atlas Railcar Design Project Status Report for FY2021 | William J. Reich | William J. Reich | None | M3SF-21OR020303056-Atlas Railcar Project Status Report-Sept 30 2021-R3.docx |  | Atlas railcar
M3SF-21OR020401018 | M3 | 1.08.02.04.01.01 | ORNL | SF-21OR02040101 | Commercial SNF Characterization - ORNL | Banerjee, Kaushik | Joseph, Robby | Status report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | validation of UNF-ST&DARDS as-loaded analysis methodology | Report documenting validation of UNF-ST&DARDS as-loaded analysis methodology using detail fuel design and reactor operation data | 2021-09-30 |  | 2021-09-30 | The detailed analysis report documents 1.) Calculations using an MPC-32 from the D.C. Cook site. Calculations performed include assembly and canister decay heat as well as assembly reactivity and canister criticality calculations. The results showed that the UNF-ST&DARDS analysis pipeline is conservative for the canister analyzed. and 2.) Developed the detailed criticality analysis pipeline to perform critical experiment selection and criticality code bias assessment. | 2021 | Complete | Validation of the UNF-ST&DARDS As-Loaded Calculation Methodology for PWR Calculations | Justin Clarity | Justin Clarity | None | PWR_Detailed_Validation_2021-(M3SF-21OR020401018)_FINAL.pdf
M3SF-21OR020401024- The deliverable was a demonstration of the web app. The demo covered the Phase II features. | M3 | 1.08.02.04.01.02 | ORNL | SF-21OR02040102 | Web-application for GC-859 Data - ORNL | Banerjee, Kaushik | Joseph, Robby | Phase II demonstration of the web-app | Phase II demonstration of the web-app | Phase II demonstration of the web-app | 2021-09-30 |  | 2021-09-28 | The demonstration of the Phase II features was presented to the NTD, federal fund managers, and EIA representatives. A positive and constructive discussion period followed the demo. The team received appreciation for the accomplishments. | 2021 | Complete |  |  |  | None
M3SF-21AN020401074- Updated model version posted on the NGSAM website for access by analysts. An email was sent to the CAM and DOE informing them of the completed milestone. The model can be downloaded by approved users from the following URL: https://ngsam.gss.anl.gov/ | M3 | 1.08.02.04.01.07 | ANL | SF-21AN02040107 | NGSAM Development and Application - ANL | Craig, Brian | Howard, Rob | NGSAM Release 2.3.10.0 | NGSAM Version 2.3.10.0 | Development of NGSAM 2.3.10.0 which will include the following model improvements: Incorporate lasted UDB Changes Loading Optimization algorithm based on Christina Yancy PhD Add re-usable bare fuel casks for transportation Utility Trading of Allocation Implement a Minimum Consist Size Automated Heat Calculations Acquire route files for missing routes. | 2021-09-30 |  | 2021-09-30 | NGSAM 2.3.10.0 was completed and delivered on time 9/30/2021 | 2021 | Complete |  |  |  | None
M3SF-21SR020402202 | M3 | 1.08.02.04.02.20 | SRNL | SF-21SR02040220 | Advanced Fuel Cycle Waste Form Management and Planning - SRNL | Carter, Joe | Joseph, Robby | Summary Status Report | FY-21 Status Summary Report | Document initial findings and areas for future work. | 2022-01-28 |  |  |  | 2021 | On Schedule |  |  |  | None
M4SF-21ID020302042 | M4 | 1.08.02.03.02.04 | DOE-ID | SF-21ID02030204 | Transportation: Operational - DOE-ID (North Wind) | Davies, Jordan | Feldman, Matt | Complete Transition to Cloud Server | Completed Transition to Cloud Server | This task involves the transition to serving START through the Amazon Cloud Server rather than at INL, and subsequently hosting and troubleshooting Amazon web services for a 12-month period. | 2021-09-30 | 2022-01-31 |  |  | 2021 | On Schedule |  |  |  | None
M4SF-21OR020302067 | M4 | 1.08.02.03.02.06 | ORNL | SF-21OR02030206 | Transportation: Operational - ORNL | Bevard, Bruce | Feldman, Matt | Transportation Knowledge Management | History of Criticality Regulations | Develop a report on a historical review of the technical basis for criticality safety regulations in radioactive materials transportation. | 2021-09-30 |  | 2021-09-30 | This deliverable includes information on historical regulations for criticality safety of radioactive materials transportation. It will be combined with the rest of the Historical Transport Document in FY 2022. | 2021 | Complete | Draft Historical Transport Document: Criticality Appendices | Calvin Hopper | Kevin Connolly | None | M4SF-21OR020302067.pdf |  | criticality; IAEA; regulations; transportation
M4SF-21PN0203020711 | M4 | 1.08.02.03.02.07 | PNNL | SF-21PN02030207 | Transportation: Operational - PNNL | Maheras, Steve | Feldman, Matt | START Verification and Validation Status Report | START Verification and Validation Status Report | Develop status report describing START verification and validation. | 2021-09-30 |  | 2021-09-27 | The Stakeholder Tool for Assessing Radioactive Transport (START) is a web-based, decision-support tool developed for evaluating routing options and other aspects of transporting radioactive waste from nuclear power plant sites to disposal sites. This status report presents progress made in fiscal year 2021 (FY21) to verify and validate START. The verification and validation (V&V) efforts for determining route population within the buffer zone and route length were accomplished using an automated workflow developed for the Quantum Geographic Information System. The official suite of V&V test routes was used to verify and validate the buffer zone population and route length for START version 3.2.1 that became available in January 2021 and START version 3.2.2 that was released in July 2021. There was good agreement between START and the independent analysis; the percent difference was less than +/-5%, and the majority of cases were below +/-1%. Findings about route aberrations are presented, including noted instances of route holes, spurs, and deviations from logical route. The analysis of the transload sites included in the official V&V suite of test routes is also presented. The V&V team’s analysis of the population within the buffer zone for individual segments of a single route generated within START found good agreement between population in a segment buffer compared to an independent analysis of that segment. The percent differences for the segment populations are low with most of differences <1%; some percent differences were greater than 5% and one was greater than 10%. Finally, this report presents the results for an initial analysis of the incident-free dose presented for individual route segments. The initial evaluation of the incident free doses reported in START found good agreement between the START outputs and the independently calculated routes using the methodology outlined by Connolly (2015). | 2021 | Complete | START Verification and Validation: Status Update FY21 | Caitlin Condon | Steve Maheras | None | M4SF-21PN0203020711 START Verification and Validation Status Update FY21_signed.pdf |  | START; transportation routing; V&V; verification and validation; SNF; spent nuclear fuel
M4SF-21OR020303059- Please contact Bill Reich, reichwj@ornl.gov, to receive a copy of the document. | M4 | 1.08.02.03.03.05 | ORNL | SF-21OR02030305 | Transportation: Hardware - ORNL | Reich, Bill | Feldman, Matt | ISSMS Prototype System Design | ISSMS Prototype System Design | Document the ISSMS prototype system design for the software and hardware developed for the Atlas railcar. | 2021-09-30 |  |  | Milestone report completed on time. | 2021 | Complete | Integrated Security and Safety Monitoring System: Prototype System Design | William J. Reich | William J. Reich | OUO |  |  | ISSMS Atlas Railcar
M4SF-21PN020304032 | M4 | 1.08.02.03.04.03 | PNNL | SF-21PN02030403 | Rail Car Optimization - PNNL | Ross, Steven | Feldman, Matt | 8-Axle Railcar Year End Summary (FY21) | 8-Axle Railcar FY21 Year End Summary Report | Summary of FY21 accomplishments for the efforts associated with the fabrication and and testing of an 8-axle railcar for the transportation of spent nuclear fuel. | 2021-09-30 |  | 2021-09-30 | An email transmitting this milestone and confirming it was completed as sent to the NTD/CAM on 9/30/21. | 2021 | Complete | Fortis (8-Axle Railcar) Project Status Report - FY21 | Steven B. Ross, Matt R. Feldman | Steven B. Ross | None | M4SF-21PN020304032_Fortis Railcar Year End Summary_FY21_Final.pdf
M4SF-21OR020401042 | M4 | 1.08.02.04.01.04 | ORNL | SF-21OR02040104 | Restore Legacy Characteristics Database - ORNL | Banerjee, Kaushik | Howard, Rob | Preserve legacy Characteristics Data Base activity status report | Preserve legacy Characteristics Data Base activity status report | preserve legacy Characteristics Data Base activity status report | 2021-09-30 |  | 2021-09-30 | The Characteristics [of potential repository wastes] Database system from the 1990s is being restored to preserve the fuel characteristics, inventory, and other SNF-related data in order to inform spent fuel research today. The full data set has been restored to MySQL format to allow nuclear analysts to identify and extract the relevant data. The future work will complete the data review and import to the Unified Database. | 2021 | Complete | Restoration of Legacy Characteristics Database |  |  | None | Restoration_Legacy_Characteristics_Database_M4SF-21OR02040104.pdf
M3SF-21PN020401053 | M3 | 1.08.02.04.01.05 | PNNL | SF-21PN02040105 | COBRA-SFS Code Development - PNNL | Richmond, David | Joseph, Robby | COBRA-SFS Version 6.1 and User Manual | COBRA-SFS Version 6.1 and User Manual | User manual for COBRA-SFS Version 6.1 | 2021-10-31 |  | 2021-10-28 | An email transmitting this milestone and confirming it was completed was sent to the NTD/CAM on October 29, 2021. | 2021 | Complete | COBRA-SFS Version 6.1 User Guide: A Thermal Hydraulic Analysis Code for Spent Fuel Storage and Transportation Casks | David Richmond, Brian Hom, Ben Jensen, Christopher Grant | David Richmond | None | COBRA_SFS_V6.1_User_Guide_Final.pdf |  | Thermal Hydraulic Analysis Code